## Deployment_Plan
Unique ID | WBS | Email Sent | Task Start | Email Rec | Status (Excel) |  | Task Name | Duration | Start | Finish | Resource Names | Resource Emails | Secondary Resource Name | Secondary Resource E-Mail | Team | Unique ID Predecessors | Actual Start | Actual Finish | Constraint | Constraint Date | Baseline Start | Baseline Finish | Tags | Notes | Free Text 1 | Free Text 2
5709 | STRIVE.R2.MC1.2384 | [5 empty] | STRIVE Wave 1 - Mock Cutover 1 | 2062.27 hrs | 2025-07-14 08:00 | 2025-10-08 12:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-10-08 12:00
5710 | STRIVE.R2.MC1.2384.1 | [5 empty] | Pre-Cutover | 581.38 hrs | 2025-07-14 08:00 | 2025-08-07 15:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-08-07 15:00
18148 | STRIVE.R2.MC1.2384.1.1 | [5 empty] | BASIS | 386.93 hrs | 2025-07-14 08:00 | 2025-07-30 12:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-30 12:00
18149 | STRIVE.R2.MC1.2384.1.1.1 | [5 empty] | Infrastructure | 889.08 hrs | 2025-07-14 08:00 | 2025-08-20 11:33 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-08-20 11:33
18150 | STRIVE.R2.MC1.2384.1.1.1.1 | Y | Y | Y | Complete |  | Hana Database Backup configuration checks | 12.87 hrs | 2025-07-14 08:00 | 2025-07-15 13:52 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 13:52 | * | NA | 2025-07-14 08:00 | 2025-07-15 13:52
18151 | STRIVE.R2.MC1.2384.1.1.1.2 | Y | Y | Y | Complete |  | Cloud Connector setup - Certificate&Proxy connectivity | 12.88 hrs | 2025-07-14 08:00 | 2025-07-15 13:53 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 13:53 | * | NA | 2025-07-14 08:00 | 2025-07-15 13:53
18152 | STRIVE.R2.MC1.2384.1.1.1.3 | Y | Y | Y | Complete |  | Webdispatcher setup - Certificate&Connectivity | 12.91 hrs | 2025-07-14 08:00 | 2025-07-15 13:54 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 13:54 | * | NA | 2025-07-14 08:00 | 2025-07-15 13:54
18153 | STRIVE.R2.MC1.2384.1.1.1.4 |  |  |  | Complete |  | BTP Environment setup | 44.95 hrs | 2025-07-14 08:00 | 2025-07-21 13:57 | [6 empty] | 2025-07-14 08:00 | 2025-07-15 13:56 | * | NA | 2025-07-14 08:00 | 2025-07-21 13:57
18154 | STRIVE.R2.MC1.2384.1.1.1.4.1 | Y | Y | Y | Complete |  | Initial access provisioning to GRC | 12.93 hrs | 2025-07-14 08:00 | 2025-07-15 13:56 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 13:56 | * | NA | 2025-07-14 08:00 | 2025-07-15 13:56
18155 | STRIVE.R2.MC1.2384.1.1.1.6 |  |  |  | Complete |  | SAP Mobile Start device setup | 8 hrs | 2025-07-14 08:00 | 2025-07-14 17:00 | [6 empty] | 2025-07-14 08:00 | 2025-07-23 16:55 | * | NA | 2025-07-14 08:00 | 2025-07-14 17:00
18156 | STRIVE.R2.MC1.2384.1.1.1.6.1 | Y | Y | Y | Complete |  | Mobile phone / Tablet infra request | 63.91 hrs | 2025-07-14 08:00 | 2025-07-23 16:54 | Pierre Trankalis | pierre.trankalis@de.sasol.com | Victor Tan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Victor.Tan@ap.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-23 16:54 | * | NA | 2025-07-14 08:00 | 2025-07-23 16:54
18157 | STRIVE.R2.MC1.2384.1.1.1.6.2 | Y | Y | Y | Complete |  | Intune profile setup on devices | 63.91 hrs | 2025-07-14 08:00 | 2025-07-23 16:55 | Pierre Trankalis | pierre.trankalis@de.sasol.com | Victor Tan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Victor.Tan@ap.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-23 16:55 | * | NA | 2025-07-14 08:00 | 2025-07-23 16:55
18158 | STRIVE.R2.MC1.2384.1.1.1.6.3 | Y | Y | Y | Complete |  | Azure AD setup for mobile devices | 63.92 hrs | 2025-07-14 08:00 | 2025-07-23 16:55 | Pierre Trankalis | pierre.trankalis@de.sasol.com | Victor Tan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Victor.Tan@ap.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-23 16:55 | * | NA | 2025-07-14 08:00 | 2025-07-23 16:55
18159 | STRIVE.R2.MC1.2384.1.1.1.10 | Y | Y | Y | Complete |  | WWI Server&Application setup | 20.83 hrs | 2025-07-14 08:00 | 2025-07-16 13:50 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-16 13:50 | * | NA | 2025-07-14 08:00 | 2025-07-16 13:50
18160 | STRIVE.R2.MC1.2384.1.1.1.11 | Y | Y | N | In-Progress |  | Printer infrastructure setup | 8 hrs | 2025-08-18 13:43 | 2025-08-18 21:43 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-08-18 13:43 |  | * | NA | 2025-08-18 13:43 | 2025-08-18 21:43
18161 | STRIVE.R2.MC1.2384.1.1.1.12 | Y | Y | N | In-Progress |  | DMS&Archiving infra setup | 8 hrs | 2025-08-18 13:42 | 2025-08-18 21:42 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-08-18 13:42 |  | * | NA | 2025-08-18 13:42 | 2025-08-18 21:42
18162 | STRIVE.R2.MC1.2384.1.1.1.13 | Y | Y | Y | Complete |  | Citrix accessiblity checks | 31.08 hrs | 2025-07-16 13:55 | 2025-07-22 12:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-16 13:55 | 2025-07-22 12:00 | * | NA | 2025-07-16 13:55 | 2025-07-22 12:00
18163 | STRIVE.R2.MC1.2384.1.1.15 | [5 empty] | System Readiness | 192.37 hrs | 2025-07-14 08:00 | 2025-07-22 08:54 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-22 08:54
18164 | STRIVE.R2.MC1.2384.1.1.15.1 | Y | Y | Y | Complete |  | Initial S/4HANA and MDG system Technical setup | 13.33 hrs | 2025-07-14 08:00 | 2025-07-15 14:20 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:20 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:20
18165 | STRIVE.R2.MC1.2384.1.1.15.2 | Y | Y | Y | Complete |  | Transport route checks | 13.34 hrs | 2025-07-14 08:00 | 2025-07-15 14:21 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:21 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:21
18166 | STRIVE.R2.MC1.2384.1.1.15.3 | Y | Y | Y | Complete |  | Basis Transport import ( Business Function , BC sets ,External TRs) Charm/Manual TR's | 24 hrs | 2025-07-14 08:00 | 2025-07-16 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-16 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-16 17:00
18167 | STRIVE.R2.MC1.2384.1.1.15.4 | Y | Y | Y | Complete |  | CUST_TC user activation | 12.96 hrs | 2025-07-14 08:00 | 2025-07-15 13:57 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 13:57 | * | NA | 2025-07-14 08:00 | 2025-07-15 13:57
18168 | STRIVE.R2.MC1.2384.1.1.15.5 | Y | Y | Y | Complete |  | Charm configuration check | 13.36 hrs | 2025-07-14 08:00 | 2025-07-15 14:22 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:22 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:22
18169 | STRIVE.R2.MC1.2384.1.1.15.6 | Y | Y | Y | Complete |  | Validate Single sign-on Setup - S/4 | 20.94 hrs | 2025-07-14 08:00 | 2025-07-16 13:57 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-16 13:57 | * | NA | 2025-07-14 08:00 | 2025-07-16 13:57
18170 | STRIVE.R2.MC1.2384.1.1.15.7 | Y | Y | Y | Complete |  | Validate Single sign-on Setup - MDG | 20.96 hrs | 2025-07-14 08:00 | 2025-07-16 13:58 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-16 13:58 | * | NA | 2025-07-14 08:00 | 2025-07-16 13:58
18171 | STRIVE.R2.MC1.2384.1.1.15.8 | Y | Y | Y | Complete |  | SICF validation/activation | 13.38 hrs | 2025-07-14 08:00 | 2025-07-15 14:23 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:23 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:23
18172 | STRIVE.R2.MC1.2384.1.1.15.9 | Y | Y | Y | Complete |  | ODATA V4 Activation | 13.41 hrs | 2025-07-14 08:00 | 2025-07-15 14:25 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:25 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:25
18173 | STRIVE.R2.MC1.2384.1.1.15.10 | Y | Y | Y | Complete |  | Maintain ACL Files | 13.39 hrs | 2025-07-14 08:00 | 2025-07-15 14:24 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:24 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:24
18174 | STRIVE.R2.MC1.2384.1.1.15.11 | Y | Y | Y | Complete |  | Webdispatcher configuration | 13.42 hrs | 2025-07-14 08:00 | 2025-07-15 14:25 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:25 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:25
18175 | STRIVE.R2.MC1.2384.1.1.15.12 | Y | Y | Y | Complete |  | Fiori Launchpad setup ( HTTPURLOC and Cross Origin) | 13.61 hrs | 2025-07-14 08:00 | 2025-07-15 14:36 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:36 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:36
18176 | STRIVE.R2.MC1.2384.1.1.15.13 | Y | Y | Y | Complete |  | Printer configuration ( SPAD) | 13.64 hrs | 2025-07-14 08:00 | 2025-07-15 14:39 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:39 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:39
18177 | STRIVE.R2.MC1.2384.1.1.15.14 | Y | Y | Y | Complete |  | Principle Propagation setup for BTP applications | 13.66 hrs | 2025-07-14 08:00 | 2025-07-15 14:39 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:39 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:39
18178 | STRIVE.R2.MC1.2384.1.1.15.15 | Y | Y | Y | Complete |  | SCOT settings | 13.74 hrs | 2025-07-14 08:00 | 2025-07-15 14:44 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:44 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:44
18179 | STRIVE.R2.MC1.2384.1.1.15.16 | Y | Y | Y | Complete |  | Raise Incident to ECS team for ADS configuration&setup | 13.75 hrs | 2025-07-14 08:00 | 2025-07-15 14:45 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:45 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:45
18180 | STRIVE.R2.MC1.2384.1.1.15.17 | Y | Y | Y | Complete |  | SWU3 workflow customizing settings | 13.76 hrs | 2025-07-14 08:00 | 2025-07-15 14:46 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:46 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:46
18181 | STRIVE.R2.MC1.2384.1.1.15.18 | Y | Y | Y | Complete |  | SRT_ADMIN , SXMB_ADMIN - Queue registation checks | 13.77 hrs | 2025-07-14 08:00 | 2025-07-15 14:46 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:46 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:46
18182 | STRIVE.R2.MC1.2384.1.1.15.19 | Y | Y | Y | Complete |  | SAP system Parameter validation | 13.79 hrs | 2025-07-14 08:00 | 2025-07-15 14:47 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:47 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:47
18183 | STRIVE.R2.MC1.2384.1.1.15.20 | Y | Y | Y | Complete |  | Request PPDS Activation to basis | 1.56 hrs | 2025-07-16 12:27 | 2025-07-16 14:33 | Shivani Kulkarni | shivankulkarni@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  | 2025-07-16 12:27 | 2025-07-16 14:33 | * | NA | 2025-07-16 12:27 | 2025-07-16 14:33
18184 | STRIVE.R2.MC1.2384.1.1.15.21 | Y | Y | Y | Complete |  | PPDS Activation and setup based on request from R2P team | 0 hrs | 2025-07-16 16:41 | 2025-07-16 16:41 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER; Shreyas Singh Kunwar | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; shkunwar@deloitte.com | Basis | 18183 | 2025-07-16 16:41 | 2025-07-16 16:41 | * | NA | 2025-07-16 16:41 | 2025-07-16 16:41
18185 | STRIVE.R2.MC1.2384.1.1.15.22 | Y | Y | Y | Complete |  | Schedule Fiori Job ( /UI5/APP_INDEX_CALCULATE) | 13.8 hrs | 2025-07-14 08:00 | 2025-07-15 14:48 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:48 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:48
18186 | STRIVE.R2.MC1.2384.1.1.15.23 | N | N | N | Ready |  | Batchman - provide destination information to Deloitte Basis for connectivity (Open Client) | 4 hrs | 2025-09-10 08:00 | 2025-09-10 12:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS; Jens Nissen | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; Jens.Nissen@de.sasol.com | Sasol Infrastructure |  |  |  |  | 2025-09-10 08:00 | 2025-09-10 08:00 | 2025-09-10 12:00
18187 | STRIVE.R2.MC1.2384.1.1.15.24 | N | N | N | Ready |  | Connectivity setup with Batchman for job scheduling | 4 hrs | 2025-09-10 08:00 | 2025-09-10 12:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS; Jens Nissen | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; Jens.Nissen@de.sasol.com | Sasol Infrastructure |  |  |  |  | 2025-09-10 08:00 | 2025-09-10 08:00 | 2025-09-10 12:00
18188 | STRIVE.R2.MC1.2384.1.1.15.25 | Y | Y | Y | Complete |  | Maintain logical system relationship from SD1 to target system SP1 | 13.82 hrs | 2025-07-14 08:00 | 2025-07-15 14:49 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 14:49 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:49
18189 | STRIVE.R2.MC1.2384.1.1.15.26 | Y | Y | Y | Complete |  | Setup RFC user for logical system from SD1 to SP1 | 13.99 hrs | 2025-07-14 08:00 | 2025-07-15 14:59 | Somitra Thapa | sothapa@deloitte.com | Ankush; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amisri@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-07-15 14:59 | * | NA | 2025-07-14 08:00 | 2025-07-15 14:59
18190 | STRIVE.R2.MC1.2384.1.1.15.27 | Y | Y | Y | Complete |  | Provide object links for PPM Projects and PS | 14.02 hrs | 2025-07-14 08:00 | 2025-07-15 15:01 | Deloitte BASIS | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar | priyankaspatel@deloitte.de; trsagar@deloitte.com | BASIS |  | 2025-07-14 08:00 | 2025-07-15 15:01 | * | NA | 2025-07-14 08:00 | 2025-07-15 15:01
18191 | STRIVE.R2.MC1.2384.1.1.15.28 | Y | Y | Y | Complete |  | Activation Of SICF services forAIF alert inbox | 14.09 hrs | 2025-07-14 08:00 | 2025-07-15 15:05 | Tripti Sagar | trsagar@deloitte.com | Satheesh Pula; Basis; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | BASIS |  | 2025-07-14 08:00 | 2025-07-15 15:05 | * | NA | 2025-07-14 08:00 | 2025-07-15 15:05
20886 | STRIVE.R2.MC1.2384.1.1.15.29 | Y | Y | Y | Complete |  | Retrofit NCs are created and synced up in N+1 landscape by 18th July, EOD | 16.59 hrs | 2025-07-21 14:16 | 2025-07-23 14:51 | Paresh Patel | paresh.patel@us.sasol.com | Manasa; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | mha@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol Infrastructure |  | 2025-07-21 14:16 | 2025-07-23 14:51 |  | 2025-07-18 08:00 | 2025-07-21 14:16 | 2025-07-23 14:51
18192 | STRIVE.R2.MC1.2384.1.1.44 |  |  |  | Complete |  | Transports Import | 361.6 hrs | 2025-07-14 08:00 | 2025-09-15 09:36 | [6 empty] | 2025-07-14 08:00 | 2025-08-04 17:00 | * | NA | 2025-07-14 08:00 | 2025-09-15 09:36
18193 | STRIVE.R2.MC1.2384.1.1.44.1 |  |  |  | Complete |  | Pre import | 112.88 hrs | 2025-07-14 08:00 | 2025-08-01 08:53 | [6 empty] | 2025-07-15 16:21 | 2025-07-29 11:37 | * | NA | 2025-07-14 08:00 | 2025-08-01 08:53
18194 | STRIVE.R2.MC1.2384.1.1.44.1.1 | Y | Y | Y | Complete |  | Confirmation on Retrofit of all transports | 0 hrs | 2025-07-23 14:51 | 2025-07-23 14:51 | Pooja Babli | babli.p@hcltech.com | Christian Hogrefe; Paresh Patel; Priyanka Patel; Tripti Sagar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | Christian.Hogrefe@de.sasol.com; paresh.patel@us.sasol.com; priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-23 14:51 | 2025-07-23 14:51 | * | NA | 2025-07-23 14:51 | 2025-07-23 14:51
18195 | STRIVE.R2.MC1.2384.1.1.44.1.2 | Y | Y | Y | Complete |  | Validation of Retrofit and External Transports | 22.56 hrs | 2025-07-23 15:09 | 2025-07-28 13:43 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18194 | 2025-07-23 15:09 | 2025-07-28 13:43 | * | NA | 2025-07-23 15:09 | 2025-07-28 13:43
18196 | STRIVE.R2.MC1.2384.1.1.44.1.3 | Y | Y | Y | Complete |  | Check HANA Replication status ( For Production only ) | 0 hrs | 2025-07-15 16:21 | 2025-07-15 16:21 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18195 | 2025-07-15 16:21 | 2025-07-15 16:21 | * | NA | 2025-07-15 16:21 | 2025-07-15 16:21
18197 | STRIVE.R2.MC1.2384.1.1.44.1.4 | Y | Y | Y | Complete |  | Validate/Rebuild transport import buffer | 76.26 hrs | 2025-07-15 16:21 | 2025-07-29 11:36 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18196 | 2025-07-15 16:21 | 2025-07-29 11:36 | * | NA | 2025-07-15 16:21 | 2025-07-29 11:36
18198 | STRIVE.R2.MC1.2384.1.1.44.1.5 | Y | Y | Y | Complete |  | Verify TR sequence in task list with the TR sequence provided by the process stream | 19.15 hrs | 2025-07-25 08:28 | 2025-07-29 11:37 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18197 | 2025-07-25 08:28 | 2025-07-29 11:37 | * | NA | 2025-07-25 08:28 | 2025-07-29 11:37
18199 | STRIVE.R2.MC1.2384.1.1.44.7 |  |  |  | Complete |  | Import | 45.95 hrs | 2025-07-14 08:00 | 2025-07-21 14:57 | [5 empty] | 18193 | 2025-07-14 08:00 | 2025-07-29 11:39 | * | NA | 2025-07-14 08:00 | 2025-07-21 14:57
18200 | STRIVE.R2.MC1.2384.1.1.44.7.1 | Y | Y | Y | Complete |  | Check and validate TR sequence of task list | 91.63 hrs | 2025-07-14 08:00 | 2025-07-29 11:38 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-29 11:38 | * | NA | 2025-07-14 08:00 | 2025-07-29 11:38
18201 | STRIVE.R2.MC1.2384.1.1.44.7.2 | Y | Y | Y | Complete |  | Run consistency check | 0 hrs | 2025-07-15 17:46 | 2025-07-15 17:46 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18200 | 2025-07-15 17:46 | 2025-07-15 17:46 | * | NA | 2025-07-15 17:46 | 2025-07-15 17:46
18202 | STRIVE.R2.MC1.2384.1.1.44.7.3 | Y | Y | Y | Complete |  | Check all inconsistencies cleared | 0 hrs | 2025-07-15 17:45 | 2025-07-15 17:45 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18201 | 2025-07-15 17:45 | 2025-07-15 17:45 | * | NA | 2025-07-15 17:45 | 2025-07-15 17:45
18203 | STRIVE.R2.MC1.2384.1.1.44.7.4 | Y | Y | Y | Complete |  | Trigger bulk TR import via charm | 75.65 hrs | 2025-07-16 08:00 | 2025-07-29 11:39 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18202 | 2025-07-16 08:00 | 2025-07-29 11:39 | * | NA | 2025-07-16 08:00 | 2025-07-29 11:39
18209 | STRIVE.R2.MC1.2384.1.1.44.17 |  |  |  | Complete |  | Post Import | 45.95 hrs | 2025-07-14 08:00 | 2025-07-21 14:57 | [5 empty] | 18199 | 2025-07-23 15:38 | 2025-08-04 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-21 14:57
18210 | STRIVE.R2.MC1.2384.1.1.44.17.1 | Y | Y | Y | Complete |  | Verify the TR import | 33.37 hrs | 2025-07-23 15:38 | 2025-07-29 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18203 | 2025-07-23 15:38 | 2025-07-29 17:00 | * | NA | 2025-07-23 15:38 | 2025-07-29 17:00
18211 | STRIVE.R2.MC1.2384.1.1.44.17.2 | Y | Y | Y | Complete |  | Check TR import errors&Fixes ( development , Functional , Basis) | 29.37 hrs | 2025-07-24 10:38 | 2025-07-29 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18210 | 2025-07-24 10:38 | 2025-07-29 17:00 | * | NA | 2025-07-24 10:38 | 2025-07-29 17:00
18212 | STRIVE.R2.MC1.2384.1.1.44.17.3 | Y | Y | Y | Complete |  | Resume batch jobs | 25.37 hrs | 2025-07-24 15:38 | 2025-07-29 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18211 | 2025-07-24 15:38 | 2025-07-29 17:00 | * | NA | 2025-07-24 15:38 | 2025-07-29 17:00
18213 | STRIVE.R2.MC1.2384.1.1.44.17.4 | Y | Y | Y | Complete |  | Fiori cache cleanup | 20.57 hrs | 2025-07-25 10:38 | 2025-07-29 16:12 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18212 | 2025-07-25 10:38 | 2025-07-29 16:12 | * | NA | 2025-07-25 10:38 | 2025-07-29 16:12
18214 | STRIVE.R2.MC1.2384.1.1.44.17.5 | Y | Y | Y | Complete |  | BWZ content update | 16.56 hrs | 2025-07-25 15:38 | 2025-07-29 16:12 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18213 | 2025-07-25 15:38 | 2025-07-29 16:12 | * | NA | 2025-07-25 15:38 | 2025-07-29 16:12
18215 | STRIVE.R2.MC1.2384.1.1.44.17.6 | Y | Y | Y | Complete |  | Validate SSL&SSO configuration | 20.81 hrs | 2025-07-29 16:12 | 2025-08-01 12:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Bernd Gawehn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rico.vandenberg@sasol.com; Bernd.Gawehn@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure | 18214 | 2025-07-29 16:12 | 2025-08-01 12:00 | * | NA | 2025-07-29 16:12 | 2025-08-01 12:00
18216 | STRIVE.R2.MC1.2384.1.1.44.17.7 | Y | Y | Y | Complete |  | Run consistency check for Enterprise search (SAP_ESH_CONSISTENCY_CHECK). | 0 hrs | 2025-07-25 19:34 | 2025-07-25 19:34 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18215 | 2025-07-25 19:34 | 2025-07-25 19:34 | * | NA | 2025-07-25 19:34 | 2025-07-25 19:34
18217 | STRIVE.R2.MC1.2384.1.1.44.17.8 | Y | Y | Y | Complete |  | Refresh runtime buffer for enterprise search (ESH_REFRESH_RUNTIME_BUFFER). | 0 hrs | 2025-07-25 19:34 | 2025-07-25 19:34 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18216 | 2025-07-25 19:34 | 2025-07-25 19:34 | * | NA | 2025-07-25 19:34 | 2025-07-25 19:34
18218 | STRIVE.R2.MC1.2384.1.1.44.17.9 | Y | Y | Y | Complete |  | Validate client settings | 0 hrs | 2025-07-25 19:33 | 2025-07-25 19:33 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18217 | 2025-07-25 19:33 | 2025-07-25 19:33 | * | NA | 2025-07-25 19:33 | 2025-07-25 19:33
18219 | STRIVE.R2.MC1.2384.1.1.44.17.10 | Y | Y | Y | Complete |  | Check system dumps after transport import ( SM21 , SR22) | 48 hrs | 2025-07-28 08:00 | 2025-08-04 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18218 | 2025-07-28 08:00 | 2025-08-04 17:00 | * | NA | 2025-07-28 08:00 | 2025-08-04 17:00
18220 | STRIVE.R2.MC1.2384.1.1.72 | Y | Y | Y | Complete |  | Migration Client 100(DR) is established | 22.88 hrs | 2025-08-05 08:00 | 2025-08-07 15:53 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis | 18219 | 2025-08-05 08:00 | 2025-08-07 15:53 | * | NA | 2025-08-05 08:00 | 2025-08-07 15:53
77616 | STRIVE.R2.MC1.2384.1.1.75 | Y | Y | Y | Complete |  | Share S/4 connection details to OMP team | 82.55 hrs | 2025-08-18 08:00 | 2025-08-21 18:46 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-08-18 08:00 | 2025-08-21 18:46 |  | 2025-08-18 08:00 | 2025-08-18 08:00 | 2025-08-21 18:46
77615 | STRIVE.R2.MC1.2384.1.1.74 | Y | Y | Y | Complete |  | OMP namespace program execution | 175.07 hrs | 2025-08-18 08:00 | 2025-08-25 15:33 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-08-18 08:00 | 2025-08-25 15:33 |  | 2025-08-18 08:00 | 2025-08-18 08:00 | 2025-08-25 15:33
77614 | STRIVE.R2.MC1.2384.1.1.73 | Y | Y | Y | Complete |  | Maintain OMP Gateway access entry | 175.07 hrs | 2025-08-18 08:00 | 2025-08-25 15:33 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-08-18 08:00 | 2025-08-25 15:33 |  | 2025-08-18 08:00 | 2025-08-18 08:00 | 2025-08-25 15:33
18221 | STRIVE.R2.MC1.2384.1.74 |  |  |  | Complete |  | GRC | 386.93 hrs | 2025-07-14 08:00 | 2025-07-30 12:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-30 12:00
18222 | STRIVE.R2.MC1.2384.1.74.1 |  |  |  | Complete |  | Client Open Activity | 61.93 hrs | 2025-07-14 08:00 | 2025-07-23 14:56 | [6 empty] | 2025-07-14 08:00 | 2025-08-04 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-23 14:56
18223 | STRIVE.R2.MC1.2384.1.74.1.1 | Y | Y | Y | Complete |  | Validate RFC Roles | 128 hrs | 2025-07-14 08:00 | 2025-08-04 17:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-04 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-04 17:00
18224 | STRIVE.R2.MC1.2384.1.74.1.2 |  |  |  | Complete |  | Build Workzone setup | 533.64 hrs | 2025-07-14 08:00 | 2025-10-14 14:38 | [6 empty] | 2025-07-14 08:00 | 2025-07-18 13:58 | * | NA | 2025-07-14 08:00 | 2025-10-14 14:38
18225 | STRIVE.R2.MC1.2384.1.74.1.2.1 | Y | Y | Y | Complete |  | Principal propagation setup on Build Workzone. | 15.44 hrs | 2025-07-14 08:00 | 2025-07-15 16:26 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 16:26 | * | NA | 2025-07-14 08:00 | 2025-07-15 16:26
18226 | STRIVE.R2.MC1.2384.1.74.1.2.2 | Y | Y | Y | Complete |  | Destination Setup Build Workzone. | 15.45 hrs | 2025-07-14 08:00 | 2025-07-15 16:27 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 16:27 | * | NA | 2025-07-14 08:00 | 2025-07-15 16:27
18227 | STRIVE.R2.MC1.2384.1.74.1.2.3 | Y | Y | Y | Complete |  | Build work zone Notification setup. | 29.55 hrs | 2025-07-14 08:00 | 2025-07-17 14:33 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-17 14:33 | * | NA | 2025-07-14 08:00 | 2025-07-17 14:33
18228 | STRIVE.R2.MC1.2384.1.74.1.2.4 | Y | Y | Y | Complete |  | Create sites. | 32.96 hrs | 2025-07-14 13:00 | 2025-07-18 13:58 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18227 | 2025-07-14 13:00 | 2025-07-18 13:58 | * | NA | 2025-07-14 13:00 | 2025-07-18 13:58
18230 | STRIVE.R2.MC1.2384.1.74.1.8 | Y | Y | Y | Complete |  | SMTP Configuration (Email maintenance&job scheduling) | 16 hrs | 2025-07-14 08:00 | 2025-07-15 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-15 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-15 17:00
18231 | STRIVE.R2.MC1.2384.1.74.10 |  |  |  | Complete |  | System Validation (S4, MDG, SOLMAN) | 2181.81 hrs | 2025-07-14 08:00 | 2025-10-13 11:53 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-10-13 11:53
18232 | STRIVE.R2.MC1.2384.1.74.10.1 | Y | Y | Y | Complete |  | Charm TR Validation. | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-07-14 12:00 | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18233 | STRIVE.R2.MC1.2384.1.74.10.2 | Y | Y | Y | Complete |  | RFC checks - S4. (Not relevant for MC1) | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18234 | STRIVE.R2.MC1.2384.1.74.10.3 | Y | Y | Y | Complete |  | RFC checks - MDG. (Not relevant for MC1) | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18235 | STRIVE.R2.MC1.2384.1.74.10.4 | Y | Y | Y | Complete |  | RFC checks - SolMan. (Not relevant for MC1) | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18236 | STRIVE.R2.MC1.2384.1.74.10.5 | Y | Y | Y | Complete |  | RFC checks - BTP sub account. (Not relevant for MC1) | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18237 | STRIVE.R2.MC1.2384.1.74.10.6 | Y | Y | Y | Complete |  | RFC checks - IAG. (Not relevant for MC1) | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18238 | STRIVE.R2.MC1.2384.1.74.10.7 | Y | Y | Y | Complete |  | RFC checks - SF. (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18239 | STRIVE.R2.MC1.2384.1.74.10.8 | Y | Y | Y | Complete |  | System Time Zone Validations (Including all satellite systems) (Not relevant for MC1) | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18240 | STRIVE.R2.MC1.2384.1.74.10.9 |  |  |  | Complete |  | Build Workzone setup - Validation | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-07-15 15:00 | 2025-07-15 15:01 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18241 | STRIVE.R2.MC1.2384.1.74.10.9.1 | Y | Y | Y | Complete |  | Principal propogation setup on Build Workzone- Validation. | 0 hrs | 2025-07-15 15:00 | 2025-07-15 15:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18225 | 2025-07-15 15:00 | 2025-07-15 15:00 | * | NA | 2025-07-15 15:00 | 2025-07-15 15:00
18242 | STRIVE.R2.MC1.2384.1.74.10.9.2 | Y | Y | Y | Complete |  | Destination Setup BuildWorkzone- Validation. | 0 hrs | 2025-07-15 15:00 | 2025-07-15 15:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18226 | 2025-07-15 15:00 | 2025-07-15 15:00 | * | NA | 2025-07-15 15:00 | 2025-07-15 15:00
18243 | STRIVE.R2.MC1.2384.1.74.10.9.3 | Y | Y | Y | Complete |  | Create sites- Validation. | 0 hrs | 2025-07-15 15:01 | 2025-07-15 15:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18228 | 2025-07-15 15:01 | 2025-07-15 15:01 | * | NA | 2025-07-15 15:01 | 2025-07-15 15:01
18244 | STRIVE.R2.MC1.2384.1.74.10.13 | Y | Y | Y | Complete |  | Plugins and GRC Components Install Validations (GRC). (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18245 | STRIVE.R2.MC1.2384.1.74.24 |  |  |  | Complete |  | Technical Post Installation | 2058.5 hrs | 2025-07-14 08:00 | 2025-10-08 08:14 | [5 empty] | 18231 |  |  | * | NA | 2025-07-14 08:00 | 2025-10-08 08:14
18246 | STRIVE.R2.MC1.2384.1.74.24.1 |  |  |  | Complete |  | Common Component Settings (Base Configuration) | 934.1 hrs | 2025-07-14 08:00 | 2025-08-22 08:42 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-08-22 08:42
18247 | STRIVE.R2.MC1.2384.1.74.24.1.1 | Y | Y | Y | Complete |  | Application Activation- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18248 | STRIVE.R2.MC1.2384.1.74.24.1.2 | Y | Y | Y | Complete |  | Package -Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18249 | STRIVE.R2.MC1.2384.1.74.24.1.3 | Y | Y | Y | Complete |  | ICF Service validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18250 | STRIVE.R2.MC1.2384.1.74.24.5 |  |  |  | Complete |  | BC Set Activation/Validation | 25.93 hrs | 2025-07-14 08:00 | 2025-07-15 10:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-15 10:00
18251 | STRIVE.R2.MC1.2384.1.74.24.5.1 | Y | Y | Y | Complete |  | Access Risk Analysis BC Sets (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18252 | STRIVE.R2.MC1.2384.1.74.24.5.2 | Y | Y | Y | Complete |  | Access Request Management BC Sets (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18253 | STRIVE.R2.MC1.2384.1.74.24.5.3 | Y | Y | Y | Complete |  | Business Role Management BC Sets (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18254 | STRIVE.R2.MC1.2384.1.74.24.5.4 | Y | Y | Y | Complete |  | Emergency Access Management BC Sets (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18255 | STRIVE.R2.MC1.2384.1.74.24.5.5 | Y | Y | Y | Complete |  | Workflow Configuration BC Sets (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18256 | STRIVE.R2.MC1.2384.1.74.24.11 |  |  |  | Complete |  | Automatic Workflow Customizing | 2040.2 hrs | 2025-07-14 08:00 | 2025-10-07 13:53 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-10-07 13:53
18257 | STRIVE.R2.MC1.2384.1.74.24.11.1 | Y | Y | Y | Complete |  | SAP_WFRT&Batch ID for Job scheduling (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18258 | STRIVE.R2.MC1.2384.1.74.24.13 | Y | Y | Y | Complete |  | Task Specific Customizing(Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18259 | STRIVE.R2.MC1.2384.1.74.24.14 | Y | Y | Y | Complete |  | Catalog, Space&Pages in FIORI (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18260 | STRIVE.R2.MC1.2384.1.74.24.15 | Y | Y | Y | Complete |  | Organization (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18261 | STRIVE.R2.MC1.2384.1.74.24.16 | Y | Y | Y | Complete |  | NWBC Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18262 | STRIVE.R2.MC1.2384.1.74.24.17 | Y | Y | Y | Complete |  | Fiori APP Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18263 | STRIVE.R2.MC1.2384.1.74.24.18 | Y | Y | Y | Complete |  | SPRO->MSMP ->Activate MSMP Workflow for Access Request, FF Log Function, Risk, Control Maintenance Process ID, UAR (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18264 | STRIVE.R2.MC1.2384.1.74.24.19 | Y | Y | Y | Complete |  | Validate RFC Users (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18265 | STRIVE.R2.MC1.2384.1.74.44 |  |  |  | Complete |  | Access Risk Analysis | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18266 | STRIVE.R2.MC1.2384.1.74.44.1 | Y | Y | Y | Complete |  | Upload Ruleset (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18267 | STRIVE.R2.MC1.2384.1.74.44.2 | Y | Y | Y | Complete |  | Generate Ruleset (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18268 | STRIVE.R2.MC1.2384.1.74.44.3 | Y | Y | Y | Complete |  | Validate Ruleset (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18269 | STRIVE.R2.MC1.2384.1.74.44.4 | Y | Y | Y | Complete |  | Validate Critical Roles and Profiles (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18270 | STRIVE.R2.MC1.2384.1.74.44.5 | Y | Y | Y | Complete |  | Setup Mitigation approvers in nwbc (Access control Owners) (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18271 | STRIVE.R2.MC1.2384.1.74.44.6 | Y | Y | Y | Complete |  | Create Mitigation Controls (Not relevant for MC1) | 4 hrs | 2025-07-14 12:01 | 2025-07-14 16:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18270 |  |  | * | NA | 2025-07-14 12:01 | 2025-07-14 16:01
18272 | STRIVE.R2.MC1.2384.1.74.44.7 | Y | Y | Y | Complete |  | Notification Template for Mitigation Assignments - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18273 | STRIVE.R2.MC1.2384.1.74.44.8 | Y | Y | Y | Complete |  | Maintain ARA Access Control Owners (Master Data) (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18274 | STRIVE.R2.MC1.2384.1.74.44.9 | Y | Y | Y | Complete |  | Setup Distribute Jobs for Parallel Processing-Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18275 | STRIVE.R2.MC1.2384.1.74.44.10 | Y | Y | Y | Complete |  | Access Risk Levels - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18276 | STRIVE.R2.MC1.2384.1.74.44.11 | Y | Y | Y | Complete |  | Run Authorization Sync and Repositor Sync (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18277 | STRIVE.R2.MC1.2384.1.74.44.12 | Y | Y | Y | Complete |  | Run Ad-hoc Batch Risk Analysis (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18278 | STRIVE.R2.MC1.2384.1.74.44.13 | Y | Y | Y | Complete |  | MSMP Validation- Function, Riks Maintenance (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18279 | STRIVE.R2.MC1.2384.1.74.58 |  |  |  | Complete |  | Emergency Access Management | 78.78 hrs | 2025-07-14 08:00 | 2025-07-17 15:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-17 15:00
18280 | STRIVE.R2.MC1.2384.1.74.58.1 | Y | Y | Y | Complete |  | Validate Criticality for Emergency Access Management (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18281 | STRIVE.R2.MC1.2384.1.74.58.2 | Y | Y | Y | Complete |  | Set up FF owners and controllers in nwbc (Access Control Owner) (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18282 | STRIVE.R2.MC1.2384.1.74.58.3 | Y | Y | Y | Complete |  | Import FF IDs to GRC (Sync Jobs) (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18283 | STRIVE.R2.MC1.2384.1.74.58.4 | Y | Y | Y | Complete |  | Set up Owners (Not relevant for MC1) | 4 hrs | 2025-07-14 12:01 | 2025-07-14 16:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18281,18282 |  |  | * | NA | 2025-07-14 12:01 | 2025-07-14 16:01
18284 | STRIVE.R2.MC1.2384.1.74.58.5 | Y | Y | Y | Complete |  | Set up Controllers (Not relevant for MC1) | 4 hrs | 2025-07-14 12:01 | 2025-07-14 16:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18281,18282 |  |  | * | NA | 2025-07-14 12:01 | 2025-07-14 16:01
18285 | STRIVE.R2.MC1.2384.1.74.58.6 | Y | Y | Y | Complete |  | Set up Reason Codes (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18286 | STRIVE.R2.MC1.2384.1.74.58.7 | Y | Y | Y | Complete |  | Validate all FF ids have Owner/ Controller assignments (Not relevant for MC1) | 4 hrs | 2025-07-14 16:01 | 2025-07-14 20:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18283,18284 |  |  | * | NA | 2025-07-14 16:01 | 2025-07-14 20:01
18287 | STRIVE.R2.MC1.2384.1.74.58.8 | Y | Y | Y | Complete |  | Maintain Custom Notification Messages for EAM - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18288 | STRIVE.R2.MC1.2384.1.74.58.9 | Y | Y | Y | Complete |  | Maintain Text for Custom Notification Message - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18289 | STRIVE.R2.MC1.2384.1.74.58.10 | Y | Y | Y | Complete |  | Firefighter User Exit (S4, Solman, MDG, System)- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18290 | STRIVE.R2.MC1.2384.1.74.58.11 | Y | Y | Y | Complete |  | MSMP Validation- FF log review (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18291 | STRIVE.R2.MC1.2384.1.74.58.12 | Y | Y | Y | Complete |  | Maintain Service Level Agreeements- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18292 | STRIVE.R2.MC1.2384.1.74.71 |  |  |  | Complete |  | Business Role Management | 1414.66 hrs | 2025-07-14 08:00 | 2025-09-11 10:35 | [5 empty] | 18279 |  |  | * | NA | 2025-07-14 08:00 | 2025-09-11 10:35
18293 | STRIVE.R2.MC1.2384.1.74.71.1 | Y | Y | Y | Complete |  | Maintain Project and Product Release Names - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18294 | STRIVE.R2.MC1.2384.1.74.71.2 | Y | Y | Y | Complete |  | Define Role Sensitivity - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18295 | STRIVE.R2.MC1.2384.1.74.71.3 | Y | Y | Y | Complete |  | Maintain Role Status - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18296 | STRIVE.R2.MC1.2384.1.74.71.4 | Y | Y | Y | Complete |  | Specify Critical Level - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18297 | STRIVE.R2.MC1.2384.1.74.71.5 | Y | Y | Y | Complete |  | Business Process&Sub Process- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18298 | STRIVE.R2.MC1.2384.1.74.71.6 | Y | Y | Y | Complete |  | Generate BRF plus Application, Approvers and Methodology Functions - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18299 | STRIVE.R2.MC1.2384.1.74.71.7 | Y | Y | Y | Complete |  | Define Methodology Process and Steps - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18300 | STRIVE.R2.MC1.2384.1.74.71.8 | Y | Y | Y | Complete |  | Associate Methodology Process and Steps - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18301 | STRIVE.R2.MC1.2384.1.74.71.9 | Y | Y | Y | Complete |  | Setup Role Owners in nwbc (Access Control Owner) (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18302 | STRIVE.R2.MC1.2384.1.74.71.10 | Y | Y | Y | Complete |  | Upload Single/Master/Derived roles to GRC (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18303 | STRIVE.R2.MC1.2384.1.74.71.11 | Y | Y | Y | Complete |  | Upload Composite Roles to GRC (Not relevant for MC1) | 4 hrs | 2025-07-14 12:01 | 2025-07-14 16:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18302 |  |  | * | NA | 2025-07-14 12:01 | 2025-07-14 16:01
18304 | STRIVE.R2.MC1.2384.1.74.71.12 | Y | Y | Y | Complete |  | Upload Business Roles to GRC (Not relevant for MC1) | 4 hrs | 2025-07-14 16:01 | 2025-07-14 20:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18302,18303 |  |  | * | NA | 2025-07-14 16:01 | 2025-07-14 20:01
18305 | STRIVE.R2.MC1.2384.1.74.71.13 | Y | Y | Y | Complete |  | Validate Business roles and its components (Not relevant for MC1) | 4 hrs | 2025-07-14 20:01 | 2025-07-15 00:03 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18304 |  |  | * | NA | 2025-07-14 20:01 | 2025-07-15 00:03
18306 | STRIVE.R2.MC1.2384.1.74.85 |  |  |  | Complete |  | Access Request Management | 747.28 hrs | 2025-07-14 08:00 | 2025-08-14 13:22 | [5 empty] | 18292 | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-08-14 13:22
18307 | STRIVE.R2.MC1.2384.1.74.85.1 | Y | Y | Y | Complete |  | SFEC Setup- Validation (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18308 | STRIVE.R2.MC1.2384.1.74.85.2 | Y | Y | Y | Complete |  | Define Request Type- Validation (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18309 | STRIVE.R2.MC1.2384.1.74.85.3 | Y | Y | Y | Complete |  | Maintain Priority Configurations- Validation (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18310 | STRIVE.R2.MC1.2384.1.74.85.4 | Y | Y | Y | Complete |  | Maintain End User Personalization- Validation (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18311 | STRIVE.R2.MC1.2384.1.74.85.5 | Y | Y | Y | Complete |  | Role Search Criteria- Validation (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18312 | STRIVE.R2.MC1.2384.1.74.85.6 | Y | Y | Y | Complete |  | Maintain Provisioning Settings (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18313 | STRIVE.R2.MC1.2384.1.74.85.7 | Y | Y | Y | Complete |  | Global Provisioning Settings- Validation (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18314 | STRIVE.R2.MC1.2384.1.74.85.8 | Y | Y | Y | Complete |  | Maintain AC Application and BRF Plus Function Mapping- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18315 | STRIVE.R2.MC1.2384.1.74.85.9 | Y | Y | Y | Complete |  | Decision Tables (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18316 | STRIVE.R2.MC1.2384.1.74.85.10 | Y | Y | Y | Complete |  | ARM MSMP-Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18317 | STRIVE.R2.MC1.2384.1.74.85.11 | Y | Y | Y | Complete |  | Maintain Service Level Agreements- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18318 | STRIVE.R2.MC1.2384.1.74.85.12 | Y | Y | Y | Complete |  | Maintain Custom Notification Messages for ARM - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18319 | STRIVE.R2.MC1.2384.1.74.85.13 | Y | Y | Y | Complete |  | Maintain Text for Custom Notification Message for ARM - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18320 | STRIVE.R2.MC1.2384.1.74.85.14 | Y | Y | Y | Complete |  | User group Creation - SUGR | 16 hrs | 2025-07-14 08:00 | 2025-07-15 17:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-07-15 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-15 17:00
18321 | STRIVE.R2.MC1.2384.1.74.100 |  |  |  | Complete |  | User Access Review (UAR) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18322 | STRIVE.R2.MC1.2384.1.74.100.1 | Y | Y | Y | Complete |  | Request Type- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18323 | STRIVE.R2.MC1.2384.1.74.100.2 | Y | Y | Y | Complete |  | Maintain Priority- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18324 | STRIVE.R2.MC1.2384.1.74.100.3 | Y | Y | Y | Complete |  | Maintain Configuration Settings- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18325 | STRIVE.R2.MC1.2384.1.74.100.4 | Y | Y | Y | Complete |  | Maintain Review Rejection Reasons- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18326 | STRIVE.R2.MC1.2384.1.74.100.5 | Y | Y | Y | Complete |  | Maintain Service LevelAgreements- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18327 | STRIVE.R2.MC1.2384.1.74.100.6 | Y | Y | Y | Complete |  | UAR MSMP- Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18328 | STRIVE.R2.MC1.2384.1.74.100.7 | Y | Y | Y | Complete |  | Manage Coordinators - Setup (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18329 | STRIVE.R2.MC1.2384.1.74.100.8 | Y | Y | Y | Complete |  | Maintain Custom Notification Messages for UAR - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18330 | STRIVE.R2.MC1.2384.1.74.100.9 | Y | Y | Y | Complete |  | Maintain Text for Custom Notification Message for UAR - Validation (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18331 | STRIVE.R2.MC1.2384.1.74.110 |  |  |  | Complete |  | GRC AC Batch Jobs - Setup | 0.25 hrs | 2025-07-14 08:00 | 2025-07-14 08:15 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-14 08:15
18332 | STRIVE.R2.MC1.2384.1.74.110.1 | Y | Y | Y | Complete |  | PFCG Authorization Data Synchronization (S4, MDG, Solman, SF) (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18333 | STRIVE.R2.MC1.2384.1.74.110.2 | Y | Y | Y | Complete |  | Repository Object Synchronization (S4, MDG, Solman, SF, IAG) (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18334 | STRIVE.R2.MC1.2384.1.74.110.3 | Y | Y | Y | Complete |  | Action Usage Synchronization (S4, MDG, Solman) (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18335 | STRIVE.R2.MC1.2384.1.74.110.4 | Y | Y | Y | Complete |  | Role Usage Synchronization (S4, MDG, Solman) (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18336 | STRIVE.R2.MC1.2384.1.74.110.5 | Y | Y | Y | Complete |  | Batch Risk Analysis (S4, MDG, Solman) (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18337 | STRIVE.R2.MC1.2384.1.74.110.6 | Y | Y | Y | Complete |  | Firefighter Log Sync (S4, MDG, Solman) (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18338 | STRIVE.R2.MC1.2384.1.74.110.7 | Y | Y | Y | Complete |  | Firefighter Workflow Sync (S4, MDG, Solman) (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18339 | STRIVE.R2.MC1.2384.1.74.110.8 | Y | Y | Y | Complete |  | EAM Master Data Sync (S4, MDG, Solman) (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18340 | STRIVE.R2.MC1.2384.1.74.110.9 | Y | Y | Y | Complete |  | Email Reminder (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18341 | STRIVE.R2.MC1.2384.1.74.110.10 | Y | Y | Y | Complete |  | Stale Requests (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18342 | STRIVE.R2.MC1.2384.1.74.110.11 | Y | Y | Y | Complete |  | Delete Report Spool (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18343 | STRIVE.R2.MC1.2384.1.74.110.12 | Y | Y | Y | Complete |  | Delete Violation Data (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18344 | STRIVE.R2.MC1.2384.1.74.123 |  |  |  | Complete |  | SFEC to GRC HR Trigger Configuration | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18345 | STRIVE.R2.MC1.2384.1.74.123.1 | Y | Y | Y | Complete |  | Maintain SPRO Parameter for detailed SFEC log (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18346 | STRIVE.R2.MC1.2384.1.74.123.2 | Y | Y | Y | Complete |  | Maintain Connectors for Termination Request Type (Not relevant for MC1) | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18347 | STRIVE.R2.MC1.2384.1.74.123.3 | Y | Y | Y | Complete |  | provide the GRC(username&password) and successfactors(username & password) credentials to the integration team(GRC_I_001) (Not relevant for MC1) | 4 hrs | 2025-07-14 12:01 | 2025-07-14 16:01 | Jayasurya | jayasur@deloitte.com | Sasol GRC; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Naga; ; Pragyesh; Aman Anand | dttsasolsecuritygrcteam@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; nnagasubbareddy@deloitte.com; ; pkumargoyal@deloitte.com; amananand2@deloitte.com | GRC | 18346 |  |  | * | NA | 2025-07-14 12:01 | 2025-07-14 16:01
18354 | STRIVE.R2.MC1.2384.1.74.133 |  |  |  | Complete |  | IAG integration with BTP Sub Account | 1 hrs | 2025-07-14 08:00 | 2025-07-14 09:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-14 09:00
18355 | STRIVE.R2.MC1.2384.1.74.133.1 | Y | Y | Y | Complete |  | Add BTP sub account in the application app of IAG (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18356 | STRIVE.R2.MC1.2384.1.74.133.2 | Y | Y | Y | Complete |  | Sync data from BTP sub account to IAG (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18357 | STRIVE.R2.MC1.2384.1.74.136 |  |  |  | Complete |  | IAG integration with GRC | 0.5 hrs | 2025-07-14 08:00 | 2025-07-14 08:30 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-14 08:30
18358 | STRIVE.R2.MC1.2384.1.74.136.1 | Y | Y | Y | Complete |  | Configure Parameters for Cloud Integration (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18359 | STRIVE.R2.MC1.2384.1.74.136.2 | Y | Y | Y | Complete |  | Create Connector and Connector groups for cloud application (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18360 | STRIVE.R2.MC1.2384.1.74.136.3 | Y | Y | Y | Complete |  | Sync data from IAG to GRC--GRC (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18361 | STRIVE.R2.MC1.2384.1.74.136.4 | Y | Y | Y | Complete |  | Sync data from GRC to IAG--GRC (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18362 | STRIVE.R2.MC1.2384.1.74.141 |  |  |  | Complete |  | Business User load | 72.75 hrs | 2025-07-14 08:00 | 2025-07-17 08:57 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-17 08:57
18363 | STRIVE.R2.MC1.2384.1.74.141.1 | Y | Y | Y | Complete |  | Loading all the Business users (Not relevant for MC1) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18364 | STRIVE.R2.MC1.2384.1.74.141.2 | Y | Y | Y | Complete |  | Validating the users (Not relevant for MC1) | 2 hrs | 2025-07-14 10:00 | 2025-07-14 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18363 |  |  | * | NA | 2025-07-14 10:00 | 2025-07-14 12:00
18365 | STRIVE.R2.MC1.2384.1.218 |  |  |  | Complete |  | Security | 193.6 hrs | 2025-07-14 08:00 | 2025-08-15 09:36 | [6 empty] | 2025-07-14 08:00 | 2025-08-04 12:00 | * | NA | 2025-07-14 08:00 | 2025-08-15 09:36
18366 | STRIVE.R2.MC1.2384.1.218.1 | Y | Y | Y | Complete |  | Validate Secure Super Users in S4&MDG | 36.99 hrs | 2025-07-14 08:00 | 2025-07-18 13:59 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 13:59 | * | NA | 2025-07-14 08:00 | 2025-07-18 13:59
18367 | STRIVE.R2.MC1.2384.1.218.2 | Y | Y | Y | Complete |  | System Accounts /RFC Accounts Set-up in S/4&MDG | 37 hrs | 2025-07-14 08:00 | 2025-07-18 14:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 14:00 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:00
18368 | STRIVE.R2.MC1.2384.1.218.3 | Y | Y | Y | Complete |  | Perform SU25 - Profile Generator in S/4&MDG: Upgrade&First Installation as necessary | 16 hrs | 2025-07-14 08:00 | 2025-07-15 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-15 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-15 17:00
18369 | STRIVE.R2.MC1.2384.1.218.4 | Y | Y | Y | Complete |  | Define Security Background Jobs in S/4&MDG | 37 hrs | 2025-07-14 08:00 | 2025-07-18 14:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 14:00 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:00
18370 | STRIVE.R2.MC1.2384.1.218.5 | Y | Y | Y | Complete |  | Update USR40 table in S/4&MDG | 38.8 hrs | 2025-07-14 08:00 | 2025-07-18 15:48 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 15:48 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:48
18371 | STRIVE.R2.MC1.2384.1.218.6 | Y | Y | Y | Complete |  | Validate Security system parameters in S/4&MDG | 24 hrs | 2025-07-14 08:00 | 2025-07-16 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-16 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-16 17:00
18372 | STRIVE.R2.MC1.2384.1.218.7 | Y | Y | Y | Complete |  | Validate Business Role to Task Role mapping in S/4&MDG | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-14 10:00 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18373 | STRIVE.R2.MC1.2384.1.218.8 | Y | Y | Y | Complete |  | Validate Task Role to Org value in S/4&MDG | 36.03 hrs | 2025-07-14 08:00 | 2025-07-18 13:02 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 13:02 | * | NA | 2025-07-14 08:00 | 2025-07-18 13:02
18374 | STRIVE.R2.MC1.2384.1.218.9 | Y | Y | Y | Complete |  | Validate Auth objects status as per the agreed design in S/4&MDG | 38.79 hrs | 2025-07-14 08:00 | 2025-07-18 15:48 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 15:48 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:48
18375 | STRIVE.R2.MC1.2384.1.218.10 | Y | Y | Y | Complete |  | Validate Maintain access in Disp role - Disp role should not have maintain access in S/4&MDG | 38.78 hrs | 2025-07-14 08:00 | 2025-07-18 15:47 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 15:47 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:47
18376 | STRIVE.R2.MC1.2384.1.218.11 | Y | Y | Y | Complete |  | Validate Profile Generation Status in S/4&MDG - AGR_TIMEB should match for the roles also profile should be in green | 38.81 hrs | 2025-07-14 08:00 | 2025-07-18 15:48 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 15:48 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:48
18377 | STRIVE.R2.MC1.2384.1.218.12 | Y | Y | Y | Complete |  | Validate tables - AGR_1251, AGR_1252, USOBT_C, USOBX_C, AGR_TIMEB, /UI2/FLC (for Fiori), for post transport import validations in S/4&MDG | 38.8 hrs | 2025-07-14 08:00 | 2025-07-18 15:48 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-18 15:48 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:48
18378 | STRIVE.R2.MC1.2384.1.218.13 | Y | Y | Y | Complete |  | Validate security roles ( Cutover / FF / IT / System ID roles / Business Roles ) if roles are moved accurately without any issues in S/4&MDG | 16 hrs | 2025-07-14 08:00 | 2025-07-15 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-15 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-15 17:00
18379 | STRIVE.R2.MC1.2384.1.218.14 | Y | Y | Y | Complete |  | Enable SM19 logs with the filters on S/4&MDG - Static parameter needs to have a restart of system confirm with basis | 24 hrs | 2025-07-14 08:00 | 2025-07-16 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-16 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-16 17:00
18380 | STRIVE.R2.MC1.2384.1.218.15 | Y | Y | Y | Complete |  | Create the User Groups in S/4&MDG | 16 hrs | 2025-07-14 08:00 | 2025-07-15 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-15 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-15 17:00
18381 | STRIVE.R2.MC1.2384.1.218.16 | Y | Y | Y | Complete |  | Create / Validate the System IDs and communicate the password to Basis team in S/4&MDG | 8.17 hrs | 2025-07-18 14:00 | 2025-07-21 14:11 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18367 | 2025-07-18 14:00 | 2025-07-21 14:11 | * | NA | 2025-07-18 14:00 | 2025-07-21 14:11
18382 | STRIVE.R2.MC1.2384.1.218.17 | Y | Y | Y | Complete |  | Maintain User Parameter EVO = 01 for Integration Suite user(N_R_INTSUITE) in S4 environment | 20.62 hrs | 2025-07-21 14:11 | 2025-07-24 09:48 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; | Security | 18381 | 2025-07-21 14:11 | 2025-07-24 09:48 | * | NA | 2025-07-21 14:11 | 2025-07-24 09:48
18383 | STRIVE.R2.MC1.2384.1.218.18 | Y | Y | Y | Complete |  | Create Cutover and Validation User IDs / assign cutover roles based on RITM approvals on S/4&MDG | 47.66 hrs | 2025-07-16 08:00 | 2025-07-23 16:40 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18378 | 2025-07-16 08:00 | 2025-07-23 16:40 | * | NA | 2025-07-16 08:00 | 2025-07-23 16:40
18384 | STRIVE.R2.MC1.2384.1.218.19 | Y | Y | Y | Complete |  | Communicate login credentials for cutover IDs via email for S/4 | 75.07 hrs | 2025-07-16 10:00 | 2025-07-29 14:04 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18383 | 2025-07-16 10:00 | 2025-07-29 14:04 | * | NA | 2025-07-16 10:00 | 2025-07-29 14:04
18385 | STRIVE.R2.MC1.2384.1.218.20 | Y | Y | Y | Complete |  | Communicate login credentials for cutover IDs via email for MDG | 75.07 hrs | 2025-07-16 10:00 | 2025-07-29 14:04 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18383 | 2025-07-16 10:00 | 2025-07-29 14:04 | * | NA | 2025-07-16 10:00 | 2025-07-29 14:04
18386 | STRIVE.R2.MC1.2384.1.218.21 | Y | Y | Y | Complete |  | Mass creation of Business Users / IT based on Business role mappings provided by OCM team in S/4&MDG | 65.82 hrs | 2025-07-14 08:00 | 2025-07-24 09:49 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-07-24 09:49 | * | NA | 2025-07-14 08:00 | 2025-07-24 09:49
18387 | STRIVE.R2.MC1.2384.1.218.22 | Y | Y | Y | Complete |  | Add SNC parmater to all the users for SSO login in S/4&MDG | 8.18 hrs | 2025-07-18 14:00 | 2025-07-21 14:11 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18369 | 2025-07-18 14:00 | 2025-07-21 14:11 | * | NA | 2025-07-18 14:00 | 2025-07-21 14:11
18388 | STRIVE.R2.MC1.2384.1.218.23 | Y | Y | Y | Complete |  | Assign user parameters via SU10 and validate security related system parameter settings in S/4&MDG | 77.66 hrs | 2025-07-14 10:00 | 2025-07-25 16:40 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18386 | 2025-07-14 10:00 | 2025-07-25 16:40 | * | NA | 2025-07-14 10:00 | 2025-07-25 16:40
18389 | STRIVE.R2.MC1.2384.1.218.24 | Y | Y | Y | Complete |  | Communicate login credentials for end users via email ( a day before go-live) | 39.9 hrs | 2025-07-25 16:40 | 2025-08-01 16:34 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18388 | 2025-07-25 16:40 | 2025-08-01 16:34 | * | NA | 2025-07-25 16:40 | 2025-08-01 16:34
18390 | STRIVE.R2.MC1.2384.1.218.25 | Y | Y | Y | Complete |  | Run PFUD in S/4&MDG | 8.19 hrs | 2025-07-18 14:00 | 2025-07-21 14:11 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18369 | 2025-07-18 14:00 | 2025-07-21 14:11 | * | NA | 2025-07-18 14:00 | 2025-07-21 14:11
18391 | STRIVE.R2.MC1.2384.1.218.26 | Y | Y | Y | Complete |  | Fiori APP Validation for EPPM | 124 hrs | 2025-07-14 08:00 | 2025-08-04 12:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-08-04 12:00 | * | NA | 2025-07-14 08:00 | 2025-08-04 12:00
18392 | STRIVE.R2.MC1.2384.1.245 | [5 empty] | Transport Validation in S/4HANA | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | [5 empty] | 18384 | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18393 | STRIVE.R2.MC1.2384.1.245.1 | Y | Y | Y | Complete |  | Transport Validation - R2P in S/4HANA | 15.29 hrs | 2025-07-28 13:43 | 2025-07-30 12:00 | Amit das | amitdas3@deloitte.com | Claudiu; Aniket Kulkarni; Pamela Mihali; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande | cljipa@deloitte.de; anikulkarni@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P | 18195 | 2025-07-28 13:43 | 2025-07-30 12:00 | * | NA | 2025-07-28 13:43 | 2025-07-30 12:00
18394 | STRIVE.R2.MC1.2384.1.245.2 | Y | Y | Y | Complete |  | Transport Validation - S2P in S/4HANA | 4 hrs | 2025-07-28 13:43 | 2025-07-28 17:43 | Prasanth Kallakuri | kalprasanth@deloitte.com | Sandeep Galhotra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | sagalhotra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 18195 |  |  | * | NA | 2025-07-28 13:43 | 2025-07-28 17:43
18395 | STRIVE.R2.MC1.2384.1.245.3 | Y | Y | Y | Complete |  | Transport Validation - P2C in S/4HANA | 96 hrs | 2025-07-14 08:00 | 2025-07-29 17:00 | Vaishali Singh | vaishsingh@deloitte.com | Shubham Mishra; Diego Zarate; Malta; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; mawilhelm@deloitte.de; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 18195 | 2025-07-14 08:00 | 2025-07-29 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-29 17:00
18396 | STRIVE.R2.MC1.2384.1.245.4 | Y | Y | Y | Complete |  | Transport Validation - R2D in S/4HANA | 3.67 hrs | 2025-07-29 11:28 | 2025-07-29 16:08 | Roshanlal Hemwani | rohemwani@deloitte.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Daniel Lohmann; | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dlohmann@deloitte.de; | R2D | 18195 | 2025-07-29 11:28 | 2025-07-29 16:08 | * | NA | 2025-07-29 11:28 | 2025-07-29 16:08
18397 | STRIVE.R2.MC1.2384.1.245.5 | Y | Y | Y | Complete |  | Transport Validation - MOR - PM in S/4HANA | 4 hrs | 2025-07-29 14:31 | 2025-07-29 18:31 | Vinod Kumar | vinodkumar692@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 18195 | 2025-07-29 14:31 |  | * | NA | 2025-07-29 14:31 | 2025-07-29 18:31
95106 | STRIVE.R2.MC1.2384.1.245.12 | N | N | N | Ready |  | Transport Validation - MOR - PS in S/4HANA | 4 hrs | 2025-07-28 13:43 | 2025-07-28 17:43 | Krishna Teja | krishn@deloitte.com | Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 18195 |  |  | * | NA | 2025-07-28 13:43 | 2025-07-28 17:43
95105 | STRIVE.R2.MC1.2384.1.245.11 | N | N | N | Ready |  | Transport Validation - MOR - PPM in S/4HANA | 4 hrs | 2025-07-28 13:43 | 2025-07-28 17:43 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod Kumar; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 18195 |  |  | * | NA | 2025-07-28 13:43 | 2025-07-28 17:43
18398 | STRIVE.R2.MC1.2384.1.245.6 | Y | Y | Y | Complete |  | PRE TR IMPORT FGL_MIG_REGENERATE_CDS_BCF (With Checkbox: Reset to Delivery) | 4 hrs | 2025-07-28 13:43 | 2025-07-28 17:43 | Ashish patil | ashishspatil@deloitte.com | Shivraj; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | shivrsinha@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | ABAP | 18195 |  |  | * | NA | 2025-07-28 13:43 | 2025-07-28 17:43
18399 | STRIVE.R2.MC1.2384.1.245.7 | Y | Y | Y | Complete |  | Transport Validation - ABAP in S/4HANA | 4 hrs | 2025-07-28 17:43 | 2025-07-28 21:43 | Ashish patil | ashishspatil@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale; Gurmandeep Singh | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com; gurmandsingh@deloitte.com | ABAP | 18398 |  |  | * | NA | 2025-07-28 17:43 | 2025-07-28 21:43
18400 | STRIVE.R2.MC1.2384.1.245.8 | Y | Y | Y | Complete |  | Transport Validation - Data in S/4HANA | 4 hrs | 2025-07-28 13:43 | 2025-07-28 17:43 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar | roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com | DM | 18195 |  |  | * | NA | 2025-07-28 13:43 | 2025-07-28 17:43
18401 | STRIVE.R2.MC1.2384.1.245.9 | Y | Y | Y | Complete |  | Transport Validation - Security/GRC in S/4HANA | 59.29 hrs | 2025-07-28 13:43 | 2025-08-06 17:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Shubhathakur@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18195 | 2025-07-28 13:43 | 2025-08-06 17:00 | * | NA | 2025-07-28 13:43 | 2025-08-06 17:00
18402 | STRIVE.R2.MC1.2384.1.245.10 | Y | Y | Y | Complete |  | S4: Validate MDG related Transport Requests in S/4HANA | 0 hrs | 2025-08-01 12:30 | 2025-08-01 12:30 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18195 | 2025-08-01 12:30 | 2025-08-01 12:30 | * | NA | 2025-08-01 12:30 | 2025-08-01 12:30
18403 | STRIVE.R2.MC1.2384.1.256 |  |  |  | Complete |  | Transport Validation in MDG | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | [5 empty] | 18385 | 2025-07-28 13:43 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18404 | STRIVE.R2.MC1.2384.1.256.1 | Y | Y | Y | Complete |  | Transport Validation - R2P in MDG | 15.29 hrs | 2025-07-28 13:43 | 2025-07-30 12:00 | Amit das | amitdas3@deloitte.com | Claudiu; Pamela Mihali; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande; Aniket Kulkarni | cljipa@deloitte.de; pamihali@deloitte.de; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; anikulkarni@deloitte.com | R2P | 18195 | 2025-07-28 13:43 | 2025-07-30 12:00 | * | NA | 2025-07-28 13:43 | 2025-07-30 12:00
18405 | STRIVE.R2.MC1.2384.1.256.2 | Y | Y | Y | Complete |  | Transport Validation - S2P in MDG | 4 hrs | 2025-07-28 13:43 | 2025-07-28 17:43 | Prasanth Kallakuri | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sandeep Galhotra; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sagalhotra@deloitte.com; usisasols2p@deloitte.com | S2P | 18195 |  |  | * | NA | 2025-07-28 13:43 | 2025-07-28 17:43
18406 | STRIVE.R2.MC1.2384.1.256.3 | Y | Y | Y | Complete |  | Transport Validation - P2C in MDG | 0.14 hrs | 2025-07-29 16:10 | 2025-07-29 16:19 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Malta; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ramesh SathishKumar | dzarate@deloitte.com; mawilhelm@deloitte.de; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; satramesh@deloitte.com | P2C | 18195 | 2025-07-29 16:10 | 2025-07-29 16:19 | * | NA | 2025-07-29 16:10 | 2025-07-29 16:19
18407 | STRIVE.R2.MC1.2384.1.256.4 | Y | Y | Y | Complete |  | Transport Validation - R2D in MDG | 3.28 hrs | 2025-07-29 11:52 | 2025-07-29 16:09 | Roshanlal Hemwani | rohemwani@deloitte.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Daniel Lohmann; | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dlohmann@deloitte.de; | R2D | 18195 | 2025-07-29 11:52 | 2025-07-29 16:09 | * | NA | 2025-07-29 11:52 | 2025-07-29 16:09
18408 | STRIVE.R2.MC1.2384.1.256.5 | Y | Y | Y | Complete |  | Transport Validation - Data in MDG | 4 hrs | 2025-07-28 13:43 | 2025-07-28 17:43 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar | roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com | DM | 18195 |  |  | * | NA | 2025-07-28 13:43 | 2025-07-28 17:43
18409 | STRIVE.R2.MC1.2384.1.256.6 | Y | Y | Y | Complete |  | Transport Validation - Security/GRC in MDG | 59.29 hrs | 2025-07-28 13:43 | 2025-08-06 17:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Shubhathakur@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security | 18195 | 2025-07-28 13:43 | 2025-08-06 17:00 | * | NA | 2025-07-28 13:43 | 2025-08-06 17:00
18410 | STRIVE.R2.MC1.2384.1.256.7 | Y | Y | Y | Complete |  | MDG: Validate MDG related Transport Requests in MDG | 0 hrs | 2025-08-01 12:30 | 2025-08-01 12:30 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18195 | 2025-08-01 12:30 | 2025-08-01 12:30 | * | NA | 2025-08-01 12:30 | 2025-08-01 12:30
18411 | STRIVE.R2.MC1.2384.1.264 |  |  |  | Complete |  | MOR- EPPM Master Data | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-08-08 13:04 | 2025-08-29 20:48 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18412 | STRIVE.R2.MC1.2384.1.264.1 | Y | Y | Y | Complete |  | Update Portfolio Structure for Chemicals North hemisphere | 0.46 hrs | 2025-08-08 13:04 | 2025-08-08 13:32 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18391,18397 | 2025-08-08 13:04 | 2025-08-08 13:32 | * | NA | 2025-08-08 13:04 | 2025-08-08 13:32
18413 | STRIVE.R2.MC1.2384.1.264.2 | Y | Y | Y | Complete |  | Create Portfolio Structure for Maintenance portfolio | 289.12 hrs | 2025-08-14 13:32 | 2025-08-26 15:27 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18412 | 2025-08-14 13:32 | 2025-08-26 15:27 |  | 2025-08-14 13:32 | 2025-08-14 13:32 | 2025-08-26 15:27
18414 | STRIVE.R2.MC1.2384.1.264.3 | Y | Y | Y | Complete |  | Upload Checklist templates | 46.62 hrs | 2025-08-26 15:27 | 2025-08-28 14:12 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18413 | 2025-08-26 15:27 | 2025-08-28 14:12 |  | 2025-08-20 17:32 | 2025-08-26 15:27 | 2025-08-28 14:12
18415 | STRIVE.R2.MC1.2384.1.264.4 | Y | Y | Y | Complete |  | Upload Project templates | 30.31 hrs | 2025-08-28 14:12 | 2025-08-29 20:35 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18414 | 2025-08-28 14:12 | 2025-08-29 20:35 | * | NA | 2025-08-28 14:12 | 2025-08-29 20:35
18416 | STRIVE.R2.MC1.2384.1.264.5 | Y | Y | Y | Complete |  | Create NON-MOR PS operative projects with respective project profiles | 26.52 hrs | 2025-08-28 18:12 | 2025-08-29 20:48 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18415 | 2025-08-28 18:12 | 2025-08-29 20:48 | * | NA | 2025-08-28 18:12 | 2025-08-29 20:48
18417 | STRIVE.R2.MC1.2384.1.270 | [5 empty] | Client Open Activities | 24.91 hrs | 2025-07-14 08:00 | 2025-07-15 08:59 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-15 08:59 |  |  |  | 18392, 18403 should be completed to start with Open Client
18418 | STRIVE.R2.MC1.2384.1.270.1 |  |  |  | Complete |  | R2D | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18419 | STRIVE.R2.MC1.2384.1.270.1.1 | Y | Y | Y | Complete |  | Generate susbtitution RGUGBR00 | 12.85 hrs | 2025-07-29 16:09 | 2025-07-31 12:00 | Jitender Chhabra | jkchhabra.ext@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alexandra Ruff; Daniel Lohmann | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; aruff@deloitte.de; dlohmann@deloitte.de | R2D | 18396,18407 | 2025-07-29 16:09 | 2025-07-31 12:00 | * | NA | 2025-07-29 16:09 | 2025-07-31 12:00
18420 | STRIVE.R2.MC1.2384.1.270.1.2 | Y | Y | Y | Complete |  | OMSY Update - Production S/4HANA | 12.85 hrs | 2025-07-29 16:09 | 2025-07-31 12:00 | Jitender Chhabra | jkchhabra.ext@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alexandra Ruff; Daniel Lohmann | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; aruff@deloitte.de; dlohmann@deloitte.de | R2D | 18396,18407 | 2025-07-29 16:09 | 2025-07-31 12:00 | * | NA | 2025-07-29 16:09 | 2025-07-31 12:00
18421 | STRIVE.R2.MC1.2384.1.270.1.3 | Y | Y | Y | Complete |  | OMSY Update - Production MDG | 12.85 hrs | 2025-07-29 16:09 | 2025-07-31 12:00 | Jitender Chhabra | jkchhabra.ext@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alexandra Ruff; Daniel Lohmann | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; aruff@deloitte.de; dlohmann@deloitte.de | R2D | 18407,18396 | 2025-07-29 16:09 | 2025-07-31 12:00 | * | NA | 2025-07-29 16:09 | 2025-07-31 12:00
18422 | STRIVE.R2.MC1.2384.1.270.1.4 | Y | Y | Y | Complete |  | Chart of accounts upload | 0 hrs | 2025-07-31 12:23 | 2025-07-31 12:23 | Mohamed Ibrahim | mibrahimjs@deloitte.com | Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D | 18396,18407 | 2025-07-31 12:23 | 2025-07-31 12:23 | * | NA | 2025-07-31 12:23 | 2025-07-31 12:23
18423 | STRIVE.R2.MC1.2384.1.270.1.5 | Y | Y | Y | Complete |  | Create cost element groups - Not Open Client, Not relevant for MC 1 | 2 hrs | 2025-07-29 16:09 | 2025-07-29 18:09 | Sandeep (R2D) | ssandeep4@deloitte.com | Alexandra Ruff; ; Roshan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | aruff@deloitte.de; ; rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D | 18396,18407 |  |  | * | NA | 2025-07-29 16:09 | 2025-07-29 18:09 |  |  |  | Jitender C : Not open client activity, Not relevant for MC1
18424 | STRIVE.R2.MC1.2384.1.270.1.6 | Y | Y | Y | Complete |  | Number range for change requests | 0 hrs | 2025-07-31 15:29 | 2025-07-31 15:29 | Nirali Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D | 18396,18407 | 2025-07-31 15:29 | 2025-07-31 15:29 | * | NA | 2025-07-31 15:29 | 2025-07-31 15:29
18425 | STRIVE.R2.MC1.2384.1.270.1.7 | Y | Y | Y | Complete |  | Create Bank Master for Sasol Banks | 0.06 hrs | 2025-07-31 13:29 | 2025-07-31 13:33 | Nirali Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D | 18555,18396,18407 | 2025-07-31 13:29 | 2025-07-31 13:33 | * | NA | 2025-07-31 13:29 | 2025-07-31 13:33
18426 | STRIVE.R2.MC1.2384.1.270.1.8 | Y | Y | Y | Complete |  | House Bank Updates- Production S/4HANA | 16.85 hrs | 2025-07-29 16:09 | 2025-07-31 17:00 | Nirali Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D | 18396,18407 | 2025-07-29 16:09 | 2025-07-31 17:00 | * | NA | 2025-07-29 16:09 | 2025-07-31 17:00
18427 | STRIVE.R2.MC1.2384.1.270.1.9 | Y | Y | Y | Complete |  | House Bank Updates- Production MDG | 0.24 hrs | 2025-07-31 15:08 | 2025-07-31 15:22 | Nirali Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D | 18407,18396 | 2025-07-31 15:08 | 2025-07-31 15:22 | * | NA | 2025-07-31 15:08 | 2025-07-31 15:22
18428 | STRIVE.R2.MC1.2384.1.270.1.10 | Y | Y | Y | Complete |  | ML Activation- Production S/4HANA | 12.85 hrs | 2025-07-29 16:09 | 2025-07-31 12:00 | Jitender Chhabra | jkchhabra.ext@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alexandra Ruff; Daniel Lohmann | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; aruff@deloitte.de; dlohmann@deloitte.de | R2D | 18396,18407 | 2025-07-29 16:09 | 2025-07-31 12:00 | * | NA | 2025-07-29 16:09 | 2025-07-31 12:00
18429 | STRIVE.R2.MC1.2384.1.270.1.11 | Y | Y | Y | Complete |  | ML Activation- Production MDG | 12.85 hrs | 2025-07-29 16:09 | 2025-07-31 12:00 | Jitender Chhabra | jkchhabra.ext@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alexandra Ruff; Daniel Lohmann | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; aruff@deloitte.de; dlohmann@deloitte.de | R2D | 18407,18396 | 2025-07-29 16:09 | 2025-07-31 12:00 | * | NA | 2025-07-29 16:09 | 2025-07-31 12:00
18430 | STRIVE.R2.MC1.2384.1.270.1.12 | Y | Y | Y | Complete |  | Posting period Update under OB52 in S/4HANA | 0 hrs | 2025-07-31 12:14 | 2025-07-31 12:14 | Mohamed Ibrahim | mibrahimjs@deloitte.com | Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D | 18396,18407 | 2025-07-31 12:14 | 2025-07-31 12:14 | * | NA | 2025-07-31 12:14 | 2025-07-31 12:14
18431 | STRIVE.R2.MC1.2384.1.270.1.13 | Y | Y | Y | Complete |  | Partner profile set up for exchange rate IDOC in S/4HANA | 0 hrs | 2025-07-31 12:42 | 2025-07-31 12:42 | Gurmandeep Singh | gurmandsingh@deloitte.com | Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Roshanlal Hemwani | pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rohemwani@deloitte.com | R2D | 18396,18407 | 2025-07-31 12:42 | 2025-07-31 12:42 | * | NA | 2025-07-31 12:42 | 2025-07-31 12:42
18432 | STRIVE.R2.MC1.2384.1.270.1.14 | Y | Y | Y | Complete |  | Assign roles to release Step - Not Open Client | 15.96 hrs | 2025-08-28 19:12 | 2025-08-29 11:13 | Nirali Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D | 18396,18407 | 2025-08-28 19:12 | 2025-08-29 11:13 |  | 2025-08-25 16:09 | 2025-08-28 19:12 | 2025-08-29 11:13
18433 | STRIVE.R2.MC1.2384.1.270.1.15 | Y | Y | Y | Complete |  | Open client for assigning cost center to Splitting structure ( Transaction code - OKEW) | 139.85 hrs | 2025-09-04 16:09 | 2025-09-10 12:24 | Jitender Chhabra | jkchhabra.ext@deloitte.com | Sandeep (R2D); USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | ssandeep4@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | R2D | 19427,18396,18407 | 2025-09-04 16:09 | 2025-09-10 12:24 |  | 2025-09-04 16:09 | 2025-09-04 16:09 | 2025-09-10 12:24
40106 | STRIVE.R2.MC1.2384.1.270.1.16 | Y | Y | Y | Complete |  | Creation of Rule for BCM | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Dhaval | dhavalshah@deloitte.com | Niral Trivedi; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nirtrivedi@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18434 | STRIVE.R2.MC1.2384.1.270.17 |  |  |  | Complete |  | MDG | 8.98 hrs | 2025-07-14 08:00 | 2025-07-15 08:59 | [6 empty] | 2025-07-14 08:00 | 2025-08-05 10:45 | * | NA | 2025-07-14 08:00 | 2025-07-15 08:59
18435 | STRIVE.R2.MC1.2384.1.270.17.1 | Y | Y | Y | Complete |  | Validate SWU3 Workflow customizing set up done by Basis - Not Open Client | 1.26 hrs | 2025-08-01 13:30 | 2025-08-01 14:46 | Amol Paswan | ampaswan@deloitte.com | ; Tushar Amrutkar; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; tamrutkar@deloitte.de; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-08-01 13:30 | 2025-08-01 14:46 | * | NA | 2025-08-01 13:30 | 2025-08-01 14:46
18436 | STRIVE.R2.MC1.2384.1.270.17.2 | Y | Y | Y | Complete |  | MDG: MM (Validate Direct output) Replication model activation | 0.4 hrs | 2025-07-31 11:36 | 2025-07-31 12:00 | Amol Paswan | ampaswan@deloitte.com | ; Tushar Amrutkar; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; tamrutkar@deloitte.de; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-07-31 11:36 | 2025-07-31 12:00 | * | NA | 2025-07-31 11:36 | 2025-07-31 12:00
18437 | STRIVE.R2.MC1.2384.1.270.17.3 | Y | Y | Y | Complete |  | MDG: BP Replication model activation - Not Open Client | 0.39 hrs | 2025-08-01 12:50 | 2025-08-01 13:24 | Amol Paswan | ampaswan@deloitte.com | ; Tushar Amrutkar; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; tamrutkar@deloitte.de; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-08-01 12:50 | 2025-08-01 13:24 | * | NA | 2025-08-01 12:50 | 2025-08-01 13:24
18438 | STRIVE.R2.MC1.2384.1.270.17.4 | Y | Y | Y | Complete |  | MDG: SM Replication model activation - Not Open Client | 0.4 hrs | 2025-08-01 12:50 | 2025-08-01 13:24 | Amol Paswan | ampaswan@deloitte.com | ; Tushar Amrutkar; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; tamrutkar@deloitte.de; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-08-01 12:50 | 2025-08-01 13:24 | * | NA | 2025-08-01 12:50 | 2025-08-01 13:24
18439 | STRIVE.R2.MC1.2384.1.270.17.5 | Y | Y | Y | Complete |  | Validate DRFIMG configuration for MM | 0.39 hrs | 2025-07-31 11:36 | 2025-07-31 12:00 | Amol Paswan | ampaswan@deloitte.com | ; Tushar Amrutkar; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; tamrutkar@deloitte.de; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-07-31 11:36 | 2025-07-31 12:00 | * | NA | 2025-07-31 11:36 | 2025-07-31 12:00
18440 | STRIVE.R2.MC1.2384.1.270.17.6 | Y | Y | Y | Complete |  | Validate DRFIMG configuration for BP | 0.39 hrs | 2025-07-31 11:37 | 2025-07-31 12:00 | Amol Paswan | ampaswan@deloitte.com | ; Tushar Amrutkar; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; tamrutkar@deloitte.de; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-07-31 11:37 | 2025-07-31 12:00 | * | NA | 2025-07-31 11:37 | 2025-07-31 12:00
18441 | STRIVE.R2.MC1.2384.1.270.17.7 | Y | Y | Y | Complete |  | MDG: Activation and Adjustment of Data model - Not Open Client | 1.24 hrs | 2025-08-01 13:31 | 2025-08-01 14:46 | Amol Paswan | ampaswan@deloitte.com | ; Tushar Amrutkar; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; tamrutkar@deloitte.de; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-08-01 13:31 | 2025-08-01 14:46 | * | NA | 2025-08-01 13:31 | 2025-08-01 14:46
18442 | STRIVE.R2.MC1.2384.1.270.17.8 | Y | Y | Y | Complete |  | Validate TVARVC | 1.95 hrs | 2025-07-31 12:46 | 2025-07-31 14:57 | Ashish Sarangi | assarangi@deloitte.com | ; Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-07-31 12:46 | 2025-07-31 14:57 | * | NA | 2025-07-31 12:46 | 2025-07-31 14:57
18443 | STRIVE.R2.MC1.2384.1.270.17.9 | Y | Y | Y | Complete |  | Activate certificate for SOA and SLD setting | 36.99 hrs | 2025-07-14 08:00 | 2025-07-18 13:59 | Priyanka Patel | priyankaspatel@deloitte.de | Deloitte BASIS; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER | DeloitteSASOLBasisTeam@deloitte.com; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | BASIS | 18410,18402 | 2025-07-14 08:00 | 2025-07-18 13:59 | * | NA | 2025-07-14 08:00 | 2025-07-18 13:59
18444 | STRIVE.R2.MC1.2384.1.270.17.10 | Y | Y | Y | Complete |  | Create HANA procedure for Intelligent MDG - Not Open Client | 4.4 hrs | 2025-08-04 15:21 | 2025-08-05 10:45 | Ashish Sarangi | assarangi@deloitte.com | ; Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-08-04 15:21 | 2025-08-05 10:45 | * | NA | 2025-08-04 15:21 | 2025-08-05 10:45
18445 | STRIVE.R2.MC1.2384.1.270.17.11 | Y | Y | Y | Complete |  | DRFF filters to be maintained | 0.28 hrs | 2025-07-31 11:46 | 2025-07-31 13:03 | Tulika Pal | tupal@deloitte.com | ; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-07-31 11:46 | 2025-07-31 13:03 | * | NA | 2025-07-31 11:46 | 2025-07-31 13:03
18446 | STRIVE.R2.MC1.2384.1.270.17.12 | Y | Y | Y | Complete |  | Validate custom table entries including Wonof - Not Open Client | 0.64 hrs | 2025-08-01 14:47 | 2025-08-01 15:26 | Ashish Sarangi | assarangi@deloitte.com | ; Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 18410,18402 | 2025-08-01 14:47 | 2025-08-01 15:26 | * | NA | 2025-08-01 14:47 | 2025-08-01 15:26
18450 | STRIVE.R2.MC1.2384.1.270.17.16 | Y | Y | Y | Complete |  | Updating the switch ON for supplier initial load | 0.22 hrs | 2025-07-31 16:46 | 2025-07-31 16:59 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Tushar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MDG | 18410,18402 | 2025-07-31 16:46 | 2025-07-31 16:59 | * | NA | 2025-07-31 16:46 | 2025-07-31 16:59
21021 | STRIVE.R2.MC1.2384.1.270.17.18 | Y | Y | Y | Complete |  | Updating the switch OFF for supplier initial load | 0.02 hrs | 2025-07-31 16:59 | 2025-07-31 17:00 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Tushar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MDG |  | 2025-07-31 16:59 | 2025-07-31 17:00 | * | NA | 2025-07-31 16:59 | 2025-07-31 17:00
18452 | STRIVE.R2.MC1.2384.1.270.35 |  |  |  | Complete |  | MOR- EPPM | 8 hrs | 2025-07-14 08:00 | 2025-07-14 17:00 | [5 empty] | 18397 | 2025-07-31 15:44 | 2025-09-10 12:16 | * | NA | 2025-07-14 08:00 | 2025-07-14 17:00
18453 | STRIVE.R2.MC1.2384.1.270.35.1 | Y | Y | Y | Complete |  | Define object link types | 0.23 hrs | 2025-08-07 14:03 | 2025-08-07 14:17 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18190,18189,18188,18397 | 2025-08-07 14:03 | 2025-08-07 14:17 | * | NA | 2025-08-07 14:03 | 2025-08-07 14:17
18454 | STRIVE.R2.MC1.2384.1.270.35.2 | Y | Y | Y | Complete |  | Map item type to PPM Project templates | 0.72 hrs | 2025-08-07 13:17 | 2025-08-07 14:00 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18190,18189,18188,18397 | 2025-08-07 13:17 | 2025-08-07 14:00 | * | NA | 2025-08-07 13:17 | 2025-08-07 14:00
18455 | STRIVE.R2.MC1.2384.1.270.35.3 | Y | Y | Y | Complete |  | Define financial planning settings in Base system interfaces | 0 hrs | 2025-07-31 18:01 | 2025-07-31 18:01 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18423,18397 | 2025-07-31 18:01 | 2025-07-31 18:01 | * | NA | 2025-07-31 18:01 | 2025-07-31 18:01
18456 | STRIVE.R2.MC1.2384.1.270.35.4 | Y | Y | Y | Complete |  | Map Item Type to PS Project templates (NON MOR) - Open Client Activity | 0.45 hrs | 2025-09-10 11:48 | 2025-09-10 12:16 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18453,18409,18397,18416 | 2025-09-10 11:48 | 2025-09-10 12:16 | * | NA | 2025-09-10 11:48 | 2025-09-10 12:16
18457 | STRIVE.R2.MC1.2384.1.270.35.5 | Y | Y | Y | Complete |  | Maintain DFM object links | 0.04 hrs | 2025-07-31 15:44 | 2025-07-31 15:47 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18190,18397 | 2025-07-31 15:44 | 2025-07-31 15:47 | * | NA | 2025-07-31 15:44 | 2025-07-31 15:47
18458 | STRIVE.R2.MC1.2384.1.270.35.6 | Y | Y | Y | Complete |  | Update FICO INT PLAN batch job for PPM | 0 hrs | 2025-08-07 17:50 | 2025-08-07 17:50 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18455,18397 | 2025-08-07 17:50 | 2025-08-07 17:50 | * | NA | 2025-08-07 17:50 | 2025-08-07 17:50
18459 | STRIVE.R2.MC1.2384.1.270.35.7 | Y | Y | Y | Complete |  | Check connection to external systems to make settings for linked objects | 0.62 hrs | 2025-08-07 14:55 | 2025-08-07 15:32 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18190,18397 | 2025-08-07 14:55 | 2025-08-07 15:32 | * | NA | 2025-08-07 14:55 | 2025-08-07 15:32
18460 | STRIVE.R2.MC1.2384.1.270.35.8 | Y | Y | Y | Complete |  | Define Web server alias | 0.94 hrs | 2025-08-07 15:01 | 2025-08-07 15:58 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18190,18397 | 2025-08-07 15:01 | 2025-08-07 15:58 | * | NA | 2025-08-07 15:01 | 2025-08-07 15:58
18461 | STRIVE.R2.MC1.2384.1.270.35.9 | Y | Y | Y | Complete |  | Make settings for linked SAP objects | 0 hrs | 2025-08-07 18:04 | 2025-08-07 18:04 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18397 | 2025-08-07 18:04 | 2025-08-07 18:04 | * | NA | 2025-08-07 18:04 | 2025-08-07 18:04
18462 | STRIVE.R2.MC1.2384.1.270.35.10 | Y | Y | Y | Complete |  | Create the status profile for documents in Project management | 0.5 hrs | 2025-08-14 15:15 | 2025-08-14 15:45 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18397 | 2025-08-14 15:15 | 2025-08-14 15:45 | * | NA | 2025-08-14 15:15 | 2025-08-14 15:45
18471 | STRIVE.R2.MC1.2384.1.270.54 |  |  |  | Complete |  | R2P | 0.05 hrs | 2025-07-14 08:00 | 2025-07-14 08:03 | [6 empty] | 2025-07-31 12:20 | 2025-07-31 15:34 | * | NA | 2025-07-14 08:00 | 2025-07-14 08:03
18472 | STRIVE.R2.MC1.2384.1.270.54.1 | Y | Y | Y | Complete |  | Specify SAP APO Release | 0 hrs | 2025-07-31 12:20 | 2025-07-31 12:20 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 12:20 | 2025-07-31 12:20 | * | NA | 2025-07-31 12:20 | 2025-07-31 12:20
18473 | STRIVE.R2.MC1.2384.1.270.54.2 | Y | Y | Y | Complete |  | Assign RFC Destinations to Different Application Cases | 0 hrs | 2025-07-31 12:23 | 2025-07-31 12:23 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 12:23 | 2025-07-31 12:23 | * | NA | 2025-07-31 12:23 | 2025-07-31 12:23
18474 | STRIVE.R2.MC1.2384.1.270.54.3 | Y | Y | Y | Complete |  | Set Target System and Queue Type | 0 hrs | 2025-07-31 12:25 | 2025-07-31 12:25 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 12:25 | 2025-07-31 12:25 | * | NA | 2025-07-31 12:25 | 2025-07-31 12:25
18475 | STRIVE.R2.MC1.2384.1.270.54.4 | Y | Y | Y | Complete |  | Create Model& Version | 0 hrs | 2025-07-31 12:28 | 2025-07-31 12:28 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 12:28 | 2025-07-31 12:28 | * | NA | 2025-07-31 12:28 | 2025-07-31 12:28
18476 | STRIVE.R2.MC1.2384.1.270.54.5 | Y | Y | Y | Complete |  | Specify SAP APO Release | 0 hrs | 2025-07-31 12:46 | 2025-07-31 12:46 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 12:46 | 2025-07-31 12:46 | * | NA | 2025-07-31 12:46 | 2025-07-31 12:46
18477 | STRIVE.R2.MC1.2384.1.270.54.6 | Y | Y | Y | Complete |  | Assign RFC Destinations to Different Application Cases | 2.53 hrs | 2025-07-31 12:47 | 2025-07-31 15:32 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 12:47 | 2025-07-31 15:32 | * | NA | 2025-07-31 12:47 | 2025-07-31 15:32
18478 | STRIVE.R2.MC1.2384.1.270.54.7 | Y | Y | Y | Complete |  | Set Target System and Queue Type | 0 hrs | 2025-07-31 15:32 | 2025-07-31 15:32 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 15:32 | 2025-07-31 15:32 | * | NA | 2025-07-31 15:32 | 2025-07-31 15:32
18479 | STRIVE.R2.MC1.2384.1.270.54.8 | Y | Y | Y | Complete |  | Create Model& Version | 0.02 hrs | 2025-07-31 15:33 | 2025-07-31 15:34 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18393,18404 | 2025-07-31 15:33 | 2025-07-31 15:34 | * | NA | 2025-07-31 15:33 | 2025-07-31 15:34
18483 | STRIVE.R2.MC1.2384.1.270.66 | [5 empty] | S2P | 7.96 hrs | 2025-07-14 08:00 | 2025-07-14 15:59 | [6 empty] | 2025-07-31 17:41 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 15:59
18484 | STRIVE.R2.MC1.2384.1.270.66.1 | Y | Y | Y | Complete |  | Maintain number range for purchasing documents. | 0 hrs | 2025-07-31 17:41 | 2025-07-31 17:41 | Prasanth Kallakuri | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Prasanth; Manoj Dombar; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; mdombar@deloitte.com; usisasols2p@deloitte.com | S2P | 18394,18405 | 2025-07-31 17:41 | 2025-07-31 17:41 | * | NA | 2025-07-31 17:41 | 2025-07-31 17:41
18485 | STRIVE.R2.MC1.2384.1.270.66.2 | N | N | N | Planned |  | Update Business Partner for Advance IC STO ( owners S2P and P2C) | 2 hrs | 2025-09-15 06:17 | 2025-09-15 08:18 | Prasanth Kallakuri | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Prasanth; Manoj Dombar; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; mdombar@deloitte.com; usisasols2p@deloitte.com | S2P | 19548,19518,18394,18405 |  |  |  | 2025-09-15 06:17 | 2025-09-15 06:17 | 2025-09-15 08:18
18486 | STRIVE.R2.MC1.2384.1.270.66.3 | N | N | N | Planned |  | Update Advance IC STO Invoicing Config (Owners S2P and R2D) | 2 hrs | 2025-09-15 06:17 | 2025-09-15 08:18 | Prasanth Kallakuri | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Prasanth; Manoj Dombar; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; mdombar@deloitte.com; usisasols2p@deloitte.com | S2P | 19548,19518,18394,18405 |  |  |  | 2025-09-15 06:17 | 2025-09-15 06:17 | 2025-09-15 08:18
18487 | STRIVE.R2.MC1.2384.1.270.66.4 | N | N | N | Planned |  | Update shipping data for Intracompany scenario (S2P) | 2 hrs | 2025-09-15 06:17 | 2025-09-15 08:18 | Prasanth Kallakuri | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Manoj Dombar; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; mdombar@deloitte.com; usisasols2p@deloitte.com | S2P | 19548,19518,18394,18405 |  |  |  | 2025-09-15 06:17 | 2025-09-15 06:17 | 2025-09-15 08:18
18488 | STRIVE.R2.MC1.2384.1.270.66.5 | N | N | N | Planned |  | Update shipping data for Advance STO scenario (S2P) | 2 hrs | 2025-09-15 06:17 | 2025-09-15 08:18 | Prasanth Kallakuri | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Prasanth; Manoj Dombar; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; mdombar@deloitte.com; usisasols2p@deloitte.com | S2P | 19548,19518,18394,18405 |  |  |  | 2025-09-15 06:17 | 2025-09-15 06:17 | 2025-09-15 08:18
20896 | STRIVE.R2.MC1.2384.1.270.72 | [5 empty] | R2P - EHS (Open Client) | 988.27 hrs | 2025-07-31 11:29 | 2025-09-10 18:30 | [6 empty] | 2025-07-31 11:29 |  | * | NA | 2025-07-31 11:29 | 2025-09-10 18:30
20897 | STRIVE.R2.MC1.2384.1.270.72.16 | Y | Y | Y | Complete |  | R2P- EHS- Specify Generation Servers along with Root | 1.95 hrs | 2025-07-31 11:29 | 2025-07-31 14:26 | Shahid Sheikh | smohdshahid@deloitte.com | Sheena Gour; Priyanka Singhal; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; priyasinghal@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20976,18393,18404 | 2025-07-31 11:29 | 2025-07-31 14:26 | * | NA | 2025-07-31 11:29 | 2025-07-31 14:26
20898 | STRIVE.R2.MC1.2384.1.270.72.17 | Y | Y | Y | Complete |  | R2P- EHS- Check WWI Destinations and Assign Generation Servers | 1.56 hrs | 2025-07-31 11:54 | 2025-07-31 14:27 | Shahid Sheikh | smohdshahid@deloitte.com | Sheena Gour; Priyanka Singhal; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; priyasinghal@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20976,18393,18404 | 2025-07-31 11:54 | 2025-07-31 14:27 | * | NA | 2025-07-31 11:54 | 2025-07-31 14:27
20899 | STRIVE.R2.MC1.2384.1.270.72.18 | Y | Y | Y | Complete |  | R2P-EHS- Configure WWI Server for Print Request Generation | 1.58 hrs | 2025-07-31 11:54 | 2025-07-31 14:29 | Shahid Sheikh | smohdshahid@deloitte.com | Sheena Gour; Priyanka Singhal; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; priyasinghal@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20976,18393,18404 | 2025-07-31 11:54 | 2025-07-31 14:29 | * | NA | 2025-07-31 11:54 | 2025-07-31 14:29
20900 | STRIVE.R2.MC1.2384.1.270.72.19 | Y | Y | Y | Complete |  | R2P-EHS- Specify Environment Parameter- WWI_GENSERVER_SYN_DEST | 1.61 hrs | 2025-07-31 11:55 | 2025-07-31 14:31 | Shahid Sheikh | smohdshahid@deloitte.com | Sheena Gour; Priyanka Singhal; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; priyasinghal@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20976,18393,18404 | 2025-07-31 11:55 | 2025-07-31 14:31 | * | NA | 2025-07-31 11:55 | 2025-07-31 14:31
20901 | STRIVE.R2.MC1.2384.1.270.72.20 | Y | Y | Y | Complete |  | R2P-EHS- GLM- Make settings for Basic Data | 1.66 hrs | 2025-07-31 11:55 | 2025-07-31 14:34 | Shahid Sheikh | smohdshahid@deloitte.com | Sheena Gour; Priyanka Singhal; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; priyasinghal@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20976,18393,18404 | 2025-07-31 11:55 | 2025-07-31 14:34 | * | NA | 2025-07-31 11:55 | 2025-07-31 14:34
20902 | STRIVE.R2.MC1.2384.1.270.72.21 | Y | Y | Y | Complete |  | R2P- EHS- Configure the table-based value assignment for new properties | 49.77 hrs | 2025-09-08 12:57 | 2025-09-10 14:51 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20985,18393,18404 | 2025-09-08 12:57 | 2025-09-10 14:51 |  | 2025-09-05 08:00 | 2025-09-08 12:57 | 2025-09-10 14:51
20891 | STRIVE.R2.MC1.2384.1.270.72.10 | Y | Y | N | In-Progress |  | R2P- EHS- Configure the table based value assignment for new characteristics in existing properties | 1 hrs | 2025-09-10 17:30 | 2025-09-10 18:30 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20902,18393,18404 | 2025-09-10 17:30 |  | * | NA | 2025-09-10 17:30 | 2025-09-10 18:30
20892 | STRIVE.R2.MC1.2384.1.270.72.11 | N | N | N | Planned |  | R2P-EHS- Maintain Address number for legal entities- Opesus | 1 hrs | 2025-09-08 08:48 | 2025-09-08 09:48 | Claudia | claudia.valdes@opesus.com | Sheena Gour; Priyanka Singhal; Shahid Sheikh; Alex Larionov; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Harish Kristapati | shgour@deloitte.com; priyasinghal@deloitte.com; smohdshahid@deloitte.com; allarionov@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hkristapati@deloitte.com | R2P | 20991,18393,18404 |  |  |  | 2025-09-08 08:48 | 2025-09-08 08:48 | 2025-09-08 09:48
18489 | STRIVE.R2.MC1.2384.1.342 | [5 empty] | Manual Configuration | 1203.83 hrs | 2025-07-14 08:00 | 2025-09-02 15:11 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-09-02 15:11
18490 | STRIVE.R2.MC1.2384.1.342.1 | [5 empty] | Tech | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18491 | STRIVE.R2.MC1.2384.1.342.1.1 | N | N | N | Planned |  | Validate RFC connection destination of CPI end points | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 10:00
18492 | STRIVE.R2.MC1.2384.1.342.1.2 | N | N | N | Planned |  | Set up partner profile | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18493 | STRIVE.R2.MC1.2384.1.342.1.3 | N | N | N | Planned |  | Validate TVARVC entries in subsequent systems | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18494 | STRIVE.R2.MC1.2384.1.342.1.4 | N | N | N | Planned |  | Execute the report FCO_CDS_VIEW_GENERATE to generate COBL structures | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18495 | STRIVE.R2.MC1.2384.1.342.1.5 | N | N | N | Planned |  | Generate Validations&Substitutions (Execute Prog - RGUGBR00) | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18496 | STRIVE.R2.MC1.2384.1.342.1.6 | N | N | N | Planned |  | Regenerate HDBVIEWS | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18497 | STRIVE.R2.MC1.2384.1.342.1.7 | N | N | N | Planned |  | Run FDC_GENERATE_COBL to regenerate services | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18498 | STRIVE.R2.MC1.2384.1.342.1.8 | N | N | N | Planned |  | FGL_MIG_REGENERATE_CDS_BCF (Without Checkbox: Reset to Delivery) | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Sarath; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; ssiripurapu@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18499 | STRIVE.R2.MC1.2384.1.342.1.9 | N | N | N | Planned |  | Activate APIs in SAP S4HANA backend system using the correct transport packages | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Gurmandeep Singh | gurmandsingh@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ashish patil | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ashishspatil@deloitte.com | ABAP |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18500 | STRIVE.R2.MC1.2384.1.342.1.10 | N | N | N | Planned |  | Reporting objects validation | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Manasa | mha@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Analytics |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
18501 | STRIVE.R2.MC1.2384.1.342.1.11 | N | N | N | Planned |  | Validation of the Fiori tiles for the reporting objects | 2 hrs | 2025-09-22 08:00 | 2025-09-22 10:00 | Manasa | mha@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Analytics |  |  |  |  | 2025-09-22 08:00 | 2025-09-22 08:00 | 2025-09-22 10:00
21025 | STRIVE.R2.MC1.2384.1.342.1.14 | Y | Y | Y | Complete |  | CPI team to provide LIMS provider system details to MDG | 132 hrs | 2025-07-14 08:00 | 2025-08-05 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga; Saurabh Kumar; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Amol; Tulika Pal | nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ampaswan@deloitte.com; tupal@deloitte.com | Integration |  | 2025-07-14 08:00 | 2025-08-05 12:00 | * | NA | 2025-07-14 08:00 | 2025-08-05 12:00
21026 | STRIVE.R2.MC1.2384.1.342.1.15 | Y | Y | Y | Complete |  | DRFIMG conifguration for BP LIMS | 4 hrs | 2025-08-05 13:00 | 2025-08-05 17:00 | Amol | ampaswan@deloitte.com | Tulika Pal; Tushar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Rajat Sharma | tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; rajatsharma67@deloitte.com | MDG | 21025 | 2025-08-05 13:00 | 2025-08-05 17:00 | * | NA | 2025-08-05 13:00 | 2025-08-05 17:00
18502 | STRIVE.R2.MC1.2384.1.342.13 | [5 empty] | R2D | 335.9 hrs | 2025-07-14 08:00 | 2025-07-28 08:50 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-28 08:50
18503 | STRIVE.R2.MC1.2384.1.342.13.1 | Y | N | N | Sent |  | Create exact Variants as per MBC in FF_5 | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Niral Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18504 | STRIVE.R2.MC1.2384.1.342.13.2 | Y | Y | Y | Complete |  | Maintain Number Range for MBC Message ID | 0 hrs | 2025-08-06 11:33 | 2025-08-06 11:33 | Niral Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D |  | 2025-08-06 11:33 | 2025-08-06 11:33 | * | NA | 2025-08-06 11:33 | 2025-08-06 11:33
18505 | STRIVE.R2.MC1.2384.1.342.13.3 | Y | Y | Y | Complete |  | Sasol House Bank Business Partner Request creation in MDG | 896.69 hrs | 2025-07-14 08:00 | 2025-08-20 19:10 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Michaela Schulz; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | michaela.schulz@de.sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-20 19:10 | * | NA | 2025-07-14 08:00 | 2025-08-20 19:10
18506 | STRIVE.R2.MC1.2384.1.342.13.4 | Y | Y | Y | Complete |  | Sasol House Bank Business Partner Request Approval in MDG | 0 hrs | 2025-08-11 18:33 | 2025-08-11 18:33 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Michaela Schulz; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | michaela.schulz@de.sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | R2D |  | 2025-08-11 18:33 | 2025-08-11 18:33 | * | NA | 2025-08-11 18:33 | 2025-08-11 18:33
18507 | STRIVE.R2.MC1.2384.1.342.13.5 | Y | Y | Y | Complete |  | Assign Bank BP to bank accounts | 24.94 hrs | 2025-08-21 13:54 | 2025-08-22 14:54 | Niral Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D | 18505,18506 | 2025-08-21 13:54 | 2025-08-22 14:54 | * | NA | 2025-08-21 13:54 | 2025-08-22 14:54
18508 | STRIVE.R2.MC1.2384.1.342.13.6 | Y | Y | Y | Complete |  | Maintenance of number ranges for the company codes SNRO: RF_BELEG | 0.44 hrs | 2025-08-08 15:12 | 2025-08-08 15:38 | Mohamed Ibrahim | mibrahimjs@deloitte.com | Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-08-08 15:12 | 2025-08-08 15:38 | * | NA | 2025-08-08 15:12 | 2025-08-08 15:38
18509 | STRIVE.R2.MC1.2384.1.342.13.7 | Y | Y | Y | Complete |  | Activation of material ledger CKMSTART | 0 hrs | 2025-08-08 13:55 | 2025-08-08 13:55 | Alexandra Ruff | aruff@deloitte.de | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-08-08 13:55 | 2025-08-08 13:55 | * | NA | 2025-08-08 13:55 | 2025-08-08 13:55
18510 | STRIVE.R2.MC1.2384.1.342.13.8 | Y | Y | Y | Complete |  | CO number ranges SNRO: RK_BELEG | 123.47 hrs | 2025-07-14 08:00 | 2025-08-04 11:28 | Sandeep (R2D) | ssandeep4@deloitte.com | Jitender Chhabra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | jkchhabra.ext@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-04 11:28 | * | NA | 2025-07-14 08:00 | 2025-08-04 11:28
18511 | STRIVE.R2.MC1.2384.1.342.13.9 | Y | Y | Y | Complete |  | ML number ranges etc. SNRO: ML_BELEG | 123.48 hrs | 2025-07-14 08:00 | 2025-08-04 11:29 | Sandeep (R2D) | ssandeep4@deloitte.com | Jitender Chhabra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | jkchhabra.ext@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-04 11:29 | * | NA | 2025-07-14 08:00 | 2025-08-04 11:29
18512 | STRIVE.R2.MC1.2384.1.342.13.10 | Y | Y | Y | Complete |  | Fixed Assets- Number ranges SNRO: ANLAGENNR | 42.18 hrs | 2025-08-01 12:02 | 2025-08-08 15:11 | Mohamed Ibrahim | mibrahimjs@deloitte.com | Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-08-01 12:02 | 2025-08-08 15:11 | * | NA | 2025-08-01 12:02 | 2025-08-08 15:11
18513 | STRIVE.R2.MC1.2384.1.342.13.11 | Y | Y | Y | Complete |  | Fixed assets - take over date | 42.26 hrs | 2025-08-01 11:43 | 2025-08-08 14:58 | Mohamed Ibrahim | mibrahimjs@deloitte.com | Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-08-01 11:43 | 2025-08-08 14:58 | * | NA | 2025-08-01 11:43 | 2025-08-08 14:58
18514 | STRIVE.R2.MC1.2384.1.342.13.12 | Y | Y | Y | Complete |  | Maintain OB08 EURX Exchange rate for Asset Migration (USD – EUR) as per 28.02.2025 and 1970, remove standard rates | 0 hrs | 2025-08-11 18:16 | 2025-08-11 18:16 | Daniel Lohmann | dlohmann@deloitte.de | Alexandra Ruff; Roshanlal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | aruff@deloitte.de; rohemwani@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D |  | 2025-08-11 18:16 | 2025-08-11 18:16 | * | NA | 2025-08-11 18:16 | 2025-08-11 18:16
18515 | STRIVE.R2.MC1.2384.1.342.13.13 | Y | Y | Y | Complete |  | ECS Number Range SNRO GLE_AWREF | 0.12 hrs | 2025-08-01 11:49 | 2025-08-01 11:56 | Mohamed Ibrahim | mibrahimjs@deloitte.com | Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-08-01 11:49 | 2025-08-01 11:56 | * | NA | 2025-08-01 11:49 | 2025-08-01 11:56
18516 | STRIVE.R2.MC1.2384.1.342.13.14 | Y | Y | Y | Complete |  | Maintain global accounting hierachies | 158.76 hrs | 2025-07-14 08:00 | 2025-08-08 15:46 | Sandeep (R2D) | ssandeep4@deloitte.com | Jitender Chhabra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | jkchhabra.ext@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-08 15:46 | * | NA | 2025-07-14 08:00 | 2025-08-08 15:46
18517 | STRIVE.R2.MC1.2384.1.342.13.15 | Y | Y | Y | Complete |  | Profit Center/hierarchy upload | 133.39 hrs | 2025-07-14 08:00 | 2025-08-05 14:23 | Sandeep (R2D) | ssandeep4@deloitte.com | Jitender Chhabra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | jkchhabra.ext@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-05 14:23 | * | NA | 2025-07-14 08:00 | 2025-08-05 14:23
18518 | STRIVE.R2.MC1.2384.1.342.13.16 | Y | Y | Y | Complete |  | Cost Center/hierarchy upload | 123.47 hrs | 2025-07-14 08:00 | 2025-08-04 11:28 | Sandeep (R2D) | ssandeep4@deloitte.com | Jitender Chhabra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | jkchhabra.ext@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-04 11:28 | * | NA | 2025-07-14 08:00 | 2025-08-04 11:28
18519 | STRIVE.R2.MC1.2384.1.342.13.17 | Y | Y | I | Issue |  | Partner profile set up, RFC set up to S4 and job set up in ECC client for exchange rates | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Michaela | michaela.schulz@de.sasol.com | Himanshu; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dixit.h@hcltech.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
18520 | STRIVE.R2.MC1.2384.1.342.13.18 | Y | Y | Y | Complete |  | ALE set up for GL account transfer. | 44 hrs | 2025-07-14 08:00 | 2025-07-21 12:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-21 12:00 | * | NA | 2025-07-14 08:00 | 2025-07-21 12:00
18521 | STRIVE.R2.MC1.2384.1.342.13.19 | Y | Y | Y | Complete |  | Partner profile set up for transfer pricing conditions IDOC in S4 | 0 hrs | 2025-08-11 17:28 | 2025-08-11 17:28 | Gurmandeep Singh | gurmandsingh@deloitte.com | Satheesh Pula; Roshanlal Hemwani; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | pusatheesh@deloitte.com; rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-08-11 17:28 | 2025-08-11 17:28 | * | NA | 2025-08-11 17:28 | 2025-08-11 17:28
18522 | STRIVE.R2.MC1.2384.1.342.13.20 | N | N | N | Ready |  | Upload of internal transfer prices | 4 hrs | 2025-09-05 00:08 | 2025-09-05 04:08 | Jitender Chhabra | jkchhabra.ext@deloitte.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Roshanlal; Tatiana | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D | 19634 |  |  |  | 2025-09-05 00:08 | 2025-09-05 00:08 | 2025-09-05 04:08
18523 | STRIVE.R2.MC1.2384.1.342.13.21 | Y | Y | Y | Complete |  | Create&Assign Varinant to Payment Medium Format | 160 hrs | 2025-07-14 08:00 | 2025-08-08 17:00 | Nirali Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-08 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-08 17:00
18524 | STRIVE.R2.MC1.2384.1.342.13.22 | Y | Y | Y | Complete |  | FIFO level setting (cco level): OMWL | 158.42 hrs | 2025-07-14 08:00 | 2025-08-08 15:25 | Alexandra Ruff | aruff@deloitte.de | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-07-14 08:00 | 2025-08-08 15:25 | * | NA | 2025-07-14 08:00 | 2025-08-08 15:25
18525 | STRIVE.R2.MC1.2384.1.342.13.23 | Y | Y | Y | Complete |  | Create batch user (N_I_R2DINTUS) in higher enviroments for R2D | 124 hrs | 2025-07-14 08:00 | 2025-08-04 12:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-04 12:00 | * | NA | 2025-07-14 08:00 | 2025-08-04 12:00
18526 | STRIVE.R2.MC1.2384.1.342.13.24 | Y | Y | Y | Complete |  | Background job to be created for exchange rates interface to Coupa | 365.06 hrs | 2025-08-13 11:33 | 2025-08-28 17:38 | Prasanth | kalprasanth@deloitte.com | Pournami Nair; Rabbani; Roshanlal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aparajita Mukherjee; S2P Team | pounair@deloitte.com; skhadarmohammadra@deloitte.com; rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; apamukherjee@deloitte.com; usisasols2p@deloitte.com | S2P |  | 2025-08-13 11:33 | 2025-08-28 17:38 | * | NA | 2025-08-13 11:33 | 2025-08-28 17:38
18527 | STRIVE.R2.MC1.2384.1.342.13.25 | N | N | N | Planned |  | Setup EDI Configuration for RRB | 4 hrs | 2025-09-05 12:01 | 2025-09-05 16:01 | Daniel Lohmann | dlohmann@deloitte.de | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D | 18783,18784,18785,18786,18787,18788 |  |  | * | NA | 2025-09-05 12:01 | 2025-09-05 16:01
18528 | STRIVE.R2.MC1.2384.1.342.13.26 | Y | Y | Y | Complete |  | Setup Approval Workflow for Park&Post Functionality - Not relevant for MC1 | 0 hrs | 2025-08-05 22:19 | 2025-08-05 22:19 | Daniel Lohmann | dlohmann@deloitte.de | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  | 2025-08-05 22:19 | 2025-08-05 22:19 | * | NA | 2025-08-05 22:19 | 2025-08-05 22:19
18529 | STRIVE.R2.MC1.2384.1.342.13.27 | Y | Y | Y | Complete |  | Setup Teams&Responsibilities for Park& Post Functionality - Not relevant for MC1 | 0 hrs | 2025-08-05 22:20 | 2025-08-05 22:20 | Daniel Lohmann | dlohmann@deloitte.de | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Roshanlal; Mousikta chanda; Tatiana | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de | R2D |  | 2025-08-05 22:20 | 2025-08-05 22:20 | * | NA | 2025-08-05 22:20 | 2025-08-05 22:20
18530 | STRIVE.R2.MC1.2384.1.342.41 |  |  |  | Complete |  | BASIS | 5.98 hrs | 2025-07-14 08:00 | 2025-07-14 14:59 | [6 empty] | 2025-07-14 08:00 | 2025-07-25 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-14 14:59
18531 | STRIVE.R2.MC1.2384.1.342.41.1 | Y | Y | Y | Complete |  | Update Currency to USD in SCC4 for S/4 system | 37.01 hrs | 2025-07-14 08:00 | 2025-07-18 14:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:00 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:00
18532 | STRIVE.R2.MC1.2384.1.342.41.2 | Y | Y | Y | Complete |  | Update Currency to USD in SCC4 for MDG system. | 37.02 hrs | 2025-07-14 08:00 | 2025-07-18 14:01 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:01 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:01
18533 | STRIVE.R2.MC1.2384.1.342.41.3 | Y | Y | Y | Complete |  | Validate proxy(type G) and IDOC connectivity with Integration Suite and S4 | 80 hrs | 2025-07-14 08:00 | 2025-07-25 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-25 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-25 17:00
18534 | STRIVE.R2.MC1.2384.1.342.41.4 | Y | Y | Y | Complete |  | Validate proxy(type G) and IDOC connectivity with Integration Suite and MDG | 80 hrs | 2025-07-14 08:00 | 2025-07-25 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-25 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-25 17:00
18535 | STRIVE.R2.MC1.2384.1.342.41.5 | Y | Y | Y | Complete |  | CA signed Integration suite certificate to be installed in STRUST of SU1 system | 37.04 hrs | 2025-07-14 08:00 | 2025-07-18 14:03 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:03 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:03
18536 | STRIVE.R2.MC1.2384.1.342.41.6 | Y | Y | Y | Complete |  | CA signed Integration suite certificate to be installed in STRUST of SU2 system | 37.06 hrs | 2025-07-14 08:00 | 2025-07-18 14:04 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:04 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:04
18537 | STRIVE.R2.MC1.2384.1.342.41.7 | Y | Y | Y | Complete |  | Validate SLD setup in MDG and S4. | 37.08 hrs | 2025-07-14 08:00 | 2025-07-18 14:05 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:05 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:05
18538 | STRIVE.R2.MC1.2384.1.342.41.8 | Y | Y | Y | Complete |  | Validate SOAMANAGER Setup in S4&MDG. | 37.31 hrs | 2025-07-14 08:00 | 2025-07-18 14:19 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:19 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:19
18539 | STRIVE.R2.MC1.2384.1.342.41.9 | Y | Y | Y | Complete |  | Create RFC Destination in SM59 for Tungsten Interface P2C_I_006 | 37.75 hrs | 2025-07-14 08:00 | 2025-07-18 14:45 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER; Naga; ; Yashwanth; Saurabh Kumar | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nnagasubbareddy@deloitte.com; ; myakumar@deloitte.com; saurabhkumar397@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:45 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:45
18540 | STRIVE.R2.MC1.2384.1.342.41.10 | Y | Y | Y | Complete |  | Create PORT in WE21 for Tungsten Interface P2C_I_006 | 42.25 hrs | 2025-07-18 14:45 | 2025-07-25 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Deloitte BASIS; Dhruv Kansal; USI STRIVE CUTOVER; Naga; ; Yashwanth; Saurabh Kumar | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nnagasubbareddy@deloitte.com; ; myakumar@deloitte.com; saurabhkumar397@deloitte.com | Basis | 18539 | 2025-07-18 14:45 | 2025-07-25 17:00 | * | NA | 2025-07-18 14:45 | 2025-07-25 17:00
18541 | STRIVE.R2.MC1.2384.1.342.52 |  |  |  | Complete |  | MDG | 29.9 hrs | 2025-07-14 08:00 | 2025-07-15 13:59 | [6 empty] | 2025-07-14 08:00 | 2025-08-28 14:55 | * | NA | 2025-07-14 08:00 | 2025-07-15 13:59
18542 | STRIVE.R2.MC1.2384.1.342.52.1 | Y | Y | Y | Complete |  | Provide SOA Certificate details to MDG Team | 16.22 hrs | 2025-08-01 13:00 | 2025-08-05 13:13 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Basis; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | trsagar@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Basis | 18410,18538 | 2025-08-01 13:00 | 2025-08-05 13:13 | * | NA | 2025-08-01 13:00 | 2025-08-05 13:13
18543 | STRIVE.R2.MC1.2384.1.342.52.2 | Y | Y | Y | Complete |  | MDG: Validate SOA Configuration setup for material | 19.78 hrs | 2025-08-05 13:13 | 2025-08-07 17:00 | Tulika Pal | tupal@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Tushar Amrutkar; Mousikta chanda; Amol Paswan | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tamrutkar@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com | MDG | 18542,18410,18538 | 2025-08-05 13:13 | 2025-08-07 17:00 | * | NA | 2025-08-05 13:13 | 2025-08-07 17:00
18544 | STRIVE.R2.MC1.2384.1.342.52.3 | Y | Y | Y | Complete |  | S4: Validate SOA Configuration setup for material | 19.78 hrs | 2025-08-05 13:13 | 2025-08-07 17:00 | Tulika Pal | tupal@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Tushar Amrutkar; Mousikta chanda; Amol Paswan | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tamrutkar@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com | MDG | 18542,18402,18538 | 2025-08-05 13:13 | 2025-08-07 17:00 | * | NA | 2025-08-05 13:13 | 2025-08-07 17:00
18545 | STRIVE.R2.MC1.2384.1.342.52.4 | Y | Y | Y | Complete |  | S4: Validate SOA Configuration setup for BP | 19.78 hrs | 2025-08-05 13:13 | 2025-08-07 17:00 | Tulika Pal | tupal@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Tushar Amrutkar; Mousikta chanda; Amol Paswan | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tamrutkar@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com | MDG | 18542,18402,18538 | 2025-08-05 13:13 | 2025-08-07 17:00 | * | NA | 2025-08-05 13:13 | 2025-08-07 17:00
18546 | STRIVE.R2.MC1.2384.1.342.52.5 | Y | Y | Y | Complete |  | MDG: Validate SOA Configuration setup for BP | 19.78 hrs | 2025-08-05 13:13 | 2025-08-07 17:00 | Tulika Pal | tupal@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Tushar Amrutkar; Mousikta chanda; Amol Paswan | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tamrutkar@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com | MDG | 18542,18410,18538 | 2025-08-05 13:13 | 2025-08-07 17:00 | * | NA | 2025-08-05 13:13 | 2025-08-07 17:00
18547 | STRIVE.R2.MC1.2384.1.342.52.6 | Y | Y | Y | Complete |  | Verify Jobs (Wonof 2, RBDMIDOC 1) | 341.97 hrs | 2025-08-14 08:00 | 2025-08-28 14:55 | Amol | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Tushar Amrutkar; Mousikta chanda | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tamrutkar@deloitte.de; mouchanda@deloitte.com | MDG |  | 2025-08-14 08:00 | 2025-08-28 14:55 |  | 2025-08-14 08:00 | 2025-08-14 08:00 | 2025-08-28 14:55
18548 | STRIVE.R2.MC1.2384.1.342.52.7 | Y | Y | Y | Complete |  | Run USMD_RULE tcode | 116.39 hrs | 2025-07-14 08:00 | 2025-08-01 13:24 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Tushar; Mousikta chanda | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tamrutkar@deloitte.de; mouchanda@deloitte.com | MDG |  | 2025-07-14 08:00 | 2025-08-01 13:24 | * | NA | 2025-07-14 08:00 | 2025-08-01 13:24
18549 | STRIVE.R2.MC1.2384.1.342.52.8 | Y | Y | Y | Complete |  | MDG: Review decision tables for BRF workflows | 128 hrs | 2025-07-14 13:00 | 2025-08-05 12:00 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Tushar; Mousikta chanda | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tamrutkar@deloitte.de; mouchanda@deloitte.com | MDG | 18548 | 2025-07-14 13:00 | 2025-08-05 12:00 | * | NA | 2025-07-14 13:00 | 2025-08-05 12:00
18550 | STRIVE.R2.MC1.2384.1.342.52.9 | Y | Y | Y | Complete |  | Coupa team to provide System ID to MDG | 42 hrs | 2025-08-01 15:00 | 2025-08-08 17:00 | Pournami Nair | pounair@deloitte.com | Aparajita Mukherjee; S2P Team; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tulika Pal; Amol Paswan | apamukherjee@deloitte.com; usisasols2p@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; tupal@deloitte.com; ampaswan@deloitte.com | MDG | 18849 | 2025-08-01 15:00 | 2025-08-08 17:00 | * | NA | 2025-08-01 15:00 | 2025-08-08 17:00
18552 | STRIVE.R2.MC1.2384.1.342.63 |  |  |  | Complete |  | Security | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18553 | STRIVE.R2.MC1.2384.1.342.63.1 | Y | Y | Y | Complete |  | Provide basis with list of System parameters(RZ11) to be updated | 124 hrs | 2025-07-14 08:00 | 2025-08-04 12:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Jan Bannik; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | jan.bannick@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  | 2025-07-14 08:00 | 2025-08-04 12:00 | * | NA | 2025-07-14 08:00 | 2025-08-04 12:00
18554 | STRIVE.R2.MC1.2384.1.342.63.2 | Y | Y | Y | Complete |  | Create User Groups | 124 hrs | 2025-07-14 08:00 | 2025-08-04 12:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-04 12:00 | * | NA | 2025-07-14 08:00 | 2025-08-04 12:00
18555 | STRIVE.R2.MC1.2384.1.342.63.3 | Y | Y | Y | Complete |  | GRC to assign Bank Master creation role in MDG (Not relevant for MC1) | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | Somitra Thapa | sothapa@deloitte.com | Naman Jaswani; Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | njaswani@deloitte.com; dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18556 | STRIVE.R2.MC1.2384.1.342.63.4 | Y | Y | Y | Complete |  | Assign ESB.messaging.send role to the user in the certificate to send the data from S4HANA backend to integration Suite | 139.94 hrs | 2025-07-14 08:00 | 2025-08-06 11:56 | Somitra Thapa | sothapa@deloitte.com | Naman Jaswani; Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | njaswani@deloitte.com; dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-06 11:56 | * | NA | 2025-07-14 08:00 | 2025-08-06 11:56
18557 | STRIVE.R2.MC1.2384.1.342.63.5 | Y | Y | Y | Complete |  | Roles assignment for ODATA APIs. | 139.93 hrs | 2025-07-14 08:00 | 2025-08-06 11:56 | Somitra Thapa | sothapa@deloitte.com | Naman Jaswani; Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | njaswani@deloitte.com; dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-06 11:56 | * | NA | 2025-07-14 08:00 | 2025-08-06 11:56
18558 | STRIVE.R2.MC1.2384.1.342.63.6 | Y | Y | Y | Complete |  | Creation of SOA user in MDG and S4 system | 124 hrs | 2025-07-14 08:00 | 2025-08-04 12:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-07-14 08:00 | 2025-08-04 12:00 | * | NA | 2025-07-14 08:00 | 2025-08-04 12:00
18559 | STRIVE.R2.MC1.2384.1.342.70 | [5 empty] | MOR | 26.91 hrs | 2025-07-14 08:00 | 2025-07-15 10:59 | [6 empty] | 2025-07-30 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-15 10:59
18560 | STRIVE.R2.MC1.2384.1.342.70.1 | Y | Y | Y | Complete |  | Maintain Number range for Equipment | 2.5 hrs | 2025-08-01 14:30 | 2025-08-01 17:00 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 18397 | 2025-08-01 14:30 | 2025-08-01 17:00 | * | NA | 2025-08-01 14:30 | 2025-08-01 17:00
18561 | STRIVE.R2.MC1.2384.1.342.70.2 | Y | Y | Y | Complete |  | Maintain Number range for Notification | 2.48 hrs | 2025-08-01 14:31 | 2025-08-01 17:00 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 18397 | 2025-08-01 14:31 | 2025-08-01 17:00 | * | NA | 2025-08-01 14:31 | 2025-08-01 17:00
18562 | STRIVE.R2.MC1.2384.1.342.70.3 | Y | Y | Y | Complete |  | Maintain Number range for Work Order | 24 hrs | 2025-07-30 08:00 | 2025-08-01 17:00 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 18397 | 2025-07-30 08:00 | 2025-08-01 17:00 | * | NA | 2025-07-30 08:00 | 2025-08-01 17:00
18563 | STRIVE.R2.MC1.2384.1.342.70.4 | Y | Y | Y | Complete |  | Maintain Number range for Task List | 38.03 hrs | 2025-08-01 17:44 | 2025-08-08 15:02 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 18397 | 2025-08-01 17:44 | 2025-08-08 15:02 | * | NA | 2025-08-01 17:44 | 2025-08-08 15:02
18564 | STRIVE.R2.MC1.2384.1.342.70.5 | Y | Y | Y | Complete |  | Maintain Number range for Maintenance plan and Maintenance Item | 38.18 hrs | 2025-08-01 17:44 | 2025-08-08 15:11 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 18397 | 2025-08-01 17:44 | 2025-08-08 15:11 | * | NA | 2025-08-01 17:44 | 2025-08-08 15:11
18565 | STRIVE.R2.MC1.2384.1.342.70.6 | Y | Y | Y | Complete |  | Maintain Number range for Work pack | 38.5 hrs | 2025-08-01 17:44 | 2025-08-08 15:30 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 18397 | 2025-08-01 17:44 | 2025-08-08 15:30 | * | NA | 2025-08-01 17:44 | 2025-08-08 15:30
18566 | STRIVE.R2.MC1.2384.1.342.70.7 | Y | Y | Y | Complete |  | Maintain Inspection checklist type IW99 | 502.9 hrs | 2025-08-01 14:27 | 2025-08-22 14:45 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  | 2025-08-01 14:27 | 2025-08-22 14:45 | * | NA | 2025-08-01 14:27 | 2025-08-22 14:45
18567 | STRIVE.R2.MC1.2384.1.342.70.8 | Y | Y | Y | Complete |  | Activate allocation of valuation categories | 88.01 hrs | 2025-08-01 14:27 | 2025-08-18 14:28 | Vinod Kumar | vinodkumar692@deloitte.com | Abhishek Sharma; Jay Patel; suyash Chhawala; Chaitnya; Nikhil Gupta; Krishna Teja; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | abhisheksharma59@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; csudhakarraut@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  | 2025-08-01 14:27 | 2025-08-18 14:28 | * | NA | 2025-08-01 14:27 | 2025-08-18 14:28
18568 | STRIVE.R2.MC1.2384.1.342.70.9 | Y | Y | N | In-Progress |  | Data migration-Porfolio Item, provide item templatefiles | 2 hrs | 2025-08-20 11:13 | 2025-08-20 13:14 | Elisa Latona | elisa.latona@it.sasol.com | Vinod Kumar; Jay Patel; Amit Jha; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sven Gelking; Krishna Teja; Nikhil Gupta; Mythili | vinodkumar692@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sven.gelking@de.sasol.com; krishn@deloitte.com; mrgupta3@deloitte.com; myboyapati@deloitte.com | MOR | 19483,19477 | 2025-08-20 11:13 |  | * | NA | 2025-08-20 11:13 | 2025-08-20 13:14
18569 | STRIVE.R2.MC1.2384.1.342.70.10 | N | N | N | Planned |  | validation for portfolio items upload and linkage to PS project | 2 hrs | 2025-09-15 21:58 | 2025-09-15 23:58 | Elisa Latona | elisa.latona@it.sasol.com | Jay Patel; Amit Jha; USI STRIVE CUTOVER; Mythili; Mousikta chanda; Dhruv Kansal; Vinod Kumar; Sven Gelking; Krishna Teja; Nikhil Gupta | jaypatel6@deloitte.com; ajha2@deloitte.no; usistrivecutover@deloitte.com; myboyapati@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; vinodkumar692@deloitte.com; sven.gelking@de.sasol.com; krishn@deloitte.com; mrgupta3@deloitte.com | MOR | 19488 |  |  |  | 2025-09-15 21:58 | 2025-09-15 21:58 | 2025-09-15 23:58
18570 | STRIVE.R2.MC1.2384.1.342.70.11 | N | N | N | Planned |  | Prepare the file and then upload to the system - Decision Point | 2 hrs | 2025-09-15 23:58 | 2025-09-16 02:00 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no | MOR | 18569 |  |  | * | NA | 2025-09-15 23:58 | 2025-09-16 02:00
18571 | STRIVE.R2.MC1.2384.1.342.70.12 | N | N | N | Planned |  | Validation and signoff - Decision Point | 2 hrs | 2025-09-16 02:00 | 2025-09-16 04:00 | Elisa Latona | elisa.latona@it.sasol.com | Jay Patel; Amit Jha; USI STRIVE CUTOVER; Mythili; Mousikta chanda; Dhruv Kansal; Vinod Kumar; Sven Gelking; Krishna Teja; Nikhil Gupta | jaypatel6@deloitte.com; ajha2@deloitte.no; usistrivecutover@deloitte.com; myboyapati@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; vinodkumar692@deloitte.com; sven.gelking@de.sasol.com; krishn@deloitte.com; mrgupta3@deloitte.com | MOR | 18570 |  |  | * | NA | 2025-09-16 02:00 | 2025-09-16 04:00
18572 | STRIVE.R2.MC1.2384.1.342.70.13 | N | N | N | Planned |  | Make number range as internal for PR creation for MOR PPM | 2 hrs | 2025-09-15 21:58 | 2025-09-15 23:58 | Manoj Dombar | mdombar@deloitte.com | Prasanth Kallakuri; Krishna Teja; Jay Patel; Mousikta chanda; S2P Team | kalprasanth@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19487 |  |  |  | 2025-09-15 21:58 | 2025-09-15 21:58 | 2025-09-15 23:58
18573 | STRIVE.R2.MC1.2384.1.342.70.14 | Y | Y | Y | Complete |  | Provide distribution list for Data& Technical failure for interface | 5.81 hrs | 2025-08-19 18:57 | 2025-08-20 00:47 | Elisa Latona | elisa.latona@it.sasol.com | Vinod Kumar; Mythili; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Jay Patel; Amit Jha; Sergio; Joseph Barber | vinodkumar692@deloitte.com; myboyapati@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com | MOR |  | 2025-08-19 18:57 | 2025-08-20 00:47 | * | NA | 2025-08-19 18:57 | 2025-08-20 00:47
77618 | STRIVE.R2.MC1.2384.1.342.70.29 | Y | Y | Y | Complete |  | Create Class/Characteristics for MOR Materials in MDG system | 0.85 hrs | 2025-08-14 13:20 | 2025-08-14 14:11 | Abhishek Sharma | abhisheksharma59@deloitte.com | Chaitnya; Jay Patel; Amit Jha; Vinod; Sven Gelking; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | csudhakarraut@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; vinodkumar692@deloitte.com; sven.gelking@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  | 2025-08-14 13:20 | 2025-08-14 14:11 | * | NA | 2025-08-14 13:20 | 2025-08-14 14:11
77619 | STRIVE.R2.MC1.2384.1.342.70.30 | Y | Y | Y | Complete |  | Create Maintenance Strategies in S4 system | 0.15 hrs | 2025-08-14 16:51 | 2025-08-14 17:00 | Abhishek Sharma | abhisheksharma59@deloitte.com | Chaitnya; Jay Patel; Amit Jha; Vinod; Sven Gelking; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | csudhakarraut@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; vinodkumar692@deloitte.com; sven.gelking@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  | 2025-08-14 16:51 | 2025-08-14 17:00 | * | NA | 2025-08-14 16:51 | 2025-08-14 17:00
18574 | STRIVE.R2.MC1.2384.1.342.85 | [5 empty] | P2C | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18575 | STRIVE.R2.MC1.2384.1.342.85.1 | Y | Y | Y | Complete |  | P2C-TM - Activate Archive Info Structure | 179.43 hrs | 2025-07-14 08:00 | 2025-08-13 11:26 | Diego Zarate | dzarate@deloitte.com | Shubham Mishra; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  | 2025-07-14 08:00 | 2025-08-13 11:26 | * | NA | 2025-07-14 08:00 | 2025-08-13 11:26
18577 | STRIVE.R2.MC1.2384.1.342.85.3 | Y | N | N | Sent |  | Validate sales order with minimum quantity is applied with Rejection reason Z6 | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Ramesh SathishKumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Andrea Ludeke; Tobias Wilmering; Viktoria Kormanikova | satramesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; viktoria.kormanikova@sk.sasol.com | P2C |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18578 | STRIVE.R2.MC1.2384.1.342.85.4 | Y | Y | Y | Complete |  | OPD Configuration Sales Documents | 158.6 hrs | 2025-07-14 08:00 | 2025-08-08 15:36 | Vaishali Singh | vaishsingh@deloitte.com | Rajeev Mishra; Tripti mehta; Siddhesh; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | rajeemishra@deloitte.com; trimehta@deloitte.com; sibaraskar@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C |  | 2025-07-14 08:00 | 2025-08-08 15:36 | * | NA | 2025-07-14 08:00 | 2025-08-08 15:36
20872 | STRIVE.R2.MC1.2384.1.342.85.5 | Y | Y | Y | Complete |  | OPD Configuration Billing Documents | 8.53 hrs | 2025-08-04 13:36 | 2025-08-05 14:08 | Josep Ferrando | jferrandobretones@deloitte.de | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Siddhesh; Rajeev Mishra | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; sibaraskar@deloitte.com; rajeemishra@deloitte.com | P2C |  | 2025-08-04 13:36 | 2025-08-05 14:08 | * | NA | 2025-08-04 13:36 | 2025-08-05 14:08
20881 | STRIVE.R2.MC1.2384.1.342.206 |  |  |  | Complete |  | Output Condition Records (P2C - IM) | 604.45 hrs | 2025-07-14 08:00 | 2025-08-08 14:08 | [6 empty] | 2025-07-14 08:00 | 2025-08-08 14:08 | * | NA | 2025-07-14 08:00 | 2025-08-08 14:08
20882 | STRIVE.R2.MC1.2384.1.342.206.11 | Y | Y | Y | Complete |  | Output Condition Records for Delivery Note Form | 157.13 hrs | 2025-07-14 08:00 | 2025-08-08 14:08 | Manuel | Manuel.Roellinghoff@de.sasol.com | Aaron Dean; Siddhesh; Tripti mehta; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | aaalmeida@deloitte.com; sibaraskar@deloitte.com; trimehta@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  | 2025-07-14 08:00 | 2025-08-08 14:08 | * | NA | 2025-07-14 08:00 | 2025-08-08 14:08
20879 | STRIVE.R2.MC1.2384.1.342.206.8 | Y | Y | Y | Complete |  | Output Condition Records for Proof of Export Form | 157.13 hrs | 2025-07-14 08:00 | 2025-08-08 14:08 | Manuel | Manuel.Roellinghoff@de.sasol.com | Aaron Dean; Siddhesh; Tripti mehta; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | aaalmeida@deloitte.com; sibaraskar@deloitte.com; trimehta@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  | 2025-07-14 08:00 | 2025-08-08 14:08 | * | NA | 2025-07-14 08:00 | 2025-08-08 14:08
20880 | STRIVE.R2.MC1.2384.1.342.206.9 | Y | Y | Y | Complete |  | Output Condition Records for SPED output | 157.12 hrs | 2025-07-14 08:00 | 2025-08-08 14:07 | Manuel | Manuel.Roellinghoff@de.sasol.com | Aaron Dean; Siddhesh; Tripti mehta; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | aaalmeida@deloitte.com; sibaraskar@deloitte.com; trimehta@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  | 2025-07-14 08:00 | 2025-08-08 14:07 | * | NA | 2025-07-14 08:00 | 2025-08-08 14:07
18579 | STRIVE.R2.MC1.2384.1.342.90 |  |  |  | Complete |  | Onesource | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-07-14 08:00 | 2025-08-05 19:39 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18580 | STRIVE.R2.MC1.2384.1.342.90.1 | Y | Y | Y | Complete |  | User/password maintain in /N/IDT/WS -Onesource | 36.96 hrs | 2025-07-14 08:00 | 2025-07-18 13:57 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | BASIS |  | 2025-07-14 08:00 | 2025-07-18 13:57 | * | NA | 2025-07-14 08:00 | 2025-07-18 13:57
18581 | STRIVE.R2.MC1.2384.1.342.90.2 | Y | Y | Y | Complete |  | Set log config to debug | 0 hrs | 2025-08-05 19:38 | 2025-08-05 19:38 | Sachin Yadav | sachinkyadav@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Venkatramana; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; sovenkatramana@deloitte.com; mouchanda@deloitte.com | Onesource |  | 2025-08-05 19:38 | 2025-08-05 19:38 | * | NA | 2025-08-05 19:38 | 2025-08-05 19:38
18582 | STRIVE.R2.MC1.2384.1.342.90.3 | Y | Y | Y | Complete |  | Review Number Ranges for Logs in SAP and set up if not transported | 0 hrs | 2025-08-05 19:39 | 2025-08-05 19:39 | Sachin Yadav | sachinkyadav@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Venkatramana; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; sovenkatramana@deloitte.com; mouchanda@deloitte.com | Onesource |  | 2025-08-05 19:39 | 2025-08-05 19:39 | * | NA | 2025-08-05 19:39 | 2025-08-05 19:39
18583 | STRIVE.R2.MC1.2384.1.342.90.4 | Y | Y | Y | Complete |  | One source certificate in strust | 36.97 hrs | 2025-07-14 08:00 | 2025-07-18 13:58 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Basis; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | BASIS |  | 2025-07-14 08:00 | 2025-07-18 13:58 | * | NA | 2025-07-14 08:00 | 2025-07-18 13:58
18585 | STRIVE.R2.MC1.2384.1.342.96 |  |  |  | Complete |  | R2P-QM | 1275.92 hrs | 2025-07-14 08:00 | 2025-09-05 15:28 | [6 empty] | 2025-08-08 20:32 | 2025-08-29 17:06 | * | NA | 2025-07-14 08:00 | 2025-09-05 15:28
18586 | STRIVE.R2.MC1.2384.1.342.96.1 | Y | Y | Y | Complete |  | R2P-QM-Verify the Number Range - Master inspection characteristics | 0.02 hrs | 2025-08-13 10:04 | 2025-08-13 10:05 | Abhishek Parab | abhparab@deloitte.com | Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Amit das | pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com | R2P |  | 2025-08-13 10:04 | 2025-08-13 10:05 | * | NA | 2025-08-13 10:04 | 2025-08-13 10:05
18587 | STRIVE.R2.MC1.2384.1.342.96.2 | Y | Y | Y | Complete |  | R2P-QM-Verify the Number Range - Inspection Plan | 0.21 hrs | 2025-08-13 09:52 | 2025-08-13 10:05 | Abhishek Parab | abhparab@deloitte.com | Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Amit das | pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com | R2P |  | 2025-08-13 09:52 | 2025-08-13 10:05 | * | NA | 2025-08-13 09:52 | 2025-08-13 10:05
18588 | STRIVE.R2.MC1.2384.1.342.96.3 | Y | Y | Y | Complete |  | R2P-QM - Create Variant for Automatic Usage Decision | 0.81 hrs | 2025-08-29 16:18 | 2025-08-29 17:06 | Pamela Mihali | pamihali@deloitte.de | Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Amit das; Abhishek Parab | dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; abhparab@deloitte.com | R2P |  | 2025-08-29 16:18 | 2025-08-29 17:06 | * | NA | 2025-08-29 16:18 | 2025-08-29 17:06
40155 | STRIVE.R2.MC1.2384.1.342.96.4 | Y | Y | Y | Complete |  | Create Classification-Characteristics for the Inspection Plan | 0 hrs | 2025-08-08 20:32 | 2025-08-08 20:32 | Suruthi | ssubramaniamgovin@deloitte.com | Abhishek Parab; Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Amit das | abhparab@deloitte.com; pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com | R2P |  | 2025-08-08 20:32 | 2025-08-08 20:32 | * | NA | 2025-08-08 20:32 | 2025-08-08 20:32
18589 | STRIVE.R2.MC1.2384.1.342.100 | [5 empty] | S2P - Coupa | 412.7 hrs | 2025-07-14 08:00 | 2025-07-31 13:51 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-31 13:51
18590 | STRIVE.R2.MC1.2384.1.342.100.1 | [5 empty] | Pre Cutover - Manual Activities | 604.07 hrs | 2025-07-14 08:00 | 2025-08-08 13:45 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-08-08 13:45
18591 | STRIVE.R2.MC1.2384.1.342.100.1.1 | Y | Y | Y | Complete |  | Update coupa configuration document - Relevant for Production cutover only | 0 hrs | 2025-08-29 19:00 | 2025-08-29 19:00 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18596,18619,18628,18633,18642 | 2025-08-29 19:00 | 2025-08-29 19:00 |  | 2025-08-25 20:11 | 2025-08-29 19:00 | 2025-08-29 19:00
18592 | STRIVE.R2.MC1.2384.1.342.100.1.2 | Y | Y | Y | Complete |  | Sasol to provide sing-off on the configuration document - Relevant for Production cutover only | 0 hrs | 2025-08-29 19:00 | 2025-08-29 19:00 | Tina Vidrine | tina.vidrine@us.sasol.com | Rahul Sengupta; Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Myriam; Frank Toedter | rahusengupta@deloitte.com; adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P_Coupa | 18591 | 2025-08-29 19:00 | 2025-08-29 19:00 | * | NA | 2025-08-29 19:00 | 2025-08-29 19:00
18593 | STRIVE.R2.MC1.2384.1.342.100.1.3 | Y | Y | Y | Complete |  | Configure homepage content - Relevant for Production cutover only | 0 hrs | 2025-07-31 16:17 | 2025-07-31 16:17 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-07-31 16:17 | 2025-07-31 16:17 | * | NA | 2025-07-31 16:17 | 2025-07-31 16:17
18595 | STRIVE.R2.MC1.2384.1.342.100.1.5 | Y | Y | Y | Complete |  | Load company addresses | 0 hrs | 2025-09-10 17:42 | 2025-09-10 17:42 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-09-10 17:42 | 2025-09-10 17:42 | * | NA | 2025-09-10 17:42 | 2025-09-10 17:42
18596 | STRIVE.R2.MC1.2384.1.342.100.1.6 | Y | Y | Y | Complete |  | R2P to provide final UoM list | 19.21 hrs | 2025-07-29 08:43 | 2025-07-31 11:55 | Hans Jorg | hansjorg.becker@de.sasol.com | Roshanlal; Tatiana; Rahul Sengupta; Adelin Apotsu; Aparajita Mukherjee; Milton; USI STRIVE CUTOVER; Amit das; Mousikta chanda; Dhruv Kansal; Nilesh Deshpande; Torsten Freydt | rohemwani@deloitte.com; tvinogradova@deloitte.de; rahusengupta@deloitte.com; aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; amitdas3@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P | 18393 | 2025-07-29 08:43 | 2025-07-31 11:55 | * | NA | 2025-07-29 08:43 | 2025-07-31 11:55
18597 | STRIVE.R2.MC1.2384.1.342.100.1.7 | Y | Y | Y | Complete |  | Prepare upload files for Unit of Measure | 0 hrs | 2025-08-13 17:07 | 2025-08-13 17:07 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18595 | 2025-08-13 17:07 | 2025-08-13 17:07 | * | NA | 2025-08-13 17:07 | 2025-08-13 17:07
18598 | STRIVE.R2.MC1.2384.1.342.100.1.8 | Y | Y | Y | Complete |  | Load Unit of Measure | 0 hrs | 2025-08-13 17:09 | 2025-08-13 17:09 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18597 | 2025-08-13 17:09 | 2025-08-13 17:09 | * | NA | 2025-08-13 17:09 | 2025-08-13 17:09
18599 | STRIVE.R2.MC1.2384.1.342.100.1.9 | Y | Y | Y | Complete |  | Prepare upload files for content groups | 0 hrs | 2025-07-30 19:00 | 2025-07-30 19:00 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-07-30 19:00 | 2025-07-30 19:00 | * | NA | 2025-07-30 19:00 | 2025-07-30 19:00
18600 | STRIVE.R2.MC1.2384.1.342.100.1.10 | Y | Y | Y | Complete |  | Load Content Groups in Coupa | 0 hrs | 2025-08-04 14:22 | 2025-08-04 14:22 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18599 | 2025-08-04 14:22 | 2025-08-04 14:22 | * | NA | 2025-08-04 14:22 | 2025-08-04 14:22
18601 | STRIVE.R2.MC1.2384.1.342.100.1.11 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Lookup | 0 hrs | 2025-08-04 14:22 | 2025-08-04 14:22 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18600 | 2025-08-04 14:22 | 2025-08-04 14:22 | * | NA | 2025-08-04 14:22 | 2025-08-04 14:22
18602 | STRIVE.R2.MC1.2384.1.342.100.1.12 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Lookup Values | 0 hrs | 2025-08-04 14:23 | 2025-08-04 14:23 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18601 | 2025-08-04 14:23 | 2025-08-04 14:23 | * | NA | 2025-08-04 14:23 | 2025-08-04 14:23
18604 | STRIVE.R2.MC1.2384.1.342.100.1.14 | Y | Y | Y | Complete |  | Finalize data values for lookup Tables | 0 hrs | 2025-08-08 14:18 | 2025-08-08 14:18 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-08 14:18 | 2025-08-08 14:18 | * | NA | 2025-08-08 14:18 | 2025-08-08 14:18
18605 | STRIVE.R2.MC1.2384.1.342.100.1.15 | Y | Y | Y | Complete |  | Create Lookup Tables in Coupa | 0 hrs | 2025-08-08 14:22 | 2025-08-08 14:22 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18604 | 2025-08-08 14:22 | 2025-08-08 14:22 | * | NA | 2025-08-08 14:22 | 2025-08-08 14:22
18606 | STRIVE.R2.MC1.2384.1.342.100.1.16 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Contracting | 0 hrs | 2025-08-08 14:21 | 2025-08-08 14:21 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18605 | 2025-08-08 14:21 | 2025-08-08 14:21 | * | NA | 2025-08-08 14:21 | 2025-08-08 14:21
18607 | STRIVE.R2.MC1.2384.1.342.100.1.17 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Supplier Information | 0 hrs | 2025-08-08 14:21 | 2025-08-08 14:21 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18606 | 2025-08-08 14:21 | 2025-08-08 14:21 | * | NA | 2025-08-08 14:21 | 2025-08-08 14:21
18608 | STRIVE.R2.MC1.2384.1.342.100.1.18 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Suppliers | 0 hrs | 2025-08-08 14:20 | 2025-08-08 14:20 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18607 | 2025-08-08 14:20 | 2025-08-08 14:20 | * | NA | 2025-08-08 14:20 | 2025-08-08 14:20
18609 | STRIVE.R2.MC1.2384.1.342.100.1.19 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Requisition | 0 hrs | 2025-08-08 14:20 | 2025-08-08 14:20 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18608 | 2025-08-08 14:20 | 2025-08-08 14:20 | * | NA | 2025-08-08 14:20 | 2025-08-08 14:20
18610 | STRIVE.R2.MC1.2384.1.342.100.1.20 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Purchase orders | 0 hrs | 2025-08-08 14:19 | 2025-08-08 14:19 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18609 | 2025-08-08 14:19 | 2025-08-08 14:19 | * | NA | 2025-08-08 14:19 | 2025-08-08 14:19
18611 | STRIVE.R2.MC1.2384.1.342.100.1.21 | Y | Y | I | Issue |  | Create Custom Fields in Coupa for Receipts | 2 hrs | 2025-08-08 14:19 | 2025-08-08 16:19 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18610 |  |  | * | NA | 2025-08-08 14:19 | 2025-08-08 16:19
18612 | STRIVE.R2.MC1.2384.1.342.100.1.22 | Y | N | N | Sent |  | Create Custom Fields in Coupa for Invoicing | 2 hrs | 2025-08-25 16:19 | 2025-08-25 18:19 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18611 |  |  |  | 2025-08-25 16:19 | 2025-08-25 16:19 | 2025-08-25 18:19
18613 | STRIVE.R2.MC1.2384.1.342.100.1.23 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Items | 0 hrs | 2025-08-31 10:42 | 2025-08-31 10:42 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18612 | 2025-08-31 10:42 | 2025-08-31 10:42 | * | NA | 2025-08-31 10:42 | 2025-08-31 10:42
18614 | STRIVE.R2.MC1.2384.1.342.100.1.24 | Y | Y | Y | Complete |  | Create Custom Fields in Coupa for Service/time sheet | 0 hrs | 2025-08-31 10:42 | 2025-08-31 10:43 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18613 | 2025-08-31 10:42 | 2025-08-31 10:43 | * | NA | 2025-08-31 10:42 | 2025-08-31 10:43
18615 | STRIVE.R2.MC1.2384.1.342.100.1.25 | Y | Y | Y | Complete |  | Finalize data values and prepare upload files for Lookups: SAP Plant/Sites (Needed for Contract&COA) | 0 hrs | 2025-07-30 19:16 | 2025-07-30 19:16 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-07-30 19:16 | 2025-07-30 19:16 | * | NA | 2025-07-30 19:16 | 2025-07-30 19:16
18616 | STRIVE.R2.MC1.2384.1.342.100.1.26 | Y | Y | Y | Complete |  | Load lookup values for SAP Plant/Site | 0 hrs | 2025-08-04 14:23 | 2025-08-04 14:23 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18615 | 2025-08-04 14:23 | 2025-08-04 14:23 | * | NA | 2025-08-04 14:23 | 2025-08-04 14:23
18619 | STRIVE.R2.MC1.2384.1.342.100.1.29 | Y | Y | Y | Complete |  | S2P S4 Team to provide final list of Purchasing Org | 54.92 hrs | 2025-07-29 08:43 | 2025-08-06 16:38 | Prasanth | kalprasanth@deloitte.com | Rahul Sengupta; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Adelin Apotsu; Aparajita Mukherjee; S2P Team | rahusengupta@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; aapostu@deloittece.com; apamukherjee@deloitte.com; usisasols2p@deloitte.com | S2P | 18394 | 2025-07-29 08:43 | 2025-08-06 16:38 | * | NA | 2025-07-29 08:43 | 2025-08-06 16:38
18620 | STRIVE.R2.MC1.2384.1.342.100.1.30 | Y | Y | Y | Complete |  | Prepare upload files for Lookups: Purchasing org (SIM) | 0 hrs | 2025-08-08 14:16 | 2025-08-08 14:16 | Rahul Sengupta | rahusengupta@deloitte.com | Pournami; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-08 14:16 | 2025-08-08 14:16 | * | NA | 2025-08-08 14:16 | 2025-08-08 14:16
18621 | STRIVE.R2.MC1.2384.1.342.100.1.31 | Y | Y | Y | Complete |  | Load Lookup values for Purchasing Org | 0 hrs | 2025-08-08 14:15 | 2025-08-08 14:15 | Rahul Sengupta | rahusengupta@deloitte.com | Pournami; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18620 | 2025-08-08 14:15 | 2025-08-08 14:15 | * | NA | 2025-08-08 14:15 | 2025-08-08 14:15
18628 | STRIVE.R2.MC1.2384.1.342.100.1.38 | Y | Y | Y | Complete |  | S2P S4 Team to provide final list of Purchasing Groups | 54.99 hrs | 2025-07-29 08:43 | 2025-08-06 16:42 | Prasanth | kalprasanth@deloitte.com | Rahul Sengupta; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Adelin Apotsu; Aparajita Mukherjee; S2P Team | rahusengupta@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; aapostu@deloittece.com; apamukherjee@deloitte.com; usisasols2p@deloitte.com | S2P | 18394 | 2025-07-29 08:43 | 2025-08-06 16:42 | * | NA | 2025-07-29 08:43 | 2025-08-06 16:42
18629 | STRIVE.R2.MC1.2384.1.342.100.1.39 | Y | Y | Y | Complete |  | Prepare upload files for Lookups: Purchasing Group (Commodity) | 0 hrs | 2025-08-08 14:12 | 2025-08-08 14:12 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-08 14:12 | 2025-08-08 14:12 | * | NA | 2025-08-08 14:12 | 2025-08-08 14:12
18630 | STRIVE.R2.MC1.2384.1.342.100.1.40 | Y | Y | Y | Complete |  | Load Lookup values for Purchasing Group | 0 hrs | 2025-08-13 17:11 | 2025-08-13 17:11 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18629 | 2025-08-13 17:11 | 2025-08-13 17:11 | * | NA | 2025-08-13 17:11 | 2025-08-13 17:11
18633 | STRIVE.R2.MC1.2384.1.342.100.1.43 | Y | Y | Y | Complete |  | R2D team to provide final list of Invoicing&Payment WHT | 48 hrs | 2025-08-05 19:06 | 2025-08-13 17:00 | Aquib Iqbal | aquiqbal@deloitte.com | Michaela; Roshanlal; Tatiana; Rahul Sengupta; Adelin Apotsu; Aparajita Mukherjee; Milton; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | michaela.schulz@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; rahusengupta@deloitte.com; aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | R2D | 18396 | 2025-08-05 19:06 | 2025-08-13 17:00 | * | NA | 2025-08-05 19:06 | 2025-08-13 17:00
18634 | STRIVE.R2.MC1.2384.1.342.100.1.44 | Y | Y | Y | Complete |  | Finalize applicable tax codes and prepare upload files for Coupa(WHT and 1 dummy) | 0 hrs | 2025-08-21 15:00 | 2025-08-21 15:00 | Akshat Pradeep | akspradeep@deloitte.com | Rahul Sengupta; Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18633 | 2025-08-21 15:00 | 2025-08-21 15:00 | * | NA | 2025-08-21 15:00 | 2025-08-21 15:00
18635 | STRIVE.R2.MC1.2384.1.342.100.1.45 | Y | Y | Y | Complete |  | Load Tax Codes in Tax Table | 0 hrs | 2025-09-01 11:15 | 2025-09-01 11:15 | Akshat Pradeep | akspradeep@deloitte.com | Rahul Sengupta; Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18634 | 2025-09-01 11:15 | 2025-09-01 11:15 |  | 2025-08-25 19:00 | 2025-09-01 11:15 | 2025-09-01 11:15
18636 | STRIVE.R2.MC1.2384.1.342.100.1.46 | Y | Y | Y | Complete |  | Finalize data for COA | 0 hrs | 2025-08-04 15:31 | 2025-08-04 15:31 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-04 15:31 | 2025-08-04 15:31 | * | NA | 2025-08-04 15:31 | 2025-08-04 15:31
18637 | STRIVE.R2.MC1.2384.1.342.100.1.47 | Y | Y | Y | Complete |  | Create COA in Coupa | 0 hrs | 2025-08-04 15:31 | 2025-08-04 15:31 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18636 | 2025-08-04 15:31 | 2025-08-04 15:31 | * | NA | 2025-08-04 15:31 | 2025-08-04 15:31
18638 | STRIVE.R2.MC1.2384.1.342.100.1.48 | Y | Y | Y | Complete |  | Prepare upload files | 0 hrs | 2025-08-04 15:32 | 2025-08-04 15:32 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-04 15:32 | 2025-08-04 15:32 | * | NA | 2025-08-04 15:32 | 2025-08-04 15:32
18639 | STRIVE.R2.MC1.2384.1.342.100.1.49 | Y | Y | Y | Complete |  | Load Account Security Group | 0 hrs | 2025-08-13 17:33 | 2025-08-13 17:33 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18638 | 2025-08-13 17:33 | 2025-08-13 17:33 | * | NA | 2025-08-13 17:33 | 2025-08-13 17:33
18640 | STRIVE.R2.MC1.2384.1.342.100.1.50 | Y | N | N | Sent |  | Prepare upload files for approval groups | 2 hrs | 2025-08-13 17:33 | 2025-08-13 19:33 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18639 |  |  | * | NA | 2025-08-13 17:33 | 2025-08-13 19:33
18641 | STRIVE.R2.MC1.2384.1.342.100.1.51 | N | N | N | Planned |  | Load Approval Groups in Coupa (Users will be added later) | 2 hrs | 2025-09-15 21:58 | 2025-09-15 23:58 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18640 |  |  |  | 2025-09-15 21:58 | 2025-09-15 21:58 | 2025-09-15 23:58
18642 | STRIVE.R2.MC1.2384.1.342.100.1.52 | Y | Y | Y | Complete |  | R2D team to provide final list of Payment Terms | 47.67 hrs | 2025-07-29 16:08 | 2025-08-06 15:48 | Aquib Iqbal | aquiqbal@deloitte.com | Michaela; Roshanlal; Tatiana; Rahul Sengupta; Adelin Apotsu; Aparajita Mukherjee; Milton; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | michaela.schulz@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; rahusengupta@deloitte.com; aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | R2D | 18396 | 2025-07-29 16:08 | 2025-08-06 15:48 | * | NA | 2025-07-29 16:08 | 2025-08-06 15:48
18643 | STRIVE.R2.MC1.2384.1.342.100.1.53 | Y | Y | Y | Complete |  | Prepare upload files for Payment Terms | 0 hrs | 2025-08-06 14:11 | 2025-08-06 14:11 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18641 | 2025-08-06 14:11 | 2025-08-06 14:11 | * | NA | 2025-08-06 14:11 | 2025-08-06 14:11
18644 | STRIVE.R2.MC1.2384.1.342.100.1.54 | Y | Y | Y | Complete |  | Load payment Terms in Coupa | 0 hrs | 2025-08-06 14:11 | 2025-08-06 14:11 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18643 | 2025-08-06 14:11 | 2025-08-06 14:11 | * | NA | 2025-08-06 14:11 | 2025-08-06 14:11
18654 | STRIVE.R2.MC1.2384.1.342.100.1.64 | Y | N | N | Sent |  | Update Invoice tolerances in Coupa | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18655 | STRIVE.R2.MC1.2384.1.342.100.1.65 | Y | N | N | Sent |  | Update Receiving tolerances in Coupa | 2 hrs | 2025-07-14 10:00 | 2025-07-14 12:00 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18654 |  |  | * | NA | 2025-07-14 10:00 | 2025-07-14 12:00
18656 | STRIVE.R2.MC1.2384.1.342.100.1.66 | Y | N | N | Sent |  | Upload PO Liquid Template in Coupa | 2 hrs | 2025-07-14 12:01 | 2025-07-14 14:01 | Supriya | supriychakraborty@deloitte.com | Adelin Apotsu; Milton; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; miltjones@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18655 |  |  | * | NA | 2025-07-14 12:01 | 2025-07-14 14:01
18657 | STRIVE.R2.MC1.2384.1.342.100.1.67 | Y | N | N | Sent |  | Add legal entity name for each PO template by CoA | 2 hrs | 2025-07-14 14:01 | 2025-07-14 16:01 | Supriya | supriychakraborty@deloitte.com | Adelin Apotsu; Milton; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; miltjones@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18656 |  |  | * | NA | 2025-07-14 14:01 | 2025-07-14 16:01
18658 | STRIVE.R2.MC1.2384.1.342.100.1.68 | Y | N | N | Sent |  | Activate Invoice Presentations | 2 hrs | 2025-07-14 14:01 | 2025-07-14 16:01 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18656 |  |  | * | NA | 2025-07-14 14:01 | 2025-07-14 16:01
18659 | STRIVE.R2.MC1.2384.1.342.100.1.69 | Y | Y | Y | Complete |  | Update requester access settings | 0 hrs | 2025-08-08 14:22 | 2025-08-08 14:22 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-08 14:22 | 2025-08-08 14:22 | * | NA | 2025-08-08 14:22 | 2025-08-08 14:22
18661 | STRIVE.R2.MC1.2384.1.342.100.1.71 | Y | Y | Y | Complete |  | Get the user list from GRC Team - Relevant for DR and Production cutover | 0 hrs | 2025-08-29 19:00 | 2025-08-29 19:00 | Milton | miltjones@deloitte.com | Adelin Apotsu; Adrian Naidoo; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-29 19:00 | 2025-08-29 19:00 | * | NA | 2025-08-29 19:00 | 2025-08-29 19:00
18662 | STRIVE.R2.MC1.2384.1.342.100.1.72 | Y | Y | Y | Complete |  | Validate Role to Position Mapping - Relevant for DR and Production cutover | 0 hrs | 2025-08-29 19:00 | 2025-08-29 19:00 | Adelin Apotsu | aapostu@deloittece.com | Adrian Naidoo; Milton; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; miltjones@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18661 | 2025-08-29 19:00 | 2025-08-29 19:00 |  | 2025-09-02 16:12 | 2025-08-29 19:00 | 2025-08-29 19:00
18663 | STRIVE.R2.MC1.2384.1.342.100.1.73 | Y | Y | Y | Complete |  | Share final list of users - Relevant for DR and Production cutover | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Jan Bannik | jan.bannick@de.sasol.com | Sasol GRC; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18664 | STRIVE.R2.MC1.2384.1.342.100.1.74 | Y | Y | Y | Complete |  | Finalize user list and appropriate roles - Relevant for DR and Production cutover | 0 hrs | 2025-08-29 19:00 | 2025-08-29 19:00 | Adelin Apotsu | aapostu@deloittece.com | Adrian Naidoo; Milton; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; miltjones@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18662 | 2025-08-29 19:00 | 2025-08-29 19:00 |  | 2025-08-25 20:22 | 2025-08-29 19:00 | 2025-08-29 19:00
18665 | STRIVE.R2.MC1.2384.1.342.100.1.75 | Y | Y | Y | Complete |  | Define approval groups, content groups, account security groups and custom roles to all elevated users - Relevant for DR and Production cutover | 0 hrs | 2025-08-29 19:01 | 2025-08-29 19:01 | Adelin Apotsu | aapostu@deloittece.com | Adrian Naidoo; Milton; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; miltjones@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18664 | 2025-08-29 19:01 | 2025-08-29 19:01 | * | NA | 2025-08-29 19:01 | 2025-08-29 19:01
18666 | STRIVE.R2.MC1.2384.1.342.100.1.76 | Y | Y | Y | Complete |  | Load users in Coupa in inactive state - Relevant for DR and Production cutover | 0 hrs | 2025-08-29 19:01 | 2025-08-29 19:01 | Rahul Sengupta | rahusengupta@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18665 | 2025-08-29 19:01 | 2025-08-29 19:01 | * | NA | 2025-08-29 19:01 | 2025-08-29 19:01
18672 | STRIVE.R2.MC1.2384.1.342.100.1.82 | Y | Y | Y | Complete |  | Create SIM Forms (TBD on final list of SIM Forms) | 0.03 hrs | 2025-09-01 00:25 | 2025-09-01 00:26 | Manoj manickraj | mmanickrajkovilpi@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-09-01 00:25 | 2025-09-01 00:26 |  | 2025-08-25 22:22 | 2025-09-01 00:25 | 2025-09-01 00:26
18673 | STRIVE.R2.MC1.2384.1.342.100.1.83 | Y | Y | Y | Complete |  | Create SIM Forms (External Supplier Creation) | 0 hrs | 2025-09-01 00:25 | 2025-09-01 00:27 | Manoj manickraj | mmanickrajkovilpi@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18672 | 2025-09-01 00:25 | 2025-09-01 00:27 |  | 2025-08-25 22:22 | 2025-09-01 00:25 | 2025-09-01 00:27
18674 | STRIVE.R2.MC1.2384.1.342.100.1.84 | Y | Y | Y | Complete |  | Create SIM Forms (Internal Supplier Creation) | 0.04 hrs | 2025-09-01 00:25 | 2025-09-01 00:27 | Manoj manickraj | mmanickrajkovilpi@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18673 | 2025-09-01 00:25 | 2025-09-01 00:27 | * | NA | 2025-09-01 00:25 | 2025-09-01 00:27
18675 | STRIVE.R2.MC1.2384.1.342.100.1.85 | Y | Y | Y | Complete |  | Create SIM Forms (Supplier Update and Extension) | 0.04 hrs | 2025-09-01 00:25 | 2025-09-01 00:28 | Manoj manickraj | mmanickrajkovilpi@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18674 | 2025-09-01 00:25 | 2025-09-01 00:28 | * | NA | 2025-09-01 00:25 | 2025-09-01 00:28
18676 | STRIVE.R2.MC1.2384.1.342.100.1.86 | Y | Y | Y | Complete |  | Create SIM Forms (Remit-To Subform) | 0 hrs | 2025-08-26 12:26 | 2025-08-26 12:26 | Manoj manickraj | mmanickrajkovilpi@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-26 12:26 | 2025-08-26 12:26 | * | NA | 2025-08-26 12:26 | 2025-08-26 12:26
18677 | STRIVE.R2.MC1.2384.1.342.100.1.87 | Y | Y | Y | Complete |  | Create SIM Forms (Block/Deactivation) | 0.03 hrs | 2025-09-01 00:25 | 2025-09-01 00:27 | Manoj manickraj | mmanickrajkovilpi@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18676 | 2025-09-01 00:25 | 2025-09-01 00:27 | * | NA | 2025-09-01 00:25 | 2025-09-01 00:27
18678 | STRIVE.R2.MC1.2384.1.342.100.1.88 | Y | Y | Y | Complete |  | Create Custom Forms (Supplier complaint and Feedback) | 0 hrs | 2025-09-01 16:30 | 2025-09-01 16:31 | Manoj manickraj | mmanickrajkovilpi@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18677 | 2025-09-01 16:30 | 2025-09-01 16:31 | * | NA | 2025-09-01 16:30 | 2025-09-01 16:31
18680 | STRIVE.R2.MC1.2384.1.342.100.1.90 | Y | Y | I | Issue |  | Create Contract Template | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18682 | STRIVE.R2.MC1.2384.1.342.100.1.92 | Y | N | N | Sent |  | Configure Coupa Contract Clause Library | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18683 | STRIVE.R2.MC1.2384.1.342.100.1.93 | N | N | N | Planned |  | Configure DocuSign e-signature account | 2 hrs | 2025-09-15 21:58 | 2025-09-15 23:58 | Rabbani | skhadarmohammadra@deloitte.com | Aparajita Mukherjee; Dhruv Kansal; Milton; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; dhkansal@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18682 |  |  |  | 2025-09-15 21:58 | 2025-09-15 21:58 | 2025-09-15 23:58
18686 | STRIVE.R2.MC1.2384.1.342.100.1.96 | Y | Y | Y | Complete |  | Configure and validate Requester Access settings | 0 hrs | 2025-08-13 17:14 | 2025-08-13 17:14 | Rahul Sengupta | rahusengupta@deloitte.com | Adelin Apotsu; Milton; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; miltjones@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  | 2025-08-13 17:14 | 2025-08-13 17:14 | * | NA | 2025-08-13 17:14 | 2025-08-13 17:14
18687 | STRIVE.R2.MC1.2384.1.342.100.1.97 | Y | Y | I | Issue |  | Configure Dispute Reasons | 2 hrs | 2025-08-14 10:00 | 2025-08-14 12:00 | Akshat Pradeep | akspradeep@deloitte.com | Pournami Nair; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18686 |  |  |  | 2025-08-14 10:00 | 2025-08-14 10:00 | 2025-08-14 12:00
18688 | STRIVE.R2.MC1.2384.1.342.100.1.98 | Y | Y | Y | Complete |  | Create API filters Po reciepts, SES and invoices | 3.91 hrs | 2025-09-04 16:21 | 2025-09-04 20:15 | Pournami Nair | pounair@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18592 | 2025-09-04 16:21 | 2025-09-04 20:15 |  | 2025-09-02 16:12 | 2025-09-04 16:21 | 2025-09-04 20:15
18689 | STRIVE.R2.MC1.2384.1.342.100.1.99 | Y | Y | I | Issue |  | Create Endpoint,Custom filter and Callouts: PR initial check,PR Final check,PO change initial check&PO Change Final check S2P_I_036 | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Pournami Nair | pounair@deloitte.com | Rabbani; S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | skhadarmohammadra@deloitte.com; usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P_Coupa |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18690 | STRIVE.R2.MC1.2384.1.342.100.1.100 | N | N | N | Planned |  | Create Invoice Views | 2 hrs | 2025-09-15 21:58 | 2025-09-15 23:58 | Akshat Pradeep | akspradeep@deloitte.com | Pournami Nair; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18687 |  |  |  | 2025-09-15 21:58 | 2025-09-15 21:58 | 2025-09-15 23:58
18691 | STRIVE.R2.MC1.2384.1.342.100.1.101 | N | N | N | Planned |  | Create P2R views | 2 hrs | 2025-09-15 21:58 | 2025-09-15 23:58 | Supriya | supriychakraborty@deloitte.com | Pournami Nair; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18687 |  |  |  | 2025-09-15 21:58 | 2025-09-15 21:58 | 2025-09-15 23:58
18692 | STRIVE.R2.MC1.2384.1.342.100.1.102 | Y | N | N | Sent |  | Validate all configurations are completed in Coupa | 2 hrs | 2025-09-05 21:58 | 2025-09-05 23:58 | Adelin Apotsu | aapostu@deloittece.com | Rahul Sengupta; Milton; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rahusengupta@deloitte.com; miltjones@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18688 |  |  |  | 2025-09-05 21:58 | 2025-09-05 21:58 | 2025-09-05 23:58
77620 | STRIVE.R2.MC1.2384.1.342.100.1.106 | Y | Y | Y | Complete |  | Update Italy contracts with appropriate contract type - Relevant for Production cutover only | 0 hrs | 2025-08-13 20:37 | 2025-08-13 20:37 | Amanda Ihli | amanda.ihli@us.sasol.com | Aparajita Mukherjee; Rabbani; S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | apamukherjee@deloitte.com; skhadarmohammadra@deloitte.com; usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P_Coupa | 18680 | 2025-08-13 20:37 | 2025-08-13 20:37 |  | 2025-08-14 08:00 | 2025-08-13 20:37 | 2025-08-13 20:37
94527 | STRIVE.R2.MC1.2384.1.342.100.1.107 | Y | Y | Y | Complete |  | Update approval chain for Italy - Relevant for Production cutover only | 0 hrs | 2025-08-29 19:01 | 2025-08-29 19:01 | Amanda Ihli | amanda.ihli@us.sasol.com | Aparajita Mukherjee; Rabbani; S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | apamukherjee@deloitte.com; skhadarmohammadra@deloitte.com; usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P_Coupa | 77620 | 2025-08-29 19:01 | 2025-08-29 19:01 |  | 2025-09-15 08:00 | 2025-08-29 19:01 | 2025-08-29 19:01
94528 | STRIVE.R2.MC1.2384.1.342.100.1.108 | Y | Y | Y | Complete |  | Create requisition line form - Relevant for Production cutover only | 0 hrs | 2025-08-29 19:01 | 2025-08-29 19:01 | Supriya | supriychakraborty@deloitte.com | Pournami Nair; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 18691 | 2025-08-29 19:01 | 2025-08-29 19:01 |  | 2025-09-15 08:00 | 2025-08-29 19:01 | 2025-08-29 19:01
18695 | STRIVE.R2.MC1.2384.1.548 | [5 empty] | Load Preparation | 774.85 hrs | 2025-07-14 08:00 | 2025-08-15 17:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-08-15 17:00
18696 | STRIVE.R2.MC1.2384.1.548.1 | [5 empty] | Upload/Enrichment file Readiness | 434.8 hrs | 2025-08-01 08:00 | 2025-08-19 12:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-08-01 08:00 | 2025-08-19 12:00
18698 | STRIVE.R2.MC1.2384.1.548.1.2 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Inspection Plan | 604.82 hrs | 2025-08-01 08:00 | 2025-08-26 14:30 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:30 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:30
18699 | STRIVE.R2.MC1.2384.1.548.1.3 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Inspection SetUp (MIC) | 604.82 hrs | 2025-08-01 08:00 | 2025-08-26 14:30 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:30 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:30
18700 | STRIVE.R2.MC1.2384.1.548.1.4 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Material Receipe/ Routing | 604.81 hrs | 2025-08-01 08:00 | 2025-08-26 14:30 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:30 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:30
18701 | STRIVE.R2.MC1.2384.1.548.1.5 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Resource/ Capacities | 604.75 hrs | 2025-08-01 08:00 | 2025-08-26 14:26 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:26 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:26
18702 | STRIVE.R2.MC1.2384.1.548.1.6 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Master Inspection Characteristics | 604.81 hrs | 2025-08-01 08:00 | 2025-08-26 14:30 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:30 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:30
18703 | STRIVE.R2.MC1.2384.1.548.1.7 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Production Version | 604.8 hrs | 2025-08-01 08:00 | 2025-08-26 14:29 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:29 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:29
21029 | STRIVE.R2.MC1.2384.1.548.1.60 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Inspection Method | 604.8 hrs | 2025-08-01 08:00 | 2025-08-26 14:29 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:29 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:29
21028 | STRIVE.R2.MC1.2384.1.548.1.59 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Quality Certificate Profile | 604.8 hrs | 2025-08-01 08:00 | 2025-08-26 14:29 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:29 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:29
21027 | STRIVE.R2.MC1.2384.1.548.1.58 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Bill of Material | 604.79 hrs | 2025-08-01 08:00 | 2025-08-26 14:29 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:29 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:29
18704 | STRIVE.R2.MC1.2384.1.548.1.8 | Y | Y | Y | Complete |  | Upload files are made available - Work Center | 40.21 hrs | 2025-08-04 11:28 | 2025-08-11 11:40 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR | 19497 | 2025-08-04 11:28 | 2025-08-11 11:40 | * | NA | 2025-08-04 11:28 | 2025-08-11 11:40
18705 | STRIVE.R2.MC1.2384.1.548.1.9 | Y | Y | Y | Complete |  | Upload files are made available - EAM Class | 653.01 hrs | 2025-08-01 08:00 | 2025-08-28 14:50 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-08-01 08:00 | 2025-08-28 14:50 | * | NA | 2025-08-01 08:00 | 2025-08-28 14:50
18706 | STRIVE.R2.MC1.2384.1.548.1.10 | Y | Y | Y | Complete |  | Upload files are made available - EAM Characteristics | 653.02 hrs | 2025-08-01 08:00 | 2025-08-28 14:50 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-08-01 08:00 | 2025-08-28 14:50 | * | NA | 2025-08-01 08:00 | 2025-08-28 14:50
18707 | STRIVE.R2.MC1.2384.1.548.1.11 | Y | Y | Y | Complete |  | Verify Xref files are made available - Project | 165.1 hrs | 2025-07-21 08:00 | 2025-08-18 14:06 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-18 14:06 | * | NA | 2025-07-21 08:00 | 2025-08-18 14:06
18708 | STRIVE.R2.MC1.2384.1.548.1.12 | Y | Y | Y | Complete |  | Verify Xref files are made available - WBS | 165.09 hrs | 2025-07-21 08:00 | 2025-08-18 14:05 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-18 14:05 | * | NA | 2025-07-21 08:00 | 2025-08-18 14:05
18709 | STRIVE.R2.MC1.2384.1.548.1.13 | Y | Y | Y | Complete |  | Verify Xref files are made available - Equipment BOM | 143.68 hrs | 2025-07-21 08:00 | 2025-08-13 16:41 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:41 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:41
18710 | STRIVE.R2.MC1.2384.1.548.1.14 | Y | Y | Y | Complete |  | Verify Xref files are made available - DIR | 143.68 hrs | 2025-07-21 08:00 | 2025-08-13 16:41 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:41 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:41
18711 | STRIVE.R2.MC1.2384.1.548.1.15 | Y | Y | Y | Complete |  | Verify Xref files are made available - Equipment | 71.68 hrs | 2025-08-01 08:00 | 2025-08-13 16:41 | Sven Gelking | sven.gelking@de.sasol.com | Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-08-01 08:00 | 2025-08-13 16:41 | * | NA | 2025-08-01 08:00 | 2025-08-13 16:41
18712 | STRIVE.R2.MC1.2384.1.548.1.16 | Y | Y | Y | Complete |  | Verify Xref files are made available - Functional Location | 143.69 hrs | 2025-07-21 08:00 | 2025-08-13 16:41 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:41 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:41
18713 | STRIVE.R2.MC1.2384.1.548.1.17 | Y | Y | Y | Complete |  | Verify Xref files are made available - Technical Assignment to Object classification | 143.69 hrs | 2025-07-21 08:00 | 2025-08-13 16:42 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:42 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:42
18714 | STRIVE.R2.MC1.2384.1.548.1.18 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Customer Sales area deduplication list​ | 0 hrs | 2025-08-13 15:06 | 2025-08-13 15:06 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Ramesh SathishKumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Andrea Ludeke; Tobias Wilmering; Viktoria Kormanikova | satramesh@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; viktoria.kormanikova@sk.sasol.com | P2C |  | 2025-08-13 15:06 |  | * | NA | 2025-08-13 15:06 | 2025-08-13 15:06
18715 | STRIVE.R2.MC1.2384.1.548.1.19 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Customer exclusion list​ | 0 hrs | 2025-08-13 15:07 | 2025-08-13 15:07 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Ramesh SathishKumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Andrea Ludeke; Tobias Wilmering; Viktoria Kormanikova | satramesh@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; viktoria.kormanikova@sk.sasol.com | P2C |  | 2025-08-13 15:07 |  | * | NA | 2025-08-13 15:07 | 2025-08-13 15:07
18716 | STRIVE.R2.MC1.2384.1.548.1.20 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Material Inclusion/Exclusion​ | 0 hrs | 2025-08-13 15:05 | 2025-08-13 15:05 | Ines Tesch | ines.tesch@de.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Cross-team |  | 2025-08-13 15:05 | 2025-08-13 15:05 | * | NA | 2025-08-13 15:05 | 2025-08-13 15:05
18717 | STRIVE.R2.MC1.2384.1.548.1.21 | Y | Y | Y | Complete |  | Verify Xref files are made available - General Maintenance Task List​ | 0 hrs | 2025-08-19 18:54 | 2025-08-19 18:54 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-08-19 18:54 | 2025-08-19 18:54 |  | 2025-07-21 08:00 | 2025-08-19 18:54 | 2025-08-19 18:54
18718 | STRIVE.R2.MC1.2384.1.548.1.22 | Y | Y | Y | Complete |  | Verify Xref files are made available - Functional Location Task List | 143.7 hrs | 2025-07-21 08:00 | 2025-08-13 16:42 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:42 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:42
18719 | STRIVE.R2.MC1.2384.1.548.1.23 | Y | Y | Y | Complete |  | Verify Xref files are made available - Equipment Task List | 143.7 hrs | 2025-07-21 08:00 | 2025-08-13 16:42 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:42 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:42
18720 | STRIVE.R2.MC1.2384.1.548.1.24 | Y | Y | Y | Complete |  | Verify Xref files are made available - Maintenance Item | 143.7 hrs | 2025-07-21 08:00 | 2025-08-13 16:42 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:42 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:42
18721 | STRIVE.R2.MC1.2384.1.548.1.25 | Y | Y | Y | Complete |  | Upload/Enrichment files are made available - Quality certificate Profile | 604.76 hrs | 2025-08-01 08:00 | 2025-08-26 14:27 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini; Mousikta chanda; Nilesh Deshpande; Torsten Freydt | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-01 08:00 | 2025-08-26 14:27 | * | NA | 2025-08-01 08:00 | 2025-08-26 14:27
18722 | STRIVE.R2.MC1.2384.1.548.1.26 | Y | Y | Y | Complete |  | Verify Xref files are made available - Maintenance Notification | 143.71 hrs | 2025-07-21 08:00 | 2025-08-13 16:43 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:43 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:43
18723 | STRIVE.R2.MC1.2384.1.548.1.27 | Y | Y | Y | Complete |  | Verify Xref files are made available - Maintenance Plan | 143.71 hrs | 2025-07-21 08:00 | 2025-08-13 16:43 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:43 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:43
18724 | STRIVE.R2.MC1.2384.1.548.1.28 | Y | Y | Y | Complete |  | Verify Xref files are made available - Maintenance work orders and Historical work orders | 143.73 hrs | 2025-07-21 08:00 | 2025-08-13 16:44 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; ; | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ; | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:44 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:44
18725 | STRIVE.R2.MC1.2384.1.548.1.29 | [5 empty] | Xrefs are confirmed and ready for Migration Cycle | 2233.36 hrs | 2025-07-14 08:00 | 2025-10-15 15:35 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-10-15 15:35
18726 | STRIVE.R2.MC1.2384.1.548.1.29.1 | Y | Y | Y | Complete |  | Xrefs are confirmed and ready for Migration Cycle - R2D | 167.7 hrs | 2025-07-21 08:00 | 2025-08-18 16:42 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Tatiana; Roshanlal; Alex Miles; Satyajit; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | tvinogradova@deloitte.de; rohemwani@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | R2D |  | 2025-07-21 08:00 | 2025-08-18 16:42 |  | 2025-07-20 08:00 | 2025-07-21 08:00 | 2025-08-18 16:42
18727 | STRIVE.R2.MC1.2384.1.548.1.29.2 | Y | Y | Y | Complete |  | Xrefs are confirmed and ready for Migration Cycle - R2P | 868.01 hrs | 2025-07-21 08:00 | 2025-08-26 14:26 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Torsten Freydt; Jay Saini | alex.pradeep@us.sasol.com; amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; jaysaini4@deloitte.com | R2P |  | 2025-07-21 08:00 | 2025-08-26 14:26 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-26 14:26
18728 | STRIVE.R2.MC1.2384.1.548.1.29.3 | Y | Y | Y | Complete |  | Xrefs are confirmed and ready for Migration Cycle - MOR | 143.73 hrs | 2025-07-21 08:00 | 2025-08-13 16:44 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Elisa Latona; Sergio; Joseph Barber; ; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | Daniel.Bunge@de.sasol.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; ; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | MOR |  | 2025-07-21 08:00 | 2025-08-13 16:44 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-13 16:44
18729 | STRIVE.R2.MC1.2384.1.548.1.29.4 | Y | Y | Y | Complete |  | Xrefs are confirmed and ready for Migration Cycle - P2C | 0 hrs | 2025-08-11 20:25 | 2025-08-11 20:25 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ramesh SathishKumar; Andrea Ludeke; Tobias Wilmering | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; satramesh@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com | P2C |  | 2025-08-11 20:25 | 2025-08-11 20:25 |  | 2025-07-21 08:00 | 2025-08-11 20:25 | 2025-08-11 20:25
18730 | STRIVE.R2.MC1.2384.1.548.1.29.5 | Y | Y | Y | Complete |  | Xrefs are confirmed and ready for Migration Cycle - S2P | 773.59 hrs | 2025-07-21 08:00 | 2025-08-22 15:45 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Tina Vidrine; Frank Toedter | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de | S2P |  | 2025-07-21 08:00 | 2025-08-22 15:45 |  | 2025-07-21 08:00 | 2025-07-21 08:00 | 2025-08-22 15:45
18731 | STRIVE.R2.MC1.2384.1.548.1.29.6 | Y | Y | Y | Complete |  | Update X-ref details in Syniti - R2D | 26.41 hrs | 2025-08-18 16:42 | 2025-08-19 19:11 | Alex Miles | almiles@deloitte.de | Satyajit Patnaik; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda; Savri Sumeet Jagatap | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; ssumeetjagatap@deloitte.com | DM | 18726 | 2025-08-18 16:42 | 2025-08-19 19:11 | * | NA | 2025-08-18 16:42 | 2025-08-19 19:11
18732 | STRIVE.R2.MC1.2384.1.548.1.29.7 | Y | N | N | Sent |  | Update X-ref details in Syniti - R2P | 8 hrs | 2025-08-26 14:26 | 2025-08-26 22:26 | Alex Miles | almiles@deloitte.de | Satyajit Patnaik; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda; Savri Sumeet Jagatap | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; ssumeetjagatap@deloitte.com | DM | 18727 |  |  | * | NA | 2025-08-26 14:26 | 2025-08-26 22:26
18733 | STRIVE.R2.MC1.2384.1.548.1.29.8 | Y | Y | Y | Complete |  | Update X-ref details in Syniti - MOR | 213.14 hrs | 2025-08-13 16:44 | 2025-08-22 14:28 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Alex Miles; Satyajit Patnaik; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda | almiles@deloitte.de; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com | DM | 18728 | 2025-08-13 16:44 | 2025-08-22 14:28 | * | NA | 2025-08-13 16:44 | 2025-08-22 14:28
18734 | STRIVE.R2.MC1.2384.1.548.1.29.9 | Y | Y | Y | Complete |  | Update X-ref details in Syniti - P2C | 12.43 hrs | 2025-08-12 08:00 | 2025-08-13 13:26 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Alex Miles; Satyajit Patnaik; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda | almiles@deloitte.de; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com | DM | 18729 | 2025-08-12 08:00 | 2025-08-13 13:26 | * | NA | 2025-08-12 08:00 | 2025-08-13 13:26
18735 | STRIVE.R2.MC1.2384.1.548.1.29.10 | Y | Y | Y | Complete |  | Update X-ref details in Syniti - S2P | 2.54 hrs | 2025-08-22 15:45 | 2025-08-22 18:17 | Rishi Tirthani | rtirthani@deloitte.com | Alex Miles; Satyajit Patnaik; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda; Savri Sumeet Jagatap | almiles@deloitte.de; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; ssumeetjagatap@deloitte.com | DM | 18730 | 2025-08-22 15:45 | 2025-08-22 18:17 | * | NA | 2025-08-22 15:45 | 2025-08-22 18:17
18736 | STRIVE.R2.MC1.2384.1.548.1.29.11 |  |  |  | Complete |  | Material Master Configuration Synchronization Confirmation | 668.45 hrs | 2025-07-14 08:00 | 2025-11-06 13:27 | [6 empty] | 2025-08-05 08:00 | 2025-08-12 16:14 | * | NA | 2025-07-14 08:00 | 2025-11-06 13:27
18737 | STRIVE.R2.MC1.2384.1.548.1.29.11.1 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Prod Systems - ZFIN | 0 hrs | 2025-08-08 17:45 | 2025-08-08 17:45 | Ramesh SathishKumar | satramesh@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jessica Goffi | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com | Cross-team |  | 2025-08-08 17:45 | 2025-08-08 17:45 | * | NA | 2025-08-08 17:45 | 2025-08-08 17:45
18738 | STRIVE.R2.MC1.2384.1.548.1.29.11.2 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Prod Systems - ZRAW | 38.24 hrs | 2025-08-05 08:00 | 2025-08-11 15:15 | Prasanth | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Maria Luisa Geremicca | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; marialuisa.geremicca@it.sasol.com | Cross-team |  | 2025-08-05 08:00 | 2025-08-11 15:15 |  | 2025-08-05 08:00 | 2025-08-05 08:00 | 2025-08-11 15:15
18740 | STRIVE.R2.MC1.2384.1.548.1.29.11.4 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Prod Systems - ZSFG | 47.23 hrs | 2025-08-05 08:00 | 2025-08-12 16:14 | Amit das | amitdas3@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hans Jorg; Torsten Freydt | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com | Cross-team |  | 2025-08-05 08:00 | 2025-08-12 16:14 |  | 2025-08-05 08:00 | 2025-08-05 08:00 | 2025-08-12 16:14
18741 | STRIVE.R2.MC1.2384.1.548.1.29.11.5 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Prod Systems - ZPKG | 38.23 hrs | 2025-08-05 08:00 | 2025-08-11 15:14 | Prasanth | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Maria Luisa Geremicca | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; marialuisa.geremicca@it.sasol.com | Cross-team |  | 2025-08-05 08:00 | 2025-08-11 15:14 |  | 2025-08-05 08:00 | 2025-08-05 08:00 | 2025-08-11 15:14
18742 | STRIVE.R2.MC1.2384.1.548.1.29.11.6 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Prod Systems - ZOPS | 47.24 hrs | 2025-08-05 08:00 | 2025-08-12 16:14 | Amit das | amitdas3@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hans Jorg; Torsten Freydt | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com | Cross-team |  | 2025-08-05 08:00 | 2025-08-12 16:14 |  | 2025-08-05 08:00 | 2025-08-05 08:00 | 2025-08-12 16:14
18743 | STRIVE.R2.MC1.2384.1.548.1.29.11.7 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Prod Systems - ZCAT | 38.22 hrs | 2025-08-05 08:00 | 2025-08-11 15:13 | Prasanth | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Maria Luisa Geremicca | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; marialuisa.geremicca@it.sasol.com | Cross-team |  | 2025-08-05 08:00 | 2025-08-11 15:13 |  | 2025-08-05 08:00 | 2025-08-05 08:00 | 2025-08-11 15:13
18744 | STRIVE.R2.MC1.2384.1.548.1.29.11.8 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Prod Systems - ZMAG | 0 hrs | 2025-08-07 17:54 | 2025-08-07 17:54 | Abhishek Sharma | abhisheksharma59@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sven Gelking; Jay Patel; Amit Jha | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sven.gelking@de.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no | Cross-team |  | 2025-08-07 17:54 | 2025-08-07 17:54 | * | NA | 2025-08-07 17:54 | 2025-08-07 17:54
18745 | STRIVE.R2.MC1.2384.1.548.1.29.20 |  |  |  | Complete |  | ITC Data Load Schedule and Confirm | 176.52 hrs | 2025-07-14 08:00 | 2025-07-21 17:00 | [6 empty] | 2025-08-07 08:00 | 2025-08-21 08:53 | * | NA | 2025-07-14 08:00 | 2025-07-21 17:00
18746 | STRIVE.R2.MC1.2384.1.548.1.29.20.1 | Y | Y | Y | Complete |  | Review ITC Data Load Schedule and Confirm- R2D | 63.71 hrs | 2025-08-07 08:00 | 2025-08-18 16:43 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Roshan; Tatiana | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  | 2025-08-07 08:00 | 2025-08-18 16:43 |  | 2025-08-07 08:00 | 2025-08-07 08:00 | 2025-08-18 16:43
18747 | STRIVE.R2.MC1.2384.1.548.1.29.20.2 | Y | Y | Y | Complete |  | Review ITC Data Load Schedule and Confirm - P2C | 0 hrs | 2025-08-08 18:48 | 2025-08-08 18:48 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Ramesh SathishKumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Andrea Ludeke; Tobias Wilmering | satramesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com | P2C |  | 2025-08-08 18:48 | 2025-08-08 18:48 |  | 2025-08-07 08:00 | 2025-08-08 18:48 | 2025-08-08 18:48
18748 | STRIVE.R2.MC1.2384.1.548.1.29.20.3 | Y | Y | Y | Complete |  | Review ITC Data Load Schedule and Confirm - S2P | 335.92 hrs | 2025-08-07 08:00 | 2025-08-21 08:51 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; S2P Team; Milton; Prasanth; Tina Vidrine; Frank Toedter | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; miltjones@deloitte.com; kalprasanth@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de | S2P |  | 2025-08-07 08:00 | 2025-08-21 08:51 |  | 2025-08-07 08:00 | 2025-08-07 08:00 | 2025-08-21 08:51
18749 | STRIVE.R2.MC1.2384.1.548.1.29.20.4 | Y | Y | Y | Complete |  | Review ITC Data Load Schedule and Confirm - S2P_COUPA | 335.95 hrs | 2025-08-07 08:00 | 2025-08-21 08:53 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Tina Vidrine; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Milton; S2P Team; Aparajita Mukherjee; Frank Toedter | tina.vidrine@us.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; miltjones@deloitte.com; usisasols2p@deloitte.com; apamukherjee@deloitte.com; ft@toedter-consult.de | S2P_Coupa |  | 2025-08-07 08:00 | 2025-08-21 08:53 |  | 2025-08-07 08:00 | 2025-08-07 08:00 | 2025-08-21 08:53
18750 | STRIVE.R2.MC1.2384.1.548.1.29.20.5 | Y | Y | Y | Complete |  | Review ITC Data Load Schedule and Confirm - MDG | 23.1 hrs | 2025-08-07 08:00 | 2025-08-11 16:06 | Rajat Sharma | rajatsharma67@deloitte.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Tulika Pal; Tushar; Amol Paswan | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; tupal@deloitte.com; tamrutkar@deloitte.de; ampaswan@deloitte.com | MDG |  | 2025-08-07 08:00 | 2025-08-11 16:06 |  | 2025-08-07 08:00 | 2025-08-07 08:00 | 2025-08-11 16:06
18751 | STRIVE.R2.MC1.2384.1.548.1.29.20.6 | Y | Y | Y | Complete |  | Review ITC Data Load Schedule and Confirm - MOR | 31.74 hrs | 2025-08-07 17:52 | 2025-08-13 16:45 | Sven Gelking | sven.gelking@de.sasol.com | Vinod Kumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Amit Jha; Mythili; Abhishek Sharma; Krishna Teja; Jay Patel | vinodkumar692@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ajha2@deloitte.no; myboyapati@deloitte.com; abhisheksharma59@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com | MOR |  | 2025-08-07 17:52 | 2025-08-13 16:45 |  | 2025-08-07 08:00 | 2025-08-07 17:52 | 2025-08-13 16:45
18752 | STRIVE.R2.MC1.2384.1.548.1.29.20.7 | Y | Y | Y | Complete |  | Review ITC Data Load Schedule and Confirm - R2P | 298.04 hrs | 2025-08-07 08:00 | 2025-08-19 18:52 | Hans Jorg | hansjorg.becker@de.sasol.com | Amit das; Abhishek Parab; Pamela Mihali; Sheena Gour; Deepika Agarwal; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Nilesh Deshpande; Jay Saini; Torsten Freydt | amitdas3@deloitte.com; abhparab@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; deepikaagarwal@deloitte.de; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-07 08:00 | 2025-08-19 18:52 |  | 2025-08-07 08:00 | 2025-08-07 08:00 | 2025-08-19 18:52
18753 | STRIVE.R2.MC1.2384.1.548.58 | Y | Y | Y | Complete |  | Migration Team has full authorizations assigned - Migrate your data Fiori&Developer rights | 164.7 hrs | 2025-07-14 08:00 | 2025-08-11 13:42 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-11 13:42 | * | NA | 2025-07-14 08:00 | 2025-08-11 13:42
18754 | STRIVE.R2.MC1.2384.1.548.59 | Y | Y | Y | Complete |  | Syniti Connectivity to SAP Production System | 23.94 hrs | 2025-08-05 08:00 | 2025-08-07 16:56 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 19422 | 2025-08-05 08:00 | 2025-08-07 16:56 | * | NA | 2025-08-05 08:00 | 2025-08-07 16:56
18755 | STRIVE.R2.MC1.2384.1.548.60 | Y | Y | Y | Complete |  | SKP - Create System Connection RFC&ODBC | 22 hrs | 2025-08-05 10:00 | 2025-08-07 17:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18754 | 2025-08-05 10:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 10:00 | 2025-08-07 17:00
18756 | STRIVE.R2.MC1.2384.1.548.61 | Y | Y | Y | Complete |  | SKP - Create System Data Source | 0 hrs | 2025-08-07 18:02 | 2025-08-07 18:02 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18755 | 2025-08-07 18:02 | 2025-08-07 18:02 | * | NA | 2025-08-07 18:02 | 2025-08-07 18:02
18757 | STRIVE.R2.MC1.2384.1.548.62 | Y | Y | Y | Complete |  | SKP - Create Snapshot Data Source | 0 hrs | 2025-08-07 18:37 | 2025-08-07 18:37 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18756 | 2025-08-07 18:37 | 2025-08-07 18:37 | * | NA | 2025-08-07 18:37 | 2025-08-07 18:37
18758 | STRIVE.R2.MC1.2384.1.548.63 | Y | Y | Y | Complete |  | SKP - Create Load Environment | 0 hrs | 2025-08-07 19:05 | 2025-08-07 19:05 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18757 | 2025-08-07 19:05 | 2025-08-07 19:05 | * | NA | 2025-08-07 19:05 | 2025-08-07 19:05
18759 | STRIVE.R2.MC1.2384.1.548.64 | Y | Y | Y | Complete |  | SKP - Create Project Milestone | 0 hrs | 2025-08-07 19:07 | 2025-08-07 19:07 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18758 | 2025-08-07 19:07 | 2025-08-07 19:07 | * | NA | 2025-08-07 19:07 | 2025-08-07 19:07
18760 | STRIVE.R2.MC1.2384.1.548.65 | Y | Y | Y | Complete |  | SKP - Build of System Views to Target System | 12.98 hrs | 2025-08-08 08:00 | 2025-08-11 13:59 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18759 | 2025-08-08 08:00 | 2025-08-11 13:59 | * | NA | 2025-08-08 08:00 | 2025-08-11 13:59
18761 | STRIVE.R2.MC1.2384.1.548.66 | Y | Y | Y | Complete |  | SKP - Code Promotion | 11 hrs | 2025-08-08 10:00 | 2025-08-11 14:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18760 | 2025-08-08 10:00 | 2025-08-11 14:00 | * | NA | 2025-08-08 10:00 | 2025-08-11 14:00
18762 | STRIVE.R2.MC1.2384.1.548.67 | Y | Y | Y | Complete |  | SKP - Manual promotion of Xref values to new data source | 8.87 hrs | 2025-08-08 13:00 | 2025-08-11 13:52 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18761,18713,18727,18728,18729 | 2025-08-08 13:00 | 2025-08-11 13:52 | * | NA | 2025-08-08 13:00 | 2025-08-11 13:52
18763 | STRIVE.R2.MC1.2384.1.548.68 | Y | Y | Y | Complete |  | SKP - Manual promotion of construct data to new data source | 6.87 hrs | 2025-08-08 15:00 | 2025-08-11 13:52 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18762,18711,18712,18713 | 2025-08-08 15:00 | 2025-08-11 13:52 | * | NA | 2025-08-08 15:00 | 2025-08-11 13:52
18764 | STRIVE.R2.MC1.2384.1.548.69 | Y | Y | Y | Complete |  | SDR - Create source for BOA object | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18765 | STRIVE.R2.MC1.2384.1.548.70 | Y | Y | Y | Complete |  | SDR - Create target tables for all objects in scope of long text | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18766 | STRIVE.R2.MC1.2384.1.548.71 | Y | Y | Y | Complete |  | SDR - Syniti updates Host Config File with new host name of HANADB Schema(SYN_SYNITI, SYN_MDG) | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Roman Mäkilä | roman.makila@deloitte.fi | Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18767 | STRIVE.R2.MC1.2384.1.548.72 | Y | Y | Y | Complete |  | SDR - Migrate EXP tables into staging area of DMC | 13.05 hrs | 2025-08-08 08:00 | 2025-08-11 14:03 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18766 | 2025-08-08 08:00 | 2025-08-11 14:03 | * | NA | 2025-08-08 08:00 | 2025-08-11 14:03
18768 | STRIVE.R2.MC1.2384.1.548.73 | Y | Y | Y | Complete |  | SDR - Establish replication between source and target | 10.83 hrs | 2025-08-08 10:00 | 2025-08-11 13:50 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18767 | 2025-08-08 10:00 | 2025-08-11 13:50 | * | NA | 2025-08-08 10:00 | 2025-08-11 13:50
18769 | STRIVE.R2.MC1.2384.1.548.74 | Y | Y | Y | Complete |  | SDR - Associate synoynms to target tables | 8.84 hrs | 2025-08-08 13:00 | 2025-08-11 13:51 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18768 | 2025-08-08 13:00 | 2025-08-11 13:51 | * | NA | 2025-08-08 13:00 | 2025-08-11 13:51
18770 | STRIVE.R2.MC1.2384.1.548.75 | Y | Y | Y | Complete |  | Syniti Connectivity to MS SQL | 24 hrs | 2025-08-05 08:00 | 2025-08-07 17:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 19422 | 2025-08-05 08:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-07 17:00
18771 | STRIVE.R2.MC1.2384.1.548.76 | Y | Y | Y | Complete |  | Meta Data Scan - Target&Source | 164.94 hrs | 2025-07-14 08:00 | 2025-08-11 13:56 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  | 2025-07-14 08:00 | 2025-08-11 13:56 | * | NA | 2025-07-14 08:00 | 2025-08-11 13:56
18772 | STRIVE.R2.MC1.2384.1.548.77 | Y | Y | Y | Complete |  | D-CLEAN DATA Custom Programs Transported in MDG | 24 hrs | 2025-08-05 08:00 | 2025-08-07 17:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda; Deloitte BASIS; Rushikesh Mahendrakar; Satyajit | dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; rumahendrakar@deloitte.com; sapatnaik@deloitte.com | DM | 19422 | 2025-08-05 08:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-07 17:00
18773 | STRIVE.R2.MC1.2384.1.548.78 | Y | Y | Y | Complete |  | DMC Prerequisites MDG to Syniti (including OSS Notes) | 36.93 hrs | 2025-08-05 08:00 | 2025-08-11 13:56 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | DM | 19422 | 2025-08-05 08:00 | 2025-08-11 13:56 | * | NA | 2025-08-05 08:00 | 2025-08-11 13:56
18774 | STRIVE.R2.MC1.2384.1.548.79 | Y | Y | Y | Complete |  | DMC Prerequisites S/4 to Syniti (including OSS Notes) | 36.92 hrs | 2025-08-05 08:00 | 2025-08-11 13:55 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | DM | 19422 | 2025-08-05 08:00 | 2025-08-11 13:55 | * | NA | 2025-08-05 08:00 | 2025-08-11 13:55
18775 | STRIVE.R2.MC1.2384.1.548.80 | Y | Y | Y | Complete |  | DMC Project Migration from previous client | 9.75 hrs | 2025-08-11 13:55 | 2025-08-12 15:40 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | DM | 18774,19422 | 2025-08-11 13:55 | 2025-08-12 15:40 | * | NA | 2025-08-11 13:55 | 2025-08-12 15:40
18777 | STRIVE.R2.MC1.2384.1.548.82 | Y | Y | Y | Complete |  | Confirm Data Validation Test Scripts are uploaded in SOLMAN before cycle start | 0 hrs | 2025-08-11 21:46 | 2025-08-11 21:46 | Ines Tesch | ines.tesch@de.sasol.com | Satyajit Patnaik; Alex Miles; Jens Nissen; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; almiles@deloitte.de; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 19422 | 2025-08-11 21:46 | 2025-08-11 21:46 | * | NA | 2025-08-11 21:46 | 2025-08-11 21:46
18778 | STRIVE.R2.MC1.2384.1.548.83 | Y | Y | Y | Complete |  | Inform Data Validators about the ECC Snapshot/ Extraction date | 0 hrs | 2025-08-12 14:11 | 2025-08-12 14:11 | Ines Tesch | ines.tesch@de.sasol.com | Satyajit Patnaik; Alex Miles; Jens Nissen; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; almiles@deloitte.de; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 19422 | 2025-08-12 14:11 | 2025-08-12 14:11 | * | NA | 2025-08-12 14:11 | 2025-08-12 14:11
18779 | STRIVE.R2.MC1.2384.1.548.84 | Y | Y | Y | Complete |  | Set up Cutover IDs/Firefirefighter IDs | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18780 | STRIVE.R2.MC1.2384.1.548.85 | Y | Y | Y | Complete |  | Intercompany and Internal Plant partner roles to be assigned to the Sasol P2C Data Leads. | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18781 | STRIVE.R2.MC1.2384.1.548.86 | Y | Y | Y | Complete |  | Intercompany and Internal Plant partner roles to be assigned to the Sasol R2D Data Leads. | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18782 | STRIVE.R2.MC1.2384.1.548.87 | Y | Y | Y | Complete |  | Intercompany and Internal Plant partner roles to be assigned to the Sasol S2P Data Leads. | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18783 | STRIVE.R2.MC1.2384.1.548.88 | Y | N | N | Sent |  | Create intercompany partner by P2C in MDG system | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Diego Zarate; Malta; Ramesh SathishKumar; Shubham Mishra; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dzarate@deloitte.com; mawilhelm@deloitte.de; satramesh@deloitte.com; spratapmishra@deloitte.com; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18784 | STRIVE.R2.MC1.2384.1.548.89 | Y | N | N | Sent |  | Create Internal plant partner by P2C in MDG system | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Diego Zarate; Malta; Ramesh SathishKumar; Shubham Mishra; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dzarate@deloitte.com; mawilhelm@deloitte.de; satramesh@deloitte.com; spratapmishra@deloitte.com; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18785 | STRIVE.R2.MC1.2384.1.548.90 | Y | N | N | Sent |  | Maintain intercompany partner by R2D in MDG system | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Alexandra Ruff; Daniel Lohmann; ; Roshanlal Hemwani; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | aruff@deloitte.de; dlohmann@deloitte.de; ; rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18786 | STRIVE.R2.MC1.2384.1.548.91 | N | N | N | Ready |  | Maintain intercompany partner by S2P in MDG system | 2 hrs | 2025-09-05 10:00 | 2025-09-05 12:00 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Tina Vidrine; Frank Toedter | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de | S2P | 19518 |  |  |  | 2025-09-05 10:00 | 2025-09-05 10:00 | 2025-09-05 12:00
18787 | STRIVE.R2.MC1.2384.1.548.92 | Y | N | N | Sent |  | Maintain Internal plant partner by R2D in MDG system | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Alexandra Ruff; Daniel Lohmann; ; Roshanlal Hemwani; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | aruff@deloitte.de; dlohmann@deloitte.de; ; rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18788 | STRIVE.R2.MC1.2384.1.548.93 | N | N | N | Ready |  | Maintain Internal plant partner by S2P in MDG system | 2 hrs | 2025-09-05 10:00 | 2025-09-05 12:00 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19518 |  |  |  | 2025-09-05 10:00 | 2025-09-05 10:00 | 2025-09-05 12:00
18789 | STRIVE.R2.MC1.2384.1.548.94 | Y | N | N | Sent |  | Approve internal plant partner in MDG System | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Esmir Divljanovic; Jessica Goffi; Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tina Vidrine; Frank Toedter | edivljanovic@deloitte.de; Jessica.Goffi@it.sasol.com; kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de | S2P |  |  |  | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18790 | STRIVE.R2.MC1.2384.1.548.95 | N | N | N | Planned |  | Assignment of simple change requestor and approver role to Jessica by GRC Team | 2 hrs | 2025-09-15 21:58 | 2025-09-15 23:58 | GRC | dttsasolsecuritygrcteam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jessica Goffi; | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com; | GRC | 18789 |  |  |  | 2025-09-15 21:58 | 2025-09-15 21:58 | 2025-09-15 23:58
18791 | STRIVE.R2.MC1.2384.1.548.96 | N | N | N | Planned |  | Update identification number for internal plant partner in MDG | 2 hrs | 2025-09-15 23:58 | 2025-09-16 02:00 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Ramesh SathishKumar; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | satramesh@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C | 18790 |  |  |  | 2025-09-05 10:00 | 2025-09-15 23:58 | 2025-09-16 02:00
18792 | STRIVE.R2.MC1.2384.1.548.97 | N | N | N | Planned |  | Approval of identification number for internal plant partner in MDG | 2 hrs | 2025-09-16 02:00 | 2025-09-16 04:00 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Ramesh SathishKumar; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | satramesh@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C | 18791 |  |  |  | 2025-09-05 10:00 | 2025-09-16 02:00 | 2025-09-16 04:00
18793 | STRIVE.R2.MC1.2384.1.548.98 | N | N | N | Planned |  | Revoke the access for simple change requestor and approver role from Jessica by GRC Team | 2 hrs | 2025-09-16 04:00 | 2025-09-16 06:00 | GRC | dttsasolsecuritygrcteam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jessica Goffi; | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com; | GRC | 18792 |  |  | * | NA | 2025-09-16 04:00 | 2025-09-16 06:00
18794 | STRIVE.R2.MC1.2384.1.548.99 | Y | Y | Y | Complete |  | Vendor Payment terms and description validation in the S/4 system - R2D | 0.03 hrs | 2025-08-27 17:50 | 2025-08-27 17:52 | Michaela | michaela.schulz@de.sasol.com | Tatiana; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; Maria Luisa Geremicca; Oluf baren; Roshan; Aquib Iqbal | tvinogradova@deloitte.de; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; marialuisa.geremicca@it.sasol.com; oluf.braren@de.sasol.com; rohemwani@deloitte.com; aquiqbal@deloitte.com | R2D |  | 2025-08-27 17:50 | 2025-08-27 17:52 | * | NA | 2025-08-27 17:50 | 2025-08-27 17:52
18795 | STRIVE.R2.MC1.2384.1.548.100 | Y | Y | Y | Complete |  | Validate Bank control key, Short Key for a House Bank and Tax Number Category - R2D | 114.28 hrs | 2025-08-27 18:34 | 2025-09-01 13:11 | Michaela | michaela.schulz@de.sasol.com | Tatiana; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; Maria Luisa Geremicca | tvinogradova@deloitte.de; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; marialuisa.geremicca@it.sasol.com | R2D |  | 2025-08-27 18:34 | 2025-09-01 13:11 | * | NA | 2025-08-27 18:34 | 2025-09-01 13:11
18796 | STRIVE.R2.MC1.2384.1.548.101 | Y | Y | Y | Complete |  | Validate the Purchase Order Currency and Postal Code - S2P | 1040.74 hrs | 2025-07-14 08:00 | 2025-08-26 19:37 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Michaela; Tatiana; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Tina Vidrine; Frank Toedter | michaela.schulz@de.sasol.com; tvinogradova@deloitte.de; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de | S2P |  | 2025-07-14 08:00 | 2025-08-26 19:37 | * | NA | 2025-07-14 08:00 | 2025-08-26 19:37
18797 | STRIVE.R2.MC1.2384.1.548.102 | N | N | N | Planned |  | Intercompany and Internal Plant partner roles assigned to the Sasol P2C Data Leads to be revoked. | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18784 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18798 | STRIVE.R2.MC1.2384.1.548.103 | N | N | N | Planned |  | Intercompany and Internal Plant partner roles assigned to the Sasol R2D Data Leads to be revoked. | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18787 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18799 | STRIVE.R2.MC1.2384.1.548.104 | N | N | N | Planned |  | Intercompany and Internal Plant partner roles assigned to the Sasol S2P Data Leads to be revoked. | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 18788 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18800 | STRIVE.R2.MC1.2384.1.548.105 | Y | Y | Y | Complete |  | Vendor Inclusion and Exclusion lists need to be confirmed and provided to team DM | 188.89 hrs | 2025-07-14 08:00 | 2025-08-14 13:53 | Prasanth | kalprasanth@deloitte.com | Maria Luisa Geremicca; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | marialuisa.geremicca@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  | 2025-07-14 08:00 | 2025-08-14 13:53 | * | NA | 2025-07-14 08:00 | 2025-08-14 13:53
18801 | STRIVE.R2.MC1.2384.1.548.106 | Y | Y | Y | Complete |  | Procurement vendor exclusion list | 208 hrs | 2025-07-14 08:00 | 2025-08-18 17:00 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Tina Vidrine; Frank Toedter | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de | S2P |  | 2025-07-14 08:00 | 2025-08-18 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-18 17:00
18802 | STRIVE.R2.MC1.2384.1.548.107 | Y | Y | Y | Complete |  | Material masterZFIN and ZSFG Inclusion and Exclusion list need to be confirmed and provided to team DM | 168 hrs | 2025-07-14 08:00 | 2025-08-11 17:00 | Ines Tesch | ines.tesch@de.sasol.com | Satyajit Patnaik; Alex Miles; Jens Nissen; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; almiles@deloitte.de; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  | 2025-07-14 08:00 | 2025-08-11 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-11 17:00
18803 | STRIVE.R2.MC1.2384.1.548.108 | Y | Y | Y | Complete |  | Create Read/Write Access for Data Load Users (ODBC - SYNITI, RFC - N_R_SYNITIDM) | 181.08 hrs | 2025-07-14 08:00 | 2025-08-13 14:05 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-13 14:05 | * | NA | 2025-07-14 08:00 | 2025-08-13 14:05
18804 | STRIVE.R2.MC1.2384.1.548.109 | Y | Y | Y | Complete |  | Update refrence BPs for HR integration in MDG and S4 system with the recon account for Go-live countries | 315.68 hrs | 2025-08-13 17:23 | 2025-08-26 21:56 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  | 2025-08-13 17:23 | 2025-08-26 21:56 | * | NA | 2025-08-13 17:23 | 2025-08-26 21:56
18805 | STRIVE.R2.MC1.2384.1.548.110 | Y | Y | Y | Complete |  | System is ready for Migration Activities | 181.12 hrs | 2025-07-14 08:00 | 2025-08-13 14:07 | Roman Mäkilä | roman.makila@deloitte.fi | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  | 2025-07-14 08:00 | 2025-08-13 14:07 | * | NA | 2025-07-14 08:00 | 2025-08-13 14:07
18806 | STRIVE.R2.MC1.2384.1.548.111 | Y | Y | Y | Complete |  | Extraction for Master Data from A01 | 166 hrs | 2025-07-14 10:00 | 2025-08-11 17:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM | 18805 | 2025-07-14 10:00 | 2025-08-11 17:00 | * | NA | 2025-07-14 10:00 | 2025-08-11 17:00
18808 | STRIVE.R2.MC1.2384.1.548.113 | Y | Y | Y | Complete |  | Extraction for Transactional Data from A01 | 0 hrs | 2025-08-13 13:24 | 2025-08-13 13:24 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  | 2025-08-13 13:24 | 2025-08-13 13:24 | * | NA | 2025-08-13 13:24 | 2025-08-13 13:24
18809 | STRIVE.R2.MC1.2384.1.548.114 |  |  |  | Complete |  | Syniti | 3 hrs | 2025-07-14 08:00 | 2025-07-14 11:00 | [6 empty] | 2025-07-14 08:00 | 2025-08-12 12:00 | * | NA | 2025-07-14 08:00 | 2025-07-14 11:00
18810 | STRIVE.R2.MC1.2384.1.548.114.1 | Y | Y | Y | Complete |  | Syniti Transport import | 167.17 hrs | 2025-07-14 08:00 | 2025-08-11 16:10 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar; Savri Sumeet Jagatap | roman.makila@deloitte.fi; ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com; ssumeetjagatap@deloitte.com | DM |  | 2025-07-14 08:00 | 2025-08-11 16:10 | * | NA | 2025-07-14 08:00 | 2025-08-11 16:10
18811 | STRIVE.R2.MC1.2384.1.548.114.2 | Y | Y | Y | Complete |  | SYN_SYNITI HANA Schema creation for DMC in S/4HANA and MDG&DBCO setup. | 4.83 hrs | 2025-08-11 16:10 | 2025-08-12 12:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Basis; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis | 18810 | 2025-08-11 16:10 | 2025-08-12 12:00 | * | NA | 2025-08-11 16:10 | 2025-08-12 12:00
18812 | STRIVE.R2.MC1.2384.1.665 | [5 empty] | Delta Transport Validation in S/4HANA | 2665.3 hrs | 2025-08-05 08:00 | 2025-11-24 16:43 | [6 empty] | 2025-08-05 08:00 |  | * | NA | 2025-08-05 08:00 | 2025-11-24 16:43
18813 | STRIVE.R2.MC1.2384.1.665.1 | Y | Y | Y | Complete |  | Delta Transport Validation - R2P in S/4HANA | 0 hrs | 2025-08-08 13:27 | 2025-08-08 13:27 | Amit das | amitdas3@deloitte.com | Claudiu; Aniket Kulkarni; Pamela Mihali; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande | cljipa@deloitte.de; anikulkarni@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P |  | 2025-08-08 13:27 | 2025-08-08 13:27 | * | NA | 2025-08-08 13:27 | 2025-08-08 13:27
18814 | STRIVE.R2.MC1.2384.1.665.2 | Y | Y | Y | Complete |  | Delta Transport Validation - S2P in S/4HANA | 0 hrs | 2025-08-07 21:19 | 2025-08-07 21:19 | Prasanth Kallakuri | kalprasanth@deloitte.com | Sandeep Galhotra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Milton | sagalhotra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; miltjones@deloitte.com | S2P |  | 2025-08-07 21:19 | 2025-08-07 21:19 | * | NA | 2025-08-07 21:19 | 2025-08-07 21:19
18815 | STRIVE.R2.MC1.2384.1.665.3 | Y | Y | Y | Complete |  | Delta Transport Validation - P2C in S/4HANA | 24 hrs | 2025-08-05 08:00 | 2025-08-07 17:00 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Malta; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dzarate@deloitte.com; mawilhelm@deloitte.de; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  | 2025-08-05 08:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-07 17:00
18816 | STRIVE.R2.MC1.2384.1.665.4 | Y | Y | Y | Complete |  | Delta Transport Validation - R2D in S/4HANA | 11.22 hrs | 2025-08-05 12:16 | 2025-08-06 16:13 | Roshanlal Hemwani | rohemwani@deloitte.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Daniel Lohmann; | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dlohmann@deloitte.de; | R2D |  | 2025-08-05 12:16 | 2025-08-06 16:13 | * | NA | 2025-08-05 12:16 | 2025-08-06 16:13
18817 | STRIVE.R2.MC1.2384.1.665.5 | Y | Y | Y | Complete |  | Delta Transport Validation - MOR - PM in S/4HANA | 0.05 hrs | 2025-08-07 15:39 | 2025-08-07 15:42 | Vinod Kumar | vinodkumar692@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  | 2025-08-07 15:39 | 2025-08-07 15:42 | * | NA | 2025-08-07 15:39 | 2025-08-07 15:42
95109 | STRIVE.R2.MC1.2384.1.665.20 | N | N | N | Ready |  | Delta Transport Validation - MOR - PS in S/4HANA | 14 hrs | 2025-08-05 08:00 | 2025-08-05 22:01 | Krishna Teja | krishn@deloitte.com | Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Vinod Kumar | mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; vinodkumar692@deloitte.com | MOR |  |  |  | * | NA | 2025-08-05 08:00 | 2025-08-05 22:01
95108 | STRIVE.R2.MC1.2384.1.665.19 | N | N | N | Ready |  | Delta Transport Validation - MOR - PPM in S/4HANA | 14 hrs | 2025-08-05 08:00 | 2025-08-05 22:01 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod Kumar; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-08-05 08:00 | 2025-08-05 22:01
18818 | STRIVE.R2.MC1.2384.1.665.6 | Y | Y | Y | Complete |  | PRE TR IMPORT FGL_MIG_REGENERATE_CDS_BCF (With Checkbox: Reset to Delivery) | 0.02 hrs | 2025-08-07 13:16 | 2025-08-07 13:17 | Ashish patil | ashishspatil@deloitte.com | Shivraj; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | shivrsinha@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP |  | 2025-08-07 13:16 | 2025-08-07 13:17 | * | NA | 2025-08-07 13:16 | 2025-08-07 13:17
18819 | STRIVE.R2.MC1.2384.1.665.7 | Y | Y | Y | Complete |  | Delta Transport Validation - ABAP in S/4HANA | 0 hrs | 2025-08-07 13:54 | 2025-08-07 13:54 | Gurmandeep Singh | gurmandsingh@deloitte.com | Ashish patil; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | ashishspatil@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP | 18818 | 2025-08-07 13:54 | 2025-08-07 13:54 | * | NA | 2025-08-07 13:54 | 2025-08-07 13:54
18820 | STRIVE.R2.MC1.2384.1.665.8 | Y | N | N | Sent |  | Delta Transport Validation - Data in S/4HANA | 4 hrs | 2025-08-05 08:00 | 2025-08-05 12:00 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar | roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com | DM |  |  |  | * | NA | 2025-08-05 08:00 | 2025-08-05 12:00
18821 | STRIVE.R2.MC1.2384.1.665.9 | Y | Y | Y | Complete |  | Delta Transport Validation - Security/GRC in S/4HANA | 24 hrs | 2025-08-05 08:00 | 2025-08-07 17:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Shubhathakur@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-08-05 08:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-07 17:00
18822 | STRIVE.R2.MC1.2384.1.665.10 | Y | Y | Y | Complete |  | S4: Validate MDG related Transport Requests in S/4HANA (Delta) | 8 hrs | 2025-08-05 08:00 | 2025-08-05 17:00 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  | 2025-08-05 08:00 | 2025-08-05 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-05 17:00
18823 | STRIVE.R2.MC1.2384.1.665.11 |  |  |  | Complete |  | Delta Transport Validation in MDG | 639.72 hrs | 2025-08-05 08:00 | 2025-11-24 16:43 | [6 empty] | 2025-08-05 08:00 | 2025-08-08 13:09 | * | NA | 2025-08-05 08:00 | 2025-11-24 16:43
18824 | STRIVE.R2.MC1.2384.1.665.11.1 | Y | Y | Y | Complete |  | Delta Transport Validation - R2P in MDG | 0.02 hrs | 2025-08-08 13:08 | 2025-08-08 13:09 | Amit das | amitdas3@deloitte.com | Claudiu; Aniket Kulkarni; Pamela Mihali; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande | cljipa@deloitte.de; anikulkarni@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P |  | 2025-08-08 13:08 | 2025-08-08 13:09 | * | NA | 2025-08-08 13:08 | 2025-08-08 13:09
18825 | STRIVE.R2.MC1.2384.1.665.11.2 | Y | Y | Y | Complete |  | Delta Transport Validation - S2P in MDG | 0 hrs | 2025-08-07 21:21 | 2025-08-07 21:21 | Prasanth Kallakuri | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sandeep Galhotra; S2P Team; Milton | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sagalhotra@deloitte.com; usisasols2p@deloitte.com; miltjones@deloitte.com | S2P |  | 2025-08-07 21:21 | 2025-08-07 21:21 | * | NA | 2025-08-07 21:21 | 2025-08-07 21:21
18826 | STRIVE.R2.MC1.2384.1.665.11.3 | Y | Y | Y | Complete |  | Delta Transport Validation - P2C in MDG | 24 hrs | 2025-08-05 08:00 | 2025-08-07 17:00 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Malta; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ramesh SathishKumar | dzarate@deloitte.com; mawilhelm@deloitte.de; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; satramesh@deloitte.com | P2C |  | 2025-08-05 08:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-07 17:00
18827 | STRIVE.R2.MC1.2384.1.665.11.4 | Y | Y | Y | Complete |  | Delta Transport Validation - R2D in MDG | 11.22 hrs | 2025-08-05 12:16 | 2025-08-06 16:13 | Roshanlal Hemwani | rohemwani@deloitte.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Daniel Lohmann; | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dlohmann@deloitte.de; | R2D |  | 2025-08-05 12:16 | 2025-08-06 16:13 | * | NA | 2025-08-05 12:16 | 2025-08-06 16:13
18828 | STRIVE.R2.MC1.2384.1.665.11.5 | Y | Y | Y | Complete |  | Delta Transport Validation - Data in MDG | 24 hrs | 2025-08-05 08:00 | 2025-08-07 17:00 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar | roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com | DM |  | 2025-08-05 08:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-07 17:00
18829 | STRIVE.R2.MC1.2384.1.665.11.6 | Y | Y | Y | Complete |  | Delta Transport Validation - Security/GRC in MDG | 24 hrs | 2025-08-05 08:00 | 2025-08-07 17:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Shubhathakur@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  | 2025-08-05 08:00 | 2025-08-07 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-07 17:00
18830 | STRIVE.R2.MC1.2384.1.665.11.7 | Y | Y | Y | Complete |  | MDG: Validate MDG related Transport Requests in MDG (Delta) | 8 hrs | 2025-08-05 08:00 | 2025-08-05 17:00 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  | 2025-08-05 08:00 | 2025-08-05 17:00 | * | NA | 2025-08-05 08:00 | 2025-08-05 17:00
18831 | STRIVE.R2.MC1.2384.1.684 | [5 empty] | Integration | 1008.64 hrs | 2025-07-14 08:00 | 2025-08-25 11:26 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-08-25 11:26
18832 | STRIVE.R2.MC1.2384.1.684.1 |  |  |  | Complete |  | Pre-system Setup | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-07-14 08:00 | 2025-07-28 14:18 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18833 | STRIVE.R2.MC1.2384.1.684.1.1 | Y | Y | Y | Complete |  | Provision of user roles//Access to Integration team to BTP-IS&S/4 Production systems | 85.29 hrs | 2025-07-14 08:00 | 2025-07-28 14:18 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-07-28 14:18 | * | NA | 2025-07-14 08:00 | 2025-07-28 14:18
18834 | STRIVE.R2.MC1.2384.1.684.3 | Y | Y | Y | Complete |  | Provide host and port details of AEM to Basis team for SM59&Channel config | 85.58 hrs | 2025-07-14 08:00 | 2025-07-28 14:35 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian Hogrefe; Rico van den Berg; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Christian.Hogrefe@de.sasol.com; rico.vandenberg@sasol.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-28 14:35 | * | NA | 2025-07-14 08:00 | 2025-07-28 14:35
18835 | STRIVE.R2.MC1.2384.1.684.4 | Y | Y | Y | Complete |  | Provide host and port details for white listing GE APM | 0 hrs | 2025-08-19 01:00 | 2025-08-19 01:00 | Joseph Barber | joseph.barber@us.sasol.com | Sven Gelking; Dhruv Kansal; USI STRIVE CUTOVER; Jay Patel; Mousikta chanda; Amit Jha; Vinod Kumar; Elisa Latona | sven.gelking@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaypatel6@deloitte.com; mouchanda@deloitte.com; ajha2@deloitte.no; vinodkumar692@deloitte.com; elisa.latona@it.sasol.com | MOR |  | 2025-08-19 01:00 | 2025-08-19 01:00 | * | NA | 2025-08-19 01:00 | 2025-08-19 01:00
18836 | STRIVE.R2.MC1.2384.1.684.5 | Y | Y | Y | Complete |  | Provide host and port details for IAG&SF (Not relevant for MC1) | 0 hrs | 2025-08-08 13:00 | 2025-08-08 13:00 | Somitra Thapa | sothapa@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-08-08 13:00 | 2025-08-08 13:00 | * | NA | 2025-08-08 13:00 | 2025-08-08 13:00
18837 | STRIVE.R2.MC1.2384.1.684.6 | Y | Y | Y | Complete |  | Whitelisting of URLs from Proxy server | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-14 10:00 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18838 | STRIVE.R2.MC1.2384.1.684.7 | Y | Y | Y | Complete |  | TM optimizer installation and RFC setup with whitelisting same like SU1-100 | 37.95 hrs | 2025-07-14 08:00 | 2025-07-18 14:57 | Priyanka Patel | priyankaspatel@deloitte.de | Diego Zarate; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dzarate@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 14:57 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:57
18839 | STRIVE.R2.MC1.2384.1.684.8 | Y | Y | Y | Complete |  | Provide the password of the user to be used in SOA configuration to integration Team for AEB | 0 hrs | 2025-08-20 15:49 | 2025-08-20 15:49 | Manuel | Manuel.Roellinghoff@de.sasol.com | Rob Hall; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C |  | 2025-08-20 15:49 | 2025-08-20 15:49 | * | NA | 2025-08-20 15:49 | 2025-08-20 15:49
18840 | STRIVE.R2.MC1.2384.1.684.9 | Y | Y | Y | Complete |  | Perform the SOA Manager configuration for AEB | 28.03 hrs | 2025-08-07 16:58 | 2025-08-13 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | nnagasubbareddy@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | Integration |  | 2025-08-07 16:58 | 2025-08-13 12:00 | * | NA | 2025-08-07 16:58 | 2025-08-13 12:00
18841 | STRIVE.R2.MC1.2384.1.684.10 | Y | Y | Y | Complete |  | Provision of user roles//Access to Integration team to SAP APIM systems | 152 hrs | 2025-07-14 08:00 | 2025-08-07 17:00 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-07 17:00 | * | NA | 2025-07-14 08:00 | 2025-08-07 17:00
18843 | STRIVE.R2.MC1.2384.1.684.12 |  |  |  | Complete |  | BAS | 173.97 hrs | 2025-07-14 08:00 | 2025-07-21 14:27 | [6 empty] | 2025-07-14 08:00 | 2025-08-21 19:07 | * | NA | 2025-07-14 08:00 | 2025-07-21 14:27
18845 | STRIVE.R2.MC1.2384.1.684.12.2 | Y | Y | Y | Complete |  | Business Application Studio setup | 920.56 hrs | 2025-07-14 08:00 | 2025-08-21 19:07 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-08-21 19:07 | * | NA | 2025-07-14 08:00 | 2025-08-21 19:07
18846 | STRIVE.R2.MC1.2384.1.684.15 |  |  |  | Complete |  | Build Process Automation | 55.57 hrs | 2025-07-14 08:00 | 2025-07-16 15:43 | [6 empty] | 2025-08-29 14:23 | 2025-08-29 14:23 | * | NA | 2025-07-14 08:00 | 2025-07-16 15:43
18847 | STRIVE.R2.MC1.2384.1.684.15.1 | Y | Y | Y | Complete |  | Request to subscibe Build Process Automation | 0 hrs | 2025-08-29 14:23 | 2025-08-29 14:23 | Gurmandeep Singh | gurmandsingh@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Shivraj; Ashish patil; Satish rahangadale | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; shivrsinha@deloitte.com; ashishspatil@deloitte.com; srahangdale@deloitte.com | ABAP |  | 2025-08-29 14:23 | 2025-08-29 14:23 | * | NA | 2025-08-29 14:23 | 2025-08-29 14:23
95086 | STRIVE.R2.MC1.2384.1.684.592 | [5 empty] | MOR | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
95107 | STRIVE.R2.MC1.2384.1.684.592.1 | N | N | N | Planned |  | Update the Equipment number in Shift Connector | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Joseph Barber | joseph.barber@us.sasol.com | Elisa Latona; Sven Gelking; Vinod Kumar; Jay Patel; Chaitnya; Pragyesh; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | elisa.latona@it.sasol.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; csudhakarraut@deloitte.com; pkumargoyal@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 10:00
95085 | STRIVE.R2.MC1.2384.1.684.592.3 | N | N | N | Planned |  | Undelpoy interface equipment and Functional Location before data load (before equipment and floc load) | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Vinod; Jay Patel; Chaitnya | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; csudhakarraut@deloitte.com | Integration |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
95084 | STRIVE.R2.MC1.2384.1.684.592.2 | N | N | N | Planned |  | After data load clear AEM Q for functional location and Equipment (post equipment and floc load) | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Vinod; Jay Patel; Chaitnya | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; csudhakarraut@deloitte.com | Integration | 19688,19662 |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
18848 | STRIVE.R2.MC1.2384.1.684.17 |  |  |  | Complete |  | MDG | 2.5 hrs | 2025-07-14 08:00 | 2025-07-14 10:30 | [6 empty] | 2025-08-01 13:00 | 2025-08-11 12:00 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:30
18849 | STRIVE.R2.MC1.2384.1.684.17.1 | Y | Y | Y | Complete |  | Validation of Business System, Logical System creation for DRFIMG | 48 hrs | 2025-08-01 13:00 | 2025-08-11 12:00 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tushar | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; tamrutkar@deloitte.de | MDG | 18410 | 2025-08-01 13:00 | 2025-08-11 12:00 | * | NA | 2025-08-01 13:00 | 2025-08-11 12:00
18850 | STRIVE.R2.MC1.2384.1.684.19 |  |  |  | Complete |  | Integration Suite | 102.69 hrs | 2025-07-14 08:00 | 2025-07-18 14:58 | [6 empty] | 2025-07-14 08:00 | 2025-08-19 18:58 | * | NA | 2025-07-14 08:00 | 2025-07-18 14:58
18851 | STRIVE.R2.MC1.2384.1.684.19.1 | Y | Y | Y | Complete |  | AEM - Integration team to Provide host and port , SSL CPI Cert details for Integration suite to BASIS team, for SM59 setup | 88 hrs | 2025-07-14 08:00 | 2025-07-28 17:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  | 2025-07-14 08:00 | 2025-07-28 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-28 17:00
18852 | STRIVE.R2.MC1.2384.1.684.19.2 | Y | Y | Y | Complete |  | Integration suite destination connectivity setup in S4, based on request from integration team | 38.02 hrs | 2025-07-14 08:00 | 2025-07-18 15:01 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 15:01 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:01
18853 | STRIVE.R2.MC1.2384.1.684.19.3 | Y | Y | Y | Complete |  | Share the virtual host, port and location ID of S/4 to Integration team | 38.01 hrs | 2025-07-14 08:00 | 2025-07-18 15:01 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 15:01 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:01
18854 | STRIVE.R2.MC1.2384.1.684.19.4 | Y | Y | Y | Complete |  | Share the S/4&MDG user credentials to configure in BTP-IS security materials | 93.68 hrs | 2025-07-14 08:00 | 2025-07-29 14:41 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-07-29 14:41 | * | NA | 2025-07-14 08:00 | 2025-07-29 14:41
18855 | STRIVE.R2.MC1.2384.1.684.19.5 | Y | Y | Y | Complete |  | Deploy security artifacts for S/4 in BTP-IS | 483.39 hrs | 2025-07-29 14:41 | 2025-08-18 19:24 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18854 | 2025-07-29 14:41 | 2025-08-18 19:24 | * | NA | 2025-07-29 14:41 | 2025-08-18 19:24
18856 | STRIVE.R2.MC1.2384.1.684.19.6 | Y | Y | Y | Complete |  | Deploy security artifacts for MDG system in BTP-IS | 483.4 hrs | 2025-07-29 14:41 | 2025-08-18 19:25 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18854 | 2025-07-29 14:41 | 2025-08-18 19:25 | * | NA | 2025-07-29 14:41 | 2025-08-18 19:25
18857 | STRIVE.R2.MC1.2384.1.684.19.7 | Y | Y | Y | Complete |  | Connection test with S/4 systems | 23.49 hrs | 2025-08-18 19:24 | 2025-08-19 18:58 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18855,18853 | 2025-08-18 19:24 | 2025-08-19 18:58 | * | NA | 2025-08-18 19:24 | 2025-08-19 18:58
18858 | STRIVE.R2.MC1.2384.1.684.19.8 | Y | Y | Y | Complete |  | Connection test with MDG systems | 23.48 hrs | 2025-08-18 19:25 | 2025-08-19 18:57 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18856,18853 | 2025-08-18 19:25 | 2025-08-19 18:57 | * | NA | 2025-08-18 19:25 | 2025-08-19 18:57
18859 | STRIVE.R2.MC1.2384.1.684.19.9 | Y | Y | Y | Complete |  | SMTP Setup for Integration suite | 38.94 hrs | 2025-07-14 08:00 | 2025-07-18 15:56 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 15:56 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:56
18861 | STRIVE.R2.MC1.2384.1.684.19.11 | Y | Y | Y | Complete |  | Configure the externalized parameters for Custom and standard Global Exception iflows | 183.69 hrs | 2025-07-14 08:00 | 2025-08-13 16:41 | Yashwanth | myakumar@deloitte.com | Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration |  | 2025-07-14 08:00 | 2025-08-13 16:41 | * | NA | 2025-07-14 08:00 | 2025-08-13 16:41
18862 | STRIVE.R2.MC1.2384.1.684.31 | [5 empty] | Technical Ping Test | 48.85 hrs | 2025-07-14 08:00 | 2025-07-16 08:59 | [6 empty] | 2025-07-18 15:01 |  | * | NA | 2025-07-14 08:00 | 2025-07-16 08:59
18863 | STRIVE.R2.MC1.2384.1.684.31.1 | Y | Y | Y | Complete |  | Technical Ping Test from S/4HANA(SM59 destination test ) | 49.98 hrs | 2025-07-18 15:01 | 2025-07-28 17:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18852 | 2025-07-18 15:01 | 2025-07-28 17:00 | * | NA | 2025-07-18 15:01 | 2025-07-28 17:00
18864 | STRIVE.R2.MC1.2384.1.684.31.2 | Y | Y | Y | Complete |  | Technical Ping Test from MDG(SM59 destination test ) | 49.98 hrs | 2025-07-18 15:01 | 2025-07-28 17:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18852 | 2025-07-18 15:01 | 2025-07-28 17:00 | * | NA | 2025-07-18 15:01 | 2025-07-28 17:00
18865 | STRIVE.R2.MC1.2384.1.684.31.3 | Y | Y | Y | Complete |  | Technical Ping Test for SAP CPI (cloud connector, communication channel for Production) | 23.48 hrs | 2025-08-18 19:25 | 2025-08-19 18:57 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18856,18855 | 2025-08-18 19:25 | 2025-08-19 18:57 | * | NA | 2025-08-18 19:25 | 2025-08-19 18:57
18866 | STRIVE.R2.MC1.2384.1.684.31.4 | Y | Y | N | In-Progress |  | Validate ODATA services configured for all interfaces. | 2 hrs | 2025-08-13 13:24 | 2025-08-13 15:24 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18166 | 2025-08-13 13:24 |  | * | NA | 2025-08-13 13:24 | 2025-08-13 15:24
18867 | STRIVE.R2.MC1.2384.1.684.31.5 | Y | Y | Y | Complete |  | Testing the Advance Event Mesh Connectivity from S4 and CPI | 25.89 hrs | 2025-08-18 17:00 | 2025-08-19 18:57 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 | 2025-08-18 17:00 | 2025-08-19 18:57 | * | NA | 2025-08-18 17:00 | 2025-08-19 18:57
95101 | STRIVE.R2.MC1.2384.1.684.593 | [5 empty] | R2D_I_002 | 24.93 hrs | 2025-09-11 08:00 | 2025-09-12 09:00 | [8 empty] | * | NA | 2025-09-11 08:00 | 2025-09-12 09:00
95102 | STRIVE.R2.MC1.2384.1.684.593.11 | N | N | N | Planned |  | Request ECP system details for RFC connection (R2D_I_002) | 0.5 hrs | 2025-09-11 08:00 | 2025-09-11 08:30 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  |  |  |  | 2025-09-11 08:00 | 2025-09-11 08:00 | 2025-09-11 08:30
95103 | STRIVE.R2.MC1.2384.1.684.593.12 | N | N | N | Planned |  | Logical system creation for ECP System (R2D_I_002) - Open Client Activity | 0.5 hrs | 2025-09-11 08:00 | 2025-09-11 08:30 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  |  |  |  | 2025-09-11 08:00 | 2025-09-11 08:00 | 2025-09-11 08:30
95104 | STRIVE.R2.MC1.2384.1.684.593.13 | N | N | N | Planned |  | Port and partner profile creation for ECP System (R2D_I_002) | 1 hrs | 2025-09-11 08:00 | 2025-09-11 09:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  |  |  |  | 2025-09-11 08:00 | 2025-09-11 08:00 | 2025-09-11 09:00
95099 | STRIVE.R2.MC1.2384.1.684.593.8 | N | N | N | Planned |  | Inbound Message Type(COSMAS,GLMAST,PRCMAS) creation in ECP System (R2D_I_002) | 1 hrs | 2025-09-12 08:00 | 2025-09-12 09:00 | Yogesh(HCL) | y_yogesh@hcltech.com | Himanshu; Christian Hogrefe; Bernd Gawehn; Paresh Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dixit.h@hcltech.com; Christian.Hogrefe@de.sasol.com; Bernd.Gawehn@consultary.de; paresh.patel@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  |  |  |  | 2025-09-12 08:00 | 2025-09-12 08:00 | 2025-09-12 09:00
95100 | STRIVE.R2.MC1.2384.1.684.593.9 | N | N | N | Planned |  | Logical System creation of S4 in ECP system (R2D_I_002) | 1 hrs | 2025-09-12 08:00 | 2025-09-12 09:00 | Yogesh(HCL) | y_yogesh@hcltech.com | Himanshu; Christian Hogrefe; Bernd Gawehn; Paresh Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dixit.h@hcltech.com; Christian.Hogrefe@de.sasol.com; Bernd.Gawehn@consultary.de; paresh.patel@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  |  |  |  | 2025-09-12 08:00 | 2025-09-12 08:00 | 2025-09-12 09:00
18868 | STRIVE.R2.MC1.2384.1.684.37 |  |  |  | Complete |  | Coupa | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-07-14 08:00 | 2025-08-13 15:47 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18869 | STRIVE.R2.MC1.2384.1.684.37.1 | Y | Y | Y | Complete |  | Coupa environment's token URL and client credentials to be shared with integration team | 1.41 hrs | 2025-07-28 13:55 | 2025-07-28 15:19 | Pournami Nair | pounair@deloitte.com | Rabbani; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | skhadarmohammadra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | S2P_Coupa |  | 2025-07-28 13:55 | 2025-07-28 15:19 | * | NA | 2025-07-28 13:55 | 2025-07-28 15:19
18870 | STRIVE.R2.MC1.2384.1.684.37.2 | Y | Y | Y | Complete |  | Setup OAuth authentication from BTP-IS to Coupa | 0 hrs | 2025-08-13 15:47 | 2025-08-13 15:47 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Naga; Saurabh Kumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Aman Anand; | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; | Integration | 18869 | 2025-08-13 15:47 | 2025-08-13 15:47 | * | NA | 2025-08-13 15:47 | 2025-08-13 15:47
18874 | STRIVE.R2.MC1.2384.1.684.37.6 | Y | Y | Y | Complete |  | Provide Integration team Coupa Runtime Code and ID for all coupa interfaces. | 87.57 hrs | 2025-07-14 08:00 | 2025-07-28 16:34 | Pournami Nair | pounair@deloitte.com | Rabbani; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | skhadarmohammadra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | S2P_Coupa |  | 2025-07-14 08:00 | 2025-07-28 16:34 | * | NA | 2025-07-14 08:00 | 2025-07-28 16:34
18875 | STRIVE.R2.MC1.2384.1.684.44 |  |  |  | Complete |  | Identity Authorization Governance - IAG | 6 hrs | 2025-07-14 08:00 | 2025-07-14 15:00 | [6 empty] | 2025-08-08 13:01 | 2025-08-08 13:01 | * | NA | 2025-07-14 08:00 | 2025-07-14 15:00
18876 | STRIVE.R2.MC1.2384.1.684.44.1 | Y | Y | Y | Complete |  | IAG connection details for integration with S/4 (Not relevant for MC1) | 0 hrs | 2025-08-08 13:01 | 2025-08-08 13:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-08-08 13:01 | 2025-08-08 13:01 | * | NA | 2025-08-08 13:01 | 2025-08-08 13:01
18877 | STRIVE.R2.MC1.2384.1.684.44.2 | Y | Y | Y | Complete |  | Integration of IAG with GRC connection details (Not relevant for MC1) | 0 hrs | 2025-08-08 13:01 | 2025-08-08 13:01 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-08-08 13:01 | 2025-08-08 13:01 | * | NA | 2025-08-08 13:01 | 2025-08-08 13:01
18878 | STRIVE.R2.MC1.2384.1.684.47 | [5 empty] | Advanced Event Mesh | 266.12 hrs | 2025-07-14 08:00 | 2025-07-25 10:51 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-25 10:51
18879 | STRIVE.R2.MC1.2384.1.684.47.1 | Y | Y | Y | Complete |  | Provide required access to Integration Team for AEM | 83.14 hrs | 2025-07-14 08:00 | 2025-07-28 11:08 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Diptendu Chaudhuri ; Sats; Christian; Christian Witt | Shubhathakur@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dichaudhuri@deloitte.de; Sats.Subramoney@sasol.com; Christian.Hogrefe@de.sasol.com; christian.witt@de.sasol.com | GRC |  | 2025-07-14 08:00 | 2025-07-28 11:08 | * | NA | 2025-07-14 08:00 | 2025-07-28 11:08
18881 | STRIVE.R2.MC1.2384.1.684.47.3 | Y | Y | Y | Complete |  | Certificate signing for AEM | 1014.84 hrs | 2025-07-14 08:00 | 2025-08-25 17:40 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian Hogrefe; Rico van den Berg; Basis; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Christian.Hogrefe@de.sasol.com; rico.vandenberg@sasol.com; DeloitteSASOLBasisTeam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-08-25 17:40 | * | NA | 2025-07-14 08:00 | 2025-08-25 17:40
18882 | STRIVE.R2.MC1.2384.1.684.47.4 | Y | Y | Y | Complete |  | Basis team to provide the AEM specific certificate public key to Integration team | 38.74 hrs | 2025-07-14 08:00 | 2025-07-18 15:44 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-18 15:44 | * | NA | 2025-07-14 08:00 | 2025-07-18 15:44
18884 | STRIVE.R2.MC1.2384.1.684.47.6 | Y | Y | Y | Complete |  | Creation of Daemon user for AEM - Dialog and change it to system once the setup is completed (Send password to Basis) | 181.11 hrs | 2025-07-14 08:00 | 2025-08-13 14:06 | Shubham Thakur | Shubhathakur@deloitte.com | Sasol GRC; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dttsasolsecuritygrcteam@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  | 2025-07-14 08:00 | 2025-08-13 14:06 | * | NA | 2025-07-14 08:00 | 2025-08-13 14:06
18885 | STRIVE.R2.MC1.2384.1.684.47.7 | Y | Y | Y | Complete |  | Integration suite - AEM setup - channel creation S4/MDG | 24.28 hrs | 2025-08-13 16:44 | 2025-08-18 17:00 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Satheesh Pula; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | trsagar@deloitte.com; pusatheesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis | 18884 | 2025-08-13 16:44 | 2025-08-18 17:00 | * | NA | 2025-08-13 16:44 | 2025-08-18 17:00
18886 | STRIVE.R2.MC1.2384.1.684.47.8 | Y | Y | Y | Complete |  | Advance Event Mesh Queues creation and topic configuration | 76.3 hrs | 2025-08-05 08:00 | 2025-08-18 13:18 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  | 2025-08-05 08:00 | 2025-08-18 13:18 | * | NA | 2025-08-05 08:00 | 2025-08-18 13:18
18887 | STRIVE.R2.MC1.2384.1.684.47.9 | N | N | N | Planned | Updated | Addition of topics for channels in S4 SPRO - R2P_I_066 Process Order | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18888 | STRIVE.R2.MC1.2384.1.684.47.10 | N | N | N | Planned | Updated | Addition of topics for channels in S4 SPRO -R2P_I_074- Material Master | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18889 | STRIVE.R2.MC1.2384.1.684.47.11 | N | N | N | Planned | Updated | Addition of topics for channels in S4 SPRO - R2P_I_062- Inspection Lot | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18890 | STRIVE.R2.MC1.2384.1.684.47.12 | N | N | N | Planned | Updated | Addition of topics for channels in S4 SPRO - MOR_I_013 - Equipment | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18891 | STRIVE.R2.MC1.2384.1.684.47.13 | N | N | N | Planned | Updated | Addition of topics for channels in S4 SPRO - MOR_I_014 - Functional Location | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18892 | STRIVE.R2.MC1.2384.1.684.47.14 | N | N | N | Planned | Updated | Addition of topics for channels in S4 SPRO - MOR_I_014 -Notification | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18893 | STRIVE.R2.MC1.2384.1.684.47.15 | N | N | N | Planned |  | Addition of topics for channels in S4 SPRO - <PlaceHolder> | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18894 | STRIVE.R2.MC1.2384.1.684.47.16 | N | N | N | Planned |  | Addition of topics for channels in S4 SPRO - <PlaceHolder> | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18885 |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 12:00
18895 | STRIVE.R2.MC1.2384.1.684.47.17 | N | N | N | Planned | Updated | Validation Advance event mesh topics for channels created under SPRO R2P_I_066 Process Order | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Jay Saini | jaysaini4@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Abhishek Parab; Deepika Agarwal | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18887 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18896 | STRIVE.R2.MC1.2384.1.684.47.18 | N | N | N | Planned | Updated | Validation Advance event mesh topics for channels created under SPRO R2P_I_074- Material Master | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Jay Saini | jaysaini4@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Abhishek Parab; Deepika Agarwal | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18888 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18897 | STRIVE.R2.MC1.2384.1.684.47.19 | N | N | N | Planned | Updated | Validation Advance event mesh topics for channels created under SPRO R2P_I_062- Inspection Lot | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Oguz | okorkmazlar@deloitte.it | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P | 18889 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18898 | STRIVE.R2.MC1.2384.1.684.47.20 | N | N | N | Planned | Updated | Validation Advance event mesh topics for channels created under SPRO MOR_I_013 - Equipment | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com | MOR | 18890 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18899 | STRIVE.R2.MC1.2384.1.684.47.21 | N | N | N | Planned | Updated | Validation Advance event mesh topics for channels created under SPRO MOR_I_014 - Functional Location | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com | MOR | 18891 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18900 | STRIVE.R2.MC1.2384.1.684.47.22 | N | N | N | Planned | Updated | Validation Advance event mesh topics for channels created under SPRO MOR_I_014 -Notification | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com | MOR | 18892 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18901 | STRIVE.R2.MC1.2384.1.684.47.23 | N | N | N | Planned |  | Validation Advance event mesh topics for channels created under SPRO - <PlaceHolder> | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Rajat Sharma |  |  |  |  | 18893 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18902 | STRIVE.R2.MC1.2384.1.684.47.24 | N | N | N | Planned |  | Validation Advance event mesh topics for channels created under SPRO - <PlaceHolder> | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Vinod Kumar |  |  |  |  | 18894 |  |  |  | 2025-09-15 10:00 | 2025-09-15 12:01 | 2025-09-15 14:01
18903 | STRIVE.R2.MC1.2384.1.684.72 |  |  |  | Complete |  | S/4->OMP | 1 hrs | 2025-07-14 08:00 | 2025-07-14 09:00 | [6 empty] | 2025-08-20 08:00 | 2025-08-26 14:49 | * | NA | 2025-07-14 08:00 | 2025-07-14 09:00
18904 | STRIVE.R2.MC1.2384.1.684.72.1 | Y | Y | Y | Complete |  | Integration connectivity setup with OMP based on the request from OMP team | 150.4 hrs | 2025-08-20 08:00 | 2025-08-26 14:49 | Priyanka Patel | priyankaspatel@deloitte.de | Tripti Sagar; Sats; Christophe; Edurado; David Conradie; Rajat Sahgal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | trsagar@deloitte.com; Sats.Subramoney@sasol.com; csnoeys@deloitte.com; eduardo.gouveia@us.sasol.com; david.conradie1@sasol.com; rasahgal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | OMP |  | 2025-08-20 08:00 | 2025-08-26 14:49 |  | 2025-08-20 08:00 | 2025-08-20 08:00 | 2025-08-26 14:49
18905 | STRIVE.R2.MC1.2384.1.684.74 | [5 empty] | BW->OMP | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18907 | STRIVE.R2.MC1.2384.1.684.74.2 | Y | N | N | Sent |  | Sasol Infra to setup cloud connector connection to BW system from BTP IS | 2 hrs | 2025-09-01 08:00 | 2025-09-01 10:00 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Sats; Edurado; Priyanka Patel; Christophe; David Conradie; Rajat Sahgal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | Sats.Subramoney@sasol.com; eduardo.gouveia@us.sasol.com; priyankaspatel@deloitte.de; csnoeys@deloitte.com; david.conradie1@sasol.com; rasahgal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure |  |  |  |  | 2025-09-01 08:00 | 2025-09-01 08:00 | 2025-09-01 10:00
18908 | STRIVE.R2.MC1.2384.1.684.74.3 | N | N | N | Planned |  | Sasol to provide BW ODP URLs, virtual host&port, location ID to integration team | 2 hrs | 2025-09-09 10:00 | 2025-09-09 12:00 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Sats; Edurado; Priyanka Patel; Christophe; David Conradie; Rajat Sahgal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | Sats.Subramoney@sasol.com; eduardo.gouveia@us.sasol.com; priyankaspatel@deloitte.de; csnoeys@deloitte.com; david.conradie1@sasol.com; rasahgal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure | 18907 |  |  |  | 2025-09-09 10:00 | 2025-09-09 10:00 | 2025-09-09 12:00
94455 | STRIVE.R2.MC1.2384.1.684.590 | [5 empty] | EVONNIK | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94457 | STRIVE.R2.MC1.2384.1.684.590.9 | Y | N | N | Sent |  | Share the SAP Passport cert with CPI Team | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Sasol Infrastructure |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94456 | STRIVE.R2.MC1.2384.1.684.590.8 | N | N | N | Planned |  | Import SAP Passport cert into Security Material | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar; Pragyesh | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com; pkumargoyal@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94454 | STRIVE.R2.MC1.2384.1.684.590.6 | N | N | N | Planned |  | Share the public key with Evonik Team | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar; Pragyesh | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com; pkumargoyal@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94453 | STRIVE.R2.MC1.2384.1.684.590.5 | N | N | N | Planned |  | SOAMANAGER configuration | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar; Pragyesh | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com; pkumargoyal@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Brenntag | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Share the SAP public passport cert with CPI Team | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Sasol Infrastructure |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Share the SAP private key with Brenntag | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Sasol Infrastructure |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Create a custom role Cust.Brenntag for Brenntag in CPI | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Yashwanth | myakumar@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar;Aman | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Import public cert into BTP to generate service key for Brenntag custom role | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis |  |  |  | Basis |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | ELSTER | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Cross validate the field value of 'digitale signatur keystore entry' | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aquib Iqbal | aquiqbal@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | import the certificate into keystore | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Yashwanth | myakumar@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar;Aman | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | cross verify the note implementation 3531377 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aquib Iqbal | aquiqbal@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
18956 | STRIVE.R2.MC1.2384.1.684.125 |  |  |  | Complete |  | BN4L | 2.48 hrs | 2025-07-14 08:00 | 2025-07-14 10:29 | [6 empty] | 2025-07-14 08:00 | 2025-08-28 15:12 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:29
18957 | STRIVE.R2.MC1.2384.1.684.125.1 | Y | Y | Y | Complete |  | Subscribe to BN4L | 96 hrs | 2025-07-14 08:00 | 2025-07-29 17:00 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian Hogrefe; Rico van den Berg; Manuel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | Christian.Hogrefe@de.sasol.com; rico.vandenberg@sasol.com; Manuel.Roellinghoff@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-29 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-29 17:00
18958 | STRIVE.R2.MC1.2384.1.684.125.2 | Y | Y | Y | Complete |  | Destination creation on BTP for BN4L integration with S/4 | 716.19 hrs | 2025-07-29 17:00 | 2025-08-28 15:11 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian Hogrefe; Rico van den Berg; Manuel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | Christian.Hogrefe@de.sasol.com; rico.vandenberg@sasol.com; Manuel.Roellinghoff@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure | 18957 | 2025-07-29 17:00 | 2025-08-28 15:11 | * | NA | 2025-07-29 17:00 | 2025-08-28 15:11
18959 | STRIVE.R2.MC1.2384.1.684.125.3 | Y | Y | Y | Complete |  | Certificate based connectivity setup with BN4L<->S/4 | 1084.18 hrs | 2025-07-14 08:00 | 2025-08-28 15:12 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian Hogrefe; Rico van den Berg; Manuel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | Christian.Hogrefe@de.sasol.com; rico.vandenberg@sasol.com; Manuel.Roellinghoff@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-08-28 15:12 | * | NA | 2025-07-14 08:00 | 2025-08-28 15:12
18960 | STRIVE.R2.MC1.2384.1.684.129 |  |  |  | Complete |  | AEB | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-07-14 08:00 | 2025-07-25 16:33 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18961 | STRIVE.R2.MC1.2384.1.684.129.1 | Y | Y | Y | Complete |  | Add AEB Certificates in STRUST | 79.54 hrs | 2025-07-14 08:00 | 2025-07-25 16:33 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-25 16:33 | * | NA | 2025-07-14 08:00 | 2025-07-25 16:33
18962 | STRIVE.R2.MC1.2384.1.684.131 | [5 empty] | Opesus | 24.91 hrs | 2025-07-14 08:00 | 2025-07-15 08:59 | [6 empty] | 2025-09-05 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-07-15 08:59
18964 | STRIVE.R2.MC1.2384.1.684.131.2 | Y | Y | Y | Complete |  | Connectivity setup between S/4&ECHA Opesus (Step 1 to Step 5) | 4.85 hrs | 2025-09-05 08:00 | 2025-09-05 12:52 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-09-05 08:00 | 2025-09-05 12:52 |  | 2025-09-05 08:00 | 2025-09-05 08:00 | 2025-09-05 12:52
18965 | STRIVE.R2.MC1.2384.1.684.131.3 | Y | Y | Y | Complete |  | Add Opesus Telia Certificates in STRUST | 8.3 hrs | 2025-09-05 10:00 | 2025-09-05 18:19 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis | 18964 | 2025-09-05 10:00 | 2025-09-05 18:19 | * | NA | 2025-09-05 10:00 | 2025-09-05 18:19
18966 | STRIVE.R2.MC1.2384.1.684.131.4 | Y | N | N | Sent |  | Notify the Basis Team to move Opesus (R2P_I_022) to Production | 2 hrs | 2025-09-05 08:00 | 2025-09-05 10:00 | Sheena Gour | shgour@deloitte.com | Basis; Diptendu Chaudhuri ; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Priyanka Singhal; Naga reddy; Yaswanth | DeloitteSASOLBasisTeam@deloitte.com; dichaudhuri@deloitte.de; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; priyasinghal@deloitte.com; nnagasubbareddy@deloitte.com; myakumar@deloitte.com | R2P |  |  |  |  | 2025-09-05 08:00 | 2025-09-05 08:00 | 2025-09-05 10:00
18967 | STRIVE.R2.MC1.2384.1.684.131.5 | N | N | N | Planned |  | Basis Team to move Opesus (R2P_I_022) to Production | 2 hrs | 2025-09-05 10:00 | 2025-09-05 12:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Diptendu Chaudhuri ; Naga reddy | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dichaudhuri@deloitte.de; nnagasubbareddy@deloitte.com | R2P | 18966 |  |  |  | 2025-09-01 08:00 | 2025-09-05 10:00 | 2025-09-05 12:00
18968 | STRIVE.R2.MC1.2384.1.684.137 |  |  |  | Complete |  | WWI | 7.96 hrs | 2025-07-14 08:00 | 2025-07-14 15:59 | [6 empty] | 2025-07-14 08:00 | 2025-08-26 11:23 | * | NA | 2025-07-14 08:00 | 2025-07-14 15:59
18969 | STRIVE.R2.MC1.2384.1.684.137.1 | Y | Y | Y | Complete |  | Create EHS TCP IP connections | 79.56 hrs | 2025-07-14 08:00 | 2025-07-25 16:34 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS; Harish Kristapati; Sheena Gour; Priyanka Singhal | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com; hkristapati@deloitte.com; shgour@deloitte.com; priyasinghal@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-07-25 16:34 | * | NA | 2025-07-14 08:00 | 2025-07-25 16:34
18970 | STRIVE.R2.MC1.2384.1.684.137.2 | Y | Y | Y | Complete |  | Register program on gateway | 91.69 hrs | 2025-07-14 10:00 | 2025-07-29 14:42 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis | 18969 | 2025-07-14 10:00 | 2025-07-29 14:42 | * | NA | 2025-07-14 10:00 | 2025-07-29 14:42
18971 | STRIVE.R2.MC1.2384.1.684.137.3 | Y | Y | Y | Complete |  | send RFC&Program ID details to Sasol WWI Team | 70.31 hrs | 2025-07-29 14:42 | 2025-08-11 12:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis | 18970 | 2025-07-29 14:42 | 2025-08-11 12:00 | * | NA | 2025-07-29 14:42 | 2025-08-11 12:00
18972 | STRIVE.R2.MC1.2384.1.684.137.4 | Y | Y | Y | Complete |  | Maintain RFC&register the program on WWI | 341.62 hrs | 2025-08-11 12:01 | 2025-08-25 18:34 | Pooja Babli | babli.p@hcltech.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 18971 | 2025-08-11 12:01 | 2025-08-25 18:34 | * | NA | 2025-08-11 12:01 | 2025-08-25 18:34
18973 | STRIVE.R2.MC1.2384.1.684.137.5 | Y | Y | Y | Complete |  | Check CGSADM to verify the setup | 27.31 hrs | 2025-08-25 08:00 | 2025-08-26 11:23 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis | 18972 | 2025-08-25 08:00 | 2025-08-26 11:23 |  | 2025-08-25 08:00 | 2025-08-25 08:00 | 2025-08-26 11:23
18974 | STRIVE.R2.MC1.2384.1.684.143 |  |  |  | Complete |  | VES | 1 hrs | 2025-07-14 08:00 | 2025-07-14 09:00 | [6 empty] | 2025-07-14 08:00 | 2025-08-13 15:05 | * | NA | 2025-07-14 08:00 | 2025-07-14 09:00
18975 | STRIVE.R2.MC1.2384.1.684.143.1 | Y | Y | Y | Complete |  | Create HTTPS VIES_DIRECT connection | 179.35 hrs | 2025-07-14 08:00 | 2025-08-13 11:21 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis |  | 2025-07-14 08:00 | 2025-08-13 11:21 | * | NA | 2025-07-14 08:00 | 2025-08-13 11:21
18976 | STRIVE.R2.MC1.2384.1.684.143.2 | Y | Y | Y | Complete |  | Add One VIES Certificates in STRUST | 2.74 hrs | 2025-08-13 11:21 | 2025-08-13 15:05 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Basis | 18975 | 2025-08-13 11:21 | 2025-08-13 15:05 | * | NA | 2025-08-13 11:21 | 2025-08-13 15:05
18977 | STRIVE.R2.MC1.2384.1.684.146 |  |  |  | Complete |  | MBC/Multibanking | 56.3 hrs | 2025-07-14 08:00 | 2025-07-16 16:27 | [6 empty] | 2025-07-14 08:00 | 2025-08-28 15:12 | * | NA | 2025-07-14 08:00 | 2025-07-16 16:27
18978 | STRIVE.R2.MC1.2384.1.684.146.1 | Y | Y | Y | Complete |  | Import MBC Transports | 96 hrs | 2025-07-14 08:00 | 2025-07-29 17:00 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Christian.Hogrefe@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  | 2025-07-14 08:00 | 2025-07-29 17:00 | * | NA | 2025-07-14 08:00 | 2025-07-29 17:00
18979 | STRIVE.R2.MC1.2384.1.684.146.2 | Y | Y | Y | Complete |  | Generate PSE and share with SAP MBC onboarding Team | 77.25 hrs | 2025-07-30 08:00 | 2025-08-12 14:15 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Christian.Hogrefe@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure | 18978 | 2025-07-30 08:00 | 2025-08-12 14:15 | * | NA | 2025-07-30 08:00 | 2025-08-12 14:15
18980 | STRIVE.R2.MC1.2384.1.684.146.3 | Y | Y | Y | Complete |  | Generate Application Token in IAS for MBC | 104.82 hrs | 2025-08-15 10:00 | 2025-08-19 19:06 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Christian.Hogrefe@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure | 18979 | 2025-08-15 10:00 | 2025-08-19 19:06 |  | 2025-08-15 10:00 | 2025-08-15 10:00 | 2025-08-19 19:06
18981 | STRIVE.R2.MC1.2384.1.684.146.4 | Y | Y | Y | Complete |  | Configure OAuth in S/4 | 28.67 hrs | 2025-08-19 19:06 | 2025-08-20 23:51 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Christian.Hogrefe@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure | 18980 | 2025-08-19 19:06 | 2025-08-20 23:51 | * | NA | 2025-08-19 19:06 | 2025-08-20 23:51
18982 | STRIVE.R2.MC1.2384.1.684.146.5 | Y | Y | Y | Complete |  | Create RFC connections from S/4 to MBC | 182.83 hrs | 2025-08-20 23:51 | 2025-08-28 15:12 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Christian.Hogrefe@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure | 18981 | 2025-08-20 23:51 | 2025-08-28 15:12 | * | NA | 2025-08-20 23:51 | 2025-08-28 15:12
18983 | STRIVE.R2.MC1.2384.1.684.152 |  |  |  | Complete |  | OneSource (R2D_I_013) | 2 hrs | 2025-07-14 08:00 | 2025-07-14 10:00 | [6 empty] | 2025-08-13 14:53 | 2025-08-18 14:06 | * | NA | 2025-07-14 08:00 | 2025-07-14 10:00
18984 | STRIVE.R2.MC1.2384.1.684.152.1 | Y | Y | Y | Complete |  | Share onesource credentials, URL with integration team | 0 hrs | 2025-08-18 14:06 | 2025-08-18 14:06 | Priyanka Patel | priyankaspatel@deloitte.de | USI STRIVE CUTOVER; Tripti Sagar; Dhruv Kansal; Mousikta chanda | usistrivecutover@deloitte.com; trsagar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | BASIS |  | 2025-08-18 14:06 | 2025-08-18 14:06 | * | NA | 2025-08-18 14:06 | 2025-08-18 14:06
18985 | STRIVE.R2.MC1.2384.1.684.152.2 | Y | Y | Y | Complete |  | SOAMANAGER configuration OneSource (R2D_I_013)- Manual port creation in web service configuration | 1.22 hrs | 2025-08-13 14:53 | 2025-08-13 16:06 | Pragyesh Kumar | pkumargoyal@deloitte.com | Naga; Saurabh Kumar; Yashwanth; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; myakumar@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | Integration |  | 2025-08-13 14:53 | 2025-08-13 16:06 | * | NA | 2025-08-13 14:53 | 2025-08-13 16:06
94466 | STRIVE.R2.MC1.2384.1.684.591 | [5 empty] | MDI(Master Data Integration) | 14 hrs | 2025-09-15 08:00 | 2025-09-15 22:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
[6 empty] | Add | Create Subaccount where MDI Service available(EX: Frankfort etc..) |  |  |  | Basis
94467 | STRIVE.R2.MC1.2384.1.684.591.15 | Y | N | N | Sent |  | Provision of MDI Service in SAP BTP | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94468 | STRIVE.R2.MC1.2384.1.684.591.16 | Y | N | N | Sent |  | Create a service instance and a service key (S4 and Successfactor) for MDI | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Share MDI related virtual host and port details to CPI team |  |  |  | Basis
94469 | STRIVE.R2.MC1.2384.1.684.591.17 | Y | N | N | Sent |  | Creating an OAuth 2.0 Client in SAP S4 for MDI | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94470 | STRIVE.R2.MC1.2384.1.684.591.18 | Y | N | N | Sent |  | Create RFC Destination under SM59 for MDI | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94471 | STRIVE.R2.MC1.2384.1.684.591.19 | Y | N | N | Sent |  | Configure the destination created in the previous step to be used to connect toSAP Master Data Integration(S_SAL_71000052) | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94472 | STRIVE.R2.MC1.2384.1.684.591.20 | N | N | N | Planned | Updated | Create MDI_LOG & MDO_DRF_INBOUND Inbound destination via sbgrfcconf transaction | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94473 | STRIVE.R2.MC1.2384.1.684.591.21 | N | N | N | Planned |  | Extract AIF Content for MDI | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94462 | STRIVE.R2.MC1.2384.1.684.591.10 | N | N | N | Planned |  | Publish MDO OData V4 Service Groups | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94463 | STRIVE.R2.MC1.2384.1.684.591.11 | N | N | N | Planned |  | Create Technical User for MDI (MDO_USER) and Maintain Roles | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | GRC | dttsasolsecuritygrcteam@deloitte.com | Somitra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | sothapa@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | GRC |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94464 | STRIVE.R2.MC1.2384.1.684.591.12 | N | N | N | Planned |  | Set Up Destinations in theSAP BTP Cockpit for MDI | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94465 | STRIVE.R2.MC1.2384.1.684.591.13 | N | N | N | Planned |  | Share Oauth Credentails with Successfactor Team | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Patel; Tripti Sagar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | priyankaspatel@deloitte.de; trsagar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94460 | STRIVE.R2.MC1.2384.1.684.591.8 | N | N | N | Planned |  | SF Team needs to create Oauth profile and enable Cost Center Business Scenario | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Oliver Ditt | Oliver.Ditt@de.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Sasol Infrastructure |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19010 | STRIVE.R2.MC1.2384.1.684.179 | [5 empty] | Iflow Configuration | 1847.91 hrs | 2025-08-25 08:00 | 2025-11-10 13:04 | [8 empty] | * | NA | 2025-08-25 08:00 | 2025-11-10 13:04
19011 | STRIVE.R2.MC1.2384.1.684.179.1 | [5 empty] | S/4HANA-COUPA (Placeholder for Wave 1 Interfaces) | 1847.91 hrs | 2025-08-25 08:00 | 2025-11-10 13:04 | [8 empty] | * | NA | 2025-08-25 08:00 | 2025-11-10 13:04
19012 | STRIVE.R2.MC1.2384.1.684.179.1.1 |  |  |  |  | Updated | S2P_I_045-Integration of PIR from Coupa to S4 | 30.88 hrs | 2025-09-24 08:00 | 2025-09-16 14:58 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 14:58
19013 | STRIVE.R2.MC1.2384.1.684.179.1.1.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - S2P_I_045 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Prasanth | kalprasanth@deloitte.com | Pournami Nair; Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19014 | STRIVE.R2.MC1.2384.1.684.179.1.1.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - S2P_I_045 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19013 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19015 | STRIVE.R2.MC1.2384.1.684.179.1.1.3 | N | N | N | Planned | Updated | Check iflows dependencies -S2P_I_045 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19014 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19016 | STRIVE.R2.MC1.2384.1.684.179.1.1.4 | N | N | N | Planned | Updated | Validate the import of Iflow's -S2P_I_045 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19015 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19017 | STRIVE.R2.MC1.2384.1.684.179.1.1.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_045 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19016 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19018 | STRIVE.R2.MC1.2384.1.684.179.1.7 |  |  |  |  | Updated | S2P_I_046_Integration of Invoices from S4 to Coupa (ERS Invoice) | 30.88 hrs | 2025-10-24 08:00 | 2025-09-16 14:58 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 14:58
19019 | STRIVE.R2.MC1.2384.1.684.179.1.7.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - S2P_I_046 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 09:00 | Prasanth | kalprasanth@deloitte.com | Pournami Nair; Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19020 | STRIVE.R2.MC1.2384.1.684.179.1.7.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - S2P_I_046 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19019 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19021 | STRIVE.R2.MC1.2384.1.684.179.1.7.3 | N | N | N | Planned | Updated | Check iflows dependencies - S2P_I_046 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19020 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19022 | STRIVE.R2.MC1.2384.1.684.179.1.7.4 | N | N | N | Planned | Updated | Validate the import of Iflow's -S2P_I_046 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19021 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19023 | STRIVE.R2.MC1.2384.1.684.179.1.7.5 | N | N | N | Planned | Updated | Configure the End system URL's, Security Artifacts, UserNames and other externalized values including Control Records for each interface accordingly.- S2P_I_046 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19022 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19024 | STRIVE.R2.MC1.2384.1.684.179.1.13 |  |  |  |  | Updated | S2P_I_047_Quantity Contract Interface for PR | 27.91 hrs | 2025-10-01 08:00 | 2025-09-16 11:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 11:59
19025 | STRIVE.R2.MC1.2384.1.684.179.1.13.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - S2P_I_047 | 1 hrs | 2025-10-01 08:00 | 2025-09-15 09:00 | Pournami Nair | pounair@deloitte.com | Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19026 | STRIVE.R2.MC1.2384.1.684.179.1.13.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - S2P_I_047 | 1 hrs | 2025-10-01 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19025 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19027 | STRIVE.R2.MC1.2384.1.684.179.1.13.3 | N | N | N | Planned | Updated | Check iflows dependencies - S2P_I_047 | 1 hrs | 2025-10-01 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19026 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19028 | STRIVE.R2.MC1.2384.1.684.179.1.13.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - S2P_I_047 | 1 hrs | 2025-10-01 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19027 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19029 | STRIVE.R2.MC1.2384.1.684.179.1.13.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_047 | 1 hrs | 2025-10-01 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19028 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
[6 empty] | Add | Share the CPI URL to coupa Team - S2P_I_047 | 1 hrs | 2025-10-01 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19028
19030 | STRIVE.R2.MC1.2384.1.684.179.1.19 |  |  |  |  | Updated | S2P_I_048_Quantity Contract Interface for PO | 29.9 hrs | 2025-09-19 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19031 | STRIVE.R2.MC1.2384.1.684.179.1.19.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - S2P_I_048 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 09:00 | Pournami Nair | pounair@deloitte.com | Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19032 | STRIVE.R2.MC1.2384.1.684.179.1.19.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - S2P_I_048 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19031 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19033 | STRIVE.R2.MC1.2384.1.684.179.1.19.3 | N | N | N | Planned | Updated | Check iflows dependencies - S2P_I_048 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19032 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19034 | STRIVE.R2.MC1.2384.1.684.179.1.19.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - S2P_I_048 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19033 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19035 | STRIVE.R2.MC1.2384.1.684.179.1.19.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_048 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19034 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
[6 empty] | Add | Share the CPI URL to coupa Team - S2P_I_048 | 1 hrs | 2025-10-01 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19028
19036 | STRIVE.R2.MC1.2384.1.684.179.1.25 |  |  |  |  | Updated | S2P_I_049-PO Closure automation | 29.9 hrs | 2025-10-03 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19037 | STRIVE.R2.MC1.2384.1.684.179.1.25.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - S2P_I_049 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Prasanth | kalprasanth@deloitte.com | Pournami Nair; Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19038 | STRIVE.R2.MC1.2384.1.684.179.1.25.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - S2P_I_049 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19037 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19039 | STRIVE.R2.MC1.2384.1.684.179.1.25.3 | N | N | N | Planned | Updated | Check iflows dependencies - S2P_I_049 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19038 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19040 | STRIVE.R2.MC1.2384.1.684.179.1.25.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - S2P_I_049 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19039 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19041 | STRIVE.R2.MC1.2384.1.684.179.1.25.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_049 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19040 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19042 | STRIVE.R2.MC1.2384.1.684.179.1.31 |  |  |  |  | Updated | S2P_I_050-Supplier Interface Coupa to MDG redesign (Part of CR059) | 29.9 hrs | 2025-10-06 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19043 | STRIVE.R2.MC1.2384.1.684.179.1.31.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - S2P_I_050 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 09:00 | Pournami Nair | pounair@deloitte.com | Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19044 | STRIVE.R2.MC1.2384.1.684.179.1.31.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - S2P_I_050 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19043 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19045 | STRIVE.R2.MC1.2384.1.684.179.1.31.3 | N | N | N | Planned | Updated | Check iflows dependencies - S2P_I_050 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19044 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19046 | STRIVE.R2.MC1.2384.1.684.179.1.31.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - S2P_I_050 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19045 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19047 | STRIVE.R2.MC1.2384.1.684.179.1.31.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_050 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 19046 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19048 | STRIVE.R2.MC1.2384.1.684.179.1.37 |  |  |  |  | Updated | S2P_I_057-Integrate Ok2Pay file from Coupa to S4 (Non PO Invoice, PO Invoice, Credit Memos) | 29.9 hrs | 2025-10-10 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19049 | STRIVE.R2.MC1.2384.1.684.179.1.37.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - S2P_I_057 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Prasanth | kalprasanth@deloitte.com | Pournami Nair; Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19050 | STRIVE.R2.MC1.2384.1.684.179.1.37.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - S2P_I_057 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19051 | STRIVE.R2.MC1.2384.1.684.179.1.37.3 | N | N | N | Planned | Updated | Check iflows dependencies - S2P_I_057 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19052 | STRIVE.R2.MC1.2384.1.684.179.1.37.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - S2P_I_057 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19053 | STRIVE.R2.MC1.2384.1.684.179.1.37.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_057 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
[6 empty] | Add | S2P_I_010-Integration of MRP PR from S4 to Coupa ( (configure the Plant for Wave1)) | 29.9 hrs | 2025-10-10 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
[6 empty] | Add | Notify the integration team to move objects to the next higher environment - S2P_I_010 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Pournami Nair | pounair@deloitte.com | Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Create Transport request from CPI DEV to CPI QA/Production package -S2P_I_010 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
[6 empty] | Add | Check iflows dependencies - S2P_I_010 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
[6 empty] | Add | Validate the import of Iflow's - S2P_I_010 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
[6 empty] | Add | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_010 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
[6 empty] | Add | S2P_I_053/55 -Integrate the Purchase Order changes done in Coupa to S/4 HANA | 29.9 hrs | 2025-10-10 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
[6 empty] | Add | Notify the integration team to move objects to the next higher environment - S2P_I_053/55 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Pournami Nair | pounair@deloitte.com | Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Create Transport request from CPI DEV to CPI QA/Production package -S2P_I_053/55 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
[6 empty] | Add | Check iflows dependencies - S2P_I_053/55 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
[6 empty] | Add | Validate the import of Iflow's - S2P_I_053/55 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
[6 empty] | Add | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_053/55 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
[6 empty] | Add | S2P_I_058-Integrate Payment status from S/4 to Coupa in case of Payment | 29.9 hrs | 2025-10-10 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
[6 empty] | Add | Notify the integration team to move objects to the next higher environment - S2P_I_058 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Pournami Nair | pounair@deloitte.com | Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Create Transport request from CPI DEV to CPI QA/Production package -S2P_I_058 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
[6 empty] | Add | Check iflows dependencies - S2P_I_058 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
[6 empty] | Add | Validate the import of Iflow's - S2P_I_058 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
[6 empty] | Add | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - S2P_I_058 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
[6 empty] | Add | Retrofit(N+1) - Coupa Pilot Interface- Only Relevant to MC1 | 29.9 hrs | 2025-10-10 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
[6 empty] | Add | Notify Integration Team to Retrofit the Pilot interface Coupa interface i.e : S2P_I_009,S2P_I_020,S2P_I_022,S2P_I_024,S2P_I_025,S2P_I_036,S2P_I_035 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Pournami Nair | pounair@deloitte.com | Pournami Nair; Saurabh Kumar; Yashwanth; Naga reddy; Rabbani; Pournami; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; saurabhkumar397@deloitte.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Retrofit the Pilot interface Coupa interface i.e : S2P_I_009,S2P_I_020,S2P_I_022,S2P_I_024,S2P_I_025,S2P_I_036,S2P_I_035 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19119 | STRIVE.R2.MC1.2384.1.684.179.109 |  |  |  |  | Updated | MDG (Placeholder for Wave 1 Interfaces) | 72.75 hrs | 2025-09-15 08:00 | 2025-09-18 08:57 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-18 08:57
19129 | STRIVE.R2.MC1.2384.1.684.179.109.10 |  |  |  |  | Updated | MDG_I_200_STRIVE_MDG_Customer_MDG_to_Sample_Manager_LIMS | 72.75 hrs | 2025-09-26 08:00 | 2025-09-18 08:57 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-18 08:57
19130 | STRIVE.R2.MC1.2384.1.684.179.109.10.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - MDG_I_200 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; | tupal@deloitte.com; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; | MDG |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19131 | STRIVE.R2.MC1.2384.1.684.179.109.10.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package -MDG_I_200 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Yaswanth; Pragyesh | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; myakumar@deloitte.com; pkumargoyal@deloitte.com | Integration | 19130 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19132 | STRIVE.R2.MC1.2384.1.684.179.109.10.3 | N | N | N | Planned | Updated | Check iflows dependencies - MDG_I_200 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Yaswanth; Pragyesh | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; myakumar@deloitte.com; pkumargoyal@deloitte.com | Integration | 19131 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19133 | STRIVE.R2.MC1.2384.1.684.179.109.10.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - MDG_I_200 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Yaswanth; Pragyesh | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; myakumar@deloitte.com; pkumargoyal@deloitte.com | Integration | 19132 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19134 | STRIVE.R2.MC1.2384.1.684.179.109.10.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly - MDG_I_200 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Yaswanth; Pragyesh | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; myakumar@deloitte.com; pkumargoyal@deloitte.com | Integration | 19133 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19136 | STRIVE.R2.MC1.2384.1.684.179.109.10.7 | N | N | N | Planned | Updated | Deploy the Iflow in CPI -MDG_I_200 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 14:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Yaswanth; Pragyesh | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; myakumar@deloitte.com; pkumargoyal@deloitte.com | Integration | 19134 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
19137 | STRIVE.R2.MC1.2384.1.684.179.109.10.8 | N | N | N | Planned | Updated | Validate, if interface is activated - MDG_I_200 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 15:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Yaswanth; Pragyesh | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; myakumar@deloitte.com; pkumargoyal@deloitte.com | Integration | 19136 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
19138 | STRIVE.R2.MC1.2384.1.684.179.109.19 |  |  |  |  | Updated | MDG_I_210_STRIVE_MDG_SUPPLIER_MDG_TO_COUPA (Part of CR059) | 1245.87 hrs | 2025-09-19 08:00 | 2025-11-06 09:20 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-11-06 09:20
19139 | STRIVE.R2.MC1.2384.1.684.179.109.19.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 09:00 | Tulika Pal | tupal@deloitte.com | ; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19140 | STRIVE.R2.MC1.2384.1.684.179.109.19.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 19139 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19141 | STRIVE.R2.MC1.2384.1.684.179.109.19.3 | N | N | N | Planned | Updated | Check iflows dependencies-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 19140 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19142 | STRIVE.R2.MC1.2384.1.684.179.109.19.4 | N | N | N | Planned | Updated | Validate the import of Iflow's-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 19141 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19143 | STRIVE.R2.MC1.2384.1.684.179.109.19.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 19142 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19144 | STRIVE.R2.MC1.2384.1.684.179.109.19.6 | N | N | N | Planned | Updated | Provide confirmation to the integration team for interface activation-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 14:01 | Tulika Pal | tupal@deloitte.com | Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 19143 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
19145 | STRIVE.R2.MC1.2384.1.684.179.109.19.7 | N | N | N | Planned | Updated | Deploy the Iflow in CPI-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 15:01 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 19144 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
19146 | STRIVE.R2.MC1.2384.1.684.179.109.19.8 | N | N | N | Planned | Updated | Validate, if interface is activated-MDG_I_210 | 1 hrs | 2025-09-19 08:00 | 2025-09-15 16:01 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 19145 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
19147 | STRIVE.R2.MC1.2384.1.684.179.109.28 |  |  |  |  | Updated | MDG_I_230-STRIVE_MDG_Material_MDG_TO_COUPA | 771.55 hrs | 2025-10-06 08:00 | 2025-10-17 13:42 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-17 13:42
19148 | STRIVE.R2.MC1.2384.1.684.179.109.28.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 09:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; | tupal@deloitte.com; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; | MDG |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19149 | STRIVE.R2.MC1.2384.1.684.179.109.28.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pragyesh | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pkumargoyal@deloitte.com | Integration | 19148 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19150 | STRIVE.R2.MC1.2384.1.684.179.109.28.3 | N | N | N | Planned | Updated | Check iflows dependencies-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pragyesh | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pkumargoyal@deloitte.com | Integration | 19149 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19151 | STRIVE.R2.MC1.2384.1.684.179.109.28.4 | N | N | N | Planned | Updated | Validate the import of Iflow's-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 12:00 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pragyesh | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pkumargoyal@deloitte.com | Integration | 19150 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19152 | STRIVE.R2.MC1.2384.1.684.179.109.28.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 13:01 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pragyesh | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pkumargoyal@deloitte.com | Integration | 19151 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
21022 | STRIVE.R2.MC1.2384.1.684.179.109.28.9 | N | N | N | Planned | Updated | Supplier DM Legacy number identification type value change in CPI | 1 hrs | 2025-10-06 08:00 | 2025-09-15 14:01 | Pragyesh | pkumargoyal@deloitte.com | Yashwanth; Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 19152 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
19153 | STRIVE.R2.MC1.2384.1.684.179.109.28.6 | N | N | N | Planned | Updated | Provide confirmation to the integration team for interface activation-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 14:01 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG | 19152 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
19154 | STRIVE.R2.MC1.2384.1.684.179.109.28.7 | N | N | N | Planned | Updated | Deploy the Iflow in CPI-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 15:01 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pragyesh | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pkumargoyal@deloitte.com | Integration | 19153 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
19155 | STRIVE.R2.MC1.2384.1.684.179.109.28.8 | N | N | N | Planned | Updated | Validate, if interface is activated-MDG_I_230 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 16:01 | Naga reddy | nnagasubbareddy@deloitte.com | Yashwanth; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19154 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
19175 | STRIVE.R2.MC1.2384.1.684.179.165 |  |  |  |  | Updated | S/4HANA-ShiftConnector | 75.39 hrs | 2025-09-15 08:00 | 2025-09-18 11:35 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-18 11:35
19176 | STRIVE.R2.MC1.2384.1.684.179.165.1 |  |  |  |  | Updated | MOR_I_013-Shift-connector Equipment (outbound) | 54.55 hrs | 2025-09-26 08:00 | 2025-09-17 14:42 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 14:42
19177 | STRIVE.R2.MC1.2384.1.684.179.165.1.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-MOR_I_013 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Chaitnya | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19178 | STRIVE.R2.MC1.2384.1.684.179.165.1.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - MOR_I_013 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; | Integration | 19177 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19179 | STRIVE.R2.MC1.2384.1.684.179.165.1.3 | N | N | N | Planned | Updated | Check iflows dependencies - MOR_I_013 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 19178 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19180 | STRIVE.R2.MC1.2384.1.684.179.165.1.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - MOR_I_013 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 19179 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19181 | STRIVE.R2.MC1.2384.1.684.179.165.1.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - MOR_I_013 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 19180 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19182 | STRIVE.R2.MC1.2384.1.684.179.165.7 |  |  |  |  | Updated | MOR_I_014-Shift-connector Functional location (outbound) | 75.37 hrs | 2025-09-26 08:00 | 2025-09-18 11:34 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-18 11:34
19183 | STRIVE.R2.MC1.2384.1.684.179.165.7.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - MOR_I_014 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Chaitnya | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19184 | STRIVE.R2.MC1.2384.1.684.179.165.7.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - MOR_I_014 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 19183 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19185 | STRIVE.R2.MC1.2384.1.684.179.165.7.3 | N | N | N | Planned | Updated | Check iflows dependencies - MOR_I_014 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 19184 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19186 | STRIVE.R2.MC1.2384.1.684.179.165.7.4 | N | N | N | Planned | Updated | Validate the import of Iflow's - MOR_I_014 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 19185 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19187 | STRIVE.R2.MC1.2384.1.684.179.165.7.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - MOR_I_014 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 19186 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94505 | STRIVE.R2.MC1.2384.1.684.179.165.13 |  |  |  |  | Updated | MOR_I_016-Shift-connector notifications create/update (outbound) | 5 hrs | 2025-10-06 12:01 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94506 | STRIVE.R2.MC1.2384.1.684.179.165.13.23 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - MOR_I_016 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Chaitnya | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94507 | STRIVE.R2.MC1.2384.1.684.179.165.13.24 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - MOR_I_016 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94506 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94508 | STRIVE.R2.MC1.2384.1.684.179.165.13.25 | N | N | N | Planned | Updated | Check iflows dependencies - MOR_I_016 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94507 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94509 | STRIVE.R2.MC1.2384.1.684.179.165.13.26 | N | N | N | Planned | Updated | Validate the import of Iflow's - MOR_I_016 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94508 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94510 | STRIVE.R2.MC1.2384.1.684.179.165.13.27 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - MOR_I_016 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94509 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94511 | STRIVE.R2.MC1.2384.1.684.179.165.14 |  |  |  |  | Updated | MOR_I_015-Shift-connector notifications update (inbound) | 5 hrs | 2025-10-06 12:01 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94512 | STRIVE.R2.MC1.2384.1.684.179.165.14.29 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - MOR_I_015 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Chaitnya | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94513 | STRIVE.R2.MC1.2384.1.684.179.165.14.30 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - MOR_I_015 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94512 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94514 | STRIVE.R2.MC1.2384.1.684.179.165.14.31 | N | N | N | Planned | Updated | Check iflows dependencies - MOR_I_015 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94513 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94515 | STRIVE.R2.MC1.2384.1.684.179.165.14.32 | N | N | N | Planned | Updated | Validate the import of Iflow's - MOR_I_015 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 12:00 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94514 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94516 | STRIVE.R2.MC1.2384.1.684.179.165.14.33 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - MOR_I_015 | 1 hrs | 2025-10-06 12:01 | 2025-09-15 13:01 | Pragyesh | pkumargoyal@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 94515 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94517 | STRIVE.R2.MC1.2384.1.684.179.366 |  |  |  |  | Updated | S/4HANA-COMOS | 14 hrs | 2025-10-15 08:00 | 2025-09-15 22:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94518 | STRIVE.R2.MC1.2384.1.684.179.366.16 |  |  |  |  | Updated | MOR_I_017-COMOS interface - 1 | 5 hrs | 2025-10-15 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94519 | STRIVE.R2.MC1.2384.1.684.179.366.16.36 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment - MOR_I_017 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Chaitnya | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94520 | STRIVE.R2.MC1.2384.1.684.179.366.16.37 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package - MOR_I_017 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 10:00 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94519 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94497 | STRIVE.R2.MC1.2384.1.684.179.366.16.14 | N | N | N | Planned | Updated | Check iflows dependencies - MOR_I_017 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 11:00 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94520 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94498 | STRIVE.R2.MC1.2384.1.684.179.366.16.15 | N | N | N | Planned | Updated | Validate the import of Iflow's - MOR_I_017 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 12:00 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94497 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94499 | STRIVE.R2.MC1.2384.1.684.179.366.16.16 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - MOR_I_017 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 13:01 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94498 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94500 | STRIVE.R2.MC1.2384.1.684.179.366.1 |  |  |  |  | Delete | MOR_I_018-COMOS interface - 2 | 5 hrs | 2025-09-15 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94501 | STRIVE.R2.MC1.2384.1.684.179.366.1.18 | N | N | N | Planned | Delete | Notify the integration team to move objects to the next higher environment - MOR_I_018 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Chaitnya | jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94502 | STRIVE.R2.MC1.2384.1.684.179.366.1.19 | N | N | N | Planned | Delete | Create Transport request from CPI DEV to CPI QA/Production package - MOR_I_018 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94501 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94503 | STRIVE.R2.MC1.2384.1.684.179.366.1.20 | N | N | N | Planned | Delete | Check iflows dependencies - MOR_I_018 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94502 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94504 | STRIVE.R2.MC1.2384.1.684.179.366.1.21 | N | N | N | Planned | Delete | Validate the import of Iflow's - MOR_I_018 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94503 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94493 | STRIVE.R2.MC1.2384.1.684.179.366.1.10 | N | N | N | Planned | Delete | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly. - MOR_I_018 | 1 hrs | 2025-09-15 12:01 | 2025-09-15 13:01 | Sonali Prakash | soprakash@deloitte.com | Saurabh Kumar; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand; Pragyesh | saurabhkumar397@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com; pkumargoyal@deloitte.com | Integration | 94504 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19248 | STRIVE.R2.MC1.2384.1.684.179.238 | [5 empty] | S/4HANA-EHS | 54.82 hrs | 2025-09-24 08:00 | 2025-09-17 14:58 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 14:58
19249 | STRIVE.R2.MC1.2384.1.684.179.238.1 |  |  |  |  | Updated | R2P_I_050-EHS:Transit Interface (MARL)- Includes Dangerous Goods | 54.82 hrs | 2025-09-24 08:00 | 2025-09-17 14:58 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 14:58
19250 | STRIVE.R2.MC1.2384.1.684.179.238.1.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_050 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Alex Larionov | allarionov@deloitte.de | Sheena Gour; Priyanka Singhal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar; Nilesh Deshpande | shgour@deloitte.com; priyasinghal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19251 | STRIVE.R2.MC1.2384.1.684.179.238.1.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_050 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19250 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19252 | STRIVE.R2.MC1.2384.1.684.179.238.1.3 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_050 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19251 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19253 | STRIVE.R2.MC1.2384.1.684.179.238.1.4 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_050 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19252 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19254 | STRIVE.R2.MC1.2384.1.684.179.238.1.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_050 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19253 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19255 | STRIVE.R2.MC1.2384.1.684.179.238.7 |  |  |  |  | Updated | R2P_I_051_EHS: Transit Interface(MARL) : Transfer Specification data toEBSOFT via EVONIK CPI | 53.82 hrs | 2025-10-03 08:00 | 2025-09-17 13:58 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 13:58
19256 | STRIVE.R2.MC1.2384.1.684.179.238.7.1 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_051 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Alex Larionov | allarionov@deloitte.de | Sheena Gour; Priyanka Singhal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar; Nilesh Deshpande | shgour@deloitte.com; priyasinghal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19257 | STRIVE.R2.MC1.2384.1.684.179.238.7.2 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_051 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19256 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
19258 | STRIVE.R2.MC1.2384.1.684.179.238.7.3 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_051 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19257 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
19259 | STRIVE.R2.MC1.2384.1.684.179.238.7.4 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_051 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19258 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19260 | STRIVE.R2.MC1.2384.1.684.179.238.7.5 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_051 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19259 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94525 | STRIVE.R2.MC1.2384.1.684.179.238.13 |  |  |  |  | Updated | R2P_I_052-EHS: Shipment of phrases to EBSOFT via EVONIK CPI(MARL Specific) | 5 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94526 | STRIVE.R2.MC1.2384.1.684.179.238.13.11 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_052 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Alex Larionov | allarionov@deloitte.de | Sheena Gour; Priyanka Singhal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar; Nilesh Deshpande | shgour@deloitte.com; priyasinghal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94523 | STRIVE.R2.MC1.2384.1.684.179.238.13.8 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_052 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94526 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94524 | STRIVE.R2.MC1.2384.1.684.179.238.13.9 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_052 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94523 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94522 | STRIVE.R2.MC1.2384.1.684.179.238.13.7 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_052 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94524 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94521 | STRIVE.R2.MC1.2384.1.684.179.238.13.6 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_052 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94522 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94545 | STRIVE.R2.MC1.2384.1.684.179.238.14 | [5 empty] | R2P_I_060-EHS: Opesus - PCN Germany | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94546 | STRIVE.R2.MC1.2384.1.684.179.238.14.28 | N | N | N | Planned |  | Validate Config for Opesus | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Naga | priyasinghal@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; nnagasubbareddy@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94547 | STRIVE.R2.MC1.2384.1.684.179.238.15 |  |  |  |  | Delete | R2P_I_061-Lab analytical equipment (Gas chromatograph) interface with S/4 QM - Site MARL. Receive inspection lot data from Analytical Devices | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94548 | STRIVE.R2.MC1.2384.1.684.179.238.15.30 | N | N | N | Planned | Delete | Validate ABAP TR | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Gurmandeep Singh | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; gurmandsingh@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94549 | STRIVE.R2.MC1.2384.1.684.179.238.16 | [5 empty] | R2P_I_071-SAP EHS- TDS Interface to ProductDatabse -Digital | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94550 | STRIVE.R2.MC1.2384.1.684.179.238.16.32 | N | N | N | Planned | Updated | Validate PDB configuration | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Naga | priyasinghal@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; nnagasubbareddy@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94551 | STRIVE.R2.MC1.2384.1.684.179.238.16.33 | N | N | N | Planned | Delete | Check iflows dependencies-R2P_I_071 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94550 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94552 | STRIVE.R2.MC1.2384.1.684.179.238.16.34 | N | N | N | Planned | Delete | Validate the import of Iflow's-R2P_I_071 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94551 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94553 | STRIVE.R2.MC1.2384.1.684.179.238.16.35 | N | N | N | Planned | Delete | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_071 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94552 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94554 | STRIVE.R2.MC1.2384.1.684.179.238.17 | [5 empty] | R2P_I_072-SAP EHS- Interface to EasyTra (Plug In and not an Integration) | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94555 | STRIVE.R2.MC1.2384.1.684.179.238.17.37 | N | N | N | Planned |  | Validate EasyTra config | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Naga | priyasinghal@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; nnagasubbareddy@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94556 | STRIVE.R2.MC1.2384.1.684.179.367 | [5 empty] | S/4HANA-KRUSE | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94557 | STRIVE.R2.MC1.2384.1.684.179.367.19 |  |  |  |  | Updated | R2P_I_056-KRUSE high storage warehouse - Inbound - STOs | 5 hrs | 2025-10-24 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94558 | STRIVE.R2.MC1.2384.1.684.179.367.19.40 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_056 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94559 | STRIVE.R2.MC1.2384.1.684.179.367.19.41 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_056 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94558 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94560 | STRIVE.R2.MC1.2384.1.684.179.367.19.42 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_056 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94559 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94537 | STRIVE.R2.MC1.2384.1.684.179.367.19.19 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_056 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94560 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94538 | STRIVE.R2.MC1.2384.1.684.179.367.19.20 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_056 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94537 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94539 | STRIVE.R2.MC1.2384.1.684.179.367.1 |  |  |  |  | Updated | R2P_I_057-KRUSE high storage warehouse - Inbound - Deliveries | 5 hrs | 2025-10-24 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94540 | STRIVE.R2.MC1.2384.1.684.179.367.1.22 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_057 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94541 | STRIVE.R2.MC1.2384.1.684.179.367.1.23 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_057 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94540 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94542 | STRIVE.R2.MC1.2384.1.684.179.367.1.24 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_057 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94541 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94543 | STRIVE.R2.MC1.2384.1.684.179.367.1.25 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_057 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94542 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94544 | STRIVE.R2.MC1.2384.1.684.179.367.1.26 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_057 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94543 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94533 | STRIVE.R2.MC1.2384.1.684.179.367.20 |  |  |  |  | Updated | R2P_I_059-KRUSE high storage warehouse - Inbound - Repack | 5 hrs | 2025-10-24 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94534 | STRIVE.R2.MC1.2384.1.684.179.367.20.16 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_059 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94535 | STRIVE.R2.MC1.2384.1.684.179.367.20.17 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_059 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94534 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94536 | STRIVE.R2.MC1.2384.1.684.179.367.20.18 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_059 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94535 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94531 | STRIVE.R2.MC1.2384.1.684.179.367.20.13 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_059 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94536 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94532 | STRIVE.R2.MC1.2384.1.684.179.367.20.14 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_059 | 1 hrs | 2025-10-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94531 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94575 | STRIVE.R2.MC1.2384.1.684.179.367.21 |  |  |  |  | Delete | R2P_I_075-FICO - Fair Issac services for planning and scheduling | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94576 | STRIVE.R2.MC1.2384.1.684.179.367.21.33 | N | N | N | Planned | Delete | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_075 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94591 | STRIVE.R2.MC1.2384.1.684.179.367.21.48 | N | N | N | Planned | Delete | Check iflows dependencies-R2P_I_075 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94576 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94592 | STRIVE.R2.MC1.2384.1.684.179.367.21.49 | N | N | N | Planned | Delete | Validate the import of Iflow's-R2P_I_075 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94591 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94593 | STRIVE.R2.MC1.2384.1.684.179.367.21.50 | N | N | N | Planned | Delete | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_075 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94592 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94594 | STRIVE.R2.MC1.2384.1.684.179.367.22 | [5 empty] | R2P_I_XXX-Kruse Spares handling in BBT warehouse through HU's | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94595 | STRIVE.R2.MC1.2384.1.684.179.367.22.52 | N | N | N | Planned |  | Notify the integration team to move objects to the next higher environment-R2P_I_XXX | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94596 | STRIVE.R2.MC1.2384.1.684.179.367.22.53 | N | N | N | Planned |  | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_XXX | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94595 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94597 | STRIVE.R2.MC1.2384.1.684.179.367.22.54 | N | N | N | Planned |  | Check iflows dependencies-R2P_I_XXX | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94596 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94598 | STRIVE.R2.MC1.2384.1.684.179.367.22.55 | N | N | N | Planned |  | Validate the import of Iflow's-R2P_I_XXX | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94597 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94599 | STRIVE.R2.MC1.2384.1.684.179.367.22.56 | N | N | N | Planned |  | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_XXX | 1 hrs | 2025-09-15 12:01 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94598 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94600 | STRIVE.R2.MC1.2384.1.684.179.367.23 | [5 empty] | R2P_I_077-Relabeling, Repackaging, Refilling Outbound Process Order Interface from S4 to Kruse | 5 hrs | 2025-09-15 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94601 | STRIVE.R2.MC1.2384.1.684.179.367.23.58 | N | N | N | Planned |  | Notify the integration team to move objects to the next higher environment-R2P_I_077 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94602 | STRIVE.R2.MC1.2384.1.684.179.367.23.59 | N | N | N | Planned |  | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_077 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94601 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94603 | STRIVE.R2.MC1.2384.1.684.179.367.23.60 | N | N | N | Planned |  | Check iflows dependencies-R2P_I_077 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94602 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94604 | STRIVE.R2.MC1.2384.1.684.179.367.23.61 | N | N | N | Planned |  | Validate the import of Iflow's-R2P_I_077 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94603 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94605 | STRIVE.R2.MC1.2384.1.684.179.367.23.62 | N | N | N | Planned |  | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_077 | 1 hrs | 2025-09-15 12:01 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94604 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94606 | STRIVE.R2.MC1.2384.1.684.179.367.24 | [5 empty] | R2P_I_078-GR, GI, Confirm Process Order Inbound Interface from Kruse | 5 hrs | 2025-09-15 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94607 | STRIVE.R2.MC1.2384.1.684.179.367.24.64 | N | N | N | Planned |  | Notify the integration team to move objects to the next higher environment-R2P_I_078 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94608 | STRIVE.R2.MC1.2384.1.684.179.367.24.65 | N | N | N | Planned |  | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_078 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94607 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94609 | STRIVE.R2.MC1.2384.1.684.179.367.24.66 | N | N | N | Planned |  | Check iflows dependencies-R2P_I_078 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94608 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94610 | STRIVE.R2.MC1.2384.1.684.179.367.24.67 | N | N | N | Planned |  | Validate the import of Iflow's-R2P_I_078 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94609 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94611 | STRIVE.R2.MC1.2384.1.684.179.367.24.68 | N | N | N | Planned |  | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_078 | 1 hrs | 2025-09-15 12:01 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94610 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94612 | STRIVE.R2.MC1.2384.1.684.179.367.25 | [5 empty] | R2P_I_076-Kruse Material Master data interface from S4 to KRUSE | 5 hrs | 2025-09-15 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94613 | STRIVE.R2.MC1.2384.1.684.179.367.25.70 | N | N | N | Planned |  | Notify the integration team to move objects to the next higher environment-R2P_I_076 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94614 | STRIVE.R2.MC1.2384.1.684.179.367.25.71 | N | N | N | Planned |  | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_076 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94613 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94615 | STRIVE.R2.MC1.2384.1.684.179.367.25.72 | N | N | N | Planned |  | Check iflows dependencies-R2P_I_076 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94614 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94616 | STRIVE.R2.MC1.2384.1.684.179.367.25.73 | N | N | N | Planned |  | Validate the import of Iflow's-R2P_I_076 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94615 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94617 | STRIVE.R2.MC1.2384.1.684.179.367.25.74 | N | N | N | Planned |  | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_076 | 1 hrs | 2025-09-15 12:01 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94616 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94864 | STRIVE.R2.MC1.2384.1.684.179.371 | [5 empty] | S/4HANA-LIMS | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94865 | STRIVE.R2.MC1.2384.1.684.179.371.30 |  |  |  |  | Updated | R2P_I_062-LIMS 1 : Samplemanager (Brunsbüttel) - Outbound inventory update | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94879 | STRIVE.R2.MC1.2384.1.684.179.371.30.335 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_062 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | Oguz | okorkmazlar@deloitte.it | Sheena Gour; Deepika Agarwal; Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | shgour@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94880 | STRIVE.R2.MC1.2384.1.684.179.371.30.336 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_062 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94879 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94881 | STRIVE.R2.MC1.2384.1.684.179.371.30.337 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_062 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94880 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94882 | STRIVE.R2.MC1.2384.1.684.179.371.30.338 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_062 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94881 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94883 | STRIVE.R2.MC1.2384.1.684.179.371.30.339 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_062 | 1 hrs | 2025-09-26 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94882 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94884 | STRIVE.R2.MC1.2384.1.684.179.371.1 |  |  |  |  | Updated | R2P_I_063-LIMS 1 : Samplemanager (Brunsbüttel) - Inbound process order details | 5 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94885 | STRIVE.R2.MC1.2384.1.684.179.371.1.341 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_063 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Oguz | okorkmazlar@deloitte.it | Sheena Gour; Deepika Agarwal; Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | shgour@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94886 | STRIVE.R2.MC1.2384.1.684.179.371.1.342 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_063 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94885 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94887 | STRIVE.R2.MC1.2384.1.684.179.371.1.343 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_063 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94886 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94888 | STRIVE.R2.MC1.2384.1.684.179.371.1.344 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_063 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94887 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94889 | STRIVE.R2.MC1.2384.1.684.179.371.1.345 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_063 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94888 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94890 | STRIVE.R2.MC1.2384.1.684.179.371.31 |  |  |  |  | Delete | R2P_I_064-LIMS OMA Digital (off-spec-management) IS a Brunsbuttel Alumina Tool- Only S4 Hana data sets - Using IS and CPI | 5 hrs | 2025-09-15 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94891 | STRIVE.R2.MC1.2384.1.684.179.371.31.347 | N | N | N | Planned | Delete | Notify the integration team to move objects to the next higher environment-R2P_I_064 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94892 | STRIVE.R2.MC1.2384.1.684.179.371.31.348 | N | N | N | Planned | Delete | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_064 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration | 94891 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94893 | STRIVE.R2.MC1.2384.1.684.179.371.31.349 | N | N | N | Planned | Delete | Check iflows dependencies-R2P_I_064 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration | 94892 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94894 | STRIVE.R2.MC1.2384.1.684.179.371.31.350 | N | N | N | Planned | Delete | Validate the import of Iflow's-R2P_I_064 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration | 94893 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94895 | STRIVE.R2.MC1.2384.1.684.179.371.31.351 | N | N | N | Planned | Delete | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_064 | 1 hrs | 2025-09-15 12:01 | 2025-09-15 13:01 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration | 94894 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94896 | STRIVE.R2.MC1.2384.1.684.179.372 | [5 empty] | S/4HANA-MES LISA | 14 hrs | 2025-09-15 08:00 | 2025-09-15 22:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94897 | STRIVE.R2.MC1.2384.1.684.179.372.32 |  |  |  |  | Updated | R2P_I_066-MES LISA Brunsbuttel, outbound process order info to LISA | 5 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94898 | STRIVE.R2.MC1.2384.1.684.179.372.32.354 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_066 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94899 | STRIVE.R2.MC1.2384.1.684.179.372.32.355 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_066 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94898 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94900 | STRIVE.R2.MC1.2384.1.684.179.372.32.356 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_066 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94899 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94901 | STRIVE.R2.MC1.2384.1.684.179.372.32.357 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_066 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94900 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94902 | STRIVE.R2.MC1.2384.1.684.179.372.32.358 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_066 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94901 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94903 | STRIVE.R2.MC1.2384.1.684.179.372.1 |  |  |  |  | Updated | R2P_I_067-MES LISA Brunsbuttel,Goods receipt, inbound to S4 | 5 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94904 | STRIVE.R2.MC1.2384.1.684.179.372.1.360 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_067 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94905 | STRIVE.R2.MC1.2384.1.684.179.372.1.361 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_067 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94904 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94906 | STRIVE.R2.MC1.2384.1.684.179.372.1.362 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_067 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94905 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94907 | STRIVE.R2.MC1.2384.1.684.179.372.1.363 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_067 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94906 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94866 | STRIVE.R2.MC1.2384.1.684.179.372.1.322 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_067 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94907 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94867 | STRIVE.R2.MC1.2384.1.684.179.372.33 |  |  |  |  | Updated | R2P_I_068-MES LISA Brunsbuttel,Goods issue, inbound to S4 | 5 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94868 | STRIVE.R2.MC1.2384.1.684.179.372.33.324 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_068 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94869 | STRIVE.R2.MC1.2384.1.684.179.372.33.325 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_068 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94868 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94870 | STRIVE.R2.MC1.2384.1.684.179.372.33.326 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_068 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94869 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94871 | STRIVE.R2.MC1.2384.1.684.179.372.33.327 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_068 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94870 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94872 | STRIVE.R2.MC1.2384.1.684.179.372.33.328 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_068 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94871 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
[6 empty] | Updated | R2P_I_069-MES Lisa Brunsbuttel, Tank levels -> SAP IP21 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Notify the integration team to move objects to the next higher environment-R2P_I_069 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Aniket | anikulkarni@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_069 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94868 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
[6 empty] | Add | Check iflows dependencies-R2P_I_069 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94869 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
[6 empty] | Add | Validate the import of Iflow's-R2P_I_069 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94870 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
[6 empty] | Add | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_069 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94871 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94875 | STRIVE.R2.MC1.2384.1.684.179.372.35 |  |  |  |  | Updated | R2P_I_070-MES Lisa Brunsbuttel, Tank levels -> SAP SAAB | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Notify the integration team to move objects to the next higher environment-R2P_I_070 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 09:00 | Aniket | anikulkarni@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
[6 empty] | Add | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_070 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94868 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
[6 empty] | Add | Check iflows dependencies-R2P_I_070 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94869 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
[6 empty] | Add | Validate the import of Iflow's-R2P_I_070 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94870 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
[6 empty] | Add | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_070 | 1 hrs | 2025-09-24 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94871 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94877 | STRIVE.R2.MC1.2384.1.684.179.372.36 |  |  |  |  | Updated | R2P_I_074-PP/EHS- O/B interface to send Material master & EHS data from S/4 to LISA | 5 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94878 | STRIVE.R2.MC1.2384.1.684.179.372.36.334 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2P_I_074 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Nilesh Deshpande | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94856 | STRIVE.R2.MC1.2384.1.684.179.372.36.312 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-R2P_I_074 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94878 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94857 | STRIVE.R2.MC1.2384.1.684.179.372.36.313 | N | N | N | Planned | Updated | Check iflows dependencies-R2P_I_074 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94856 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94858 | STRIVE.R2.MC1.2384.1.684.179.372.36.314 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2P_I_074 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94857 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94859 | STRIVE.R2.MC1.2384.1.684.179.372.36.315 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2P_I_074 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 13:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94858 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
94718 | STRIVE.R2.MC1.2384.1.684.179.372.26 | [5 empty] | P2C_I_300-KRUSE high storage warehouse - Outbound - Deliveries | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94719 | STRIVE.R2.MC1.2384.1.684.179.372.26.175 | N | N | N | Planned |  | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_300 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94720 | STRIVE.R2.MC1.2384.1.684.179.372.26.176 | N | N | N | Planned |  | Check iflows dependencies-P2C_I_300 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94719 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94721 | STRIVE.R2.MC1.2384.1.684.179.372.26.177 | N | N | N | Planned |  | Validate the import of Iflow's-P2C_I_300 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94720 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94722 | STRIVE.R2.MC1.2384.1.684.179.372.26.178 | N | N | N | Planned |  | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_300 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94721 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94723 | STRIVE.R2.MC1.2384.1.684.179.372.27 |  |  |  |  | Delete | P2C_I_301-KRUSE high storage warehouse - Outbound - STOs | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94724 | STRIVE.R2.MC1.2384.1.684.179.372.27.180 | N | N | N | Planned | Delete | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_301 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94725 | STRIVE.R2.MC1.2384.1.684.179.372.27.181 | N | N | N | Planned | Delete | Check iflows dependencies-P2C_I_301 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94724 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94726 | STRIVE.R2.MC1.2384.1.684.179.372.27.182 | N | N | N | Planned | Delete | Validate the import of Iflow's-P2C_I_301 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94725 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94727 | STRIVE.R2.MC1.2384.1.684.179.372.27.183 | N | N | N | Planned | Delete | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_301 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Naga | nnagasubbareddy@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94726 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94728 | STRIVE.R2.MC1.2384.1.684.179.368 | [5 empty] | S/4HANA-EVONIK | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94729 | STRIVE.R2.MC1.2384.1.684.179.368.28 |  |  |  |  | Updated | P2C_I_400- TM: Evonik interface (Inbound) | 4 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94730 | STRIVE.R2.MC1.2384.1.684.179.368.28.186 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_400 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94731 | STRIVE.R2.MC1.2384.1.684.179.368.28.187 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_400 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94730 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94732 | STRIVE.R2.MC1.2384.1.684.179.368.28.188 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_400 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 11:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94731 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94733 | STRIVE.R2.MC1.2384.1.684.179.368.28.189 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_400 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94732 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94734 | STRIVE.R2.MC1.2384.1.684.179.368.1 |  |  |  |  | Updated | P2C_I_401-TM: Evonik Interface (Outbound) | 4 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94735 | STRIVE.R2.MC1.2384.1.684.179.368.1.191 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_401 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94736 | STRIVE.R2.MC1.2384.1.684.179.368.1.192 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_401 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration | 94735 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94737 | STRIVE.R2.MC1.2384.1.684.179.368.1.193 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_401 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 11:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration | 94736 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94738 | STRIVE.R2.MC1.2384.1.684.179.368.1.194 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_401 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | Aman Anand | amananand2@deloitte.com | Naga; Yaswanth; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Saurabh Kumar | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; saurabhkumar397@deloitte.com | Integration | 94737 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94739 | STRIVE.R2.MC1.2384.1.684.179.369 |  |  |  |  | Updated | S/4HANA-UKL | 1 hrs | 2025-10-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94740 | STRIVE.R2.MC1.2384.1.684.179.369.29 |  |  |  |  | Updated | P2C_I_415-TM: UKL Rail Interface (Inbound) | 4 hrs | 2025-10-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94741 | STRIVE.R2.MC1.2384.1.684.179.369.29.197 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_415 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 09:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94742 | STRIVE.R2.MC1.2384.1.684.179.369.29.198 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_415 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 10:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94741 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94743 | STRIVE.R2.MC1.2384.1.684.179.369.29.199 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_415 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 11:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94742 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94744 | STRIVE.R2.MC1.2384.1.684.179.369.29.200 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_415 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 12:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94743 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94745 | STRIVE.R2.MC1.2384.1.684.179.369.1 |  |  |  |  | Updated | P2C_I_416-TM: UKL Rail Interface (Outbound) | 4 hrs | 2025-10-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94746 | STRIVE.R2.MC1.2384.1.684.179.369.1.202 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_416 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 09:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94747 | STRIVE.R2.MC1.2384.1.684.179.369.1.203 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_416 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 10:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94746 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94748 | STRIVE.R2.MC1.2384.1.684.179.369.1.204 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_416 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 11:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94747 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94749 | STRIVE.R2.MC1.2384.1.684.179.369.1.205 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_416 | 1 hrs | 2025-10-15 08:00 | 2025-09-15 12:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Integration | 94748 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94750 | STRIVE.R2.MC1.2384.1.684.179.370 | [5 empty] | S/4HANA-TM | 270.25 hrs | 2025-09-15 08:00 | 2025-09-26 15:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-26 15:00
94751 | STRIVE.R2.MC1.2384.1.684.179.370.30 |  |  |  |  | Delete | P2C_I_405-TM: Yard Management at Brunsbüttel (Inbound) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94752 | STRIVE.R2.MC1.2384.1.684.179.370.30.208 | N | N | N | Planned | Delete | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_405 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94753 | STRIVE.R2.MC1.2384.1.684.179.370.30.209 | N | N | N | Planned | Delete | Check iflows dependencies-P2C_I_405 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94752 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94754 | STRIVE.R2.MC1.2384.1.684.179.370.30.210 | N | N | N | Planned | Delete | Validate the import of Iflow's-P2C_I_405 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94753 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94755 | STRIVE.R2.MC1.2384.1.684.179.370.30.211 | N | N | N | Planned | Delete | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_405 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94754 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94756 | STRIVE.R2.MC1.2384.1.684.179.370.1 | [5 empty] | P2C_I_406- TM: Yard Management at Brunsbüttel (Outbound) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94757 | STRIVE.R2.MC1.2384.1.684.179.370.1.213 | N | N | N | Planned |  | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_406 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94758 | STRIVE.R2.MC1.2384.1.684.179.370.1.214 | N | N | N | Planned |  | Check iflows dependencies-P2C_I_406 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94757 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94759 | STRIVE.R2.MC1.2384.1.684.179.370.1.215 | N | N | N | Planned |  | Validate the import of Iflow's-P2C_I_406 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94758 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94760 | STRIVE.R2.MC1.2384.1.684.179.370.1.216 | N | N | N | Planned |  | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_406 | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94759 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94761 | STRIVE.R2.MC1.2384.1.684.179.370.31 |  |  |  |  | Updated | P2C_I_200-SD: Brenntag-Sales order interface - inbound​ | 4 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94762 | STRIVE.R2.MC1.2384.1.684.179.370.31.218 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_200 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94763 | STRIVE.R2.MC1.2384.1.684.179.370.31.219 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_200 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94762 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94764 | STRIVE.R2.MC1.2384.1.684.179.370.31.220 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_200 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94763 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94765 | STRIVE.R2.MC1.2384.1.684.179.370.31.221 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_200 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94764 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94766 | STRIVE.R2.MC1.2384.1.684.179.370.32 |  |  |  |  | Updated | P2C_I_201-Tungsten interface - Invoicing for Germany | 4 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94767 | STRIVE.R2.MC1.2384.1.684.179.370.32.223 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_201 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94768 | STRIVE.R2.MC1.2384.1.684.179.370.32.224 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_201 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94767 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94769 | STRIVE.R2.MC1.2384.1.684.179.370.32.225 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_201 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94768 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94770 | STRIVE.R2.MC1.2384.1.684.179.370.32.226 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_201 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94769 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94771 | STRIVE.R2.MC1.2384.1.684.179.370.33 |  |  |  |  | Updated | P2C_I_204: Pricing Hub (Digital Tool) - Inbound to SAP (CPI) | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 |  |  |  | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com |  |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94772 | STRIVE.R2.MC1.2384.1.684.179.370.33.228 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_204 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94773 | STRIVE.R2.MC1.2384.1.684.179.370.33.229 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_204 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94772 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94774 | STRIVE.R2.MC1.2384.1.684.179.370.33.230 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_204 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94773 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94775 | STRIVE.R2.MC1.2384.1.684.179.370.33.231 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_204 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94774 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94776 | STRIVE.R2.MC1.2384.1.684.179.370.34 |  |  |  |  | Updated | P2C_I_419-TM: Dock Appt Scheduling Updates | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94777 | STRIVE.R2.MC1.2384.1.684.179.370.34.233 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_419 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94778 | STRIVE.R2.MC1.2384.1.684.179.370.34.234 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_419 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94777 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94779 | STRIVE.R2.MC1.2384.1.684.179.370.34.235 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_419 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94778 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94780 | STRIVE.R2.MC1.2384.1.684.179.370.34.236 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_419 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94779 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94781 | STRIVE.R2.MC1.2384.1.684.179.370.35 |  |  |  |  | Updated | P2C_I_422-TM: Ext. Storage : ALBLAS (Outbound) | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94782 | STRIVE.R2.MC1.2384.1.684.179.370.35.238 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_422 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94783 | STRIVE.R2.MC1.2384.1.684.179.370.35.239 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_422 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94782 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94784 | STRIVE.R2.MC1.2384.1.684.179.370.35.240 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_422 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94783 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94785 | STRIVE.R2.MC1.2384.1.684.179.370.35.241 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_422 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94784 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94786 | STRIVE.R2.MC1.2384.1.684.179.370.36 |  |  |  |  | Updated | P2C_I_423-TM: Ext. Storage : VOPAK (Outbound) | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 |  |  |  | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com |  |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94787 | STRIVE.R2.MC1.2384.1.684.179.370.36.243 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_423 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94788 | STRIVE.R2.MC1.2384.1.684.179.370.36.244 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_423 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94787 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94789 | STRIVE.R2.MC1.2384.1.684.179.370.36.245 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_423 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94788 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94790 | STRIVE.R2.MC1.2384.1.684.179.370.36.246 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_423 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94789 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94791 | STRIVE.R2.MC1.2384.1.684.179.370.37 |  |  |  |  | Updated | P2C_I_424-TM: Ext. Storage : PALOG (Outbound) | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94792 | STRIVE.R2.MC1.2384.1.684.179.370.37.248 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_424 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94793 | STRIVE.R2.MC1.2384.1.684.179.370.37.249 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_424 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94792 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94794 | STRIVE.R2.MC1.2384.1.684.179.370.37.250 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_424 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94793 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94795 | STRIVE.R2.MC1.2384.1.684.179.370.37.251 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_424 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94794 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94796 | STRIVE.R2.MC1.2384.1.684.179.370.38 |  |  |  |  | Updated | P2C_I_425-TM: Ext. Storage : TANQUID (Outbound) | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94797 | STRIVE.R2.MC1.2384.1.684.179.370.38.253 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_425 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94798 | STRIVE.R2.MC1.2384.1.684.179.370.38.254 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_425 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94797 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94799 | STRIVE.R2.MC1.2384.1.684.179.370.38.255 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_425 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94798 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94800 | STRIVE.R2.MC1.2384.1.684.179.370.38.256 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_425 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94799 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94801 | STRIVE.R2.MC1.2384.1.684.179.370.39 |  |  |  |  | Updated | P2C_I_426-FICO - TM: Ext. Storage : DP WORLD (Outbound) | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94802 | STRIVE.R2.MC1.2384.1.684.179.370.39.258 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_426 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94803 | STRIVE.R2.MC1.2384.1.684.179.370.39.259 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_426 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94802 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94804 | STRIVE.R2.MC1.2384.1.684.179.370.39.260 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_426 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94803 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94805 | STRIVE.R2.MC1.2384.1.684.179.370.39.261 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_426 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94804 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94806 | STRIVE.R2.MC1.2384.1.684.179.370.40 |  |  |  |  | Updated | P2C_I_427-TM: Ext. Storage : VOPAK (Inbound) | 4 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
94807 | STRIVE.R2.MC1.2384.1.684.179.370.40.263 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_427 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94808 | STRIVE.R2.MC1.2384.1.684.179.370.40.264 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_427 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94807 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94809 | STRIVE.R2.MC1.2384.1.684.179.370.40.265 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_427 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94808 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94810 | STRIVE.R2.MC1.2384.1.684.179.370.40.266 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_427 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94809 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94811 | STRIVE.R2.MC1.2384.1.684.179.370.41 |  |  |  |  | Updated | P2C_I_428-TM: Ext. Storage : PALOG (Inbound) | 6.98 hrs | 2025-10-10 08:00 | 2025-09-15 15:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 15:00
94812 | STRIVE.R2.MC1.2384.1.684.179.370.41.268 | N | N | N | Planned | Updated | Create Transport request from CPI DEV to CPI QA/Production package-P2C_I_428 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 09:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94813 | STRIVE.R2.MC1.2384.1.684.179.370.41.269 | N | N | N | Planned | Updated | Check iflows dependencies-P2C_I_428 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94812 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94814 | STRIVE.R2.MC1.2384.1.684.179.370.41.270 | N | N | N | Planned | Updated | Validate the import of Iflow's-P2C_I_428 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94813 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94815 | STRIVE.R2.MC1.2384.1.684.179.370.41.271 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-P2C_I_428 | 1 hrs | 2025-10-10 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Saurabh Kumar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | saurabhkumar397@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com;amananand2@deloitte.com | Integration | 94814 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
19300 | STRIVE.R2.MC1.2384.1.684.179.370.41.304 | [5 empty] | S/4HANA-OMP (Placeholder for Wave 1 Interfaces) | 6.98 hrs | 2025-09-15 08:00 | 2025-09-15 15:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 15:00
19301 | STRIVE.R2.MC1.2384.1.684.179.370.41.304.75 | [5 empty] | IBP-I-002_S/4 to OMP integration | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
19302 | STRIVE.R2.MC1.2384.1.684.179.370.41.304.75.2 | N | N | N | Planned |  | Validate configurations - IBP-I-002_S/4 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Sats; Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Sats.Subramoney@sasol.com; nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19303 | STRIVE.R2.MC1.2384.1.684.179.370.41.304.76 | [5 empty] | IBP-I-003_OMP to S/4 interface | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
19304 | STRIVE.R2.MC1.2384.1.684.179.370.41.304.76.72 | N | N | N | Planned |  | Validate configurations - IBP-I-003 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Sats; Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Sats.Subramoney@sasol.com; nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94683 | STRIVE.R2.MC1.2384.1.684.179.373 | [5 empty] | S4-Concur | 14 hrs | 2025-09-15 08:00 | 2025-09-15 22:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94684 | STRIVE.R2.MC1.2384.1.684.179.373.42 |  |  |  |  | Updated | R2D_I_004-FS Interface for Cost center transfer & WBS elements from S4 to Concur | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94685 | STRIVE.R2.MC1.2384.1.684.179.373.42.141 | N | N | N | Planned | Updated | Validate the connection from S4 towards concur | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94686 | STRIVE.R2.MC1.2384.1.684.179.373.1 |  |  |  |  | Updated | R2D_I_017-FS Interface for travel expense reports from Concur to S4 | 2 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
94687 | STRIVE.R2.MC1.2384.1.684.179.373.1.143 | N | N | N | Planned | Updated | Validate if the ABAP TR is moved | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Yashaswi | yarahut@deloitte.com | Gurmandeep Singh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Naga; Saurabh Kumar | gurmandsingh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com | ABAP |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94688 | STRIVE.R2.MC1.2384.1.684.179.373.1.144 | N | N | N | Planned | Updated | Validate the connection from S4 towards concur | 1 hrs | 2025-10-03 08:00 | 2025-09-15 10:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Basis | 94687 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94689 | STRIVE.R2.MC1.2384.1.684.179.374 |  |  |  |  | Updated | S4-Successfactors | 14 hrs | 2025-09-26 08:00 | 2025-09-15 22:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94690 | STRIVE.R2.MC1.2384.1.684.179.374.43 |  |  |  |  | Updated | R2D_I_026-SInterface for Cost center transfer from S4 to Employee central (EC)-Successfactors | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94691 | STRIVE.R2.MC1.2384.1.684.179.374.43.147 | N | N | N | Planned | Updated | Create an Business Data Object in SAP MDI | 1 hrs | 2025-09-26 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94692 | STRIVE.R2.MC1.2384.1.684.179.374.1 |  |  |  |  | Updated | R2D_I_002-FS Interface for Cost center transfer from S4 to Employee central payroll (ECP) (German Payroll) | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94693 | STRIVE.R2.MC1.2384.1.684.179.374.1.149 | N | N | N | Planned | Updated | Validate the connection setup from S4 towards ECP | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Basis |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94694 | STRIVE.R2.MC1.2384.1.684.179.374.44 |  |  |  |  | Updated | R2D_I_028-FS Interface for payroll data to S4 (German Payroll) (ECP) | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94695 | STRIVE.R2.MC1.2384.1.684.179.374.44.151 | N | N | N | Planned | Updated | Validate the connection from ECP to S4 | 1 hrs | 2025-10-03 08:00 | 2025-09-15 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Basis |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94696 | STRIVE.R2.MC1.2384.1.684.179.375 | [5 empty] | S4-Elster | 14 hrs | 2025-10-06 08:00 | 2025-09-15 22:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94697 | STRIVE.R2.MC1.2384.1.684.179.375.45 |  |  |  |  | Updated | R2D_I_019-FS Interface for reporting to tax authorities (i.e. ELSTER) - sales and purchase tax | 5 hrs | 2025-10-06 08:00 | 2025-09-15 13:01 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 13:01
94698 | STRIVE.R2.MC1.2384.1.684.179.375.45.154 | N | N | N | Planned | Updated | Notify the integration team to move objects to the next higher environment-R2D_I_019 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 09:00 | Aquib Iqbal | aquiqbal@deloitte.com | Roshan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94699 | STRIVE.R2.MC1.2384.1.684.179.375.45.155 | N | N | N | Planned | Updated | Copy CPI Standard package from Discovery | 1 hrs | 2025-10-06 08:00 | 2025-09-15 10:00 | Yaswanth | myakumar@deloitte.com | Naga; Saurabh Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration | 94698 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94700 | STRIVE.R2.MC1.2384.1.684.179.375.45.156 | N | N | N | Planned | Updated | Check iflows dependencies-R2D_I_019 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 11:00 | Yaswanth | myakumar@deloitte.com | Naga; Saurabh Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration | 94699 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94701 | STRIVE.R2.MC1.2384.1.684.179.375.45.157 | N | N | N | Planned | Updated | Validate the import of Iflow's-R2D_I_019 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 12:00 | Yaswanth | myakumar@deloitte.com | Naga; Saurabh Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration | 94700 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
94702 | STRIVE.R2.MC1.2384.1.684.179.375.45.158 | N | N | N | Planned | Updated | Configure the End system URL's, UserNames and other externalized values including Control Records for each interface accordingly.-R2D_I_019 | 1 hrs | 2025-10-06 08:00 | 2025-09-15 13:01 | Yaswanth | myakumar@deloitte.com | Naga; Saurabh Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration | 94701 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 13:01
19375 | STRIVE.R2.MC1.2384.1.684.544 | [5 empty] | Weekend Job | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
19376 | STRIVE.R2.MC1.2384.1.684.544.1 | N | N | N | Planned |  | Meta Data Scan - Target&Source | 8 hrs | 2025-09-15 08:00 | 2025-09-15 16:01 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | DM |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 16:01
19377 | STRIVE.R2.MC1.2384.1.684.546 | [5 empty] | Batch Jobs - Setup&validations | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19378 | STRIVE.R2.MC1.2384.1.684.546.1 | N | N | N | Planned |  | Initial sync-up of Exchange rates from S/4 HANA to Coupa via program | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Prasanth | kalprasanth@deloitte.com | Pournami Nair; S2P Team; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | pounair@deloitte.com; usisasols2p@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | S2P |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
19379 | STRIVE.R2.MC1.2384.1.684.546.2 | N | N | N | Planned |  | Validate Batch Jobs for S2P | 4 hrs | 2025-09-20 12:01 | 2025-09-20 16:01 | Prasanth | kalprasanth@deloitte.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; S2P Team | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19378 |  |  | * | NA | 2025-09-20 12:01 | 2025-09-20 16:01
19380 | STRIVE.R2.MC1.2384.1.684.546.3 | N | N | N | Planned |  | MM period opening manually for Italy CC | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Manoj Dombar | mdombar@deloitte.com | Prasanth; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; S2P Team | kalprasanth@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
19381 | STRIVE.R2.MC1.2384.1.684.546.4 | N | N | N | Planned |  | Pre Cutover - Batch Jobs - Pre Setup - Identification/Frequency Validations (Brownout) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Prasanth | kalprasanth@deloitte.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; S2P Team | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
19382 | STRIVE.R2.MC1.2384.1.684.551 | [5 empty] | Production Cutover Plan Signoff (Not relevant for MC1) | 144.55 hrs | 2025-09-30 08:00 | 2025-10-06 08:57 | [8 empty] | * | NA | 2025-09-30 08:00 | 2025-10-06 08:57
19383 | STRIVE.R2.MC1.2384.1.684.551.1 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - MOR | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Jay Patel | jaypatel6@deloitte.com | Vinod Kumar; Amit Jha; Chaitnya; Abhishek Sharma; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | vinodkumar692@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19384 | STRIVE.R2.MC1.2384.1.684.551.2 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - R2P | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Amit das | amitdas3@deloitte.com | Claudiu; Abhishek Parab; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande | cljipa@deloitte.de; abhparab@deloitte.com; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19385 | STRIVE.R2.MC1.2384.1.684.551.3 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - P2C | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Malta | mawilhelm@deloitte.de | Tripti mehta; Ramesh SathishKumar; Siddhesh; Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | trimehta@deloitte.com; satramesh@deloitte.com; sibaraskar@deloitte.com; spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19386 | STRIVE.R2.MC1.2384.1.684.551.4 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - S2P | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Aparajita Mukherjee | apamukherjee@deloitte.com | Sandeep Galhotra; S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Milton | sagalhotra@deloitte.com; usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; miltjones@deloitte.com | S2P |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19387 | STRIVE.R2.MC1.2384.1.684.551.5 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - R2D | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Roshanlal Hemwani | rohemwani@deloitte.com | Tatiana; Alexandra Ruff; Sandeep (R2D); Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tvinogradova@deloitte.de; aruff@deloitte.de; ssandeep4@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19388 | STRIVE.R2.MC1.2384.1.684.551.6 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - IBP | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | IBP |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19389 | STRIVE.R2.MC1.2384.1.684.551.7 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - MDG | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Tulika Pal | tupal@deloitte.com | ; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | ; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MDG |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19390 | STRIVE.R2.MC1.2384.1.684.551.8 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - BASIS | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Jayasurya; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | jayasur@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | BASIS |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19391 | STRIVE.R2.MC1.2384.1.684.551.9 | N | N | N | Planned |  | Production Cutover Plan Review and Signoff - Integration | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yaswanth Kumar; ; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; ; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19392 | STRIVE.R2.MC1.2384.1.684.561 | [5 empty] | Business Cutover Plan Signoff (Not relevant for MC1) | 24.93 hrs | 2025-09-30 08:00 | 2025-10-01 09:00 | [8 empty] | * | NA | 2025-09-30 08:00 | 2025-10-01 09:00
19393 | STRIVE.R2.MC1.2384.1.684.561.1 | N | N | N | Planned |  | Business Cutover Plan Review and Signoff - MOR | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Elisa Latona | elisa.latona@it.sasol.com | Sven Gelking; Joseph Barber; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | sven.gelking@de.sasol.com; joseph.barber@us.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19394 | STRIVE.R2.MC1.2384.1.684.561.2 | N | N | N | Planned |  | Business Cutover Plan Review and Signoff - R2P | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Dr.Jürgen Heinrichs | Juergen.Heinrichs@de.sasol.com | Hans Jorg; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Amit das; Nilesh Deshpande; Torsten Freydt | hansjorg.becker@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19395 | STRIVE.R2.MC1.2384.1.684.561.3 | N | N | N | Planned |  | Business Cutover Plan Review and Signoff - P2C | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Rob Hall | rob.hall@sasol.com | Jessica Goffi; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | Jessica.Goffi@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19396 | STRIVE.R2.MC1.2384.1.684.561.4 | N | N | N | Planned |  | Business Cutover Plan Review and Signoff - S2P | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Evan Rademeyer | evan.rademeyer@us.sasol.com | Myriam; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | marialuisa.geremicca@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19397 | STRIVE.R2.MC1.2384.1.684.561.5 | N | N | N | Planned |  | Business Cutover Plan Review and Signoff - R2D | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | Francois Conradie | francois.conradie@de.sasol.com | Hendrik Kamsteeg; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roshanlal; Tatiana | hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19398 | STRIVE.R2.MC1.2384.1.684.561.6 | N | N | N | Planned |  | Business Cutover Plan Review and Signoff - IBP | 1 hrs | 2025-09-30 08:00 | 2025-09-30 09:00 | David Conradie | david.conradie1@sasol.com | Edurado; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | eduardo.gouveia@us.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | IBP |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 09:00
19399 | STRIVE.R2.MC1.2384.1.684.561.7 | [5 empty] | Transport Validation in S/4HANA + MDG (Date : TBD) | 48.87 hrs | 2025-08-30 08:00 | 2025-09-01 09:00 | [8 empty] | * | NA | 2025-08-30 08:00 | 2025-09-01 09:00
19400 | STRIVE.R2.MC1.2384.1.684.561.7.1 | N | N | N | Planned |  | Transport Validation - R2P in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Amit das | amitdas3@deloitte.com | Claudiu; Aniket Kulkarni; Pamela Mihali; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande | cljipa@deloitte.de; anikulkarni@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19401 | STRIVE.R2.MC1.2384.1.684.561.7.2 | N | N | N | Planned |  | Transport Validation - S2P in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Prasanth Kallakuri | kalprasanth@deloitte.com | Sandeep Galhotra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | sagalhotra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19402 | STRIVE.R2.MC1.2384.1.684.561.7.3 | N | N | N | Planned |  | Transport Validation - P2C in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Malta; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Siddhesh; Ramesh SathishKumar | dzarate@deloitte.com; mawilhelm@deloitte.de; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sibaraskar@deloitte.com; satramesh@deloitte.com | P2C |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19403 | STRIVE.R2.MC1.2384.1.684.561.7.4 | N | N | N | Planned |  | Transport Validation - R2D in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Roshanlal Hemwani | rohemwani@deloitte.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Daniel Lohmann; | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dlohmann@deloitte.de; | R2D |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19404 | STRIVE.R2.MC1.2384.1.684.561.7.5 | N | N | N | Planned |  | Transport Validation - MOR - PM in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
95111 | STRIVE.R2.MC1.2384.1.684.561.7.12 | N | N | N | Ready |  | Transport Validation - MOR - PS in S/4HANA Production + MDG Production | 14 hrs | 2025-08-30 08:00 | 2025-08-30 22:01 | Krishna Teja | krishn@deloitte.com | Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-08-30 08:00 | 2025-08-30 22:01
95110 | STRIVE.R2.MC1.2384.1.684.561.7.11 | N | N | N | Ready |  | Transport Validation - MOR - PPM in S/4HANA Production + MDG Production | 14 hrs | 2025-08-30 08:00 | 2025-08-30 22:01 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod Kumar; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-08-30 08:00 | 2025-08-30 22:01
19405 | STRIVE.R2.MC1.2384.1.684.561.7.6 | N | N | N | Planned |  | PRE TR IMPORT FGL_MIG_REGENERATE_CDS_BCF (With Checkbox: Reset to Delivery) | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Ashish patil | ashishspatil@deloitte.com | Shivraj; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Gurmandeep Singh; Satish rahangadale | shivrsinha@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; gurmandsingh@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19406 | STRIVE.R2.MC1.2384.1.684.561.7.7 | N | N | N | Planned |  | Transport Validation - ABAP in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 09:00 | 2025-09-20 10:00 | Gurmandeep Singh | gurmandsingh@deloitte.com | Ashish patil; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | ashishspatil@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP | 19405 |  |  |  | 2025-09-20 08:00 | 2025-09-20 09:00 | 2025-09-20 10:00
19407 | STRIVE.R2.MC1.2384.1.684.561.7.8 | N | N | N | Planned |  | Transport Validation - Data in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar | roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com | DM |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19408 | STRIVE.R2.MC1.2384.1.684.561.7.9 | N | N | N | Planned |  | Transport Validation - Security/GRC in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Shubhathakur@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19409 | STRIVE.R2.MC1.2384.1.684.561.7.10 | N | N | N | Planned |  | Validate MDG related Transport Requests in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
19410 | STRIVE.R2.MC1.2384.1.684.561.18 | [5 empty] | Transport Validation in S/4HANA + MDG (Date : TBD) | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
19411 | STRIVE.R2.MC1.2384.1.684.561.18.1 | N | N | N | Planned |  | Transport Validation - R2P in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Amit das | amitdas3@deloitte.com | Claudiu; Aniket Kulkarni; Pamela Mihali; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande | cljipa@deloitte.de; anikulkarni@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19412 | STRIVE.R2.MC1.2384.1.684.561.18.2 | N | N | N | Planned |  | Transport Validation - S2P in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Prasanth Kallakuri | kalprasanth@deloitte.com | Sandeep Galhotra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | sagalhotra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19413 | STRIVE.R2.MC1.2384.1.684.561.18.3 | N | N | N | Planned |  | Transport Validation - P2C in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Malta; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Siddhesh; Ramesh SathishKumar | dzarate@deloitte.com; mawilhelm@deloitte.de; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sibaraskar@deloitte.com; satramesh@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19414 | STRIVE.R2.MC1.2384.1.684.561.18.4 | N | N | N | Planned |  | Transport Validation - R2D in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Roshanlal Hemwani | rohemwani@deloitte.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Daniel Lohmann; | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dlohmann@deloitte.de; | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19415 | STRIVE.R2.MC1.2384.1.684.561.18.5 | N | N | N | Planned |  | Transport Validation - MOR - PM in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
95113 | STRIVE.R2.MC1.2384.1.684.561.18.12 | N | N | N | Planned |  | Transport Validation - MOR - PS in S/4HANA Production + MDG Production | 14 hrs | 2025-09-20 08:00 | 2025-09-20 22:01 | Krishna Teja | krishn@deloitte.com | Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 22:01
95112 | STRIVE.R2.MC1.2384.1.684.561.18.11 | N | N | N | Planned |  | Transport Validation - MOR - PPM in S/4HANA Production + MDG Production | 14 hrs | 2025-09-20 08:00 | 2025-09-20 22:01 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod Kumar; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 22:01
19416 | STRIVE.R2.MC1.2384.1.684.561.18.6 | N | N | N | Planned |  | PRE TR IMPORT FGL_MIG_REGENERATE_CDS_BCF (With Checkbox: Reset to Delivery) | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Ashish patil | ashishspatil@deloitte.com | Shivraj; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Gurmandeep Singh; Satish rahangadale | shivrsinha@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; gurmandsingh@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19417 | STRIVE.R2.MC1.2384.1.684.561.18.7 | N | N | N | Planned |  | Transport Validation - ABAP in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 09:00 | 2025-09-20 10:00 | Gurmandeep Singh | gurmandsingh@deloitte.com | Ashish patil; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale | ashishspatil@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com | ABAP | 19416 |  |  | * | NA | 2025-09-20 09:00 | 2025-09-20 10:00
19418 | STRIVE.R2.MC1.2384.1.684.561.18.8 | N | N | N | Planned |  | Transport Validation - Data in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar | roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com | DM |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19419 | STRIVE.R2.MC1.2384.1.684.561.18.9 | N | N | N | Planned |  | Transport Validation - Security/GRC in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Shubhathakur@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19420 | STRIVE.R2.MC1.2384.1.684.561.18.10 | N | N | N | Planned |  | Validate MDG related Transport Requests in S/4HANA Production + MDG Production | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19421 | STRIVE.R2.MC1.2384.1275 |  |  |  | Complete |  | Technical Go-Live | 1 hrs | 2025-07-14 08:00 | 2025-07-14 09:00 | [6 empty] | 2025-08-04 18:18 |  | * | NA | 2025-07-14 08:00 | 2025-07-14 09:00
19422 | STRIVE.R2.MC1.2384.1275.1 | Y | Y | Y | Complete |  | All technical cutover related activities completed | 1 hrs | 2025-08-04 18:18 | 2025-08-04 19:18 | Mousikta chanda | mouchanda@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER | dhkansal@deloitte.com; usistrivecutover@deloitte.com | Cutover |  | 2025-08-04 18:18 |  | * | NA | 2025-08-04 18:18 | 2025-08-04 19:18
19423 | STRIVE.R2.MC1.2384.1277 | [5 empty] | Cutover | 4358.12 hrs | 2025-08-11 08:00 | 2026-02-09 10:15 | [5 empty] | 19421 | 2025-07-14 08:00 |  | * | NA | 2025-08-11 08:00 | 2026-02-09 10:15
19424 | STRIVE.R2.MC1.2384.1277.1 | [5 empty] | Data | 3764.6 hrs | 2025-08-11 08:00 | 2026-01-15 15:05 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-08-11 08:00 | 2026-01-15 15:05
19425 | STRIVE.R2.MC1.2384.1277.1.1 | [5 empty] | Tier 1 Master Data Load's | 3209.64 hrs | 2025-08-11 08:00 | 2025-12-23 10:34 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-12-23 10:34
19426 | STRIVE.R2.MC1.2384.1277.1.1.1 |  |  |  | Complete |  | Cost center | 195.37 hrs | 2025-08-11 08:00 | 2025-08-19 11:54 | [6 empty] | 2025-08-11 06:21 |  | * | NA | 2025-08-11 08:00 | 2025-08-19 11:54
19427 | STRIVE.R2.MC1.2384.1277.1.1.1.1 | Y | Y | Y | Complete |  | Cost Center Post-Load Validation and Sign-off | 4 hrs | 2025-08-11 06:21 | 2025-08-11 12:00 | B. Matheja | Brigitte.Matheja@de.sasol.com | J. Bardenhagen; L. Theakston; Viera Chobotova; Eva Bani; Hendrik Kamsteeg; Gabriele; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Tatiana; Roman Mäkilä; Satyajit; Firat | Jana.Bardenhagen@de.sasol.com; Laraine.Theakston@eu.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; hendrik.kamsteeg@de.sasol.com; gabriele.schwemer@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; tvinogradova@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; firat.cetin@consultary.de | R2D | 19422 | 2025-08-11 06:21 |  | * | NA | 2025-08-11 06:21 | 2025-08-11 12:00
19428 | STRIVE.R2.MC1.2384.1277.1.1.1.2 | Y | Y | Y | Complete |  | Share Cost Center Details with coupa Team | 4 hrs | 2025-08-11 06:21 | 2025-08-11 12:00 | Sandeep (R2D) | ssandeep4@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Roshan; Firat; Tatiana | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; rohemwani@deloitte.com; firat.cetin@consultary.de; tvinogradova@deloitte.de | R2D | 19422 | 2025-08-11 06:21 | 2025-08-11 12:00 | * | NA | 2025-08-11 06:21 | 2025-08-11 12:00
19429 | STRIVE.R2.MC1.2384.1277.1.1.1.3 | Y | Y | Y | Complete |  | Cost Center- Pre-load Validation and Sign off - Coupa | 4 hrs | 2025-08-12 06:21 | 2025-08-12 12:00 | Tina Vidrine | tina.vidrine@us.sasol.com | Hendrik Kamsteeg; Gabriele; Prasanth; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Myriam; Frank Toedter ; Esmir Divljanovic; Firat | hendrik.kamsteeg@de.sasol.com; gabriele.schwemer@de.sasol.com; kalprasanth@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19428 | 2025-08-12 06:21 | 2025-08-12 12:00 | * | NA | 2025-08-12 06:21 | 2025-08-12 12:00
19430 | STRIVE.R2.MC1.2384.1277.1.1.1.4 | Y | Y | Y | Complete |  | Load cost center to Coupa - Coupa | 4 hrs | 2025-08-13 06:21 | 2025-08-13 12:00 | Supriya | supriychakraborty@deloitte.com | Pournami Nair; Pournami; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | pounair@deloitte.com; pounair@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19429 | 2025-08-13 06:21 | 2025-08-13 12:00 | * | NA | 2025-08-13 06:21 | 2025-08-13 12:00
19431 | STRIVE.R2.MC1.2384.1277.1.1.1.5 | Y | Y | Y | Complete |  | Cost Center-Post load Validation and sign off - Coupa | 136.05 hrs | 2025-08-13 12:01 | 2025-08-19 04:26 | Tina Vidrine | tina.vidrine@us.sasol.com | Hendrik Kamsteeg; Gabriele; Prasanth; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Adrian Naidoo; S2P Team; Myriam; Frank Toedter ; Esmir Divljanovic; Firat | hendrik.kamsteeg@de.sasol.com; gabriele.schwemer@de.sasol.com; kalprasanth@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; adnaidoo@deloitte.co.za; usisasols2p@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19430 | 2025-08-13 12:01 | 2025-08-19 04:26 |  | 2025-08-13 06:21 | 2025-08-13 12:01 | 2025-08-19 04:26
19432 | STRIVE.R2.MC1.2384.1277.1.1.7 |  |  |  | Complete |  | Profit center load | 51.9 hrs | 2025-08-11 08:00 | 2025-08-19 11:54 | [6 empty] | 2025-08-11 08:48 | 2025-08-12 20:16 | * | NA | 2025-08-11 08:00 | 2025-08-19 11:54
19433 | STRIVE.R2.MC1.2384.1277.1.1.7.1 | Y | Y | Y | Complete |  | Profit Center Post-Load Validation and Sign-off | 8 hrs | 2025-08-11 08:48 | 2025-08-12 08:48 | B. Matheja | Brigitte.Matheja@de.sasol.com | J. Bardenhagen; L. Theakston; Viera Chobotova; Eva Bani; Hendrik Kamsteeg; Gabriele; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Tatiana; Roman Mäkilä; Satyajit; Firat | Jana.Bardenhagen@de.sasol.com; Laraine.Theakston@eu.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; hendrik.kamsteeg@de.sasol.com; gabriele.schwemer@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; tvinogradova@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; firat.cetin@consultary.de | R2D | 19422 | 2025-08-11 08:48 | 2025-08-12 08:48 | * | NA | 2025-08-11 08:48 | 2025-08-12 08:48
19434 | STRIVE.R2.MC1.2384.1277.1.1.7.2 | Y | Y | Y | Complete |  | S4: Validate Profit Center replication from S/4 to MDG | 0 hrs | 2025-08-12 20:16 | 2025-08-12 20:16 | Aakanksha bapat | aatulbapat@deloitte.com | Tulika Pal; Firat; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda | tupal@deloitte.com; firat.cetin@consultary.de; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com | MDG | 19433 | 2025-08-12 20:16 | 2025-08-12 20:16 | * | NA | 2025-08-12 20:16 | 2025-08-12 20:16
19435 | STRIVE.R2.MC1.2384.1277.1.1.10 |  |  |  | Complete |  | Bank Master | 98.7 hrs | 2025-08-11 08:00 | 2025-08-15 10:58 | [6 empty] | 2025-08-11 13:55 | 2025-08-21 20:45 | * | NA | 2025-08-11 08:00 | 2025-08-15 10:58
19436 | STRIVE.R2.MC1.2384.1277.1.1.10.1 | Y | Y | Y | Complete |  | Bank Master Transformation and share Pre-Load | 1.66 hrs | 2025-08-11 13:55 | 2025-08-11 15:34 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Nils Schoch; Ulf Wendler; Firat; Tatiana; Roshan | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; nils.schoch@de.sasol.com; Ulf.Wendler@de.sasol.com; firat.cetin@consultary.de; tvinogradova@deloitte.de; rohemwani@deloitte.com | DM | 19422 | 2025-08-11 13:55 | 2025-08-11 15:34 | * | NA | 2025-08-11 13:55 | 2025-08-11 15:34
19437 | STRIVE.R2.MC1.2384.1277.1.1.10.2 | Y | Y | Y | Complete |  | Bank Master Pre-Load Validation and Sign-off | 4.27 hrs | 2025-08-11 20:03 | 2025-08-12 13:16 | Nils Schoch | nils.schoch@de.sasol.com | Ulf Wendler; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Dhruv Kansal; Hendrik Kamsteeg; Tatiana; Firat | Ulf.Wendler@de.sasol.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; dhkansal@deloitte.com; hendrik.kamsteeg@de.sasol.com; tvinogradova@deloitte.de; firat.cetin@consultary.de | R2D | 19436 | 2025-08-11 20:03 | 2025-08-12 13:16 | * | NA | 2025-08-11 20:03 | 2025-08-12 13:16
19438 | STRIVE.R2.MC1.2384.1277.1.1.10.3 | Y | Y | Y | Complete |  | Bank Master Load into S/4 and share Post-Load | 4 hrs | 2025-08-12 08:03 | 2025-08-12 13:03 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Nils Schoch; Ulf Wendler; Firat; Tatiana; Roshan | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; nils.schoch@de.sasol.com; Ulf.Wendler@de.sasol.com; firat.cetin@consultary.de; tvinogradova@deloitte.de; rohemwani@deloitte.com | DM | 19437 | 2025-08-12 08:03 | 2025-08-12 13:03 | * | NA | 2025-08-12 08:03 | 2025-08-12 13:03
19439 | STRIVE.R2.MC1.2384.1277.1.1.10.4 | Y | Y | Y | Complete |  | Bank Master Post-Load Validation and Sign-off | 28.46 hrs | 2025-08-20 14:39 | 2025-08-21 19:11 | Nils Schoch | nils.schoch@de.sasol.com | Ulf Wendler; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Dhruv Kansal; Hendrik Kamsteeg; Tatiana; Firat; Roshan | Ulf.Wendler@de.sasol.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; dhkansal@deloitte.com; hendrik.kamsteeg@de.sasol.com; tvinogradova@deloitte.de; firat.cetin@consultary.de; rohemwani@deloitte.com | R2D | 19438 | 2025-08-20 14:39 | 2025-08-21 19:11 | * | NA | 2025-08-20 14:39 | 2025-08-21 19:11
19440 | STRIVE.R2.MC1.2384.1277.1.1.10.5 | Y | Y | Y | Complete |  | S4: Validate Bank Master replication from S/4 to MDG | 1.58 hrs | 2025-08-21 19:11 | 2025-08-21 20:45 | Aakanksha bapat | aatulbapat@deloitte.com | Tulika Pal; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Satyajit | tupal@deloitte.com; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; sapatnaik@deloitte.com | MDG | 19439 | 2025-08-21 19:11 | 2025-08-21 20:45 | * | NA | 2025-08-21 19:11 | 2025-08-21 20:45
19441 | STRIVE.R2.MC1.2384.1277.1.1.16 |  |  |  | Complete |  | Chart of Accounts | 193.39 hrs | 2025-08-11 08:00 | 2025-08-19 09:55 | [6 empty] | 2025-08-11 15:03 |  | * | NA | 2025-08-11 08:00 | 2025-08-19 09:55
19442 | STRIVE.R2.MC1.2384.1277.1.1.16.1 | Y | Y | Y | Complete |  | Chart of Accounts Post-Load Validation and Sign-off | 0 hrs | 2025-08-11 15:03 | 2025-08-11 15:03 | T. Hagen | Torsten.Hagen@de.sasol.com | M. Jomrich; Viera Chobotova; Eva Bani; L. Theakston; Hendrik Kamsteeg; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat; Tatiana; Roshan | Maik.Jomrich@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de; tvinogradova@deloitte.de; rohemwani@deloitte.com | DM | 19422 | 2025-08-11 15:03 |  | * | NA | 2025-08-11 15:03 | 2025-08-11 15:03
19443 | STRIVE.R2.MC1.2384.1277.1.1.16.2 | Y | Y | Y | Complete |  | S4: Validate Chart of Accounts replication from S/4 to MDG | 1.42 hrs | 2025-08-11 15:03 | 2025-08-11 16:28 | Aakanksha bapat | aatulbapat@deloitte.com | Tulika Pal; Firat; Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda | tupal@deloitte.com; firat.cetin@consultary.de; ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com | MDG | 19442 | 2025-08-11 15:03 | 2025-08-11 16:28 | * | NA | 2025-08-11 15:03 | 2025-08-11 16:28
19444 | STRIVE.R2.MC1.2384.1277.1.1.16.3 | Y | Y | Y | Complete |  | Share the COA list with Coupa | 0 hrs | 2025-08-11 15:03 | 2025-08-11 15:03 | Mohamed Ibrahim | mibrahimjs@deloitte.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Tatiana; Roshan | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; rohemwani@deloitte.com | R2D | 19442 | 2025-08-11 15:03 |  | * | NA | 2025-08-11 15:03 | 2025-08-11 15:03
19445 | STRIVE.R2.MC1.2384.1277.1.1.16.4 | Y | Y | Y | Complete |  | COA Pre-load Validation and Sign off - Coupa | 161.11 hrs | 2025-08-12 03:03 | 2025-08-18 20:36 | Tina Vidrine | tina.vidrine@us.sasol.com | Hendrik Kamsteeg; Gabriele; Prasanth; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Adrian Naidoo; S2P Team; Myriam; Frank Toedter ; Esmir Divljanovic; Firat | hendrik.kamsteeg@de.sasol.com; gabriele.schwemer@de.sasol.com; kalprasanth@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; adnaidoo@deloitte.co.za; usisasols2p@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19444 | 2025-08-12 03:03 | 2025-08-18 20:36 |  | 2025-08-12 03:03 | 2025-08-12 03:03 | 2025-08-18 20:36
19446 | STRIVE.R2.MC1.2384.1277.1.1.16.5 | Y | Y | Y | Complete |  | Load chart of accounts to Coupa - Coupa | 0 hrs | 2025-08-18 21:47 | 2025-08-18 21:47 | Rahul Sengupta | rahusengupta@deloitte.com | Pournami Nair; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat; Supriya | pounair@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de; supriychakraborty@deloitte.com | S2P_Coupa | 19445 | 2025-08-18 21:47 |  |  | 2025-08-11 15:03 | 2025-08-18 21:47 | 2025-08-18 21:47
19447 | STRIVE.R2.MC1.2384.1277.1.1.16.6 | Y | Y | Y | Complete |  | Post load Validation and sign off - Coupa | 75.15 hrs | 2025-08-18 21:47 | 2025-08-22 01:10 | Tina Vidrine | tina.vidrine@us.sasol.com | Hendrik Kamsteeg; Gabriele; Prasanth; Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Adrian Naidoo; S2P Team; Frank Toedter ; Myriam; Esmir Divljanovic; Firat | hendrik.kamsteeg@de.sasol.com; gabriele.schwemer@de.sasol.com; kalprasanth@deloitte.com; apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; adnaidoo@deloitte.co.za; usisasols2p@deloitte.com; ft@toedter-consult.de; marialuisa.geremicca@it.sasol.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19446 | 2025-08-18 21:47 | 2025-08-22 01:10 |  | 2025-08-11 15:03 | 2025-08-18 21:47 | 2025-08-22 01:10
19471 | STRIVE.R2.MC1.2384.1277.1.1.46 | [5 empty] | Substance Specification | 74.77 hrs | 2025-08-11 08:00 | 2025-08-14 10:58 | [8 empty] | * | NA | 2025-08-11 08:00 | 2025-08-14 10:58
19473 | STRIVE.R2.MC1.2384.1277.1.1.46.2 | N | N | N | Ready |  | Substance Specification Post-Load Validation and Sign-off | 20 hrs | 2025-08-25 08:00 | 2025-08-26 04:03 | Klaus Heitkamp | klaus.heitkamp@de.sasol.com | Kira Willeke; Manfred Sprung; Michael Claußen; Hans-Jörg Becker; Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Amit das; Jay Saini; Nilesh Deshpande; Torsten Freydt; Firat | Kira.Willeke@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; hansjorg.becker@de.sasol.com; alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; amitdas3@deloitte.com; jaysaini4@deloitte.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P |  |  |  |  | 2025-08-25 08:00 | 2025-08-25 08:00 | 2025-08-26 04:03
19474 | STRIVE.R2.MC1.2384.1277.1.1.49 |  |  |  | Complete |  | Project | 79.75 hrs | 2025-08-11 08:00 | 2025-08-14 15:58 | [6 empty] | 2025-08-11 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-08-14 15:58
19475 | STRIVE.R2.MC1.2384.1277.1.1.49.1 | Y | Y | Y | Complete |  | Project Transformation and share Pre-Load | 1.26 hrs | 2025-08-11 08:00 | 2025-08-11 09:16 | Vahini | vgudisetti@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sven Gelking; Joseph Barber; Roman Mäkilä; Saketh; Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mythili; Nikhil Gupta; Krishna Teja; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sven.gelking@de.sasol.com; joseph.barber@us.sasol.com; roman.makila@deloitte.fi; sasaketh@deloitte.com; silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; myboyapati@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; firat.cetin@consultary.de | DM | 19427 | 2025-08-11 08:00 | 2025-08-11 09:16 | * | NA | 2025-08-11 08:00 | 2025-08-11 09:16
19476 | STRIVE.R2.MC1.2384.1277.1.1.49.2 | Y | Y | Y | Complete |  | Project Pre-Load Validation and Sign-off | 4 hrs | 2025-08-11 09:16 | 2025-08-11 13:17 | Joseph Barber | joseph.barber@us.sasol.com | Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mousikta chanda; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Dhruv Kansal; USI STRIVE CUTOVER; Krishna Teja; Jay Patel; Nikhil Gupta; Sven Gelking; Mythili; Alex Miles; Satyajit; Roman Mäkilä; Firat | silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; mrgupta3@deloitte.com; sven.gelking@de.sasol.com; myboyapati@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | MOR | 19475 | 2025-08-11 09:16 |  | * | NA | 2025-08-11 09:16 | 2025-08-11 13:17
19477 | STRIVE.R2.MC1.2384.1277.1.1.49.3 | Y | Y | Y | Complete |  | Project Load into S/4 and share Post-Load | 3.67 hrs | 2025-08-12 11:35 | 2025-08-12 16:15 | Vahini | vgudisetti@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sven Gelking; Joseph Barber; Roman Mäkilä; Saketh; Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mythili; Nikhil Gupta; Krishna Teja; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sven.gelking@de.sasol.com; joseph.barber@us.sasol.com; roman.makila@deloitte.fi; sasaketh@deloitte.com; silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; myboyapati@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; firat.cetin@consultary.de | DM | 19476 | 2025-08-12 11:35 | 2025-08-12 16:15 | * | NA | 2025-08-12 11:35 | 2025-08-12 16:15
19478 | STRIVE.R2.MC1.2384.1277.1.1.49.4 | Y | Y | Y | Complete |  | Project Post-Load Validation and Sign-off | 4 hrs | 2025-08-12 16:15 | 2025-08-12 20:15 | Joseph Barber | joseph.barber@us.sasol.com | Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mousikta chanda; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Dhruv Kansal; USI STRIVE CUTOVER; Krishna Teja; Jay Patel; Nikhil Gupta; Sven Gelking; Mythili; Alex Miles; Satyajit; Roman Mäkilä; Firat | silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; mrgupta3@deloitte.com; sven.gelking@de.sasol.com; myboyapati@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | MOR | 19477 | 2025-08-12 16:15 |  | * | NA | 2025-08-12 16:15 | 2025-08-12 20:15
19479 | STRIVE.R2.MC1.2384.1277.1.1.54 | [5 empty] | WBS | 96.76 hrs | 2025-08-11 08:00 | 2025-08-15 09:02 | [6 empty] | 2025-08-12 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-08-15 09:02
19480 | STRIVE.R2.MC1.2384.1277.1.1.54.1 | N | N | N | Ready |  | S2P_I_020 : Undeploy the IFlow | 4 hrs | 2025-08-12 16:15 | 2025-08-12 20:15 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19477 |  |  | * | NA | 2025-08-12 16:15 | 2025-08-12 20:15
19481 | STRIVE.R2.MC1.2384.1277.1.1.54.2 | Y | Y | Y | Complete |  | WBS Transformation and share Pre-Load | 0 hrs | 2025-08-12 08:00 | 2025-08-12 08:00 | Vahini | vgudisetti@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sven Gelking; Joseph Barber; Roman Mäkilä; Saketh; Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mythili; Nikhil Gupta; Krishna Teja; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sven.gelking@de.sasol.com; joseph.barber@us.sasol.com; roman.makila@deloitte.fi; sasaketh@deloitte.com; silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; myboyapati@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; firat.cetin@consultary.de | DM | 19477 | 2025-08-12 08:00 | 2025-08-12 08:00 |  | 2025-08-12 08:00 | 2025-08-12 08:00 | 2025-08-12 08:00
19482 | STRIVE.R2.MC1.2384.1277.1.1.54.3 | Y | Y | Y | Complete |  | WBS Pre-Load Validation and Sign-off | 2 hrs | 2025-08-12 08:00 | 2025-08-12 10:00 | Joseph Barber | joseph.barber@us.sasol.com | Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mousikta chanda; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Dhruv Kansal; USI STRIVE CUTOVER; Krishna Teja; Jay Patel; Nikhil Gupta; Sven Gelking; Mythili; Alex Miles; Satyajit; Roman Mäkilä; Firat | silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; mrgupta3@deloitte.com; sven.gelking@de.sasol.com; myboyapati@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | MOR | 19481 | 2025-08-12 08:00 |  | * | NA | 2025-08-12 08:00 | 2025-08-12 10:00
19483 | STRIVE.R2.MC1.2384.1277.1.1.54.4 | Y | Y | Y | Complete |  | WBS Load into S/4 and share Post-Load | 151.74 hrs | 2025-08-13 08:00 | 2025-08-19 16:10 | Vahini | vgudisetti@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sven Gelking; Joseph Barber; Roman Mäkilä; Saketh; Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mythili; Nikhil Gupta; Krishna Teja; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sven.gelking@de.sasol.com; joseph.barber@us.sasol.com; roman.makila@deloitte.fi; sasaketh@deloitte.com; silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; myboyapati@deloitte.com; mrgupta3@deloitte.com; krishn@deloitte.com; firat.cetin@consultary.de | DM | 19476,19482 | 2025-08-13 08:00 | 2025-08-19 16:10 | * | NA | 2025-08-13 08:00 | 2025-08-19 16:10
19484 | STRIVE.R2.MC1.2384.1277.1.1.54.5 | Y | Y | Y | Complete |  | WBS Post-Load Validation and Sign-off | 9.13 hrs | 2025-08-21 14:02 | 2025-08-21 23:10 | Joseph Barber | joseph.barber@us.sasol.com | Silke Schröter; Andre Harders; Eva Bani; L. Theakston; Mousikta chanda; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Dhruv Kansal; USI STRIVE CUTOVER; Krishna Teja; Jay Patel; Nikhil Gupta; Sven Gelking; Mythili; Firat | silke.schroeter@de.sasol.com; Andre.Harders@de.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; mrgupta3@deloitte.com; sven.gelking@de.sasol.com; myboyapati@deloitte.com; firat.cetin@consultary.de | MOR | 19483 | 2025-08-21 14:02 | 2025-08-21 23:10 |  | 2025-08-12 08:00 | 2025-08-21 14:02 | 2025-08-21 23:10
19485 | STRIVE.R2.MC1.2384.1277.1.1.54.6 | Y | N | N | Sent |  | Project / WBS creation for RRB | 5 hrs | 2025-08-21 23:10 | 2025-08-22 04:12 | Gabriele | gabriele.schwemer@de.sasol.com | Michaela Schulz; Roshanlal Hemwani; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Tatiana; Firat | michaela.schulz@de.sasol.com; rohemwani@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tvinogradova@deloitte.de; firat.cetin@consultary.de | R2D | 19484 |  |  |  | 2025-08-13 11:00 | 2025-08-21 23:10 | 2025-08-22 04:12
19487 | STRIVE.R2.MC1.2384.1277.1.1.54.8 | Y | Y | I | Issue |  | Create Portfolio Items for migrated PS projects through RPM_DX_ITEM program. | 4.95 hrs | 2025-08-21 23:10 | 2025-08-22 04:09 | Mythili | myboyapati@deloitte.com | Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha; Nikhil Gupta; Chaitnya; Abhishek Sharma; Firat | krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; firat.cetin@consultary.de | MOR | 19484,18568 |  |  |  | 2025-08-13 11:00 | 2025-08-21 23:10 | 2025-08-22 04:09
19488 | STRIVE.R2.MC1.2384.1277.1.1.54.9 | N | N | N | Planned |  | Perform Object linking between portfolio item and PS project | 4 hrs | 2025-08-22 04:09 | 2025-08-22 08:10 | Mythili | myboyapati@deloitte.com | Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha; Nikhil Gupta; Chaitnya; Abhishek Sharma; Firat | krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; firat.cetin@consultary.de | MOR | 19487 |  |  |  | 2025-08-13 11:00 | 2025-08-22 04:09 | 2025-08-22 08:10
19489 | STRIVE.R2.MC1.2384.1277.1.1.54.10 | N | N | N | Planned |  | Update the status for PS project and WBS | 1.37 hrs | 2025-09-20 13:01 | 2025-09-20 14:23 | Mythili | myboyapati@deloitte.com | Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha; Nikhil Gupta; Chaitnya; Abhishek Sharma; Firat | krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; firat.cetin@consultary.de | MOR | 19484,20778 |  |  |  | 2025-08-13 11:00 | 2025-09-20 13:01 | 2025-09-20 14:23
19490 | STRIVE.R2.MC1.2384.1277.1.1.54.11 | N | N | N | Planned |  | WBS - Share WBS Details with coupa Team | 1 hrs | 2025-09-20 14:23 | 2025-09-20 15:23 | Mythili | myboyapati@deloitte.com | Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jay Patel; Amit Jha; Nikhil Gupta; Chaitnya; Abhishek Sharma; Firat | krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; firat.cetin@consultary.de | MOR | 19489 |  |  |  | 2025-08-13 11:00 | 2025-09-20 14:23 | 2025-09-20 15:23
19491 | STRIVE.R2.MC1.2384.1277.1.1.54.12 | N | N | N | Planned |  | WBS - Populate WBS in a Coupa Acceptable Format | 1 hrs | 2025-09-20 15:23 | 2025-09-20 16:23 | Supriya | supriychakraborty@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19490 |  |  |  | 2025-08-13 11:00 | 2025-09-20 15:23 | 2025-09-20 16:23
19492 | STRIVE.R2.MC1.2384.1277.1.1.54.13 | N | N | N | Planned |  | WBS - Coupa- Pre Load Validation and sign off | 1 hrs | 2025-09-20 16:23 | 2025-09-20 17:23 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19491 |  |  |  | 2025-08-13 11:00 | 2025-09-20 16:23 | 2025-09-20 17:23
19493 | STRIVE.R2.MC1.2384.1277.1.1.54.14 | N | N | N | Planned |  | Load WBS in Coupa | 8 hrs | 2025-09-20 17:23 | 2025-09-21 01:25 | Supriya | supriychakraborty@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19492 |  |  |  | 2025-08-13 11:00 | 2025-09-20 17:23 | 2025-09-21 01:25
19494 | STRIVE.R2.MC1.2384.1277.1.1.54.15 | N | N | N | Planned |  | WBS - Coupa - Post Load Validation and sign off | 4 hrs | 2025-09-21 01:25 | 2025-09-21 05:25 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Supriya; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Mousikta chanda; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; supriychakraborty@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19493 |  |  |  | 2025-08-13 11:00 | 2025-09-21 01:25 | 2025-09-21 05:25
19495 | STRIVE.R2.MC1.2384.1277.1.1.54.16 | N | N | N | Planned |  | S2P_I_020 : Clear the AEM Q and Deploy the IFlow | 4 hrs | 2025-09-21 05:25 | 2025-09-21 09:26 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 19494,19834 |  |  |  | 2025-08-12 08:19 | 2025-09-21 05:25 | 2025-09-21 09:26
19496 | STRIVE.R2.MC1.2384.1277.1.1.71 |  |  |  | Complete |  | Activity type | 5.98 hrs | 2025-08-11 08:00 | 2025-08-11 14:59 | [5 empty] | 19421 | 2025-08-11 11:03 | 2025-08-11 21:28 | * | NA | 2025-08-11 08:00 | 2025-08-11 14:59
19497 | STRIVE.R2.MC1.2384.1277.1.1.71.1 | Y | Y | Y | Complete |  | Create Activity Type/ Maintain prices. | 0.59 hrs | 2025-08-11 11:03 | 2025-08-11 11:38 | Sandeep (R2D) | ssandeep4@deloitte.com | Jitender Chhabra; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | jkchhabra.ext@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | R2D | 18518 | 2025-08-11 11:03 | 2025-08-11 11:38 | * | NA | 2025-08-11 11:03 | 2025-08-11 11:38
19498 | STRIVE.R2.MC1.2384.1277.1.1.71.2 | Y | Y | Y | Complete |  | Activity Type Post-Load Validation and Sign-off | 0 hrs | 2025-08-11 21:28 | 2025-08-11 21:28 | Gabriele | gabriele.schwemer@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Christian Canale; Clara Mori; Tatiana; Hendrik Kamsteeg; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; tvinogradova@deloitte.de; hendrik.kamsteeg@de.sasol.com; firat.cetin@consultary.de | R2D | 19422,19497 | 2025-08-11 21:28 | 2025-08-11 21:28 | * | NA | 2025-08-11 21:28 | 2025-08-11 21:28
19499 | STRIVE.R2.MC1.2384.1277.1.1.74 |  |  |  | Complete |  | Statistical Key figures | 0.25 hrs | 2025-08-11 08:00 | 2025-08-11 08:15 | [6 empty] | 2025-08-11 21:28 | 2025-08-11 21:28 | * | NA | 2025-08-11 08:00 | 2025-08-11 08:15
19500 | STRIVE.R2.MC1.2384.1277.1.1.74.1 | Y | Y | Y | Complete |  | Statistical Key figures and hierarchies Confirm created in S4 | 0 hrs | 2025-08-11 21:28 | 2025-08-11 21:28 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Gabriele; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Christian Canale; Clara Mori; Firat | gabriele.schwemer@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; firat.cetin@consultary.de | R2D | 19422 | 2025-08-11 21:28 | 2025-08-11 21:28 | * | NA | 2025-08-11 21:28 | 2025-08-11 21:28
19501 | STRIVE.R2.MC1.2384.1277.1.1.76 | [5 empty] | Vendor master data load | 1396.51 hrs | 2025-08-12 08:00 | 2025-10-09 16:23 | [6 empty] | 2025-08-12 08:00 |  | * | NA | 2025-08-12 08:00 | 2025-10-09 16:23
19503 | STRIVE.R2.MC1.2384.1277.1.1.76.2 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA QA Systems - Vendor | 20.26 hrs | 2025-08-12 08:00 | 2025-08-14 13:16 | Prasanth Kallakuri | kalprasanth@deloitte.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Milton; S2P Team; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; miltjones@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19422 | 2025-08-12 08:00 | 2025-08-14 13:16 | * | NA | 2025-08-12 08:00 | 2025-08-14 13:16
19506 | STRIVE.R2.MC1.2384.1277.1.1.76.5 | Y | Y | Y | Complete |  | Supplier/Vendor Master Transformation and share Pre-Load - S4 & Coupa | 201.2 hrs | 2025-08-12 11:18 | 2025-08-20 21:03 | Rishi Tirthani | rtirthani@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Maria Luisa Geremicca; Roman Mäkilä; Liviana Scaricabarozzi; Zuzana Hlucha; Sandra Kaczor; Sabrina Agueli; Simonetta Confalonieri | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi; liviana.scaricabarozzi@it.sasol.com; zuzana.hlucha@sk.sasol.com; Sandra.Kaczor@de.sasol.com; sabrina.agueli@de.sasol.com; Simonetta.Confalonieri@it.sasol.com | DM | 19438,19442,18800,18801 | 2025-08-12 11:18 | 2025-08-20 21:03 | * | NA | 2025-08-12 11:18 | 2025-08-20 21:03
19507 | STRIVE.R2.MC1.2384.1277.1.1.76.6 | Y | Y | Y | Complete |  | Supplier/Vendor Master Pre-Load Validation and Sign-off - DE | 71.63 hrs | 2025-08-26 12:55 | 2025-08-29 12:45 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Sandra Kaczor; Jörn Schacher; Sabrina Agueli; Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; S2P Team; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Simonetta Confalonieri | Sandra.Kaczor@de.sasol.com; Joern.Schacher@de.sasol.com; sabrina.agueli@de.sasol.com; kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; usisasols2p@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; Simonetta.Confalonieri@it.sasol.com | S2P | 19506 | 2025-08-26 12:55 | 2025-08-29 12:45 |  | 2025-08-18 09:00 | 2025-08-26 12:55 | 2025-08-29 12:45
21157 | STRIVE.R2.MC1.2384.1277.1.1.76.33 | Y | Y | Y | Complete |  | Supplier/Vendor Master Pre-Load Validation and Sign-off - SK | 71.77 hrs | 2025-08-26 12:47 | 2025-08-29 12:45 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Prasanth; Mousikta chanda; Dhruv Kansal; Ines Tesch; Jens Nissen; USI STRIVE CUTOVER; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; kalprasanth@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; usistrivecutover@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19506 | 2025-08-26 12:47 | 2025-08-29 12:45 |  | 2025-08-18 09:00 | 2025-08-26 12:47 | 2025-08-29 12:45
21156 | STRIVE.R2.MC1.2384.1277.1.1.76.32 | Y | Y | Y | Complete |  | Supplier/Vendor Master Pre-Load Validation and Sign-off - UK | 159.77 hrs | 2025-08-22 20:31 | 2025-08-29 12:45 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | L. Theakston; Prasanth; Mousikta chanda; Dhruv Kansal; Ines Tesch; Jens Nissen; USI STRIVE CUTOVER; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat; Simonetta Confalonieri | Laraine.Theakston@eu.sasol.com; kalprasanth@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; usistrivecutover@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com | S2P | 19506 | 2025-08-22 20:31 | 2025-08-29 12:45 |  | 2025-08-18 09:00 | 2025-08-22 20:31 | 2025-08-29 12:45
19508 | STRIVE.R2.MC1.2384.1277.1.1.76.7 | Y | Y | Y | Complete |  | Supplier/Vendor Master Pre-Load Validation and Sign-off - R2D Views | 357.78 hrs | 2025-08-20 21:03 | 2025-09-04 19:50 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Michaela; Tatiana; Prasanth; USI STRIVE CUTOVER; Dhruv Kansal; Roshanlal; Mousikta chanda; Maria Luisa Geremicca; Firat | michaela.schulz@de.sasol.com; tvinogradova@deloitte.de; kalprasanth@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; rohemwani@deloitte.com; mouchanda@deloitte.com; marialuisa.geremicca@it.sasol.com; firat.cetin@consultary.de | R2D | 19506 | 2025-08-20 21:03 | 2025-09-04 19:50 |  | 2025-08-18 09:00 | 2025-08-20 21:03 | 2025-09-04 19:50
19509 | STRIVE.R2.MC1.2384.1277.1.1.76.8 | Y | Y | Y | Complete |  | Supplier/Vendor Master Handover Pre-load File to Coupa | 0 hrs | 2025-08-21 21:39 | 2025-08-21 21:39 | Rishi Tirthani | rtirthani@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; S2P Team; Maria Luisa Geremicca; Roman Mäkilä; Simonetta Confalonieri | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; usisasols2p@deloitte.com; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi; Simonetta.Confalonieri@it.sasol.com | DM | 19507,21157,21156,19508 | 2025-08-21 21:39 | 2025-08-21 21:39 |  | 2025-08-18 09:00 | 2025-08-21 21:39 | 2025-08-21 21:39
19511 | STRIVE.R2.MC1.2384.1277.1.1.76.10 | Y | Y | Y | Complete |  | Supplier: Review the files created | 19.92 hrs | 2025-08-23 01:09 | 2025-08-23 21:06 | Manoj kovilpillai | mmanickrajkovilpi@deloitte.com | Aparajita Mukherjee; Milton; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19506 | 2025-08-23 01:09 | 2025-08-23 21:06 | * | NA | 2025-08-23 01:09 | 2025-08-23 21:06
40105 | STRIVE.R2.MC1.2384.1277.1.1.76.38 | Y | Y | Y | Complete |  | Supplier/Vendor Master Run ABAP Code Transformation | 89.24 hrs | 2025-08-21 21:39 | 2025-08-25 15:09 | Chetan Patil | cpatil3@deloitte.com | Aparajita Mukherjee; Milton; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal; S2P Team; Prasanth | apamukherjee@deloitte.com; miltjones@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; kalprasanth@deloitte.com | S2P | 19509 | 2025-08-21 21:39 | 2025-08-25 15:09 | * | NA | 2025-08-21 21:39 | 2025-08-25 15:09
19512 | STRIVE.R2.MC1.2384.1277.1.1.76.11 | Y | Y | Y | Complete |  | Supplier: Update Postman Script to run Java code as per Production Lookup Values | 0 hrs | 2025-08-25 14:07 | 2025-08-25 14:08 | Rabbani | skhadarmohammadra@deloitte.com | Adrian Naidoo; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | adnaidoo@deloitte.co.za; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19511 | 2025-08-25 14:07 | 2025-08-25 14:08 | * | NA | 2025-08-25 14:07 | 2025-08-25 14:08
19513 | STRIVE.R2.MC1.2384.1277.1.1.76.12 | Y | Y | Y | Complete |  | Supplier/Vendor Master Pre-Load Validation and Sign-off - Coupa | 7.28 hrs | 2025-08-28 21:58 | 2025-08-29 05:17 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Roman Mäkilä; Satyajit; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19511,40105 | 2025-08-28 21:58 | 2025-08-29 05:17 | * | NA | 2025-08-28 21:58 | 2025-08-29 05:17
19514 | STRIVE.R2.MC1.2384.1277.1.1.76.13 | Y | Y | Y | Complete |  | Supplier/Vendor Master execution of Postman Script to upload vendor file (100 per run) | 63.97 hrs | 2025-08-22 19:17 | 2025-08-25 11:27 | Manoj kovilpillai | mmanickrajkovilpi@deloitte.com | Aparajita Mukherjee; Milton; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19513 | 2025-08-22 19:17 | 2025-08-25 11:27 | * | NA | 2025-08-22 19:17 | 2025-08-25 11:27
19515 | STRIVE.R2.MC1.2384.1277.1.1.76.14 | Y | Y | Y | Complete |  | Supplier/Vendor Master Error File from Coupa. Also based on MDG and S4 Teams post load validation report | 0 hrs | 2025-08-25 21:33 | 2025-08-25 21:34 | Manoj kovilpillai | mmanickrajkovilpi@deloitte.com | Aparajita Mukherjee; Milton; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19514 | 2025-08-25 21:33 | 2025-08-25 21:34 |  | 2025-08-20 16:00 | 2025-08-25 21:33 | 2025-08-25 21:34
21159 | STRIVE.R2.MC1.2384.1277.1.1.76.35 | Y | Y | Y | Complete |  | Supplier/Vendor Master Enrich Vendor with Finance Data in MDG | 1.89 hrs | 2025-08-26 12:07 | 2025-08-26 14:00 | Rishi Tirthani | rtirthani@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Maria Luisa Geremicca; Roman Mäkilä; Simonetta Confalonieri | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi; Simonetta.Confalonieri@it.sasol.com | DM | 19514,19515 | 2025-08-26 12:07 | 2025-08-26 14:00 |  | 2025-08-20 16:00 | 2025-08-26 12:07 | 2025-08-26 14:00
21158 | STRIVE.R2.MC1.2384.1277.1.1.76.34 | Y | Y | Y | Complete |  | Supplier/Vendor Master Create Invoicing Parties | 10.01 hrs | 2025-08-26 17:11 | 2025-08-27 03:14 | Rishi Tirthani | rtirthani@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Maria Luisa Geremicca; Roman Mäkilä; Simonetta Confalonieri | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi; Simonetta.Confalonieri@it.sasol.com | DM | 19509 | 2025-08-26 17:11 | 2025-08-27 03:14 |  | 2025-08-20 16:00 | 2025-08-26 17:11 | 2025-08-27 03:14
19530 | STRIVE.R2.MC1.2384.1277.1.1.76.29 | Y | Y | Y | Complete |  | Supplier/Vendor Master Trigger Replication from MDG to S/4 | 56.52 hrs | 2025-08-27 03:14 | 2025-08-29 11:54 | Amol | ampaswan@deloitte.com | Tulika Pal; Tushar; Firat; Dhruv Kansal; Mousikta chanda; Alex Miles; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Ines Tesch | tupal@deloitte.com; tamrutkar@deloitte.de; firat.cetin@consultary.de; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ines.tesch@de.sasol.com | MDG | 21158 | 2025-08-27 03:14 | 2025-08-29 11:54 |  | 2025-08-20 16:00 | 2025-08-27 03:14 | 2025-08-29 11:54
19527 | STRIVE.R2.MC1.2384.1277.1.1.76.26 | Y | Y | Y | Complete |  | Supplier/Vendor Master - Validate Replication MDG to S/4 | 279.44 hrs | 2025-08-29 17:52 | 2025-09-10 10:05 | Tulika Pal | tupal@deloitte.com | Amol; Dhruv Kansal; USI STRIVE CUTOVER; Alex Miles; Mousikta chanda; Satyajit Patnaik; Roman Mäkilä; Firat; Ines Tesch | ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; ines.tesch@de.sasol.com | MDG | 19530 | 2025-08-29 17:52 | 2025-09-10 10:05 |  | 2025-08-20 16:00 | 2025-08-29 17:52 | 2025-09-10 10:05
77611 | STRIVE.R2.MC1.2384.1277.1.1.76.42 | Y | Y | Y | Complete |  | Trigger replication from MDG to Coupa | 127.82 hrs | 2025-08-27 03:14 | 2025-09-01 11:24 | Amol | ampaswan@deloitte.com | Tulika Pal; Tushar; Firat; Dhruv Kansal; Mousikta chanda; Alex Miles; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Ines Tesch | tupal@deloitte.com; tamrutkar@deloitte.de; firat.cetin@consultary.de; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ines.tesch@de.sasol.com | MDG | 21158 | 2025-08-27 03:14 | 2025-09-01 11:24 |  | 2025-08-20 16:00 | 2025-08-27 03:14 | 2025-09-01 11:24
19528 | STRIVE.R2.MC1.2384.1277.1.1.76.27 | Y | Y | Y | Complete |  | Supplier/Vendor Master Check if replication completed from MDG to Coupa | 0 hrs | 2025-09-05 20:15 | 2025-09-05 20:15 | Manoj kovilpillai | mmanickrajkovilpi@deloitte.com | Pournami Nair; Prasanth; Rahul Sengupta; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Esmir Divljanovic; Firat | pounair@deloitte.com; kalprasanth@deloitte.com; rahusengupta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 77611 | 2025-09-05 20:15 | 2025-09-05 20:15 |  | 2025-08-20 16:00 | 2025-09-05 20:15 | 2025-09-05 20:15
19516 | STRIVE.R2.MC1.2384.1277.1.1.76.15 | Y | Y | Y | Complete |  | Supplier/Vendor Master Post-Load Report Generation and Distribution to Business | 32.56 hrs | 2025-08-28 12:37 | 2025-08-29 21:15 | Rishi Tirthani | rtirthani@deloitte.com | ; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Firat | ; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19515,19528 | 2025-08-28 12:37 | 2025-08-29 21:15 |  | 2025-08-20 16:00 | 2025-08-28 12:37 | 2025-08-29 21:15
19517 | STRIVE.R2.MC1.2384.1277.1.1.76.16 | Y | Y | Y | Complete |  | Supplier/Vendor Master Post-Load Validation and Sign-off - R2D | 227.08 hrs | 2025-08-29 21:15 | 2025-09-08 08:59 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Tatiana; Prasanth; USI STRIVE CUTOVER; Dhruv Kansal; Roshanlal; Mousikta chanda; Maria Luisa Geremicca; Alex Miles; Satyajit; Roman Mäkilä; Firat; Michaela Schulz | tvinogradova@deloitte.de; kalprasanth@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; rohemwani@deloitte.com; mouchanda@deloitte.com; marialuisa.geremicca@it.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; michaela.schulz@de.sasol.com | R2D | 19516 | 2025-08-29 21:15 | 2025-09-08 08:59 |  | 2025-08-20 16:00 | 2025-08-29 21:15 | 2025-09-08 08:59
19518 | STRIVE.R2.MC1.2384.1277.1.1.76.17 | Y | Y | Y | Complete |  | Supplier/Vendor Master Post-Load Validation and Sign-off - DE | 43.03 hrs | 2025-09-01 20:29 | 2025-09-03 15:39 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Sandra Kaczor; Jörn Schacher; Sabrina Agueli; Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | Sandra.Kaczor@de.sasol.com; Joern.Schacher@de.sasol.com; sabrina.agueli@de.sasol.com; kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19516 | 2025-09-01 20:29 | 2025-09-03 15:39 |  | 2025-08-20 16:00 | 2025-09-01 20:29 | 2025-09-03 15:39
21161 | STRIVE.R2.MC1.2384.1277.1.1.76.37 | Y | Y | Y | Complete |  | Supplier/Vendor Master Post-Load Validation and Sign-off - SK | 43.04 hrs | 2025-09-01 20:28 | 2025-09-03 15:38 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19516 | 2025-09-01 20:28 | 2025-09-03 15:38 |  | 2025-08-20 16:00 | 2025-09-01 20:28 | 2025-09-03 15:38
21160 | STRIVE.R2.MC1.2384.1277.1.1.76.36 | Y | Y | Y | Complete |  | Supplier/Vendor Master Post-Load Validation and Sign-off - UK | 43.04 hrs | 2025-09-01 20:28 | 2025-09-03 15:38 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | L. Theakston; Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat; Simonetta Confalonieri | Laraine.Theakston@eu.sasol.com; kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com | S2P_Coupa | 19516 | 2025-09-01 20:28 | 2025-09-03 15:38 |  | 2025-08-20 16:00 | 2025-09-01 20:28 | 2025-09-03 15:38
19529 | STRIVE.R2.MC1.2384.1277.1.1.76.28 | Y | N | N | Sent |  | Supplier/Vendor Master Bank Details Post Load Validation in Coupa R2D | 4 hrs | 2025-09-05 20:15 | 2025-09-06 00:17 | Myriam | marialuisa.geremicca@it.sasol.com | Aparajita Mukherjee; Milton; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tatiana; Prasanth; Roshan; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tvinogradova@deloitte.de; kalprasanth@deloitte.com; rohemwani@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19528 |  |  |  | 2025-08-20 16:00 | 2025-09-05 20:15 | 2025-09-06 00:17
19531 | STRIVE.R2.MC1.2384.1277.1.1.76.30 | Y | N | N | Sent |  | Supplier/Vendor Master Update Vendor/BP Xref with old to new values | 2 hrs | 2025-09-05 20:15 | 2025-09-05 22:15 | Rishi Tirthani | rtirthani@deloitte.com | ; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat | ; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 19528 |  |  |  | 2025-08-20 16:00 | 2025-09-05 20:15 | 2025-09-05 22:15
19541 | STRIVE.R2.MC1.2384.1277.1.1.116 | [5 empty] | Customer master data load | 670.91 hrs | 2025-08-12 08:00 | 2025-09-09 08:47 | [6 empty] | 2025-08-12 10:39 |  | * | NA | 2025-08-12 08:00 | 2025-09-09 08:47
19542 | STRIVE.R2.MC1.2384.1277.1.1.116.1 | Y | Y | Y | Complete |  | Customer Master​ Validate Number Range S4 and MDG before Load | 0 hrs | 2025-08-13 21:36 | 2025-08-13 21:36 | Ramesh SathishKumar | satramesh@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tripti mehta; Alex Miles; Roman Mäkilä; Satyajit; Savri Sumeet Jagatap | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; trimehta@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com | MDG | 19422 | 2025-08-13 21:36 |  | * | NA | 2025-08-13 21:36 | 2025-08-13 21:36
19543 | STRIVE.R2.MC1.2384.1277.1.1.116.2 | Y | Y | Y | Complete |  | Confirm Configuration is synchronized between MDG and S/4HANA Production Systems - Customer | 0 hrs | 2025-08-12 22:28 | 2025-08-12 22:28 | Ramesh SathishKumar | satramesh@deloitte.com | Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat | trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de | P2C | 19422 | 2025-08-12 22:28 |  | * | NA | 2025-08-12 22:28 | 2025-08-12 22:28
19544 | STRIVE.R2.MC1.2384.1277.1.1.116.3 | Y | Y | Y | Complete |  | Customer Master​ Transformation and share Pre-Load | 177.81 hrs | 2025-08-12 10:39 | 2025-08-19 20:57 | Sampath | sampaupadhya@deloitte.com | Avinash Puranik; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Jessica Goffi; R. Schmidt-Biedenkopf; Hendrik Kamsteeg; Roman Mäkilä; Firat; Lueder Nonnekamp; Cornelia Baretti; Stefanie Groenmeyer; Antonio Di Sciullo; Elisa Sasco; Chantelle; Viktoria Kormanikova; Anna Sifrova; Viera Chobotova; Tobias Wilmering; Andrea Ludeke; Ramesh SathishKumar | avpuranik@deloitte.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Lueder.Nonnenkamp@de.sasol.com; Cornelia.Baretti@de.sasol.com; Stefanie.Groenmeyer@de.sasol.com; Antonio.Sciullodi@de.sasol.com; elisa.sasco@it.sasol.com; chantelle.crause@sasol.com; viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; Viera.Chobotova@sk.sasol.com; tobias.wilmering@de.sasol.com; Andrea.Luedeke@de.sasol.com; satramesh@deloitte.com | DM | 19438,19543 | 2025-08-12 10:39 | 2025-08-19 20:57 | * | NA | 2025-08-12 10:39 | 2025-08-19 20:57
19545 | STRIVE.R2.MC1.2384.1277.1.1.116.4 | Y | Y | Y | Complete |  | Customer Master​ Pre-Load Validation and Sign-off | 39.8 hrs | 2025-08-19 20:57 | 2025-08-21 12:53 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Avinash Puranik; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; R. Schmidt-Biedenkopf; Hendrik Kamsteeg; Roman Mäkilä; Firat; Lueder Nonnekamp; Cornelia Baretti; Stefanie Groenmeyer; Antonio Di Sciullo; Elisa Sasco; Chantelle; Viktoria Kormanikova; Anna Sifrova; Viera Chobotova; Sampath; Tobias Wilmering; Andrea Ludeke; Ramesh SathishKumar | avpuranik@deloitte.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Lueder.Nonnenkamp@de.sasol.com; Cornelia.Baretti@de.sasol.com; Stefanie.Groenmeyer@de.sasol.com; Antonio.Sciullodi@de.sasol.com; elisa.sasco@it.sasol.com; chantelle.crause@sasol.com; viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; Viera.Chobotova@sk.sasol.com; sampaupadhya@deloitte.com; tobias.wilmering@de.sasol.com; Andrea.Luedeke@de.sasol.com; satramesh@deloitte.com | P2C | 19544 | 2025-08-19 20:57 | 2025-08-21 12:53 | * | NA | 2025-08-19 20:57 | 2025-08-21 12:53
19546 | STRIVE.R2.MC1.2384.1277.1.1.116.5 | Y | Y | Y | Complete |  | Customer Master​ Pre-Load Validation and Sign-off (Company Code&Bank data) | 0 hrs | 2025-08-21 19:20 | 2025-08-21 19:20 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Roshanlal; USI STRIVE CUTOVER; Dhruv Kansal; Alex Miles; Satyajit; Mousikta chanda; Firat; Tatiana; Jessica Goffi; Tobias Wilmering; Andrea Ludeke; Ramesh SathishKumar | rohemwani@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de; tvinogradova@deloitte.de; Jessica.Goffi@it.sasol.com; tobias.wilmering@de.sasol.com; Andrea.Luedeke@de.sasol.com; satramesh@deloitte.com | R2D | 19544 | 2025-08-21 19:20 |  | * | NA | 2025-08-21 19:20 | 2025-08-21 19:20
19547 | STRIVE.R2.MC1.2384.1277.1.1.116.6 | Y | Y | Y | Complete |  | Customer Master​ Load into MDG and share Post-Load | 0 hrs | 2025-08-25 14:37 | 2025-08-25 14:37 | Sampath | sampaupadhya@deloitte.com | Avinash Puranik; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Jessica Goffi; R. Schmidt-Biedenkopf; Hendrik Kamsteeg; Roman Mäkilä; Firat; Lueder Nonnekamp; Cornelia Baretti; Stefanie Groenmeyer; Antonio Di Sciullo; Elisa Sasco; Chantelle; Viktoria Kormanikova; Anna Sifrova; Viera Chobotova; Tatiana; Roshan; Andrea Ludeke; Tobias Wilmering; Ramesh SathishKumar | avpuranik@deloitte.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Lueder.Nonnenkamp@de.sasol.com; Cornelia.Baretti@de.sasol.com; Stefanie.Groenmeyer@de.sasol.com; Antonio.Sciullodi@de.sasol.com; elisa.sasco@it.sasol.com; chantelle.crause@sasol.com; viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; Viera.Chobotova@sk.sasol.com; tvinogradova@deloitte.de; rohemwani@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; satramesh@deloitte.com | DM | 19440,19545,19546 | 2025-08-25 14:37 |  |  | 2025-08-18 08:00 | 2025-08-25 14:37 | 2025-08-25 14:37
19548 | STRIVE.R2.MC1.2384.1277.1.1.116.7 | Y | Y | Y | Complete |  | Customer Master​ Post-Load Validation and Sign-off | 0 hrs | 2025-08-29 17:39 | 2025-08-29 17:39 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Avinash Puranik; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; R. Schmidt-Biedenkopf; Hendrik Kamsteeg; Roman Mäkilä; Firat; Lueder Nonnekamp; Cornelia Baretti; Stefanie Groenmeyer; Antonio Di Sciullo; Elisa Sasco; Chantelle; Viktoria Kormanikova; Anna Sifrova; Viera Chobotova; Sampath; Tobias Wilmering; Andrea Ludeke; Ramesh SathishKumar | avpuranik@deloitte.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Lueder.Nonnenkamp@de.sasol.com; Cornelia.Baretti@de.sasol.com; Stefanie.Groenmeyer@de.sasol.com; Antonio.Sciullodi@de.sasol.com; elisa.sasco@it.sasol.com; chantelle.crause@sasol.com; viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; Viera.Chobotova@sk.sasol.com; sampaupadhya@deloitte.com; tobias.wilmering@de.sasol.com; Andrea.Luedeke@de.sasol.com; satramesh@deloitte.com | P2C | 19547 | 2025-08-29 17:39 | 2025-08-29 17:39 | * | NA | 2025-08-29 17:39 | 2025-08-29 17:39
19549 | STRIVE.R2.MC1.2384.1277.1.1.116.8 | Y | N | N | Sent |  | P2C-TM Organization creation and Assignment (PPOCE/PPOME) | 8 hrs | 2025-09-08 18:34 | 2025-09-09 02:36 | Valentijn | vvandriessen@deloitte.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Firat | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de | P2C | 18395,18406,19548 |  |  |  | 2025-09-08 18:34 | 2025-09-08 18:34 | 2025-09-09 02:36
19550 | STRIVE.R2.MC1.2384.1277.1.1.116.9 | Y | Y | Y | Complete |  | Customer Master​ Post-Load Validation and Sign-off (Company Code&Bank data) | 0 hrs | 2025-09-09 20:59 | 2025-09-09 20:59 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Roshanlal; USI STRIVE CUTOVER; Dhruv Kansal; Alex Miles; Satyajit; Mousikta chanda; Firat; Tatiana; Jessica Goffi; Andrea Ludeke; Tobias Wilmering; Ramesh SathishKumar; Ruth Schmidt | rohemwani@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de; tvinogradova@deloitte.de; Jessica.Goffi@it.sasol.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; satramesh@deloitte.com; Ruth.Schmidt-Biedenkopf@de.sasol.com | R2D | 19547 | 2025-09-09 20:59 |  | * | NA | 2025-09-09 20:59 | 2025-09-09 20:59
19551 | STRIVE.R2.MC1.2384.1277.1.1.116.10 | Y | Y | Y | Complete |  | Customer Master​ Trigger Replication from MDG to S/4 | 0 hrs | 2025-09-01 18:34 | 2025-09-01 18:34 | Amol | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Tushar; Firat | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19548 | 2025-09-01 18:34 | 2025-09-01 18:34 | * | NA | 2025-09-01 18:34 | 2025-09-01 18:34
19554 | STRIVE.R2.MC1.2384.1277.1.1.116.13 | Y | Y | Y | Complete |  | Customer Master Validate Replication MDG to S/4 | 0.43 hrs | 2025-09-02 11:35 | 2025-09-02 12:02 | Tulika Pal | tupal@deloitte.com | Amol Paswan; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Miles; Satyajit Patnaik; Roman Mäkilä; Firat; Ines Tesch | ampaswan@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; ines.tesch@de.sasol.com | DM | 19551 | 2025-09-02 11:35 | 2025-09-02 12:02 | * | NA | 2025-09-02 11:35 | 2025-09-02 12:02
19556 | STRIVE.R2.MC1.2384.1277.1.1.116.15 | Y | Y | Y | Complete |  | Update Customer/BP Xref with old to new values | 114.1 hrs | 2025-08-29 17:39 | 2025-09-03 12:04 | Sampath | sampaupadhya@deloitte.com | Avinash Puranik; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Jessica Goffi; ; ; Hendrik Kamsteeg; Roman Mäkilä | avpuranik@deloitte.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; ; ; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi | DM | 19548 | 2025-08-29 17:39 | 2025-09-03 12:04 | * | NA | 2025-08-29 17:39 | 2025-09-03 12:04
19557 | STRIVE.R2.MC1.2384.1277.1.1.116.16 | Y | N | N | Sent |  | Liquidity Item Setup | 8 hrs | 2025-09-03 15:39 | 2025-09-03 23:39 | Niral Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval; Roshanlal; Tatiana | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D | 19548,19518 |  |  | * | NA | 2025-09-03 15:39 | 2025-09-03 23:39
19558 | STRIVE.R2.MC1.2384.1277.1.1.116.17 | Y | Y | N | In-Progress |  | Validate BP (PLanning group, Payment method, House Bank) | 4 hrs | 2025-09-08 14:56 | 2025-09-08 18:56 | Niral Trivedi | nirtrivedi@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dhaval; Roshanlal; Tatiana | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhavalshah@deloitte.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D | 19548,19518 | 2025-09-08 14:56 |  | * | NA | 2025-09-08 14:56 | 2025-09-08 18:56
19559 | STRIVE.R2.MC1.2384.1277.1.1.134 |  |  |  | Complete |  | Customer Material Info Record | 7.98 hrs | 2025-08-11 08:00 | 2025-08-11 16:00 | [6 empty] | 2025-08-25 16:58 | 2025-09-04 20:26 | * | NA | 2025-08-11 08:00 | 2025-08-11 16:00
19560 | STRIVE.R2.MC1.2384.1277.1.1.134.1 | Y | Y | Y | Complete |  | Customer Material Info Record Transformation and share Pre-Load | 4.94 hrs | 2025-08-25 16:58 | 2025-08-25 21:55 | Avinash Puranik | avpuranik@deloitte.com | Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat; Jessica Goffi; Ramesh SathishKumar; Andrea Ludeke; Tobias Wilmering; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Riepe Joëlle | sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; satramesh@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; Joelle.Riepe@de.sasol.com | DM | 19547,19592 | 2025-08-25 16:58 | 2025-08-25 21:55 |  | 2025-08-21 01:00 | 2025-08-25 16:58 | 2025-08-25 21:55
19561 | STRIVE.R2.MC1.2384.1277.1.1.134.2 | Y | Y | Y | Complete |  | Customer Material Info Record Pre-Load Validation and Sign-off | 25.75 hrs | 2025-08-26 18:30 | 2025-08-27 20:19 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Viktoria Kormanikova; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat; Ramesh SathishKumar; Andrea Ludeke; Tobias Wilmering; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Avinash Puranik; Satyajit; Riepe Joëlle | viktoria.kormanikova@sk.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de; satramesh@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; avpuranik@deloitte.com; sapatnaik@deloitte.com; Joelle.Riepe@de.sasol.com | P2C | 19560 | 2025-08-26 18:30 | 2025-08-27 20:19 | * | NA | 2025-08-26 18:30 | 2025-08-27 20:19
19562 | STRIVE.R2.MC1.2384.1277.1.1.134.3 | Y | Y | Y | Complete |  | Customer Material Info Record Load into S/4 and share Post-Load | 22.39 hrs | 2025-09-01 18:34 | 2025-09-02 17:02 | Avinash Puranik | avpuranik@deloitte.com | Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat; Jessica Goffi; Ramesh SathishKumar; Andrea Ludeke; Tobias Wilmering; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Riepe Joëlle | sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; satramesh@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; Joelle.Riepe@de.sasol.com | DM | 19561,19551 | 2025-09-01 18:34 | 2025-09-02 17:02 | * | NA | 2025-09-01 18:34 | 2025-09-02 17:02
19563 | STRIVE.R2.MC1.2384.1277.1.1.134.4 | Y | Y | Y | Complete |  | Customer Material Info Record Post-Load Validation and Sign-off | 31.48 hrs | 2025-09-03 12:53 | 2025-09-04 20:26 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Viktoria Kormanikova; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat; Ramesh SathishKumar; Andrea Ludeke; Tobias Wilmering; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Avinash Puranik; Satyajit; Riepe Joëlle | viktoria.kormanikova@sk.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de; satramesh@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; avpuranik@deloitte.com; sapatnaik@deloitte.com; Joelle.Riepe@de.sasol.com | P2C | 19562 | 2025-09-03 12:53 | 2025-09-04 20:26 | * | NA | 2025-09-03 12:53 | 2025-09-04 20:26
19564 | STRIVE.R2.MC1.2384.1277.1.1.139 | [5 empty] | Material master data load | 840.39 hrs | 2025-08-11 08:00 | 2025-09-15 10:43 | [6 empty] | 2025-07-18 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-09-15 10:43
19590 | STRIVE.R2.MC1.2384.1277.1.1.139.88 | Y | Y | Y | Complete |  | Material Master Provide list of active Materials to MDG for Description Updates before Load Cycle | 12 hrs | 2025-08-11 08:00 | 2025-08-12 12:00 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda | sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com | DM |  | 2025-08-11 08:00 | 2025-08-12 12:00 | * | NA | 2025-08-11 08:00 | 2025-08-12 12:00
19565 | STRIVE.R2.MC1.2384.1277.1.1.139.1 | [5 empty] | Material Master Transformation | 25.93 hrs | 2025-08-13 08:00 | 2025-08-14 10:00 | [6 empty] | 2025-08-12 08:07 | 2025-08-29 17:29 | * | NA | 2025-08-13 08:00 | 2025-08-14 10:00
19566 | STRIVE.R2.MC1.2384.1277.1.1.139.1.1 | Y | Y | Y | Complete |  | Material Master - ZFIN Transformation and share Pre-Load | 182.58 hrs | 2025-08-12 08:07 | 2025-08-19 23:11 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Jessica Goffi; Thomas Kokkindis; T. Junge; T. Hagen; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Timotej Šándor; Eva Bani; Zuzana Hlucha; Satyajit; Ines Tesch; Alex Miles; Jens Nissen; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Hans Jorg; Roman Mäkilä; Firat | Jessica.Goffi@it.sasol.com; Thomas.Kokkinidis@de.sasol.com; Tim.Junge@de.sasol.com; Torsten.Hagen@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hansjorg.becker@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19590 | 2025-08-12 08:07 | 2025-08-19 23:11 |  | 2025-08-13 09:00 | 2025-08-12 08:07 | 2025-08-19 23:11
19567 | STRIVE.R2.MC1.2384.1277.1.1.139.1.2 | Y | Y | Y | Complete |  | Material Master - ZRAW Transformation and share Pre-Load | 179.75 hrs | 2025-08-12 08:07 | 2025-08-19 20:21 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Maria Luisa Geremicca; Jana Valíková; Liviana Scaricabarozzi; ; Zuzana Hlucha; Eva Bani; Sabrina Agueli; Jark Hinrichsen; T. Junge; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Hans Jorg; Ines Tesch; Jens Nissen; Firat; Simonetta Confalonieri | marialuisa.geremicca@it.sasol.com; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; ; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Tim.Junge@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hansjorg.becker@de.sasol.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com | DM | 19590 | 2025-08-12 08:07 | 2025-08-19 20:21 | * | NA | 2025-08-12 08:07 | 2025-08-19 20:21
19568 | STRIVE.R2.MC1.2384.1277.1.1.139.1.3 | Y | Y | Y | Complete |  | Material Master - ZSFG Transformation and share Pre-Load | 180.09 hrs | 2025-08-12 08:07 | 2025-08-19 20:41 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Hans Jorg; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Firat; Ines Tesch; Jens Nissen | hansjorg.becker@de.sasol.com; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com | DM | 19590 | 2025-08-12 08:07 | 2025-08-19 20:41 | * | NA | 2025-08-12 08:07 | 2025-08-19 20:41
19569 | STRIVE.R2.MC1.2384.1277.1.1.139.1.4 | Y | Y | Y | Complete |  | Material Master - ZPKG Transformation and share Pre-Load | 201.48 hrs | 2025-08-12 08:07 | 2025-08-20 18:09 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Maria Luisa Geremicca; Liviana Scaricabarozzi; ; Timotej Šándor; Oliver Berg; T. Junge; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Jens Nissen; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hans Jorg; Firat; Simonetta Confalonieri | marialuisa.geremicca@it.sasol.com; liviana.scaricabarozzi@it.sasol.com; ; timotej.sandor@sk.sasol.com; oliver.berg@de.sasol.com; Tim.Junge@de.sasol.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com | DM | 19590 | 2025-08-12 08:07 | 2025-08-20 18:09 | * | NA | 2025-08-12 08:07 | 2025-08-20 18:09
19570 | STRIVE.R2.MC1.2384.1277.1.1.139.1.5 | Y | Y | Y | Complete |  | Material Master - ZOPS Transformation and share Pre-Load | 204.16 hrs | 2025-08-12 08:07 | 2025-08-20 20:50 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Hans Jorg; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Eva Bani; Zuzana Hlucha; Sandrika Chetty; Martin Stoffers; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat | hansjorg.becker@de.sasol.com; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19590 | 2025-08-12 08:07 | 2025-08-20 20:50 | * | NA | 2025-08-12 08:07 | 2025-08-20 20:50
19571 | STRIVE.R2.MC1.2384.1277.1.1.139.1.6 | Y | Y | Y | Complete |  | Material Master - ZCAT Transformation and share Pre-Load | 196.85 hrs | 2025-08-12 08:07 | 2025-08-20 13:31 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Maria Luisa Geremicca; Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Renate Losemann; Sascha Leysner; T. Junge; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat | marialuisa.geremicca@it.sasol.com; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; Renate.Losemann@de.sasol.com; Sascha.Leysner@de.sasol.com; Tim.Junge@de.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19590 | 2025-08-12 08:07 | 2025-08-20 13:31 | * | NA | 2025-08-12 08:07 | 2025-08-20 13:31
19572 | STRIVE.R2.MC1.2384.1277.1.1.139.1.7 | Y | Y | Y | Complete |  | Material Master - ZMAG Transformation and share Pre-Load | 178.68 hrs | 2025-08-12 12:01 | 2025-08-19 23:10 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Sven Gelking; Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Hans Jorg; Firat; Ines Tesch; Jens Nissen | sven.gelking@de.sasol.com; Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com | DM | 19590 | 2025-08-12 12:01 | 2025-08-19 23:10 |  | 2025-08-12 08:07 | 2025-08-12 12:01 | 2025-08-19 23:10
21170 | STRIVE.R2.MC1.2384.1277.1.1.139.1.12 | Y | Y | Y | Complete |  | Material Master - ZMAS Transformation and share Pre-Load | 2.97 hrs | 2025-08-12 08:07 | 2025-08-12 11:05 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Sven Gelking; Kim Borkenstein; Andre Harders; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Hans Jorg; Firat; Ines Tesch | sven.gelking@de.sasol.com; Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | DM | 19590 | 2025-08-12 08:07 | 2025-08-12 11:05 | * | NA | 2025-08-12 08:07 | 2025-08-12 11:05
21168 | STRIVE.R2.MC1.2384.1277.1.1.139.1.10 | Y | Y | Y | Complete |  | Material Master - ZRDS Transformation and share Pre-Load | 175.99 hrs | 2025-08-12 08:07 | 2025-08-19 16:35 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Hans Jorg; Jochen Kühl; Bruno van der Valk; Thomas Kokkindis; Stella Hatkova; Satyajit; Roman Mäkilä; Alex Miles; Ines Tesch; Jens Nissen; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Firat | hansjorg.becker@de.sasol.com; Jochen.Kuehl@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; stella.hatkova@sk.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; firat.cetin@consultary.de | DM | 19590 | 2025-08-12 08:07 | 2025-08-19 16:35 | * | NA | 2025-08-12 08:07 | 2025-08-19 16:35
19573 | STRIVE.R2.MC1.2384.1277.1.1.139.1.8 | Y | Y | Y | Complete |  | Validate Material Group XREF - S2P | 389.36 hrs | 2025-08-13 08:00 | 2025-08-29 14:27 | Prasanth | kalprasanth@deloitte.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Maria Luisa Geremicca; S2P Team; Sandeep Galhotra; Milton; Esmir Divljanovic | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; marialuisa.geremicca@it.sasol.com; usisasols2p@deloitte.com; sagalhotra@deloitte.com; miltjones@deloitte.com; edivljanovic@deloitte.de | S2P |  | 2025-08-13 08:00 | 2025-08-29 14:27 | * | NA | 2025-08-13 08:00 | 2025-08-29 14:27
19574 | STRIVE.R2.MC1.2384.1277.1.1.139.1.9 | Y | Y | Y | Complete |  | Provide Pre-Load files to IBP for MRP View Update | 0 hrs | 2025-08-29 17:29 | 2025-08-29 17:29 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit Patnaik; Sandrilka; Rajat Sahgal | roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; sandrika.chetty@sasol.com; rasahgal@deloitte.com | DM | 19566,19567,19568,19569,19570,19571,19572 | 2025-08-29 17:29 | 2025-08-29 17:29 | * | NA | 2025-08-29 17:29 | 2025-08-29 17:29
19575 | STRIVE.R2.MC1.2384.1277.1.1.139.11 | [5 empty] | Material Master Pre-Load Validation and Sign-off | 97.68 hrs | 2025-07-14 08:00 | 2025-07-18 09:57 | [6 empty] | 2025-08-12 11:05 |  | * | NA | 2025-07-14 08:00 | 2025-07-18 09:57
19576 | STRIVE.R2.MC1.2384.1277.1.1.139.11.1 | Y | Y | N | In-Progress |  | Material Master - ZFIN Pre-Load Validation Cross Stream Views - MDG | 4 hrs | 2025-09-01 17:21 | 2025-09-01 21:21 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Thomas Kokkindis; T. Junge; T. Hagen; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Timotej Šándor; Eva Bani; Zuzana Hlucha; Ramesh SathishKumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Firat; Ines Tesch; Bruno van der Valk | Thomas.Kokkinidis@de.sasol.com; Tim.Junge@de.sasol.com; Torsten.Hagen@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; satramesh@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com; Bruno.vanderValk@de.sasol.com | Cross-team | 19566 | 2025-09-01 17:21 |  |  | 2025-08-13 08:00 | 2025-09-01 17:21 | 2025-09-01 21:21
19577 | STRIVE.R2.MC1.2384.1277.1.1.139.11.2 | Y | Y | Y | Complete |  | Material Master - ZRAW Pre-Load Validation Cross Stream Views - MDG | 78.5 hrs | 2025-09-01 13:42 | 2025-09-04 20:24 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Zuzana Hlucha; Eva Bani; Sabrina Agueli; Jark Hinrichsen; T. Junge; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Jessica Goffi; Hans Jorg; Hendrik Kamsteeg; Savri Sumeet Jagatap; Ramesh SathishKumar; Esmir Divljanovic; Frank Toedter ; Tina Vidrine; Firat; Ines Tesch | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Tim.Junge@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Jessica.Goffi@it.sasol.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; ssumeetjagatap@deloitte.com; satramesh@deloitte.com; edivljanovic@deloitte.de; ft@toedter-consult.de; tina.vidrine@us.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19567 | 2025-09-01 13:42 | 2025-09-04 20:24 | * | NA | 2025-09-01 13:42 | 2025-09-04 20:24
19578 | STRIVE.R2.MC1.2384.1277.1.1.139.11.3 | Y | Y | Y | Complete |  | Material Master - ZSFG Pre-Load Validation Cross Stream Views - MDG | 477.48 hrs | 2025-08-20 18:32 | 2025-09-09 17:21 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Jessica Goffi; Maria Luisa Geremicca; Hendrik Kamsteeg; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Savri Sumeet Jagatap; Ramesh SathishKumar; Alex Miles; Satyajit; Roman Mäkilä; Torsten Freydt; Firat; Ines Tesch | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; Jessica.Goffi@it.sasol.com; marialuisa.geremicca@it.sasol.com; hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ssumeetjagatap@deloitte.com; satramesh@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19568 | 2025-08-20 18:32 | 2025-09-09 17:21 | * | NA | 2025-08-20 18:32 | 2025-09-09 17:21
19579 | STRIVE.R2.MC1.2384.1277.1.1.139.11.4 | Y | Y | Y | Complete |  | Material Master - ZPKG Pre-Load Validation Cross Stream Views - MDG | 361.27 hrs | 2025-08-20 18:09 | 2025-09-04 20:25 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Liviana Scaricabarozzi; Simonetta Confalonieri; Timotej Šándor; Oliver Berg; T. Junge; Hans Jorg; Hendrik Kamsteeg; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Jessica Goffi; Ramesh SathishKumar; Esmir Divljanovic; Tina Vidrine; Frank Toedter ; Firat; Ines Tesch | liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; timotej.sandor@sk.sasol.com; oliver.berg@de.sasol.com; Tim.Junge@de.sasol.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; Jessica.Goffi@it.sasol.com; satramesh@deloitte.com; edivljanovic@deloitte.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19569 | 2025-08-20 18:09 | 2025-09-04 20:25 | * | NA | 2025-08-20 18:09 | 2025-09-04 20:25
19580 | STRIVE.R2.MC1.2384.1277.1.1.139.11.5 | Y | Y | Y | Complete |  | Material Master - ZOPS Pre-Load Validation Cross Stream Views - MDG | 6.19 hrs | 2025-08-22 12:34 | 2025-08-22 18:46 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Eva Bani; Zuzana Hlucha; Sandrika Chetty; Martin Stoffers; Roman Mäkilä; Alex Miles; Satyajit; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Hendrik Kamsteeg; Maria Luisa Geremicca; Torsten Freydt; Firat; Ines Tesch | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; hendrik.kamsteeg@de.sasol.com; marialuisa.geremicca@it.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19570 | 2025-08-22 12:34 | 2025-08-22 18:46 | * | NA | 2025-08-22 12:34 | 2025-08-22 18:46
19581 | STRIVE.R2.MC1.2384.1277.1.1.139.11.6 | Y | Y | Y | Complete |  | Material Master - ZCAT Pre-Load Validation Cross Stream Views - MDG | 117.48 hrs | 2025-08-27 16:09 | 2025-09-01 13:58 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Renate Losemann; Sascha Leysner; T. Junge; Jessica Goffi; Hans Jorg; Hendrik Kamsteeg; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Roman Mäkilä; Alex Miles; Satyajit; Savri Sumeet Jagatap; Ramesh SathishKumar; Esmir Divljanovic; Tina Vidrine; Frank Toedter ; Firat; Ines Tesch | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; Renate.Losemann@de.sasol.com; Sascha.Leysner@de.sasol.com; Tim.Junge@de.sasol.com; Jessica.Goffi@it.sasol.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; satramesh@deloitte.com; edivljanovic@deloitte.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19571 | 2025-08-27 16:09 | 2025-09-01 13:58 | * | NA | 2025-08-27 16:09 | 2025-09-01 13:58
19582 | STRIVE.R2.MC1.2384.1277.1.1.139.11.7 | Y | Y | Y | Complete |  | Material Master - ZMAG Pre-Load Validation Cross Stream Views - MDG | 464.83 hrs | 2025-08-19 23:10 | 2025-09-08 09:19 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Joseph Barber; Firat; Maria Luisa Geremicca; Hans Jorg; Hendrik Kamsteeg; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Roman Mäkilä; Satyajit; Savri Sumeet Jagatap; Ines Tesch | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; marialuisa.geremicca@it.sasol.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com | Cross-team | 19572,77618 | 2025-08-19 23:10 | 2025-09-08 09:19 | * | NA | 2025-08-19 23:10 | 2025-09-08 09:19
21173 | STRIVE.R2.MC1.2384.1277.1.1.139.11.19 | Y | Y | Y | Complete |  | Material Master - ZMAS Pre-Load Validation Cross Stream Views - MDG | 482.02 hrs | 2025-08-12 11:05 | 2025-09-01 14:28 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Joseph Barber; Firat; Maria Luisa Geremicca; Hans Jorg; Hendrik Kamsteeg; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Roman Mäkilä; Satyajit; Savri Sumeet Jagatap; Ines Tesch | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; marialuisa.geremicca@it.sasol.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com | Cross-team | 21170 | 2025-08-12 11:05 | 2025-09-01 14:28 | * | NA | 2025-08-12 11:05 | 2025-09-01 14:28
21171 | STRIVE.R2.MC1.2384.1277.1.1.139.11.17 | Y | Y | Y | Complete |  | Material Master - ZRDS Pre-Load Validation Cross Stream Views - MDG | 2.75 hrs | 2025-08-21 15:00 | 2025-08-21 17:45 | Hans Jorg | hansjorg.becker@de.sasol.com | Jochen Kühl; Bruno van der Valk; Thomas Kokkindis; Stella Hatkova; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roman Mäkilä; Alex Miles; Satyajit; Savri Sumeet Jagatap; Torsten Freydt; Firat; Ines Tesch | Jochen.Kuehl@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; stella.hatkova@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 21168 | 2025-08-21 15:00 | 2025-08-21 17:45 | * | NA | 2025-08-21 15:00 | 2025-08-21 17:45
19583 | STRIVE.R2.MC1.2384.1277.1.1.139.11.8 | Y | Y | Y | Complete |  | Material Master - ZFIN Pre-Load Validation and Sign-off | 0.95 hrs | 2025-08-22 14:39 | 2025-08-22 15:36 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Thomas Kokkindis; T. Junge; T. Hagen; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Timotej Šándor; Eva Bani; Zuzana Hlucha; Ramesh SathishKumar; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Savri Sumeet Jagatap; Francesco Garofalo; Sonia Scarpanti; Christian Canale; Clara Mori; Firat; Ines Tesch | Thomas.Kokkinidis@de.sasol.com; Tim.Junge@de.sasol.com; Torsten.Hagen@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; satramesh@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ssumeetjagatap@deloitte.com; francesco.garofalo@it.sasol.com; sonia.scarpanti@it.sasol.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19566 | 2025-08-22 14:39 | 2025-08-22 15:36 | * | NA | 2025-08-22 14:39 | 2025-08-22 15:36
19584 | STRIVE.R2.MC1.2384.1277.1.1.139.11.9 | Y | Y | Y | Complete |  | Material Master - ZRAW Pre-Load Validation and Sign-off | 134.72 hrs | 2025-08-19 20:21 | 2025-08-25 11:27 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Zuzana Hlucha; Eva Bani; Sabrina Agueli; Jark Hinrichsen; T. Junge; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Jessica Goffi; Ramesh SathishKumar; Hans Jorg; Hendrik Kamsteeg; Ines Tesch; Christian Canale; Clara Mori; Esmir Divljanovic; Tina Vidrine; Frank Toedter ; Firat | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Tim.Junge@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; Jessica.Goffi@it.sasol.com; satramesh@deloitte.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; ines.tesch@de.sasol.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; edivljanovic@deloitte.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; firat.cetin@consultary.de | Cross-team | 19567 | 2025-08-19 20:21 | 2025-08-25 11:27 | * | NA | 2025-08-19 20:21 | 2025-08-25 11:27
19585 | STRIVE.R2.MC1.2384.1277.1.1.139.11.10 | Y | Y | Y | Complete |  | Material Master - ZSFG Pre-Load Validation and Sign-off | 1.9 hrs | 2025-09-01 12:44 | 2025-09-01 14:38 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roman Mäkilä; Alex Miles; Satyajit; Savri Sumeet Jagatap; Jessica Goffi; Maria Luisa Geremicca; Hendrik Kamsteeg; Ramesh SathishKumar; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Clara Mori; Christian Canale; Torsten Freydt; Firat; Ines Tesch | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jessica.Goffi@it.sasol.com; marialuisa.geremicca@it.sasol.com; hendrik.kamsteeg@de.sasol.com; satramesh@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; clara.mori@it.sasol.com; christian.canale@it.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19568 | 2025-09-01 12:44 | 2025-09-01 14:38 |  | 2025-08-13 09:00 | 2025-09-01 12:44 | 2025-09-01 14:38
19586 | STRIVE.R2.MC1.2384.1277.1.1.139.11.11 | Y | Y | Y | Complete |  | Material Master - ZPKG Pre-Load Validation and Sign-off | 1.16 hrs | 2025-08-28 14:25 | 2025-08-28 15:34 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Liviana Scaricabarozzi; Simonetta Confalonieri; Timotej Šándor; Oliver Berg; T. Junge; Savri Sumeet Jagatap; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Alex Miles; Satyajit; Hans Jorg; Hendrik Kamsteeg; Ramesh SathishKumar; Jessica Goffi; Ines Tesch; Christian Canale; Clara Mori; Esmir Divljanovic; Tina Vidrine; Frank Toedter ; Firat | liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; timotej.sandor@sk.sasol.com; oliver.berg@de.sasol.com; Tim.Junge@de.sasol.com; ssumeetjagatap@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; satramesh@deloitte.com; Jessica.Goffi@it.sasol.com; ines.tesch@de.sasol.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; edivljanovic@deloitte.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; firat.cetin@consultary.de | Cross-team | 19569 | 2025-08-28 14:25 | 2025-08-28 15:34 | * | NA | 2025-08-28 14:25 | 2025-08-28 15:34
19587 | STRIVE.R2.MC1.2384.1277.1.1.139.11.12 | Y | Y | Y | Complete |  | Material Master - ZOPS Pre-Load Validation and Sign-off | 6.18 hrs | 2025-08-22 12:35 | 2025-08-22 18:46 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Eva Bani; Zuzana Hlucha; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Savri Sumeet Jagatap; Maria Luisa Geremicca; Hendrik Kamsteeg; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat; Ines Tesch | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ssumeetjagatap@deloitte.com; marialuisa.geremicca@it.sasol.com; hendrik.kamsteeg@de.sasol.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19570 | 2025-08-22 12:35 | 2025-08-22 18:46 | * | NA | 2025-08-22 12:35 | 2025-08-22 18:46
19588 | STRIVE.R2.MC1.2384.1277.1.1.139.11.13 | Y | Y | Y | Complete |  | Material Master - ZCAT Pre-Load Validation and Sign-off | 119.4 hrs | 2025-08-20 13:31 | 2025-08-25 13:15 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Renate Losemann; Sascha Leysner; T. Junge; Savri Sumeet Jagatap; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Jessica Goffi; Hans Jorg; Hendrik Kamsteeg; Ramesh SathishKumar; Maria Rita Cavalloni; Anna Bellia; Ines Tesch; Clara Mori; Christian Canale; Roman Mäkilä; Alex Miles; Satyajit; Esmir Divljanovic; Tina Vidrine; Frank Toedter ; Firat | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; Renate.Losemann@de.sasol.com; Sascha.Leysner@de.sasol.com; Tim.Junge@de.sasol.com; ssumeetjagatap@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; Jessica.Goffi@it.sasol.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; satramesh@deloitte.com; mariarita.cavalloni@it.sasol.com; ; ines.tesch@de.sasol.com; clara.mori@it.sasol.com; christian.canale@it.sasol.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; edivljanovic@deloitte.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; firat.cetin@consultary.de | Cross-team | 19571 | 2025-08-20 13:31 | 2025-08-25 13:15 | * | NA | 2025-08-20 13:31 | 2025-08-25 13:15
19589 | STRIVE.R2.MC1.2384.1277.1.1.139.11.14 | Y | Y | Y | Complete |  | Material Master - ZMAG Pre-Load Validation and Sign-off | 0.66 hrs | 2025-08-20 14:07 | 2025-08-20 14:47 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Jay Patel; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Abhishek Sharma; Savri Sumeet Jagatap; Chaitnya; Firat; Ines Tesch | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; jaypatel6@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; abhisheksharma59@deloitte.com; ssumeetjagatap@deloitte.com; csudhakarraut@deloitte.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 19572 | 2025-08-20 14:07 | 2025-08-20 14:47 | * | NA | 2025-08-20 14:07 | 2025-08-20 14:47
21176 | STRIVE.R2.MC1.2384.1277.1.1.139.11.22 | Y | Y | Y | Complete |  | Material Master - ZMAS Pre-Load Validation and Sign-off | 576.27 hrs | 2025-08-12 11:05 | 2025-09-05 12:59 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Jay Patel; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Abhishek Sharma; Savri Sumeet Jagatap; Chaitnya; Firat; Ines Tesch | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; jaypatel6@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; abhisheksharma59@deloitte.com; ssumeetjagatap@deloitte.com; csudhakarraut@deloitte.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 21170 | 2025-08-12 11:05 | 2025-09-05 12:59 | * | NA | 2025-08-12 11:05 | 2025-09-05 12:59
21174 | STRIVE.R2.MC1.2384.1277.1.1.139.11.20 | Y | Y | Y | Complete |  | Material Master - ZRDS Pre-Load Validation and Sign-off | 49.09 hrs | 2025-08-19 16:35 | 2025-08-21 17:49 | Hans Jorg | hansjorg.becker@de.sasol.com | Jochen Kühl; Bruno van der Valk; Thomas Kokkindis; Stella Hatkova; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Torsten Freydt; Firat; Ines Tesch | Jochen.Kuehl@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; stella.hatkova@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com | Cross-team | 21168 | 2025-08-19 16:35 | 2025-08-21 17:49 | * | NA | 2025-08-19 16:35 | 2025-08-21 17:49
19592 | STRIVE.R2.MC1.2384.1277.1.1.139.28 | [5 empty] | Material Master Load into MDG | 319.97 hrs | 2025-07-18 08:00 | 2025-07-31 16:51 | [6 empty] | 2025-07-18 08:00 |  | * | NA | 2025-07-18 08:00 | 2025-07-31 16:51
19593 | STRIVE.R2.MC1.2384.1277.1.1.139.28.1 | Y | Y | Y | Complete |  | Material Master: Provide File from R2P EHS to DM for Assignment of Label Data to ZFIN | 1105.84 hrs | 2025-07-18 08:00 | 2025-09-02 12:55 | Hans Jorg | hansjorg.becker@de.sasol.com | Savri Sumeet Jagatap; Roman Mäkilä; Satyajit; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Torsten Freydt; Jay Saini; Firat | ssumeetjagatap@deloitte.com; roman.makila@deloitte.fi; sapatnaik@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; Torsten.Freydt-Olek@de.sasol.com; jaysaini4@deloitte.com; firat.cetin@consultary.de | R2P |  | 2025-07-18 08:00 | 2025-09-02 12:55 | * | NA | 2025-07-18 08:00 | 2025-09-02 12:55
19594 | STRIVE.R2.MC1.2384.1277.1.1.139.28.2 | N | N | N | Ready |  | Undeploy the Iflow - MDG_I_180 | 4 hrs | 2025-08-22 15:36 | 2025-08-22 19:36 | Yashwanth | myakumar@deloitte.com | Naga; ; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | nnagasubbareddy@deloitte.com; ; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration | 19583 |  |  |  | 2025-08-18 09:00 | 2025-08-22 15:36 | 2025-08-22 19:36
19595 | STRIVE.R2.MC1.2384.1277.1.1.139.28.3 | Y | Y | Y | Complete |  | Material Master - ZFIN Load into MDG and share Post-Load | 64.65 hrs | 2025-08-22 19:36 | 2025-08-25 12:27 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Jessica Goffi; Thomas Kokkindis; T. Junge; T. Hagen; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Timotej Šándor; Eva Bani; Zuzana Hlucha; Ines Tesch; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roman Mäkilä; Satyajit; Alex Miles; Jens Nissen; Firat | Jessica.Goffi@it.sasol.com; Thomas.Kokkinidis@de.sasol.com; Tim.Junge@de.sasol.com; Torsten.Hagen@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; sapatnaik@deloitte.com; almiles@deloitte.de; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19594 | 2025-08-22 19:36 | 2025-08-25 12:27 |  | 2025-08-18 08:00 | 2025-08-22 19:36 | 2025-08-25 12:27
19597 | STRIVE.R2.MC1.2384.1277.1.1.139.28.5 | Y | Y | Y | Complete |  | Material Master - ZRAW Load into MDG and share Post-Load | 132.28 hrs | 2025-08-20 00:23 | 2025-08-25 13:02 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Jessica Goffi; Thomas Kokkindis; T. Junge; T. Hagen; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Timotej Šándor; Eva Bani; Zuzana Hlucha; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Jens Nissen; Alex Miles; Satyajit; Roman Mäkilä; Mousikta chanda; Firat | Jessica.Goffi@it.sasol.com; Thomas.Kokkinidis@de.sasol.com; Tim.Junge@de.sasol.com; Torsten.Hagen@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 19584 | 2025-08-20 00:23 | 2025-08-25 13:02 |  | 2025-08-18 11:00 | 2025-08-20 00:23 | 2025-08-25 13:02
19599 | STRIVE.R2.MC1.2384.1277.1.1.139.28.7 | Y | Y | Y | Complete |  | Material Master - ZSFG Load into MDG and share Post-Load | 131.38 hrs | 2025-08-20 00:43 | 2025-08-25 12:28 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Hans Jorg; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Roman Mäkilä; Alex Miles; Satyajit; Ines Tesch; Jens Nissen; Firat | hansjorg.becker@de.sasol.com; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19585 | 2025-08-20 00:43 | 2025-08-25 12:28 |  | 2025-08-18 11:00 | 2025-08-20 00:43 | 2025-08-25 12:28
19600 | STRIVE.R2.MC1.2384.1277.1.1.139.28.8 | Y | Y | Y | Complete |  | Material Master - ZPKG Load into MDG and share Post-Load | 64.2 hrs | 2025-08-22 20:45 | 2025-08-25 13:09 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Maria Luisa Geremicca; Liviana Scaricabarozzi; Simonetta Confalonieri; Timotej Šándor; Oliver Berg; T. Junge; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roman Mäkilä; Alex Miles; Satyajit; Ines Tesch; Jens Nissen; Firat | marialuisa.geremicca@it.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; timotej.sandor@sk.sasol.com; oliver.berg@de.sasol.com; Tim.Junge@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19586 | 2025-08-22 20:45 | 2025-08-25 13:09 |  | 2025-08-18 11:00 | 2025-08-22 20:45 | 2025-08-25 13:09
19601 | STRIVE.R2.MC1.2384.1277.1.1.139.28.9 | Y | Y | Y | Complete |  | Material Master - ZOPS Load into MDG and share Post-Load | 66.14 hrs | 2025-08-22 12:02 | 2025-08-25 13:06 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Hans Jorg; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas Kokkindis; Timotej Šándor; Eva Bani; Zuzana Hlucha; Sandrika Chetty; Martin Stoffers; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roman Mäkilä; Alex Miles; Satyajit; Ines Tesch; Jens Nissen; Firat | hansjorg.becker@de.sasol.com; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19587 | 2025-08-22 12:02 | 2025-08-25 13:06 |  | 2025-08-18 11:00 | 2025-08-22 12:02 | 2025-08-25 13:06
19602 | STRIVE.R2.MC1.2384.1277.1.1.139.28.10 | Y | Y | Y | Complete |  | Material Master - ZCAT Load into MDG and share Post-Load | 114.62 hrs | 2025-08-20 17:31 | 2025-08-25 12:28 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Maria Luisa Geremicca; Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Renate Losemann; Sascha Leysner; T. Junge; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Ines Tesch; Jens Nissen; Firat | marialuisa.geremicca@it.sasol.com; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; Renate.Losemann@de.sasol.com; Sascha.Leysner@de.sasol.com; Tim.Junge@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19588 | 2025-08-20 17:31 | 2025-08-25 12:28 |  | 2025-08-18 11:00 | 2025-08-20 17:31 | 2025-08-25 12:28
19603 | STRIVE.R2.MC1.2384.1277.1.1.139.28.11 | Y | Y | Y | Complete |  | Material Master - ZMAG Load into MDG and share Post-Load | 191.27 hrs | 2025-08-20 14:47 | 2025-08-28 14:35 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Sven Gelking; Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Ines Tesch; Jens Nissen; Firat | sven.gelking@de.sasol.com; Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 19589 | 2025-08-20 14:47 | 2025-08-28 14:35 |  | 2025-08-18 11:00 | 2025-08-20 14:47 | 2025-08-28 14:35
21179 | STRIVE.R2.MC1.2384.1277.1.1.139.28.17 | Y | Y | Y | Complete |  | Material Master - ZMAS Load into MDG and share Post-Load | 41.18 hrs | 2025-08-23 19:57 | 2025-08-25 13:16 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Sven Gelking; Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Ines Tesch; Jens Nissen; Firat | sven.gelking@de.sasol.com; Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 21173,21176 | 2025-08-23 19:57 | 2025-08-25 13:16 |  | 2025-08-18 11:00 | 2025-08-23 19:57 | 2025-08-25 13:16
21177 | STRIVE.R2.MC1.2384.1277.1.1.139.28.15 | Y | Y | Y | Complete |  | Material Master - ZRDS Load into MDG and share Post-Load | 120.72 hrs | 2025-08-21 17:49 | 2025-08-26 18:52 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Sven Gelking; Roman Mäkilä; Satyajit; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat | sven.gelking@de.sasol.com; roman.makila@deloitte.fi; sapatnaik@deloitte.com; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | DM | 21171,21174 | 2025-08-21 17:49 | 2025-08-26 18:52 |  | 2025-08-18 11:00 | 2025-08-21 17:49 | 2025-08-26 18:52
19604 | STRIVE.R2.MC1.2384.1277.1.1.139.28.12 | Y | N | N | Sent |  | Material Master Manually Create R2D ZSER and share Post-Load | 4 hrs | 2025-08-22 15:36 | 2025-08-22 19:36 | Tatiana | tvinogradova@deloitte.de | Hendrik Kamsteeg; Roshanlal Hemwani; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Satyajit; Roman Mäkilä | hendrik.kamsteeg@de.sasol.com; rohemwani@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | R2D | 19583 |  |  |  | 2025-07-18 08:00 | 2025-08-22 15:36 | 2025-08-22 19:36
19606 | STRIVE.R2.MC1.2384.1277.1.1.139.28.14 | Y | Y | Y | Complete |  | Material Master - Valuation prices - Provide V Prices extract of ECC prices to R2D - ZOPS, ZTEQ, ZMAG | 24.97 hrs | 2025-08-28 14:35 | 2025-08-29 15:37 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Alexandra Ruff; Hendrik Kamsteeg; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda; Alex Miles; Satyajit | aruff@deloitte.de; hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com | DM | 19595,19597,19599,19600,19601,19602,19603 | 2025-08-28 14:35 | 2025-08-29 15:37 |  | 2025-07-18 08:00 | 2025-08-28 14:35 | 2025-08-29 15:37
19607 | STRIVE.R2.MC1.2384.1277.1.1.139.43 | [5 empty] | Material Master Post-Load Validation and Sign-off- MDG | 123.67 hrs | 2025-07-18 08:00 | 2025-07-23 12:00 | [6 empty] | 2025-08-21 08:00 |  | * | NA | 2025-07-18 08:00 | 2025-07-23 12:00
19608 | STRIVE.R2.MC1.2384.1277.1.1.139.43.1 | Y | N | N | Sent |  | Material Master - ZFIN Post-Load Validation Cross Stream Views - MDG | 4 hrs | 2025-08-25 12:27 | 2025-08-25 16:27 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Thomas; T. Junge; T. Hagen; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Timotej Šándor; Eva Bani; Zuzana Hlucha; Savri Sumeet Jagatap; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Hans Jorg; Firat | Thomas.Kokkinidis@de.sasol.com; Tim.Junge@de.sasol.com; Torsten.Hagen@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | Cross-team | 19595 |  |  |  | 2025-08-21 02:00 | 2025-08-25 12:27 | 2025-08-25 16:27
19609 | STRIVE.R2.MC1.2384.1277.1.1.139.43.2 | Y | Y | N | In-Progress |  | Material Master - ZRAW Post-Load Validation Cross Stream Views - MDG | 4 hrs | 2025-09-01 14:33 | 2025-09-01 18:33 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Zuzana Hlucha; Eva Bani; Sabrina Agueli; Jark Hinrichsen; T. Junge; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Roman Mäkilä; Firat; Savri Sumeet Jagatap; Hans Jorg; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Tim.Junge@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; ssumeetjagatap@deloitte.com; hansjorg.becker@de.sasol.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | Cross-team | 19597 | 2025-09-01 14:33 |  |  | 2025-08-21 08:00 | 2025-09-01 14:33 | 2025-09-01 18:33
19610 | STRIVE.R2.MC1.2384.1277.1.1.139.43.3 | Y | Y | Y | Complete |  | Material Master - ZSFG Post-Load Validation Cross Stream Views - MDG | 65.87 hrs | 2025-08-25 17:32 | 2025-08-28 11:35 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | Cross-team | 19599 | 2025-08-25 17:32 | 2025-08-28 11:35 |  | 2025-08-21 08:00 | 2025-08-25 17:32 | 2025-08-28 11:35
19611 | STRIVE.R2.MC1.2384.1277.1.1.139.43.4 | Y | Y | N | In-Progress |  | Material Master - ZPKG Post-Load Validation Cross Stream Views - MDG | 4 hrs | 2025-09-01 14:33 | 2025-09-01 18:33 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Liviana Scaricabarozzi; Simonetta Confalonieri; Timotej Šándor; Oliver Berg; T. Junge; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; timotej.sandor@sk.sasol.com; oliver.berg@de.sasol.com; Tim.Junge@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | Cross-team | 19600 | 2025-09-01 14:33 |  |  | 2025-08-21 08:00 | 2025-09-01 14:33 | 2025-09-01 18:33
19612 | STRIVE.R2.MC1.2384.1277.1.1.139.43.5 | Y | Y | Y | Complete |  | Material Master - ZOPS Post-Load Validation Cross Stream Views - MDG | 5.9 hrs | 2025-08-28 12:03 | 2025-08-28 17:57 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Eva Bani; Zuzana Hlucha; Sandrika Chetty; Martin Stoffers; Savri Sumeet Jagatap; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; ssumeetjagatap@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | Cross-team | 19601 | 2025-08-28 12:03 | 2025-08-28 17:57 |  | 2025-08-21 08:00 | 2025-08-28 12:03 | 2025-08-28 17:57
19613 | STRIVE.R2.MC1.2384.1277.1.1.139.43.6 | Y | Y | Y | Complete |  | Material Master - ZCAT Post-Load Validation Cross Stream Views - MDG | 197.43 hrs | 2025-09-01 14:34 | 2025-09-09 20:32 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Renate Losemann; Sascha Leysner; T. Junge; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Hans Jorg; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; Renate.Losemann@de.sasol.com; Sascha.Leysner@de.sasol.com; Tim.Junge@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; hansjorg.becker@de.sasol.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | Cross-team | 19602 | 2025-09-01 14:34 | 2025-09-09 20:32 |  | 2025-08-21 08:00 | 2025-09-01 14:34 | 2025-09-09 20:32
19614 | STRIVE.R2.MC1.2384.1277.1.1.139.43.7 | Y | N | N | Sent |  | Material Master - ZMAG Post-Load Validation Cross Stream Views - MDG | 4 hrs | 2025-08-28 14:35 | 2025-08-28 18:35 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Hans Jorg; Firat | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | Cross-team | 19603 |  |  |  | 2025-08-21 08:00 | 2025-08-28 14:35 | 2025-08-28 18:35
21182 | STRIVE.R2.MC1.2384.1277.1.1.139.43.35 | Y | Y | Y | Complete |  | Material Master - ZMAS Post-Load Validation Cross Stream Views - MDG | 194.33 hrs | 2025-08-25 13:16 | 2025-09-02 16:07 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Hans Jorg; Firat | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | Cross-team | 21179 | 2025-08-25 13:16 | 2025-09-02 16:07 |  | 2025-08-21 08:00 | 2025-08-25 13:16 | 2025-09-02 16:07
21180 | STRIVE.R2.MC1.2384.1277.1.1.139.43.33 | Y | N | N | Sent |  | Material Master - ZRDS Post-Load Validation Cross Stream Views - MDG | 4 hrs | 2025-08-26 18:52 | 2025-08-26 22:52 | Hans Jorg | hansjorg.becker@de.sasol.com | Jochen Kühl; Bruno van der Valk; Thomas; Stella Hatkova; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Torsten Freydt; Firat | Jochen.Kuehl@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; stella.hatkova@sk.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | Cross-team | 21177 |  |  |  | 2025-08-21 08:00 | 2025-08-26 18:52 | 2025-08-26 22:52
19616 | STRIVE.R2.MC1.2384.1277.1.1.139.43.9 | Y | Y | Y | Complete |  | Material Master - ZFIN Post-Load Validation and Sign-off- MDG | 0.55 hrs | 2025-09-03 13:21 | 2025-09-03 13:53 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Thomas; T. Junge; T. Hagen; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Timotej Šándor; Eva Bani; Zuzana Hlucha; Ramesh SathishKumar; Francesco Garofalo; Sonia Scarpanti; Christian Canale; Clara Mori; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Ines Tesch; Jens Nissen; Savri Sumeet Jagatap; Firat | Thomas.Kokkinidis@de.sasol.com; Tim.Junge@de.sasol.com; Torsten.Hagen@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; satramesh@deloitte.com; francesco.garofalo@it.sasol.com; sonia.scarpanti@it.sasol.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | Cross-team | 19595 | 2025-09-03 13:21 | 2025-09-03 13:53 |  | 2025-08-21 08:00 | 2025-09-03 13:21 | 2025-09-03 13:53
19617 | STRIVE.R2.MC1.2384.1277.1.1.139.43.10 | Y | Y | Y | Complete |  | Material Master - ZRAW Post-Load Validation and Sign-off- MDG | 35.11 hrs | 2025-09-01 14:34 | 2025-09-03 01:46 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Zuzana Hlucha; Eva Bani; Sabrina Agueli; Jark Hinrichsen; T. Junge; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Michael Robertshaw; Marvin Jarocki; Birgit Rohde; Jessica Goffi; Hendrik Kamsteeg; Hans Jorg; Ramesh SathishKumar; ; Christian Canale; Clara Mori; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Satyajit; Savri Sumeet Jagatap; Roman Mäkilä; Alex Miles; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Tim.Junge@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Michael.Robertshaw@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; Jessica.Goffi@it.sasol.com; hendrik.kamsteeg@de.sasol.com; hansjorg.becker@de.sasol.com; satramesh@deloitte.com; ; christian.canale@it.sasol.com; clara.mori@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | Cross-team | 19597 | 2025-09-01 14:34 | 2025-09-03 01:46 |  | 2025-08-21 08:00 | 2025-09-01 14:34 | 2025-09-03 01:46
19619 | STRIVE.R2.MC1.2384.1277.1.1.139.43.12 | Y | Y | Y | Complete |  | Material Master - ZSFG Post-Load Validation and Sign-off- MDG | 45.69 hrs | 2025-08-25 17:33 | 2025-08-27 15:22 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Hendrik Kamsteeg; Maria Luisa Geremicca; Jessica Goffi; Ramesh SathishKumar; Vito Piscopiello; Carlo Lombardini; Salvatore Noto; Christian Canale; Clara Mori; Alex Miles; Roman Mäkilä; Satyajit; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Torsten Freydt; Firat | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; hendrik.kamsteeg@de.sasol.com; marialuisa.geremicca@it.sasol.com; Jessica.Goffi@it.sasol.com; satramesh@deloitte.com; vito.piscopiello@it.sasol.com; Carlo.Lombardini@it.sasol.com; salvatore.noto@it.sasol.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | Cross-team | 19599 | 2025-08-25 17:33 | 2025-08-27 15:22 |  | 2025-08-21 08:00 | 2025-08-25 17:33 | 2025-08-27 15:22
19620 | STRIVE.R2.MC1.2384.1277.1.1.139.43.13 | Y | Y | Y | Complete |  | Material Master - ZPKG Post-Load Validation and Sign-off- MDG | 36 hrs | 2025-09-01 14:34 | 2025-09-03 02:40 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Liviana Scaricabarozzi; Simonetta Confalonieri; Timotej Šándor; Oliver Berg; T. Junge; Hans Jorg; Hendrik Kamsteeg; Jessica Goffi; Ramesh SathishKumar; Christian Canale; Clara Mori; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; timotej.sandor@sk.sasol.com; oliver.berg@de.sasol.com; Tim.Junge@de.sasol.com; hansjorg.becker@de.sasol.com; hendrik.kamsteeg@de.sasol.com; Jessica.Goffi@it.sasol.com; satramesh@deloitte.com; christian.canale@it.sasol.com; clara.mori@it.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | Cross-team | 19600 | 2025-09-01 14:34 | 2025-09-03 02:40 |  | 2025-08-21 08:00 | 2025-09-01 14:34 | 2025-09-03 02:40
19621 | STRIVE.R2.MC1.2384.1277.1.1.139.43.14 | Y | Y | Y | Complete |  | Material Master - ZOPS Post-Load Validation and Sign-off- MDG | 5.89 hrs | 2025-08-28 12:04 | 2025-08-28 17:57 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Eva Bani; Zuzana Hlucha; Sandrika Chetty; Martin Stoffers; Firat; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roman Mäkilä; Alex Miles; Satyajit; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Salvatore Noto; Carlo Lombardini; Vito Piscopiello; Hendrik Kamsteeg; Maria Luisa Geremicca; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; firat.cetin@consultary.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; salvatore.noto@it.sasol.com; Carlo.Lombardini@it.sasol.com; vito.piscopiello@it.sasol.com; hendrik.kamsteeg@de.sasol.com; marialuisa.geremicca@it.sasol.com; Torsten.Freydt-Olek@de.sasol.com | Cross-team | 19601 | 2025-08-28 12:04 | 2025-08-28 17:57 |  | 2025-08-21 08:00 | 2025-08-28 12:04 | 2025-08-28 17:57
19622 | STRIVE.R2.MC1.2384.1277.1.1.139.43.15 | Y | Y | Y | Complete |  | Material Master - ZCAT Post-Load Validation and Sign-off- MDG | 0 hrs | 2025-09-01 14:29 | 2025-09-01 14:29 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Renate Losemann; Sascha Leysner; T. Junge; Alex Miles; Satyajit; Savri Sumeet Jagatap; Roman Mäkilä; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Hans Jorg; Firat; Jessica Goffi; Hendrik Kamsteeg; Ramesh SathishKumar; Maria Rita Cavalloni; Anna Bellia; Christian Canale; Clara Mori; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; Renate.Losemann@de.sasol.com; Sascha.Leysner@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; hendrik.kamsteeg@de.sasol.com; satramesh@deloitte.com; mariarita.cavalloni@it.sasol.com; ; christian.canale@it.sasol.com; clara.mori@it.sasol.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | Cross-team | 19602 | 2025-09-01 14:29 | 2025-09-01 14:29 |  | 2025-08-21 08:00 | 2025-09-01 14:29 | 2025-09-01 14:29
19623 | STRIVE.R2.MC1.2384.1277.1.1.139.43.16 | Y | Y | N | In-Progress |  | Material Master - ZMAG Post-Load Validation and Sign-off- MDG | 171.91 hrs | 2025-08-21 08:00 | 2025-08-28 12:23 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Savri Sumeet Jagatap; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Hans Jorg; Joseph Barber; Firat | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; hansjorg.becker@de.sasol.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de | Cross-team |  | 2025-08-21 08:00 | 2025-08-28 12:23 |  | 2025-08-21 08:00 | 2025-08-21 08:00 | 2025-08-28 12:23
21186 | STRIVE.R2.MC1.2384.1277.1.1.139.43.39 | Y | N | N | Sent |  | Material Master - ZMAS Post-Load Validation and Sign-off- MDG | 4 hrs | 2025-08-25 13:16 | 2025-08-25 17:16 | Sven Gelking | sven.gelking@de.sasol.com | Kim Borkenstein; Andre Harders; T. Junge; Vieroslav Kratky; Savri Sumeet Jagatap; Satyajit; Roman Mäkilä; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Firat | Kim.Borkenstein@de.sasol.com; Andre.Harders@de.sasol.com; Tim.Junge@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de | Cross-team | 21179 |  |  |  | 2025-08-21 08:00 | 2025-08-25 13:16 | 2025-08-25 17:16
21183 | STRIVE.R2.MC1.2384.1277.1.1.139.43.36 | Y | N | N | Sent |  | Material Master - ZRDS Post-Load Validation and Sign-off- MDG | 4 hrs | 2025-08-26 18:52 | 2025-08-26 22:52 | Hans Jorg | hansjorg.becker@de.sasol.com | Jochen Kühl; Bruno van der Valk; Thomas; Stella Hatkova; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Sven Gelking; Torsten Freydt; Firat | Jochen.Kuehl@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; stella.hatkova@sk.sasol.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; sven.gelking@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | Cross-team | 21177 |  |  |  | 2025-08-21 08:00 | 2025-08-26 18:52 | 2025-08-26 22:52
19625 | STRIVE.R2.MC1.2384.1277.1.1.139.43.18 | N | N | N | Ready |  | Clear AEM Q and Deploy the Iflow - MDG_I_230 | 8 hrs | 2025-09-01 14:29 | 2025-09-01 22:29 | Yashwanth | myakumar@deloitte.com | Naga; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration | 19622 |  |  |  | 2025-08-21 08:00 | 2025-09-01 14:29 | 2025-09-01 22:29
19626 | STRIVE.R2.MC1.2384.1277.1.1.139.43.19 | Y | Y | Y | Complete |  | Perform DRF Out of ZFIN from MDG to S/4 | 92.88 hrs | 2025-08-25 15:47 | 2025-08-29 12:56 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Tushar; Firat | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19595 | 2025-08-25 15:47 | 2025-08-29 12:56 |  | 2025-08-21 08:00 | 2025-08-25 15:47 | 2025-08-29 12:56
19627 | STRIVE.R2.MC1.2384.1277.1.1.139.43.20 | Y | Y | Y | Complete |  | Perform DRF Out of ZRAW from MDG to S/4 | 4.62 hrs | 2025-08-25 15:48 | 2025-08-25 20:24 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Tushar; Firat | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19597 | 2025-08-25 15:48 | 2025-08-25 20:24 |  | 2025-08-21 08:00 | 2025-08-25 15:48 | 2025-08-25 20:24
19629 | STRIVE.R2.MC1.2384.1277.1.1.139.43.22 | Y | Y | Y | Complete |  | Perform DRF Out of ZSFG from MDG to S/4 | 92.79 hrs | 2025-08-25 15:53 | 2025-08-29 12:57 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Tushar; Firat | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19599 | 2025-08-25 15:53 | 2025-08-29 12:57 |  | 2025-08-21 08:00 | 2025-08-25 15:53 | 2025-08-29 12:57
19630 | STRIVE.R2.MC1.2384.1277.1.1.139.43.23 | Y | Y | Y | Complete |  | Perform DRF Out of ZPKG from MDG to S/4 | 92.82 hrs | 2025-08-25 15:54 | 2025-08-29 12:59 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Tushar; Firat | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19600 | 2025-08-25 15:54 | 2025-08-29 12:59 |  | 2025-08-21 08:00 | 2025-08-25 15:54 | 2025-08-29 12:59
19631 | STRIVE.R2.MC1.2384.1277.1.1.139.43.24 | Y | Y | Y | Complete |  | Perform DRF Out of ZOPS from MDG to S/4 | 60.97 hrs | 2025-08-23 02:48 | 2025-08-25 15:56 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Tushar; Firat | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19601 | 2025-08-23 02:48 | 2025-08-25 15:56 |  | 2025-08-21 08:00 | 2025-08-23 02:48 | 2025-08-25 15:56
19632 | STRIVE.R2.MC1.2384.1277.1.1.139.43.25 | Y | Y | Y | Complete |  | Perform DRF Out of ZCAT from MDG to S/4 | 92.53 hrs | 2025-08-25 16:09 | 2025-08-29 12:57 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Tushar; Firat | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19602 | 2025-08-25 16:09 | 2025-08-29 12:57 |  | 2025-08-21 08:00 | 2025-08-25 16:09 | 2025-08-29 12:57
19633 | STRIVE.R2.MC1.2384.1277.1.1.139.43.26 | Y | Y | Y | Complete |  | Perform DRF Out of ZMAG from MDG to S/4 | 25.46 hrs | 2025-08-28 14:35 | 2025-08-29 16:06 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol Paswan; Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Tushar; Firat | ampaswan@deloitte.com; tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tamrutkar@deloitte.de; firat.cetin@consultary.de | MDG | 19603 | 2025-08-28 14:35 | 2025-08-29 16:06 |  | 2025-08-21 08:00 | 2025-08-28 14:35 | 2025-08-29 16:06
21189 | STRIVE.R2.MC1.2384.1277.1.1.139.43.42 | Y | Y | Y | Complete |  | Perform DRF Out of ZMAS from MDG to S/4 | 210.43 hrs | 2025-08-25 17:16 | 2025-09-03 12:18 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Sven Gelking; Firat | ampaswan@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; sven.gelking@de.sasol.com; firat.cetin@consultary.de |  | 21186,21179 | 2025-08-25 17:16 | 2025-09-03 12:18 |  | 2025-08-21 08:00 | 2025-08-25 17:16 | 2025-09-03 12:18
21187 | STRIVE.R2.MC1.2384.1277.1.1.139.43.40 | Y | Y | Y | Complete |  | Perform DRF Out of ZRDS from MDG to S/4 | 187.38 hrs | 2025-08-26 22:52 | 2025-09-03 18:47 | Vinit Raverkar | vnitinraverkar@deloitte.com | Amol; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Sven Gelking; Firat | ampaswan@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; sven.gelking@de.sasol.com; firat.cetin@consultary.de | MDG | 21183,21177 | 2025-08-26 22:52 | 2025-09-03 18:47 |  | 2025-08-21 08:00 | 2025-08-26 22:52 | 2025-09-03 18:47
19634 | STRIVE.R2.MC1.2384.1277.1.1.139.43.27 | Y | Y | Y | Complete |  | Material Master Validation of Replication MDG to S4 | 76.95 hrs | 2025-08-29 16:06 | 2025-09-01 21:15 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Firat; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda; Alex Miles; Satyajit Patnaik | tupal@deloitte.com; firat.cetin@consultary.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com | DM | 19626,19633,19631,19632,19627,19629,19630 | 2025-08-29 16:06 | 2025-09-01 21:15 |  | 2025-08-21 08:00 | 2025-08-29 16:06 | 2025-09-01 21:15
19635 | STRIVE.R2.MC1.2384.1277.1.1.139.43.28 | N | N | N | Planned |  | Update Material Master Xref with old to new values | 8 hrs | 2025-08-21 08:00 | 2025-08-21 16:01 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Tulika Pal; Satyajit Patnaik; Vignesh; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat | tupal@deloitte.com; sapatnaik@deloitte.com; vignsa@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de | MDG | 19592 |  |  |  | 2025-08-21 08:00 | 2025-08-21 08:00 | 2025-08-21 16:01
19636 | STRIVE.R2.MC1.2384.1277.1.1.139.43.29 | N | N | N | Planned |  | Updating Special Procurement type for ZFIN and ZSFG – MDMA table | 8 hrs | 2025-09-10 18:01 | 2025-09-11 02:03 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Vignesh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satyajit Patnaik; Roman Mäkilä; Alex Miles; Firat | vignsa@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; firat.cetin@consultary.de | DM | 20174 |  |  |  | 2025-08-21 08:00 | 2025-09-10 18:01 | 2025-09-11 02:03
19637 | STRIVE.R2.MC1.2384.1277.1.1.139.43.30 | N | N | N | Planned |  | Updating SCM_RRP_TYPE and SCM_HEUR_ID for ZFIN , ZRAW and ZSFG – MDMA table | 8 hrs | 2025-09-10 18:01 | 2025-09-11 02:03 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Vignesh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satyajit Patnaik; Roman Mäkilä; Alex Miles; Firat | vignsa@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; firat.cetin@consultary.de | DM | 20174 |  |  |  | 2025-08-21 08:00 | 2025-09-10 18:01 | 2025-09-11 02:03
19638 | STRIVE.R2.MC1.2384.1277.1.1.139.43.31 | N | N | N | Planned |  | Manual creation of GAS material 130000094 with material type ZRAW in MDG | 8 hrs | 2025-09-03 01:46 | 2025-09-03 09:47 | Prasanth | kalprasanth@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Tripti mehta; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; trimehta@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19609,19617 |  |  |  | 2025-08-21 08:00 | 2025-09-03 01:46 | 2025-09-03 09:47
19640 | STRIVE.R2.MC1.2384.1277.1.1.139.76 | Y | Y | Y | Complete |  | Material Master: Handover to Coupa team | 21.05 hrs | 2025-08-28 14:35 | 2025-08-29 11:40 | Rishi Tirthani | rtirthani@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 19595,19597,19599,19600,19601,19602,19603 | 2025-08-28 14:35 | 2025-08-29 11:40 |  | 2025-08-21 08:00 | 2025-08-28 14:35 | 2025-08-29 11:40
19641 | STRIVE.R2.MC1.2384.1277.1.1.139.77 | Y | Y | Y | Complete |  | Prepare Material Master File for Coupa | 0 hrs | 2025-08-29 20:50 | 2025-08-29 20:51 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19616,19617,19619,19620,19621,19622 | 2025-08-29 20:50 | 2025-08-29 20:51 |  | 2025-08-21 08:00 | 2025-08-29 20:50 | 2025-08-29 20:51
19642 | STRIVE.R2.MC1.2384.1277.1.1.139.78 | Y | Y | Y | Complete |  | Material Master Coupa Pre-Load Validation and Sign-off | 16.94 hrs | 2025-09-04 03:29 | 2025-09-04 20:27 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19641 | 2025-09-04 03:29 | 2025-09-04 20:27 |  | 2025-08-21 08:00 | 2025-09-04 03:29 | 2025-09-04 20:27
19643 | STRIVE.R2.MC1.2384.1277.1.1.139.79 | Y | Y | Y | Complete |  | Load Material Master in Coupa | 0.02 hrs | 2025-09-02 19:11 | 2025-09-02 19:12 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat; Rabbani | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de; skhadarmohammadra@deloitte.com | S2P_Coupa | 19642 | 2025-09-02 19:11 | 2025-09-02 19:12 |  | 2025-08-21 08:00 | 2025-09-02 19:11 | 2025-09-02 19:12
19644 | STRIVE.R2.MC1.2384.1277.1.1.139.80 | Y | Y | Y | Complete |  | Material Master Coupa Post-Load Validation and Sign-off | 0 hrs | 2025-09-05 19:50 | 2025-09-05 19:50 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19643 | 2025-09-05 19:50 | 2025-09-05 19:50 |  | 2025-08-21 08:00 | 2025-09-05 19:50 | 2025-09-05 19:50
19645 | STRIVE.R2.MC1.2384.1277.1.1.139.81 | [5 empty] | Work Center (Plant Maintenace) | 8.98 hrs | 2025-08-11 08:00 | 2025-08-11 17:00 | [6 empty] | 2025-08-11 15:39 |  | * | NA | 2025-08-11 08:00 | 2025-08-11 17:00
19646 | STRIVE.R2.MC1.2384.1277.1.1.139.81.1 | Y | Y | Y | Complete |  | Work Center (Plant Maintenance) Simulate and Share Findings | 0 hrs | 2025-08-11 18:33 | 2025-08-11 18:33 | Moonalisa | mooghosh@deloitte.com | Vahini; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Satyajit; Firat | vgudisetti@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; sapatnaik@deloitte.com; firat.cetin@consultary.de | DM |  | 2025-08-11 18:33 |  | * | NA | 2025-08-11 18:33 | 2025-08-11 18:33
19647 | STRIVE.R2.MC1.2384.1277.1.1.139.81.2 | Y | Y | Y | Complete |  | Work Center (Plant Maintenace) Pre-Load Validation and Sign-off - BB | 0 hrs | 2025-08-11 15:39 | 2025-08-11 15:39 | Sven Gelking | sven.gelking@de.sasol.com | Andre Harders; Matthias Rudolph; Joseph Barber; Elisa Latona; Chaitnya; Abhishek Sharma; Amit Jha; Jay Patel; Sergio; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Firat | Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; sergio.guzzo@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | MOR | 19646 | 2025-08-11 15:39 | 2025-08-11 15:39 | * | NA | 2025-08-11 15:39 | 2025-08-11 15:39
21191 | STRIVE.R2.MC1.2384.1277.1.1.139.81.8 | Y | Y | Y | Complete |  | Work Center (Plant Maintenace) Pre-Load Validation and Sign-off - Marl | 1.08 hrs | 2025-08-11 15:39 | 2025-08-11 16:44 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Joseph Barber; Elisa Latona; Chaitnya; Abhishek Sharma; Amit Jha; Jay Patel; Firat; Sergio; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap | Daniel.Bunge@de.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; firat.cetin@consultary.de; sergio.guzzo@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com | MOR | 19646 | 2025-08-11 15:39 | 2025-08-11 16:44 | * | NA | 2025-08-11 15:39 | 2025-08-11 16:44
21190 | STRIVE.R2.MC1.2384.1277.1.1.139.81.7 | Y | Y | Y | Complete |  | Work Center (Plant Maintenace) Pre-Load Validation and Sign-off - SK | 523.94 hrs | 2025-08-11 18:33 | 2025-09-02 15:57 | Sven Gelking | sven.gelking@de.sasol.com | Vieroslav Kratky; Branislav Drienovsky; Joseph Barber; Elisa Latona; Chaitnya; Abhishek Sharma; Amit Jha; Jay Patel; Firat; Sergio; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap | Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; firat.cetin@consultary.de; sergio.guzzo@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com | MOR | 19646 | 2025-08-11 18:33 | 2025-09-02 15:57 |  | 2025-08-11 08:00 | 2025-08-11 18:33 | 2025-09-02 15:57
19648 | STRIVE.R2.MC1.2384.1277.1.1.139.81.3 | Y | Y | Y | Complete |  | Work Center (Plant Maintenace) Load into S/4 and share Post-Load | 0.95 hrs | 2025-08-12 08:00 | 2025-08-12 08:57 | Moonalisa | mooghosh@deloitte.com | Vahini; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Satyajit; Firat | vgudisetti@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; sapatnaik@deloitte.com; firat.cetin@consultary.de | DM | 19647,21191,21190 | 2025-08-12 08:00 | 2025-08-12 08:57 | * | NA | 2025-08-12 08:00 | 2025-08-12 08:57
19649 | STRIVE.R2.MC1.2384.1277.1.1.139.81.4 | Y | Y | Y | Complete |  | Work Center (Plant Maintenace) Post-Load Validation and Sign-off - BB | 509.74 hrs | 2025-08-12 08:57 | 2025-09-02 16:06 | Sven Gelking | sven.gelking@de.sasol.com | Andre Harders; Matthias Rudolph; Joseph Barber; Elisa Latona; Chaitnya; Abhishek Sharma; Amit Jha; Jay Patel; Firat; Sergio; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap | Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; firat.cetin@consultary.de; sergio.guzzo@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com | MOR | 19648 | 2025-08-12 08:57 | 2025-09-02 16:06 |  | 2025-08-12 08:00 | 2025-08-12 08:57 | 2025-09-02 16:06
21193 | STRIVE.R2.MC1.2384.1277.1.1.139.81.10 | Y | Y | Y | Complete |  | Work Center (Plant Maintenace) Post-Load Validation and Sign-off - Marl | 17.48 hrs | 2025-09-02 18:33 | 2025-09-03 12:06 | Sven Gelking | sven.gelking@de.sasol.com | Daniel Bunge; Joseph Barber; Elisa Latona; Chaitnya; Abhishek Sharma; Amit Jha; Jay Patel; Firat; Sergio; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap | Daniel.Bunge@de.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; firat.cetin@consultary.de; sergio.guzzo@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com | MOR | 19648 | 2025-09-02 18:33 | 2025-09-03 12:06 | * | NA | 2025-09-02 18:33 | 2025-09-03 12:06
21192 | STRIVE.R2.MC1.2384.1277.1.1.139.81.9 | Y | Y | Y | Complete |  | Work Center (Plant Maintenace) Post-Load Validation and Sign-off - SK | 509.63 hrs | 2025-08-12 08:57 | 2025-09-02 16:00 | Sven Gelking | sven.gelking@de.sasol.com | Vieroslav Kratky; Branislav Drienovsky; Joseph Barber; Elisa Latona; Chaitnya; Abhishek Sharma; Amit Jha; Jay Patel; Firat; Sergio; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap | Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; firat.cetin@consultary.de; sergio.guzzo@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com | MOR | 19648 | 2025-08-12 08:57 | 2025-09-02 16:00 | * | NA | 2025-08-12 08:57 | 2025-09-02 16:00
19650 | STRIVE.R2.MC1.2384.1277.1.1.139.81.5 | Y | N | N | Sent |  | Create Work Center Hierarchy | 69.95 hrs | 2025-09-02 16:06 | 2025-09-05 14:15 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sergio; Elisa Latona; Firat; Joseph Barber; Krishna Teja; Jay Patel; Amit Jha; ; ; | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; firat.cetin@consultary.de; joseph.barber@us.sasol.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; ; ; | MOR | 19649 |  |  | * | NA | 2025-09-02 16:06 | 2025-09-05 14:15
19652 | STRIVE.R2.MC1.2384.1277.1.228 | [5 empty] | Tier 2 Master Data Load's | 1914.72 hrs | 2025-08-11 08:00 | 2025-10-30 08:03 | [6 empty] | 2025-08-11 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-10-30 08:03
19653 | STRIVE.R2.MC1.2384.1277.1.228.1 |  |  |  | Complete |  | BOM (Bill of Materials) | 120.64 hrs | 2025-08-13 08:00 | 2025-08-18 08:58 | [6 empty] | 2025-08-25 16:48 | 2025-09-05 12:21 | * | NA | 2025-08-13 08:00 | 2025-08-18 08:58
19654 | STRIVE.R2.MC1.2384.1277.1.228.1.1 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Transformation and share findings | 0.19 hrs | 2025-08-25 16:48 | 2025-08-25 17:00 | Manikanta | manikmanikanta@deloitte.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Daniel Bunge; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Jens Nissen; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Torsten Freydt; Hans Jorg; Eva Bani; Zuzana Hlucha; Firat | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; Daniel.Bunge@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; hansjorg.becker@de.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; firat.cetin@consultary.de | R2P | 19592 | 2025-08-25 16:48 | 2025-08-25 17:00 |  | 2025-08-20 08:00 | 2025-08-25 16:48 | 2025-08-25 17:00
21228 | STRIVE.R2.MC1.2384.1277.1.228.1.39 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Simulate file and share findings | 78.52 hrs | 2025-08-26 08:36 | 2025-08-29 15:20 | Manikanta | manikmanikanta@deloitte.com | Hans Jorg; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Daniel Bunge; Savri Sumeet Jagatap; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Jens Nissen; Eva Bani; Zuzana Hlucha; Firat | hansjorg.becker@de.sasol.com; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; Daniel.Bunge@de.sasol.com; ssumeetjagatap@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; firat.cetin@consultary.de | DM | 19592 | 2025-08-26 08:36 | 2025-08-29 15:20 |  | 2025-08-20 08:00 | 2025-08-26 08:36 | 2025-08-29 15:20
19655 | STRIVE.R2.MC1.2384.1277.1.228.1.2 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Pre-Load Validation and Sign-off - BB | 0.21 hrs | 2025-09-03 12:09 | 2025-09-03 12:21 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Thomas; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Alex Miles; Roman Mäkilä; Satyajit; Savri Sumeet Jagatap; Ines Tesch; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Riepe Joëlle; Ilka Behrens; Torsten Freydt; Firat | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; Joelle.Riepe@de.sasol.com; Ilka.Behrens@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21228 | 2025-09-03 12:09 | 2025-09-03 12:21 |  | 2025-08-20 08:00 | 2025-09-03 12:09 | 2025-09-03 12:21
21227 | STRIVE.R2.MC1.2384.1277.1.228.1.38 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Pre-Load Validation and Sign-off - Marl | 0.2 hrs | 2025-09-03 12:09 | 2025-09-03 12:21 | Hans Jorg | hansjorg.becker@de.sasol.com | Daniel Bunge; Bruno van der Valk; Thomas; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Jens Nissen; Torsten Freydt; Firat | Daniel.Bunge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21228 | 2025-09-03 12:09 | 2025-09-03 12:21 |  | 2025-08-20 08:00 | 2025-09-03 12:09 | 2025-09-03 12:21
21226 | STRIVE.R2.MC1.2384.1277.1.228.1.37 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Pre-Load Validation and Sign-off - SK | 0.19 hrs | 2025-09-03 12:09 | 2025-09-03 12:21 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Jens Nissen; Torsten Freydt; Firat | timotej.sandor@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21228 | 2025-09-03 12:09 | 2025-09-03 12:21 |  | 2025-08-20 08:00 | 2025-09-03 12:09 | 2025-09-03 12:21
19656 | STRIVE.R2.MC1.2384.1277.1.228.1.3 | Y | Y | Y | Complete |  | BOM (Bill of Materials) Load into S/4 and share Post-Load | 2.15 hrs | 2025-09-03 12:47 | 2025-09-03 14:56 | Manikanta | manikmanikanta@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Hans Jorg; Roman Mäkilä; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; hansjorg.becker@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19655,21226,21227 | 2025-09-03 12:47 | 2025-09-03 14:56 |  | 2025-08-20 08:00 | 2025-09-03 12:47 | 2025-09-03 14:56
19657 | STRIVE.R2.MC1.2384.1277.1.228.1.4 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Post-Load Validation and Sign-off - BB | 19.81 hrs | 2025-09-04 16:28 | 2025-09-05 12:20 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Thomas; Sandrika Chetty; Martin Stoffers; Christiane Dampf; Uta Paulsen; Marvin Jarocki; Birgit Rohde; Alex Miles; Roman Mäkilä; Satyajit; Savri Sumeet Jagatap; Ines Tesch; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Riepe Joëlle; Ilka Behrens; Torsten Freydt; Firat | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; sandrika.chetty@sasol.com; Martin.Stoffers@de.sasol.com; Christiane.Dampf@de.sasol.com; Uta.Paulsen@de.sasol.com; Marvin.Jarocki@de.sasol.com; Birgit.Rohde@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; Joelle.Riepe@de.sasol.com; Ilka.Behrens@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19656 | 2025-09-04 16:28 | 2025-09-05 12:20 |  | 2025-08-20 08:00 | 2025-09-04 16:28 | 2025-09-05 12:20
21210 | STRIVE.R2.MC1.2384.1277.1.228.1.21 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Post-Load Validation and Sign-off - Marl | 19.82 hrs | 2025-09-04 16:28 | 2025-09-05 12:21 | Hans Jorg | hansjorg.becker@de.sasol.com | Daniel Bunge; Bruno van der Valk; Thomas; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Jens Nissen; Torsten Freydt; Firat | Daniel.Bunge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19656 | 2025-09-04 16:28 | 2025-09-05 12:21 |  | 2025-08-20 08:00 | 2025-09-04 16:28 | 2025-09-05 12:21
21211 | STRIVE.R2.MC1.2384.1277.1.228.1.22 | Y | Y | Y | Complete |  | Material Bill of Materials (BOM) Post-Load Validation and Sign-off - SK | 19.81 hrs | 2025-09-04 16:28 | 2025-09-05 12:21 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Jens Nissen; Torsten Freydt; Firat | timotej.sandor@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19656 | 2025-09-04 16:28 | 2025-09-05 12:21 |  | 2025-08-20 08:00 | 2025-09-04 16:28 | 2025-09-05 12:21
40120 | STRIVE.R2.MC1.2384.1277.1.228.63 | [5 empty] | Material Master Classification | 147.6 hrs | 2025-08-13 13:00 | 2025-08-19 17:00 | [6 empty] | 2025-09-02 14:08 |  | * | NA | 2025-08-13 13:00 | 2025-08-19 17:00
40121 | STRIVE.R2.MC1.2384.1277.1.228.63.51 | Y | Y | Y | Complete |  | Material Master Classification Transformation and share findings | 45.05 hrs | 2025-09-02 14:08 | 2025-09-04 11:19 | Manikanta | manikmanikanta@deloitte.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Daniel Bunge; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Torsten Freydt; Hans Jorg; Eva Bani; Zuzana Hlucha; Firat | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; Daniel.Bunge@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; hansjorg.becker@de.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; firat.cetin@consultary.de | DM | 19675,19676,19592 | 2025-09-02 14:08 | 2025-09-04 11:19 | * | NA | 2025-09-02 14:08 | 2025-09-04 11:19
40122 | STRIVE.R2.MC1.2384.1277.1.228.63.52 | Y | Y | I | Issue |  | Material Master Classification Pre-Load Validation and Sign-off - BB | 9 hrs | 2025-09-05 11:37 | 2025-09-05 20:38 | Andreas Biernath | Andreas.Biernath@de.sasol.com | Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Jens Nissen; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Firat | jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de | R2P | 40121 | 2025-09-05 11:37 |  | * | NA | 2025-09-05 11:37 | 2025-09-05 20:38
40123 | STRIVE.R2.MC1.2384.1277.1.228.63.53 | Y | N | N | Sent |  | Material Master Classification Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-04 11:19 | 2025-09-04 20:20 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Bruno van der Valk; Thomas; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; firat.cetin@consultary.de | R2P | 40121 |  |  | * | NA | 2025-09-04 11:19 | 2025-09-04 20:20
40124 | STRIVE.R2.MC1.2384.1277.1.228.63.54 | Y | N | N | Sent |  | Material Master Classification Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-04 11:19 | 2025-09-04 20:20 | Timotej Šándor | timotej.sandor@sk.sasol.com | Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Eva Bani; Zuzana Hlucha; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; firat.cetin@consultary.de | R2P | 40121 |  |  | * | NA | 2025-09-04 11:19 | 2025-09-04 20:20
40125 | STRIVE.R2.MC1.2384.1277.1.228.63.55 | N | N | N | Planned |  | Material Master Classification Load into S/4 and share Post-Load | 9 hrs | 2025-09-05 20:38 | 2025-09-06 05:40 | Manikanta | manikmanikanta@deloitte.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Bruno van der Valk; Thomas; Timotej Šándor; Daniel Bunge; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Torsten Freydt; Hans Jorg; Eva Bani; Zuzana Hlucha; Firat | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; Daniel.Bunge@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; hansjorg.becker@de.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; firat.cetin@consultary.de | DM | 40122,40123,40124 |  |  | * | NA | 2025-09-05 20:38 | 2025-09-06 05:40
40114 | STRIVE.R2.MC1.2384.1277.1.228.63.44 | N | N | N | Planned |  | Material Master Classification Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-06 05:40 | 2025-09-06 14:42 | Andreas Biernath | Andreas.Biernath@de.sasol.com | Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Jens Nissen; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Firat | jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de | R2P | 40125 |  |  | * | NA | 2025-09-06 05:40 | 2025-09-06 14:42
40115 | STRIVE.R2.MC1.2384.1277.1.228.63.45 | N | N | N | Planned |  | Material Master Classification Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-06 05:40 | 2025-09-06 14:42 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Bruno van der Valk; Thomas; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; firat.cetin@consultary.de | R2P | 40125 |  |  | * | NA | 2025-09-06 05:40 | 2025-09-06 14:42
40116 | STRIVE.R2.MC1.2384.1277.1.228.63.46 | N | N | N | Planned |  | Material Master Classification Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-06 05:40 | 2025-09-06 14:42 | Timotej Šándor | timotej.sandor@sk.sasol.com | Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Eva Bani; Zuzana Hlucha; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; firat.cetin@consultary.de | R2P | 40125 |  |  | * | NA | 2025-09-06 05:40 | 2025-09-06 14:42
21212 | STRIVE.R2.MC1.2384.1277.1.228.59 | [5 empty] | Inspection Method | 51.87 hrs | 2025-08-13 08:00 | 2025-08-15 12:00 | [6 empty] | 2025-09-04 14:24 |  | * | NA | 2025-08-13 08:00 | 2025-08-15 12:00
21213 | STRIVE.R2.MC1.2384.1277.1.228.59.24 | Y | Y | Y | Complete |  | Inspection Method Transformation and share findings | 0.63 hrs | 2025-09-04 14:24 | 2025-09-04 15:02 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Jens Nissen; Firat; Lisa Leben | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Lisa.Leben@de.sasol.com | DM |  | 2025-09-04 14:24 | 2025-09-04 15:02 |  | 2025-09-01 08:00 | 2025-09-04 14:24 | 2025-09-04 15:02
21214 | STRIVE.R2.MC1.2384.1277.1.228.59.25 | Y | Y | Y | Complete |  | Inspection Method Simulate file and share findings | 2.29 hrs | 2025-09-04 15:02 | 2025-09-04 17:19 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Jens Nissen; Firat; Lisa Leben | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Lisa.Leben@de.sasol.com | DM | 21213 | 2025-09-04 15:02 | 2025-09-04 17:19 | * | NA | 2025-09-04 15:02 | 2025-09-04 17:19
21215 | STRIVE.R2.MC1.2384.1277.1.228.59.26 | Y | N | N | Sent |  | Inspection Method Pre-Load Validation and Sign-off - BB | 4 hrs | 2025-09-04 17:19 | 2025-09-04 21:19 | Hans Jorg | hansjorg.becker@de.sasol.com | Jorg Hauf; Manfred Sprung; Michael Claußen; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Lisa Leben; Torsten Freydt; Firat | Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Lisa.Leben@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21214 |  |  | * | NA | 2025-09-04 17:19 | 2025-09-04 21:19
21216 | STRIVE.R2.MC1.2384.1277.1.228.59.27 | Y | Y | Y | Complete |  | Inspection Method Pre-Load Validation and Sign-off - Marl | 4.02 hrs | 2025-09-09 14:17 | 2025-09-09 18:18 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21214 | 2025-09-09 14:17 | 2025-09-09 18:18 | * | NA | 2025-09-09 14:17 | 2025-09-09 18:18
21217 | STRIVE.R2.MC1.2384.1277.1.228.59.28 | Y | N | N | Sent |  | Inspection Method Pre-Load Validation and Sign-off - SK | 4 hrs | 2025-09-04 17:19 | 2025-09-04 21:19 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21214 |  |  | * | NA | 2025-09-04 17:19 | 2025-09-04 21:19
21218 | STRIVE.R2.MC1.2384.1277.1.228.59.29 | N | N | N | Planned |  | Inspection Method Load into S/4 and share Post-Load | 3 hrs | 2025-09-09 18:18 | 2025-09-09 21:18 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Jens Nissen; Firat; Lisa Leben | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Lisa.Leben@de.sasol.com | DM | 21215,21216,21217 |  |  |  | 2025-09-02 08:00 | 2025-09-09 18:18 | 2025-09-09 21:18
21219 | STRIVE.R2.MC1.2384.1277.1.228.59.30 | N | N | N | Planned |  | Inspection Method Post-Load Validation and Sign-off - BB | 4 hrs | 2025-09-09 21:18 | 2025-09-10 01:20 | Hans Jorg | hansjorg.becker@de.sasol.com | Jorg Hauf; Manfred Sprung; Michael Claußen; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Lisa Leben; Torsten Freydt; Firat | Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Lisa.Leben@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21218 |  |  |  | 2025-09-04 08:00 | 2025-09-09 21:18 | 2025-09-10 01:20
21220 | STRIVE.R2.MC1.2384.1277.1.228.59.31 | N | N | N | Planned |  | Inspection Method Post-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-09 21:18 | 2025-09-10 01:20 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21218 |  |  |  | 2025-09-04 08:00 | 2025-09-09 21:18 | 2025-09-10 01:20
21221 | STRIVE.R2.MC1.2384.1277.1.228.59.32 | N | N | N | Planned |  | Inspection Method Post-Load Validation and Sign-off - SK | 4 hrs | 2025-09-09 21:18 | 2025-09-10 01:20 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21218 |  |  |  | 2025-09-04 08:00 | 2025-09-09 21:18 | 2025-09-10 01:20
21222 | STRIVE.R2.MC1.2384.1277.1.228.60 | [5 empty] | Inspection Setup | 51.87 hrs | 2025-09-02 08:00 | 2025-09-04 12:00 | [6 empty] | 2025-09-05 02:04 |  | * | NA | 2025-09-02 08:00 | 2025-09-04 12:00
21223 | STRIVE.R2.MC1.2384.1277.1.228.60.34 | Y | Y | Y | Complete |  | Inspection Setup Transformation and share findings | 14.96 hrs | 2025-09-05 02:04 | 2025-09-05 17:03 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Jens Nissen; Firat; Lisa Leben | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Lisa.Leben@de.sasol.com | DM | 21218 | 2025-09-05 02:04 | 2025-09-05 17:03 |  | 2025-09-02 08:00 | 2025-09-05 02:04 | 2025-09-05 17:03
21224 | STRIVE.R2.MC1.2384.1277.1.228.60.35 | Y | Y | Y | Complete |  | Inspection Setup Simulate file and share findings | 1.05 hrs | 2025-09-05 17:45 | 2025-09-05 18:47 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Jens Nissen; Firat; Lisa Leben | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Lisa.Leben@de.sasol.com | DM | 21223 | 2025-09-05 17:45 | 2025-09-05 18:47 |  | 2025-09-03 08:00 | 2025-09-05 17:45 | 2025-09-05 18:47
21225 | STRIVE.R2.MC1.2384.1277.1.228.60.36 | Y | N | N | Sent |  | Inspection Setup Pre-Load Validation and Sign-off - BB | 4 hrs | 2025-09-05 18:47 | 2025-09-05 22:47 | Hans Jorg | hansjorg.becker@de.sasol.com | Jorg Hauf; Manfred Sprung; Michael Claußen; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Lisa Leben; Torsten Freydt; Firat | Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Lisa.Leben@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21224 |  |  |  | 2025-09-03 08:00 | 2025-09-05 18:47 | 2025-09-05 22:47
21202 | STRIVE.R2.MC1.2384.1277.1.228.60.13 | Y | Y | N | In-Progress |  | Inspection Setup Pre-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-10 12:56 | 2025-09-10 16:56 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21224 | 2025-09-10 12:56 |  |  | 2025-09-03 08:00 | 2025-09-10 12:56 | 2025-09-10 16:56
21203 | STRIVE.R2.MC1.2384.1277.1.228.60.14 | Y | N | N | Sent |  | Inspection Setup Pre-Load Validation and Sign-off - SK | 4 hrs | 2025-09-05 18:47 | 2025-09-05 22:47 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21224 |  |  |  | 2025-09-03 08:00 | 2025-09-05 18:47 | 2025-09-05 22:47
21204 | STRIVE.R2.MC1.2384.1277.1.228.60.15 | N | N | N | Planned |  | Inspection Setup Load into S/4 and share Post-Load | 4 hrs | 2025-09-10 16:56 | 2025-09-10 20:56 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Jens Nissen; Firat; Lisa Leben | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Lisa.Leben@de.sasol.com | DM | 21225,21202,21203 |  |  |  | 2025-09-03 08:00 | 2025-09-10 16:56 | 2025-09-10 20:56
21205 | STRIVE.R2.MC1.2384.1277.1.228.60.16 | N | N | N | Planned |  | Inspection Setup Post-Load Validation and Sign-off - BB | 4 hrs | 2025-09-10 20:56 | 2025-09-11 00:58 | Hans Jorg | hansjorg.becker@de.sasol.com | Jorg Hauf; Manfred Sprung; Michael Claußen; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Lisa Leben; Torsten Freydt; Firat | Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Lisa.Leben@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21204 |  |  | * | NA | 2025-09-10 20:56 | 2025-09-11 00:58
21206 | STRIVE.R2.MC1.2384.1277.1.228.60.17 | N | N | N | Planned |  | Inspection Setup Post-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-10 20:56 | 2025-09-11 00:58 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21204 |  |  | * | NA | 2025-09-10 20:56 | 2025-09-11 00:58
21207 | STRIVE.R2.MC1.2384.1277.1.228.60.18 | N | N | N | Planned |  | Inspection Setup Post-Load Validation and Sign-off - SK | 4 hrs | 2025-09-10 20:56 | 2025-09-11 00:58 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21204 |  |  | * | NA | 2025-09-10 20:56 | 2025-09-11 00:58
40134 | STRIVE.R2.MC1.2384.1277.1.228.64 | [5 empty] | Physical Sample Transformation | 16 hrs | 2025-09-10 20:56 | 2025-09-11 13:00 | [8 empty] | * | NA | 2025-09-10 20:56 | 2025-09-11 13:00
40135 | STRIVE.R2.MC1.2384.1277.1.228.64.74 | N | N | N | Planned |  | Physical Sample Transformation and share findings | 4 hrs | 2025-09-10 20:56 | 2025-09-11 00:58 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 21204 |  |  |  | 2025-09-03 16:00 | 2025-09-10 20:56 | 2025-09-11 00:58
40136 | STRIVE.R2.MC1.2384.1277.1.228.64.75 | N | N | N | Planned |  | Physical Sample Pre-Load Validation and Sign-off - DE | 4 hrs | 2025-09-11 00:58 | 2025-09-11 04:58 | Medy Schröder | medy.schroeder@de.sasol.com | Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | R2P | 40135 |  |  |  | 2025-09-04 08:00 | 2025-09-11 00:58 | 2025-09-11 04:58
40137 | STRIVE.R2.MC1.2384.1277.1.228.64.76 | N | N | N | Planned |  | Physical Sample Pre-Load Validation and Sign-off - SK | 4 hrs | 2025-09-11 00:58 | 2025-09-11 04:58 | Stella Hatkova | stella.hatkova@sk.sasol.com | Hans Jorg; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | hansjorg.becker@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | R2P | 40135 |  |  |  | 2025-09-04 08:00 | 2025-09-11 00:58 | 2025-09-11 04:58
40138 | STRIVE.R2.MC1.2384.1277.1.228.64.77 | N | N | N | Planned |  | Physical Sample Load into S/4 and share Post-Load | 4 hrs | 2025-09-11 04:58 | 2025-09-11 08:59 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 40136,40137 |  |  |  | 2025-09-05 08:01 | 2025-09-11 04:58 | 2025-09-11 08:59
40139 | STRIVE.R2.MC1.2384.1277.1.228.64.78 | N | N | N | Planned |  | Physical Sample Post-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-11 08:59 | 2025-09-11 13:00 | Medy Schröder | medy.schroeder@de.sasol.com | Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | R2P | 40138 |  |  |  | 2025-09-08 08:02 | 2025-09-11 08:59 | 2025-09-11 13:00
40131 | STRIVE.R2.MC1.2384.1277.1.228.64.70 | N | N | N | Planned |  | Physical Sample Post-Load Validation and Sign-off - SK | 4 hrs | 2025-09-11 08:59 | 2025-09-11 13:00 | Stella Hatkova | stella.hatkova@sk.sasol.com | Hans Jorg; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | hansjorg.becker@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | R2P | 40138 |  |  |  | 2025-09-08 08:02 | 2025-09-11 08:59 | 2025-09-11 13:00
21229 | STRIVE.R2.MC1.2384.1277.1.228.61 | [5 empty] | Inspection Plan | 20 hrs | 2025-09-11 08:59 | 2025-09-12 05:02 | [8 empty] | * | NA | 2025-09-11 08:59 | 2025-09-12 05:02
21239 | STRIVE.R2.MC1.2384.1277.1.228.61.46 | N | N | N | Planned |  | Inspection Plan Transformation and share findings | 4 hrs | 2025-09-11 08:59 | 2025-09-11 13:00 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 40138,21311 |  |  |  | 2025-09-08 08:02 | 2025-09-11 08:59 | 2025-09-11 13:00
21240 | STRIVE.R2.MC1.2384.1277.1.228.61.47 | N | N | N | Planned |  | Inspection Plan Simulate file and share findings | 4 hrs | 2025-09-11 13:00 | 2025-09-11 17:00 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 21239 |  |  | * | NA | 2025-09-11 13:00 | 2025-09-11 17:00
21241 | STRIVE.R2.MC1.2384.1277.1.228.61.48 | N | N | N | Planned |  | Inspection Plan Pre-Load Validation and Sign-off - BB | 4 hrs | 2025-09-11 17:00 | 2025-09-11 21:00 | Hans Jorg | hansjorg.becker@de.sasol.com | Jorg Hauf; Manfred Sprung; Michael Claußen; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Lisa Leben; Torsten Freydt; Firat | Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Lisa.Leben@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21240 |  |  |  | 2025-09-09 08:03 | 2025-09-11 17:00 | 2025-09-11 21:00
21242 | STRIVE.R2.MC1.2384.1277.1.228.61.49 | N | N | N | Planned |  | Inspection Plan Pre-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-11 17:00 | 2025-09-11 21:00 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21240 |  |  |  | 2025-09-09 08:03 | 2025-09-11 17:00 | 2025-09-11 21:00
21243 | STRIVE.R2.MC1.2384.1277.1.228.61.50 | N | N | N | Planned |  | Inspection Plan Pre-Load Validation and Sign-off - SK | 4 hrs | 2025-09-11 17:00 | 2025-09-11 21:00 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21240 |  |  |  | 2025-09-09 08:03 | 2025-09-11 17:00 | 2025-09-11 21:00
21244 | STRIVE.R2.MC1.2384.1277.1.228.61.51 | N | N | N | Planned |  | Inspection Plan Load into S/4 and share Post-Load | 4 hrs | 2025-09-11 21:00 | 2025-09-12 01:02 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 21241,21242,21243 |  |  |  | 2025-09-10 08:04 | 2025-09-11 21:00 | 2025-09-12 01:02
21245 | STRIVE.R2.MC1.2384.1277.1.228.61.52 | N | N | N | Planned |  | Inspection Plan Post-Load Validation and Sign-off - BB | 4 hrs | 2025-09-12 01:02 | 2025-09-12 05:02 | Hans Jorg | hansjorg.becker@de.sasol.com | Jorg Hauf; Manfred Sprung; Michael Claußen; Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ines Tesch; Lisa Leben; Torsten Freydt; Firat | Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; Lisa.Leben@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21244 |  |  |  | 2025-09-11 08:05 | 2025-09-12 01:02 | 2025-09-12 05:02
21246 | STRIVE.R2.MC1.2384.1277.1.228.61.53 | N | N | N | Planned |  | Inspection Plan Post-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-12 01:02 | 2025-09-12 05:02 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21244 |  |  |  | 2025-09-11 08:05 | 2025-09-12 01:02 | 2025-09-12 05:02
21247 | STRIVE.R2.MC1.2384.1277.1.228.61.54 | N | N | N | Planned |  | Inspection Plan Post-Load Validation and Sign-off - SK | 4 hrs | 2025-09-12 01:02 | 2025-09-12 05:02 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21244 |  |  |  | 2025-09-11 08:05 | 2025-09-12 01:02 | 2025-09-12 05:02
21248 | STRIVE.R2.MC1.2384.1277.1.228.62 | [5 empty] | Inspection Lot | 20 hrs | 2025-09-12 01:02 | 2025-09-12 21:04 | [8 empty] | * | NA | 2025-09-12 01:02 | 2025-09-12 21:04
21249 | STRIVE.R2.MC1.2384.1277.1.228.62.56 | N | N | N | Planned |  | Inspection Lot Transformation and share findings | 4 hrs | 2025-09-12 01:02 | 2025-09-12 05:02 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 21244 |  |  |  | 2025-09-09 12:05 | 2025-09-12 01:02 | 2025-09-12 05:02
21250 | STRIVE.R2.MC1.2384.1277.1.228.62.57 | N | N | N | Planned |  | Inspection Lot Simulate file and share findings | 4 hrs | 2025-09-12 05:02 | 2025-09-12 09:03 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 21249 |  |  | * | NA | 2025-09-12 05:02 | 2025-09-12 09:03
21251 | STRIVE.R2.MC1.2384.1277.1.228.62.58 | N | N | N | Planned |  | Inspection Lot Pre-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-12 09:03 | 2025-09-12 13:04 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21250 |  |  | * | NA | 2025-09-12 09:03 | 2025-09-12 13:04
21252 | STRIVE.R2.MC1.2384.1277.1.228.62.59 | N | N | N | Planned |  | Inspection Lot Pre-Load Validation and Sign-off - SK | 4 hrs | 2025-09-12 09:03 | 2025-09-12 13:04 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21250 |  |  | * | NA | 2025-09-12 09:03 | 2025-09-12 13:04
21253 | STRIVE.R2.MC1.2384.1277.1.228.62.60 | N | N | N | Planned |  | Inspection Lot Load into S/4 and share Post-Load | 4 hrs | 2025-09-12 13:04 | 2025-09-12 17:04 | Manikanta | manikmanikanta@deloitte.com | Stella Hatkova; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Hans Jorg; Jorg Hauf; Manfred Sprung; Michael Claußen; Savri Sumeet Jagatap; Satyajit; Alex Miles; Roman Mäkilä; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Firat | stella.hatkova@sk.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; hansjorg.becker@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; firat.cetin@consultary.de | DM | 21251,21252 |  |  |  | 2025-09-11 08:07 | 2025-09-12 13:04 | 2025-09-12 17:04
21254 | STRIVE.R2.MC1.2384.1277.1.228.62.61 | N | N | N | Planned |  | Inspection Lot Post-Load Validation and Sign-off - Marl | 4 hrs | 2025-09-12 17:04 | 2025-09-12 21:04 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Roman Mäkilä; Satyajit; Ines Tesch; Torsten Freydt; Firat | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; ines.tesch@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21253 |  |  |  | 2025-09-12 08:08 | 2025-09-12 17:04 | 2025-09-12 21:04
21255 | STRIVE.R2.MC1.2384.1277.1.228.62.62 | N | N | N | Planned |  | Inspection Lot Post-Load Validation and Sign-off - SK | 4 hrs | 2025-09-12 17:04 | 2025-09-12 21:04 | Hans Jorg | hansjorg.becker@de.sasol.com | Stella Hatkova; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Ines Tesch; Alex Miles; Roman Mäkilä; Satyajit; Torsten Freydt; Firat | stella.hatkova@sk.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; ines.tesch@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 21253 |  |  |  | 2025-09-12 08:08 | 2025-09-12 17:04 | 2025-09-12 21:04
19658 | STRIVE.R2.MC1.2384.1277.1.228.6 | [5 empty] | Equipment | 218.3 hrs | 2025-08-27 08:00 | 2025-09-05 10:54 | [6 empty] | 2025-08-26 21:14 |  | * | NA | 2025-08-27 08:00 | 2025-09-05 10:54
21256 | STRIVE.R2.MC1.2384.1277.1.228.6.6 | N | N | N | Ready |  | Equipment Simulate file and share findings - SK Data | 9 hrs | 2025-09-10 10:05 | 2025-09-10 19:06 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Vahini; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; vgudisetti@deloitte.com; firat.cetin@consultary.de | DM | 19483,19527 |  |  |  | 2025-08-25 08:00 | 2025-09-10 10:05 | 2025-09-10 19:06
19660 | STRIVE.R2.MC1.2384.1277.1.228.6.2 | Y | Y | Y | Complete |  | Equipment Transformation and share Pre-Load | 0 hrs | 2025-08-26 21:14 | 2025-08-26 23:20 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Daniel Bunge; Andre Harders; Matthias Rudolph; Vahini; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; vgudisetti@deloitte.com; firat.cetin@consultary.de | DM | 19483,19527 | 2025-08-26 21:14 | 2025-08-26 23:20 |  | 2025-08-25 08:00 | 2025-08-26 21:14 | 2025-08-26 23:20
19661 | STRIVE.R2.MC1.2384.1277.1.228.6.3 | Y | Y | Y | Complete |  | Equipment Pre-Load Validation and Sign-off - BB | 324.67 hrs | 2025-08-26 23:20 | 2025-09-09 12:56 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19660 | 2025-08-26 23:20 | 2025-09-09 12:56 |  | 2025-08-25 08:00 | 2025-08-26 23:20 | 2025-09-09 12:56
21258 | STRIVE.R2.MC1.2384.1277.1.228.6.8 | Y | Y | Y | Complete |  | Equipment Pre-Load Validation and Sign-off - Marl | 28.94 hrs | 2025-09-03 12:16 | 2025-09-04 17:16 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Daniel.Bunge@de.sasol.com | MOR | 19660 | 2025-09-03 12:16 | 2025-09-04 17:16 |  | 2025-08-25 08:00 | 2025-09-03 12:16 | 2025-09-04 17:16
21257 | STRIVE.R2.MC1.2384.1277.1.228.6.7 | Y | N | N | Sent |  | Equipment Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-08-26 23:20 | 2025-08-27 08:23 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Vieroslav Kratky; Branislav Drienovsky | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com | MOR | 19660 |  |  |  | 2025-08-25 08:00 | 2025-08-26 23:20 | 2025-08-27 08:23
19662 | STRIVE.R2.MC1.2384.1277.1.228.6.4 | Y | Y | Y | Complete |  | Equipment Load into S/4 and share Post-Load | 118.43 hrs | 2025-09-04 17:16 | 2025-09-09 16:02 | Moonalisa | mooghosh@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Sven Gelking; Roman Mäkilä; Vahini; Daniel Bunge; Matthias Rudolph; Vieroslav Kratky; Branislav Drienovsky; Andre Harders | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; sven.gelking@de.sasol.com; roman.makila@deloitte.fi; vgudisetti@deloitte.com; Daniel.Bunge@de.sasol.com; Matthias.Rudolph@de.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Andre.Harders@de.sasol.com | DM | 19661,21258,21257,95085 | 2025-09-04 17:16 | 2025-09-09 16:02 |  | 2025-08-26 08:00 | 2025-09-04 17:16 | 2025-09-09 16:02
19663 | STRIVE.R2.MC1.2384.1277.1.228.6.5 | Y | N | N | Sent |  | Equipment Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-09 16:02 | 2025-09-10 01:04 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19662 |  |  |  | 2025-08-26 08:00 | 2025-09-09 16:02 | 2025-09-10 01:04
21260 | STRIVE.R2.MC1.2384.1277.1.228.6.10 | Y | N | N | Sent |  | Equipment Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-09 16:02 | 2025-09-10 01:04 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Daniel.Bunge@de.sasol.com | MOR | 19662 |  |  |  | 2025-08-26 08:00 | 2025-09-09 16:02 | 2025-09-10 01:04
21259 | STRIVE.R2.MC1.2384.1277.1.228.6.9 | Y | N | N | Sent |  | Equipment Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-09 16:02 | 2025-09-10 01:04 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Vieroslav Kratky; Branislav Drienovsky | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com | MOR | 19662 |  |  |  | 2025-08-26 08:00 | 2025-09-09 16:02 | 2025-09-10 01:04
19664 | STRIVE.R2.MC1.2384.1277.1.228.12 | [5 empty] | EAM Characteristics | 56.82 hrs | 2025-08-13 08:00 | 2025-08-15 16:58 | [6 empty] | 2025-08-25 22:13 |  | * | NA | 2025-08-13 08:00 | 2025-08-15 16:58
19665 | STRIVE.R2.MC1.2384.1277.1.228.12.1 | Y | Y | Y | Complete |  | EAM Characteristics Simulate file and share findings | 0.45 hrs | 2025-08-25 22:13 | 2025-08-25 22:40 | Vahini | vgudisetti@deloitte.com | Moonalisa; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Alex Miles; Firat | mooghosh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; almiles@deloitte.de; firat.cetin@consultary.de | DM | 19672 | 2025-08-25 22:13 | 2025-08-25 22:40 |  | 2025-08-26 08:01 | 2025-08-25 22:13 | 2025-08-25 22:40
19666 | STRIVE.R2.MC1.2384.1277.1.228.12.2 | Y | Y | Y | Complete |  | EAM Characteristics Pre-Load Validation and Sign-off - DE | 1.48 hrs | 2025-09-01 12:07 | 2025-09-01 13:36 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; Daniel.Bunge@de.sasol.com | MOR | 19665 | 2025-09-01 12:07 | 2025-09-01 13:36 | * | NA | 2025-09-01 12:07 | 2025-09-01 13:36
21261 | STRIVE.R2.MC1.2384.1277.1.228.12.5 | Y | Y | Y | Complete |  | EAM Characteristics Pre-Load Validation and Sign-off - SK | 207.42 hrs | 2025-08-25 22:40 | 2025-09-03 14:41 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Vieroslav Kratky; Branislav Drienovsky | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com | MOR | 19665 | 2025-08-25 22:40 | 2025-09-03 14:41 | * | NA | 2025-08-25 22:40 | 2025-09-03 14:41
19667 | STRIVE.R2.MC1.2384.1277.1.228.12.3 | Y | Y | Y | Complete |  | EAM Characteristics Load into S/4 and share Post-Load | 0.18 hrs | 2025-09-01 19:21 | 2025-09-01 19:32 | Vahini | vgudisetti@deloitte.com | Moonalisa; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Alex Miles; Firat | mooghosh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; almiles@deloitte.de; firat.cetin@consultary.de | DM | 19666,21261 | 2025-09-01 19:21 | 2025-09-01 19:32 | * | NA | 2025-09-01 19:21 | 2025-09-01 19:32
21262 | STRIVE.R2.MC1.2384.1277.1.228.12.6 | Y | N | N | Sent |  | EAM Characteristics Post-Load Validation and Sign-off - DE | 4 hrs | 2025-09-01 19:32 | 2025-09-01 23:32 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; Daniel.Bunge@de.sasol.com | MOR | 19667 |  |  | * | NA | 2025-09-01 19:32 | 2025-09-01 23:32
19668 | STRIVE.R2.MC1.2384.1277.1.228.12.4 | Y | Y | Y | Complete |  | EAM Characteristics Post-Load Validation and Sign-off - SK | 159.89 hrs | 2025-09-01 19:32 | 2025-09-08 11:52 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Vieroslav Kratky; Branislav Drienovsky | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com | MOR | 19667 | 2025-09-01 19:32 | 2025-09-08 11:52 | * | NA | 2025-09-01 19:32 | 2025-09-08 11:52
19669 | STRIVE.R2.MC1.2384.1277.1.228.17 | [5 empty] | EAM Classes | 56.82 hrs | 2025-08-13 08:00 | 2025-08-15 16:58 | [6 empty] | 2025-09-01 20:07 |  | * | NA | 2025-08-13 08:00 | 2025-08-15 16:58
19670 | STRIVE.R2.MC1.2384.1277.1.228.17.1 | Y | Y | Y | Complete |  | EAM Classes Simulate file and share findings | 0.36 hrs | 2025-09-01 20:07 | 2025-09-01 20:29 | Vahini | vgudisetti@deloitte.com | Moonalisa; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Alex Miles; Firat | mooghosh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; almiles@deloitte.de; firat.cetin@consultary.de | DM |  | 2025-09-01 20:07 | 2025-09-01 20:29 |  | 2025-08-25 08:00 | 2025-09-01 20:07 | 2025-09-01 20:29
19671 | STRIVE.R2.MC1.2384.1277.1.228.17.2 | Y | N | N | Sent |  | EAM Classes Pre-Load Validation and Sign-off - DE | 4 hrs | 2025-09-01 20:29 | 2025-09-02 00:31 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; Daniel.Bunge@de.sasol.com | MOR | 19670 |  |  | * | NA | 2025-09-01 20:29 | 2025-09-02 00:31
21263 | STRIVE.R2.MC1.2384.1277.1.228.17.5 | Y | N | N | Sent |  | EAM Classes Pre-Load Validation and Sign-off - SK | 4 hrs | 2025-09-01 20:29 | 2025-09-02 00:31 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; Daniel.Bunge@de.sasol.com | MOR | 19670 |  |  | * | NA | 2025-09-01 20:29 | 2025-09-02 00:31
19672 | STRIVE.R2.MC1.2384.1277.1.228.17.3 | N | N | N | Planned |  | EAM Classes Load into S/4 and share Post-Load | 4 hrs | 2025-09-02 00:31 | 2025-09-02 04:31 | Vahini | vgudisetti@deloitte.com | Moonalisa; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Alex Miles; Firat | mooghosh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; almiles@deloitte.de; firat.cetin@consultary.de | DM | 19671,21263 |  |  | * | NA | 2025-09-02 00:31 | 2025-09-02 04:31
19673 | STRIVE.R2.MC1.2384.1277.1.228.17.4 | N | N | N | Planned |  | EAM Classes Post-Load Validation and Sign-off - DE | 4 hrs | 2025-09-02 04:31 | 2025-09-02 08:32 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; Daniel.Bunge@de.sasol.com | MOR | 19672 |  |  | * | NA | 2025-09-02 04:31 | 2025-09-02 08:32
21264 | STRIVE.R2.MC1.2384.1277.1.228.17.6 | N | N | N | Planned |  | EAM Classes Post-Load Validation and Sign-off - SK | 4 hrs | 2025-09-02 04:31 | 2025-09-02 08:32 | Sven Gelking | sven.gelking@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Joseph Barber; Firat; Krishna Teja; Jay Patel; Sergio; Elisa Latona; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Andre Harders; Matthias Rudolph; Daniel Bunge | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; joseph.barber@us.sasol.com; firat.cetin@consultary.de; krishn@deloitte.com; jaypatel6@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; Daniel.Bunge@de.sasol.com | MOR | 19672 |  |  | * | NA | 2025-09-02 04:31 | 2025-09-02 08:32
19674 | STRIVE.R2.MC1.2384.1277.1.228.22 |  |  |  | Complete |  | Batch Class and Characteristics | 2 hrs | 2025-08-13 08:00 | 2025-08-13 10:00 | [6 empty] | 2025-09-02 13:54 | 2025-09-02 14:08 | * | NA | 2025-08-13 08:00 | 2025-08-13 10:00
19675 | STRIVE.R2.MC1.2384.1277.1.228.22.1 | Y | Y | Y | Complete |  | Manually Create Characteristics for Batch in MDG and S/4 | 0 hrs | 2025-09-02 14:08 | 2025-09-02 14:08 | Aniket Kulkarni | anikulkarni@deloitte.com | Amit das; Masood Mohd Abdul; USI STRIVE CUTOVER; Alex Miles; Satyajit; Dhruv Kansal; Roman Mäkilä; Mousikta chanda; Nilesh Deshpande; Sheena Gour; Priyanka Singhal; Firat | amitdas3@deloitte.com; mohmasood@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; nideshpande@deloitte.com; shgour@deloitte.com; priyasinghal@deloitte.com; firat.cetin@consultary.de | R2P | 19592 | 2025-09-02 14:08 | 2025-09-02 14:08 | * | NA | 2025-09-02 14:08 | 2025-09-02 14:08
19676 | STRIVE.R2.MC1.2384.1277.1.228.22.2 | Y | Y | Y | Complete |  | Manually Create Class for Batch in MDG and S/4 | 0 hrs | 2025-09-02 14:08 | 2025-09-02 14:08 | Aniket Kulkarni | anikulkarni@deloitte.com | Amit das; Masood Mohd Abdul; USI STRIVE CUTOVER; Alex Miles; Satyajit; Dhruv Kansal; Roman Mäkilä; Mousikta chanda; Nilesh Deshpande; Sheena Gour; Priyanka Singhal; Firat | amitdas3@deloitte.com; mohmasood@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; nideshpande@deloitte.com; shgour@deloitte.com; priyasinghal@deloitte.com; firat.cetin@consultary.de | R2P | 19592 | 2025-09-02 14:08 | 2025-09-02 14:08 | * | NA | 2025-09-02 14:08 | 2025-09-02 14:08
40140 | STRIVE.R2.MC1.2384.1277.1.228.22.3 | Y | Y | Y | Complete |  | Manually Create SVT Class in MDG and S/4 | 0.02 hrs | 2025-09-02 13:54 | 2025-09-02 13:55 | Aniket Kulkarni | anikulkarni@deloitte.com | Amit das; Masood Mohd Abdul; USI STRIVE CUTOVER; Alex Miles; Satyajit; Dhruv Kansal; Roman Mäkilä; Mousikta chanda; Nilesh Deshpande; Sheena Gour; Priyanka Singhal; Firat | amitdas3@deloitte.com; mohmasood@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; nideshpande@deloitte.com; shgour@deloitte.com; priyasinghal@deloitte.com; firat.cetin@consultary.de | R2P | 19592 | 2025-09-02 13:54 | 2025-09-02 13:55 | * | NA | 2025-09-02 13:54 | 2025-09-02 13:55
19680 | STRIVE.R2.MC1.2384.1277.1.228.28 | [5 empty] | Batch Master | 126.6 hrs | 2025-08-13 08:00 | 2025-08-18 14:57 | [6 empty] | 2025-09-02 14:36 |  | * | NA | 2025-08-13 08:00 | 2025-08-18 14:57
19681 | STRIVE.R2.MC1.2384.1277.1.228.28.1 | Y | Y | Y | Complete |  | Batch Transformation and share Pre-Load | 46.65 hrs | 2025-09-02 14:36 | 2025-09-04 13:23 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Hans Jorg; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | DM | 19674 | 2025-09-02 14:36 | 2025-09-04 13:23 |  | 2025-08-25 08:00 | 2025-09-02 14:36 | 2025-09-04 13:23
19682 | STRIVE.R2.MC1.2384.1277.1.228.28.2 | Y | N | N | Sent |  | Batch Pre-Load Validation and Sign-off - BB | 8 hrs | 2025-09-04 13:23 | 2025-09-04 21:23 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19681 |  |  | * | NA | 2025-09-04 13:23 | 2025-09-04 21:23
21267 | STRIVE.R2.MC1.2384.1277.1.228.28.7 | Y | Y | N | In-Progress |  | Batch Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-09 18:30 | 2025-09-10 03:32 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19681 | 2025-09-09 18:30 |  | * | NA | 2025-09-09 18:30 | 2025-09-10 03:32
21266 | STRIVE.R2.MC1.2384.1277.1.228.28.6 | Y | N | N | Sent |  | Batch Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-04 13:23 | 2025-09-04 22:23 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19681 |  |  | * | NA | 2025-09-04 13:23 | 2025-09-04 22:23
19683 | STRIVE.R2.MC1.2384.1277.1.228.28.3 | N | N | N | Planned |  | Batch Load into S/4 and share Post-Load | 1 hrs | 2025-09-10 10:05 | 2025-09-10 11:05 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Hans Jorg; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | DM | 19674,19682,19527,21267,21266 |  |  |  | 2025-08-26 08:01 | 2025-09-10 10:05 | 2025-09-10 11:05
19684 | STRIVE.R2.MC1.2384.1277.1.228.28.4 | N | N | N | Planned |  | Batch Post-Load Validation and Sign-off - BB | 8 hrs | 2025-09-10 11:05 | 2025-09-10 19:06 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19683 |  |  | * | NA | 2025-09-10 11:05 | 2025-09-10 19:06
21269 | STRIVE.R2.MC1.2384.1277.1.228.28.9 | N | N | N | Planned |  | Batch Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-10 11:05 | 2025-09-10 20:06 | Hans Jorg | hansjorg.becker@de.sasol.com | Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19683 |  |  | * | NA | 2025-09-10 11:05 | 2025-09-10 20:06
21268 | STRIVE.R2.MC1.2384.1277.1.228.28.8 | N | N | N | Planned |  | Batch Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-10 11:05 | 2025-09-10 20:06 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19683 |  |  | * | NA | 2025-09-10 11:05 | 2025-09-10 20:06
19685 | STRIVE.R2.MC1.2384.1277.1.228.33 | [5 empty] | Functional Location | 56.85 hrs | 2025-08-11 08:00 | 2025-08-13 17:00 | [6 empty] | 2025-08-14 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-08-13 17:00
21270 | STRIVE.R2.MC1.2384.1277.1.228.33.6 | Y | Y | I | Issue |  | Functional Location Simulate file and share findings - SK Data | 9 hrs | 2025-08-14 08:00 | 2025-08-14 17:01 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Vahini; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; vgudisetti@deloitte.com; firat.cetin@consultary.de | DM |  |  |  |  | 2025-08-14 08:00 | 2025-08-14 08:00 | 2025-08-14 17:01
19686 | STRIVE.R2.MC1.2384.1277.1.228.33.1 | Y | Y | Y | Complete |  | Functional Location Transformation and share Pre-Load | 5.41 hrs | 2025-08-19 13:23 | 2025-08-19 21:34 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Vahini; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; vgudisetti@deloitte.com; firat.cetin@consultary.de | DM | 19483 | 2025-08-19 13:23 | 2025-08-19 21:34 |  | 2025-08-14 11:00 | 2025-08-19 13:23 | 2025-08-19 21:34
19687 | STRIVE.R2.MC1.2384.1277.1.228.33.2 | Y | Y | Y | Complete |  | Functional Location Pre-Load Validation and Sign-off - BB | 141.47 hrs | 2025-08-19 21:34 | 2025-08-25 19:26 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19686 | 2025-08-19 21:34 | 2025-08-25 19:26 | * | NA | 2025-08-19 21:34 | 2025-08-25 19:26
21272 | STRIVE.R2.MC1.2384.1277.1.228.33.8 | Y | Y | Y | Complete |  | Functional Location Pre-Load Validation and Sign-off - Marl | 210.95 hrs | 2025-08-19 21:34 | 2025-08-28 17:07 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19686 | 2025-08-19 21:34 | 2025-08-28 17:07 | * | NA | 2025-08-19 21:34 | 2025-08-28 17:07
21271 | STRIVE.R2.MC1.2384.1277.1.228.33.7 | Y | N | N | Sent |  | Functional Location Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-08-19 21:34 | 2025-08-20 06:36 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19686 |  |  | * | NA | 2025-08-19 21:34 | 2025-08-20 06:36
19688 | STRIVE.R2.MC1.2384.1277.1.228.33.3 | Y | Y | Y | Complete |  | Functional Location Load into S/4 and share Post-Load | 0.56 hrs | 2025-08-21 17:28 | 2025-08-21 18:02 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Vahini; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; vgudisetti@deloitte.com; firat.cetin@consultary.de | DM | 19687,21271,21272,95085 | 2025-08-21 17:28 | 2025-08-21 18:02 |  | 2025-08-18 11:01 | 2025-08-21 17:28 | 2025-08-21 18:02
19689 | STRIVE.R2.MC1.2384.1277.1.228.33.4 | Y | N | N | Sent |  | Functional Location Post-Load Validation and Sign-off - BB | 2 hrs | 2025-08-21 18:02 | 2025-08-21 20:02 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19688 |  |  | * | NA | 2025-08-21 18:02 | 2025-08-21 20:02
21274 | STRIVE.R2.MC1.2384.1277.1.228.33.10 | Y | Y | Y | Complete |  | Functional Location Post-Load Validation and Sign-off - Marl | 165.08 hrs | 2025-08-21 18:02 | 2025-08-28 15:35 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19688 | 2025-08-21 18:02 | 2025-08-28 15:35 | * | NA | 2025-08-21 18:02 | 2025-08-28 15:35
21273 | STRIVE.R2.MC1.2384.1277.1.228.33.9 | Y | N | N | Sent |  | Functional Location Post-Load Validation and Sign-off - SK | 9 hrs | 2025-08-21 18:02 | 2025-08-22 03:04 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19688 |  |  | * | NA | 2025-08-21 18:02 | 2025-08-22 03:04
19690 | STRIVE.R2.MC1.2384.1277.1.228.33.5 | N | N | N | Planned |  | Flip the Floc status to INAC | 0.53 hrs | 2025-08-21 20:02 | 2025-08-21 20:34 | Abhishek Sharma | abhisheksharma59@deloitte.com | Vinod Kumar; Jay Patel; suyash Chhawala; Amit Jha; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Chaitnya; Firat | vinodkumar692@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; ajha2@deloitte.no; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; csudhakarraut@deloitte.com; firat.cetin@consultary.de | MOR | 19689 |  |  | * | NA | 2025-08-21 20:02 | 2025-08-21 20:34
19691 | STRIVE.R2.MC1.2384.1277.1.228.39 | [5 empty] | Equipment Bill of Material (BOM) | 77.73 hrs | 2025-08-11 08:00 | 2025-08-14 13:57 | [6 empty] | 2025-09-04 15:08 |  | * | NA | 2025-08-11 08:00 | 2025-08-14 13:57
19692 | STRIVE.R2.MC1.2384.1277.1.228.39.1 | Y | Y | Y | Complete |  | Equipment BOM Transformation and Share Pre-Loads | 0.06 hrs | 2025-09-04 15:08 | 2025-09-04 15:12 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Vahini; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; vgudisetti@deloitte.com; firat.cetin@consultary.de | DM | 19662,19592 | 2025-09-04 15:08 | 2025-09-04 15:12 | * | NA | 2025-09-04 15:08 | 2025-09-04 15:12
19693 | STRIVE.R2.MC1.2384.1277.1.228.39.2 | Y | N | N | Sent |  | Equipment Bill of Material (BOM) Pre-Load Validation and Sign-off - BB | 2.48 hrs | 2025-09-04 15:12 | 2025-09-04 17:41 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19692 |  |  |  | 2025-08-27 08:36 | 2025-09-04 15:12 | 2025-09-04 17:41
21276 | STRIVE.R2.MC1.2384.1277.1.228.39.6 | Y | N | N | Sent |  | Equipment Bill of Material (BOM) Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-04 15:12 | 2025-09-05 00:14 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19692 |  |  |  | 2025-08-27 08:36 | 2025-09-04 15:12 | 2025-09-05 00:14
21275 | STRIVE.R2.MC1.2384.1277.1.228.39.5 | Y | N | N | Sent |  | Equipment Bill of Material (BOM) Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-04 15:12 | 2025-09-05 00:14 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19692 |  |  |  | 2025-08-27 08:36 | 2025-09-04 15:12 | 2025-09-05 00:14
19694 | STRIVE.R2.MC1.2384.1277.1.228.39.3 | N | N | N | Planned |  | Equipment Bill of Material (BOM) Load into S/4 and share Post-Load | 1 hrs | 2025-09-05 00:14 | 2025-09-05 01:14 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Vahini; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; vgudisetti@deloitte.com; firat.cetin@consultary.de | DM | 19693,21275,21276 |  |  |  | 2025-08-28 08:37 | 2025-09-05 00:14 | 2025-09-05 01:14
19695 | STRIVE.R2.MC1.2384.1277.1.228.39.4 | N | N | N | Planned |  | Equipment Bill of Material (BOM) Post-Load Validation and Sign-off - BB | 1.23 hrs | 2025-09-05 01:14 | 2025-09-05 02:28 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19694 |  |  | * | NA | 2025-09-05 01:14 | 2025-09-05 02:28
21278 | STRIVE.R2.MC1.2384.1277.1.228.39.8 | N | N | N | Planned |  | Equipment Bill of Material (BOM) Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-05 01:14 | 2025-09-05 10:15 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19694 |  |  | * | NA | 2025-09-05 01:14 | 2025-09-05 10:15
21277 | STRIVE.R2.MC1.2384.1277.1.228.39.7 | N | N | N | Planned |  | Equipment Bill of Material (BOM) Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-05 01:14 | 2025-09-05 10:15 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19694 |  |  | * | NA | 2025-09-05 01:14 | 2025-09-05 10:15
19696 | STRIVE.R2.MC1.2384.1277.1.228.44 |  |  |  | Complete |  | Resources (PP-PI)/Capacities | 24.91 hrs | 2025-08-11 08:00 | 2025-08-12 08:59 | [6 empty] | 2025-08-11 12:05 | 2025-09-01 16:49 | * | NA | 2025-08-11 08:00 | 2025-08-12 08:59
40141 | STRIVE.R2.MC1.2384.1277.1.228.44.5 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Transformation and share Pre-Load | 3.58 hrs | 2025-08-11 12:05 | 2025-08-11 16:35 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Hans Jorg; Amit das; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; amitdas3@deloitte.com; firat.cetin@consultary.de | DM |  | 2025-08-11 12:05 | 2025-08-11 16:35 | * | NA | 2025-08-11 12:05 | 2025-08-11 16:35
19697 | STRIVE.R2.MC1.2384.1277.1.228.44.1 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Simulate and Share Results | 215.2 hrs | 2025-08-11 18:24 | 2025-08-20 18:12 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Hans Jorg; Amit das; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; amitdas3@deloitte.com; firat.cetin@consultary.de | DM |  | 2025-08-11 18:24 | 2025-08-20 18:12 | * | NA | 2025-08-11 18:24 | 2025-08-20 18:12
19698 | STRIVE.R2.MC1.2384.1277.1.228.44.2 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Pre-Load Validation and Sign-off - BB | 1.38 hrs | 2025-08-20 18:31 | 2025-08-20 19:54 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Andreas Biernath; Jonas Dohrn; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; Daniel Dierenfeld; T. Junge; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Tim.Junge@de.sasol.com; firat.cetin@consultary.de | R2P | 19697 | 2025-08-20 18:31 | 2025-08-20 19:54 | * | NA | 2025-08-20 18:31 | 2025-08-20 19:54
40143 | STRIVE.R2.MC1.2384.1277.1.228.44.7 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Pre-Load Validation and Sign-off - Marl | 23.53 hrs | 2025-08-20 18:12 | 2025-08-21 17:47 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Brigitte Matheja; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; Brigitte.Matheja@de.sasol.com; firat.cetin@consultary.de | R2P | 19697 | 2025-08-20 18:12 | 2025-08-21 17:47 | * | NA | 2025-08-20 18:12 | 2025-08-21 17:47
40142 | STRIVE.R2.MC1.2384.1277.1.228.44.6 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Pre-Load Validation and Sign-off - SK | 1.8 hrs | 2025-08-21 17:44 | 2025-08-21 19:32 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Timotej Šándor; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; timotej.sandor@sk.sasol.com; firat.cetin@consultary.de | R2P | 19697 | 2025-08-21 17:44 | 2025-08-21 19:32 | * | NA | 2025-08-21 17:44 | 2025-08-21 19:32
19699 | STRIVE.R2.MC1.2384.1277.1.228.44.3 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Load into S/4 and share Post-Load | 90.93 hrs | 2025-08-21 19:46 | 2025-08-25 14:58 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Hans Jorg; Roman Mäkilä; Jay Saini; Nilesh Deshpande; Amit das; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; hansjorg.becker@de.sasol.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; nideshpande@deloitte.com; amitdas3@deloitte.com; firat.cetin@consultary.de | DM | 19698,40142,40143 | 2025-08-21 19:46 | 2025-08-25 14:58 | * | NA | 2025-08-21 19:46 | 2025-08-25 14:58
19700 | STRIVE.R2.MC1.2384.1277.1.228.44.4 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Post-Load Validation and Sign-off - BB | 76.12 hrs | 2025-08-29 12:30 | 2025-09-01 16:49 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Andreas Biernath; Jonas Dohrn; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; Daniel Dierenfeld; T. Junge; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Tim.Junge@de.sasol.com; firat.cetin@consultary.de | R2P | 19699 | 2025-08-29 12:30 | 2025-09-01 16:49 |  | 2025-08-13 08:26 | 2025-08-29 12:30 | 2025-09-01 16:49
40145 | STRIVE.R2.MC1.2384.1277.1.228.44.9 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Post-Load Validation and Sign-off - Marl | 93.94 hrs | 2025-08-28 18:37 | 2025-09-01 16:49 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Brigitte Matheja; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; Brigitte.Matheja@de.sasol.com; firat.cetin@consultary.de | R2P | 19699 | 2025-08-28 18:37 | 2025-09-01 16:49 |  | 2025-08-13 08:26 | 2025-08-28 18:37 | 2025-09-01 16:49
40144 | STRIVE.R2.MC1.2384.1277.1.228.44.8 | Y | Y | Y | Complete |  | Resources (PP-PI)/Capacities Post-Load Validation and Sign-off - SK | 76.12 hrs | 2025-08-29 12:30 | 2025-09-01 16:49 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Vito Piscopiello; Carlo Sanfiorenzo; Salvatore Noto; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Timotej Šándor; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; vito.piscopiello@it.sasol.com; carlo.sanfiorenzo@it.sasol.com; salvatore.noto@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; timotej.sandor@sk.sasol.com; firat.cetin@consultary.de | R2P | 19699 | 2025-08-29 12:30 | 2025-09-01 16:49 |  | 2025-08-13 08:26 | 2025-08-29 12:30 | 2025-09-01 16:49
19701 | STRIVE.R2.MC1.2384.1277.1.228.49 | [5 empty] | Production version | 55.82 hrs | 2025-08-11 08:00 | 2025-08-13 15:58 | [6 empty] | 2025-09-08 08:36 |  | * | NA | 2025-08-11 08:00 | 2025-08-13 15:58
21279 | STRIVE.R2.MC1.2384.1277.1.228.49.5 | Y | Y | Y | Complete |  | Production version Transformation and share Pre-Load | 2.04 hrs | 2025-09-08 08:36 | 2025-09-08 10:38 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Jay Saini; Nilesh Deshpande; Hans Jorg; Claudiu; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; Bruno van der Valk; Thomas; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; nideshpande@deloitte.com; hansjorg.becker@de.sasol.com; cljipa@deloitte.de; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; firat.cetin@consultary.de | DM | 19592,19656 | 2025-09-08 08:36 | 2025-09-08 10:38 |  | 2025-08-21 08:00 | 2025-09-08 08:36 | 2025-09-08 10:38
19703 | STRIVE.R2.MC1.2384.1277.1.228.49.2 | Y | N | N | Sent |  | Production version Pre-Load Validation and Sign-off - BB | 8 hrs | 2025-09-08 10:38 | 2025-09-08 18:39 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 21279 |  |  |  | 2025-08-22 08:00 | 2025-09-08 10:38 | 2025-09-08 18:39
21281 | STRIVE.R2.MC1.2384.1277.1.228.49.7 | Y | N | N | Sent |  | Production version Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-08 10:38 | 2025-09-08 19:39 | Hans Jorg | hansjorg.becker@de.sasol.com | Bruno van der Valk; Thomas; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 21279 |  |  |  | 2025-08-22 08:00 | 2025-09-08 10:38 | 2025-09-08 19:39
21280 | STRIVE.R2.MC1.2384.1277.1.228.49.6 | Y | N | N | Sent |  | Production version Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-08 10:38 | 2025-09-08 19:39 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 21279 |  |  |  | 2025-08-22 08:00 | 2025-09-08 10:38 | 2025-09-08 19:39
19704 | STRIVE.R2.MC1.2384.1277.1.228.49.3 | N | N | N | Planned |  | Production version Load into S/4 and share Post-Load | 2 hrs | 2025-09-08 19:39 | 2025-09-08 21:39 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Jay Saini; Nilesh Deshpande; Hans Jorg; Claudiu; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; Bruno van der Valk; Thomas; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; nideshpande@deloitte.com; hansjorg.becker@de.sasol.com; cljipa@deloitte.de; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; firat.cetin@consultary.de | DM | 19703,21281,21280 |  |  | * | NA | 2025-09-08 19:39 | 2025-09-08 21:39
19705 | STRIVE.R2.MC1.2384.1277.1.228.49.4 | N | N | N | Planned |  | Production version Post-Load Validation and Sign-off - BB | 8 hrs | 2025-09-08 21:39 | 2025-09-09 05:41 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19704 |  |  |  | 2025-08-25 08:01 | 2025-09-08 21:39 | 2025-09-09 05:41
21283 | STRIVE.R2.MC1.2384.1277.1.228.49.9 | N | N | N | Planned |  | Production version Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-08 21:39 | 2025-09-09 06:41 | Hans Jorg | hansjorg.becker@de.sasol.com | Bruno van der Valk; Thomas; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19704 |  |  |  | 2025-08-25 08:01 | 2025-09-08 21:39 | 2025-09-09 06:41
21282 | STRIVE.R2.MC1.2384.1277.1.228.49.8 | N | N | N | Planned |  | Production version Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-08 21:39 | 2025-09-09 06:41 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19704 |  |  |  | 2025-08-25 08:01 | 2025-09-08 21:39 | 2025-09-09 06:41
19706 | STRIVE.R2.MC1.2384.1277.1.228.54 | [5 empty] | Master Recipe | 29.92 hrs | 2025-08-11 08:00 | 2025-08-12 14:00 | [8 empty] | * | NA | 2025-08-11 08:00 | 2025-08-12 14:00
21284 | STRIVE.R2.MC1.2384.1277.1.228.54.5 | N | N | N | Planned |  | Master Recipe Transformation and share Pre-Load | 9 hrs | 2025-09-08 21:39 | 2025-09-09 06:41 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Jay Saini; Nilesh Deshpande; Hans Jorg; Claudiu; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; Bruno van der Valk; Thomas; Timotej Šándor; T. Junge; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; nideshpande@deloitte.com; hansjorg.becker@de.sasol.com; cljipa@deloitte.de; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; Tim.Junge@de.sasol.com; firat.cetin@consultary.de | DM | 19704 |  |  |  | 2025-08-26 07:01 | 2025-09-08 21:39 | 2025-09-09 06:41
19708 | STRIVE.R2.MC1.2384.1277.1.228.54.2 | N | N | N | Planned |  | Master Recipe Pre-Load Validation and Sign-off - BB | 8 hrs | 2025-09-09 06:41 | 2025-09-09 14:43 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 21284 |  |  |  | 2025-08-26 07:01 | 2025-09-09 06:41 | 2025-09-09 14:43
21286 | STRIVE.R2.MC1.2384.1277.1.228.54.7 | N | N | N | Planned |  | Master Recipe Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-09 06:41 | 2025-09-09 15:43 | Hans Jorg | hansjorg.becker@de.sasol.com | Bruno van der Valk; Thomas; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 21284 |  |  |  | 2025-08-26 07:01 | 2025-09-09 06:41 | 2025-09-09 15:43
21285 | STRIVE.R2.MC1.2384.1277.1.228.54.6 | N | N | N | Planned |  | Master Recipe Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-09 06:41 | 2025-09-09 15:43 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 21284 |  |  |  | 2025-08-26 07:01 | 2025-09-09 06:41 | 2025-09-09 15:43
19709 | STRIVE.R2.MC1.2384.1277.1.228.54.3 | N | N | N | Planned |  | Master Recipe Load into S/4 and share Post-Load | 8 hrs | 2025-09-09 15:43 | 2025-09-09 23:43 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Jay Saini; Nilesh Deshpande; Hans Jorg; Claudiu; Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; Bruno van der Valk; Thomas; Timotej Šándor; T. Junge; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; nideshpande@deloitte.com; hansjorg.becker@de.sasol.com; cljipa@deloitte.de; Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; timotej.sandor@sk.sasol.com; Tim.Junge@de.sasol.com; firat.cetin@consultary.de | DM | 19708,21286,21285 |  |  |  | 2025-08-28 08:05 | 2025-09-09 15:43 | 2025-09-09 23:43
19710 | STRIVE.R2.MC1.2384.1277.1.228.54.4 | N | N | N | Planned |  | Master Recipe Post-Load Validation and Sign-off - BB | 8 hrs | 2025-09-09 23:43 | 2025-09-10 07:45 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19709 |  |  |  | 2025-08-26 07:01 | 2025-09-09 23:43 | 2025-09-10 07:45
21288 | STRIVE.R2.MC1.2384.1277.1.228.54.9 | N | N | N | Planned |  | Master Recipe Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-09 23:43 | 2025-09-10 08:46 | Hans Jorg | hansjorg.becker@de.sasol.com | Bruno van der Valk; Thomas; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Bruno.vanderValk@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19709 |  |  |  | 2025-08-26 07:01 | 2025-09-09 23:43 | 2025-09-10 08:46
21287 | STRIVE.R2.MC1.2384.1277.1.228.54.8 | N | N | N | Planned |  | Master Recipe Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-09 23:43 | 2025-09-10 08:46 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19709 |  |  |  | 2025-08-26 07:01 | 2025-09-09 23:43 | 2025-09-10 08:46
19711 | STRIVE.R2.MC1.2384.1277.1.287 | [5 empty] | Tier 3 Cold Transactional Data | 51.87 hrs | 2025-08-11 08:00 | 2025-08-13 12:00 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-08-13 12:00
19712 | STRIVE.R2.MC1.2384.1277.1.287.1 | [5 empty] | Functional Location Task list | 51.87 hrs | 2025-08-11 08:00 | 2025-08-13 12:00 | [6 empty] | 2025-09-03 19:16 |  | * | NA | 2025-08-11 08:00 | 2025-08-13 12:00
19713 | STRIVE.R2.MC1.2384.1277.1.287.1.1 | Y | Y | Y | Complete |  | Functional Location Task List Transformation and share Pre-Load | 0 hrs | 2025-09-03 19:16 | 2025-09-03 21:13 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19766,19787,19728 | 2025-09-03 19:16 | 2025-09-03 21:13 |  | 2025-10-03 13:55 | 2025-09-03 19:16 | 2025-09-03 21:13
19714 | STRIVE.R2.MC1.2384.1277.1.287.1.2 | Y | Y | Y | Complete |  | Functional Location Task List Pre-Load Validation and Sign-off - BB | 140.27 hrs | 2025-09-03 21:13 | 2025-09-09 17:54 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19713 | 2025-09-03 21:13 | 2025-09-09 17:54 | * | NA | 2025-09-03 21:13 | 2025-09-09 17:54
21290 | STRIVE.R2.MC1.2384.1277.1.287.1.6 | Y | N | N | Sent |  | Functional Location Task List Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-03 21:13 | 2025-09-04 06:15 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19713 |  |  | * | NA | 2025-09-03 21:13 | 2025-09-04 06:15
21289 | STRIVE.R2.MC1.2384.1277.1.287.1.5 | Y | N | N | Sent |  | Functional Location Task List Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-03 21:13 | 2025-09-04 06:15 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19713 |  |  | * | NA | 2025-09-03 21:13 | 2025-09-04 06:15
19715 | STRIVE.R2.MC1.2384.1277.1.287.1.3 | N | N | N | Planned |  | Functional Location Task List Load into S/4 and share Post-Load | 5 hrs | 2025-09-09 17:54 | 2025-09-09 22:54 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19714,21290,21289 |  |  | * | NA | 2025-09-09 17:54 | 2025-09-09 22:54
19716 | STRIVE.R2.MC1.2384.1277.1.287.1.4 | N | N | N | Planned |  | Functional Location Task List Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-09 22:54 | 2025-09-10 07:56 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19715 |  |  | * | NA | 2025-09-09 22:54 | 2025-09-10 07:56
21292 | STRIVE.R2.MC1.2384.1277.1.287.1.8 | N | N | N | Planned |  | Functional Location Task List Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-09 22:54 | 2025-09-10 07:56 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19715 |  |  | * | NA | 2025-09-09 22:54 | 2025-09-10 07:56
21291 | STRIVE.R2.MC1.2384.1277.1.287.1.7 | N | N | N | Planned |  | Functional Location Task List Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-09 22:54 | 2025-09-10 07:56 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19715 |  |  | * | NA | 2025-09-09 22:54 | 2025-09-10 07:56
19723 | STRIVE.R2.MC1.2384.1277.1.287.12 | [5 empty] | Purchasing Contracts | 509.41 hrs | 2025-08-15 08:00 | 2025-09-05 14:50 | [5 empty] | 19592,19518 | 2025-08-29 16:41 |  | * | NA | 2025-08-15 08:00 | 2025-09-05 14:50
19724 | STRIVE.R2.MC1.2384.1277.1.287.12.1 | Y | Y | Y | Complete |  | Purchasing Contracts Transformation and share Pre-Load - Coupa Format | 67.04 hrs | 2025-08-29 16:41 | 2025-09-01 11:55 | Rishi Tirthani | rtirthani@deloitte.com | ; Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; ; ; ; Liviana Scaricabarozzi; ; Maria Luisa Geremicca; Firat | ; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ; ; ; liviana.scaricabarozzi@it.sasol.com; ; marialuisa.geremicca@it.sasol.com; firat.cetin@consultary.de | DM | 19514 | 2025-08-29 16:41 | 2025-09-01 11:55 |  | 2025-08-25 08:00 | 2025-08-29 16:41 | 2025-09-01 11:55
19725 | STRIVE.R2.MC1.2384.1277.1.287.12.2 | Y | Y | Y | Complete |  | Purchasing Contracts Create and Handover Upload File to Coupa | 25.44 hrs | 2025-09-01 11:55 | 2025-09-02 13:26 | Rishi Tirthani | rtirthani@deloitte.com | ; Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat | ; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 19724 | 2025-09-01 11:55 | 2025-09-02 13:26 | * | NA | 2025-09-01 11:55 | 2025-09-02 13:26
19726 | STRIVE.R2.MC1.2384.1277.1.287.12.3 | Y | Y | N | In-Progress |  | Purchasing Contracts Pre-Load Validation and Sign-off | 9 hrs | 2025-09-09 14:45 | 2025-09-09 23:45 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Kathrin Lourenço Sarmiento; Jörn Schacher; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Kathrin.Lourenco-Sarmiento@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P_Coupa | 19727 | 2025-09-09 14:45 |  | * | NA | 2025-09-09 14:45 | 2025-09-09 23:45
19727 | STRIVE.R2.MC1.2384.1277.1.287.12.4 | Y | Y | Y | Complete |  | Purchasing Contracts: Prepare the coupa upload file | 6.54 hrs | 2025-09-03 12:25 | 2025-09-03 18:58 | Aparajita Mukherjee | apamukherjee@deloitte.com | Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rabbani; Pournami Nair; S2P Team; Esmir Divljanovic; Firat | miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19725 | 2025-09-03 12:25 | 2025-09-03 18:58 | * | NA | 2025-09-03 12:25 | 2025-09-03 18:58
19728 | STRIVE.R2.MC1.2384.1277.1.287.12.5 | Y | Y | Y | Complete |  | Purchasing Contracts Coupa Load | 0.2 hrs | 2025-09-08 10:09 | 2025-09-08 10:21 | Aparajita Mukherjee | apamukherjee@deloitte.com | Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rabbani; Pournami Nair; S2P Team; Esmir Divljanovic; Firat; Alex Miles; Satyajit; Roman Mäkilä | miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; skhadarmohammadra@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | S2P_Coupa | 19727 | 2025-09-08 10:09 | 2025-09-08 10:21 |  | 2025-08-28 08:03 | 2025-09-08 10:09 | 2025-09-08 10:21
19729 | STRIVE.R2.MC1.2384.1277.1.287.12.6 | Y | N | N | Sent |  | Purchasing Contracts Coupa Post-Load Validation / Signoff | 8 hrs | 2025-09-08 10:21 | 2025-09-08 18:22 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Kathrin Lourenço Sarmiento; Jörn Schacher; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Kathrin.Lourenco-Sarmiento@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P_Coupa | 19728 |  |  | * | NA | 2025-09-08 10:21 | 2025-09-08 18:22
19730 | STRIVE.R2.MC1.2384.1277.1.287.12.7 | N | N | N | Planned |  | Purchasing Contracts Upload the contract post load, in the XREF forlder | 8 hrs | 2025-09-08 18:22 | 2025-09-09 02:24 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19729 |  |  | * | NA | 2025-09-08 18:22 | 2025-09-09 02:24
40148 | STRIVE.R2.MC1.2384.1277.1.287.12.10 | N | N | N | Planned |  | Purchasing Contracts - Line Item file handed over to Coupa | 1 hrs | 2025-09-09 02:24 | 2025-09-09 03:24 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Kathrin Lourenço Sarmiento; Jörn Schacher; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Kathrin.Lourenco-Sarmiento@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P_Coupa | 19730 |  |  | * | NA | 2025-09-09 02:24 | 2025-09-09 03:24
40147 | STRIVE.R2.MC1.2384.1277.1.287.12.9 | N | N | N | Planned |  | Purchasing Contracts - Load Line Items within Coupa | 18 hrs | 2025-09-09 03:24 | 2025-09-09 21:26 | Aparajita Mukherjee | apamukherjee@deloitte.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Kathrin Lourenço Sarmiento; Jörn Schacher; Firat; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Kathrin.Lourenco-Sarmiento@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; edivljanovic@deloitte.de | S2P_Coupa | 40148 |  |  |  | 2025-09-02 09:07 | 2025-09-09 03:24 | 2025-09-09 21:26
40146 | STRIVE.R2.MC1.2384.1277.1.287.12.8 | N | N | N | Planned |  | Purchasing Contracts - Line Item Post-Load Validation | 8 hrs | 2025-09-09 21:26 | 2025-09-10 05:28 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Kathrin Lourenço Sarmiento; Jörn Schacher; Firat; Frank Toedter ; Tina Vidrine; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Kathrin.Lourenco-Sarmiento@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; ft@toedter-consult.de; tina.vidrine@us.sasol.com; edivljanovic@deloitte.de | S2P_Coupa | 40147 |  |  |  | 2025-09-03 08:10 | 2025-09-09 21:26 | 2025-09-10 05:28
19731 | STRIVE.R2.MC1.2384.1277.1.287.20 | [5 empty] | Purchase Info Record | 269.27 hrs | 2025-08-15 08:00 | 2025-08-26 14:01 | [6 empty] | 2025-09-08 13:46 |  | * | NA | 2025-08-15 08:00 | 2025-08-26 14:01
19732 | STRIVE.R2.MC1.2384.1277.1.287.20.1 | Y | Y | Y | Complete |  | Purchase Info Record Transformation and share Pre-Load - S/4 Format | 11.47 hrs | 2025-09-08 13:46 | 2025-09-09 01:16 | Saketh | sasaketh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Simonetta Confalonieri; Liviana Scaricabarozzi; Maria Luisa Geremicca; Roman Mäkilä; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Simonetta.Confalonieri@it.sasol.com; liviana.scaricabarozzi@it.sasol.com; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19728 | 2025-09-08 13:46 | 2025-09-09 01:16 |  | 2025-09-02 08:04 | 2025-09-08 13:46 | 2025-09-09 01:16
19733 | STRIVE.R2.MC1.2384.1277.1.287.20.2 | Y | N | N | Sent |  | Purchase Info Record Pre-Load Validation and Sign-off DE - S/4 File | 9 hrs | 2025-09-09 01:16 | 2025-09-09 10:17 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Jark Hinrichsen; Jörn Schacher; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19732 |  |  | * | NA | 2025-09-09 01:16 | 2025-09-09 10:17
21293 | STRIVE.R2.MC1.2384.1277.1.287.20.11 | Y | N | N | Sent |  | Purchase Info Record Pre-Load Validation and Sign-off SK - S/4 File | 9 hrs | 2025-09-09 01:16 | 2025-09-09 10:17 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19732 |  |  | * | NA | 2025-09-09 01:16 | 2025-09-09 10:17
19734 | STRIVE.R2.MC1.2384.1277.1.287.20.3 | N | N | N | Planned |  | Purchase Info Record Load into S/4 and share Post-Load | 6 hrs | 2025-09-09 10:17 | 2025-09-09 16:18 | Saketh | sasaketh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Simonetta Confalonieri; Liviana Scaricabarozzi; Maria Luisa Geremicca; Roman Mäkilä; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Simonetta.Confalonieri@it.sasol.com; liviana.scaricabarozzi@it.sasol.com; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19733,21293 |  |  |  | 2025-09-03 08:07 | 2025-09-09 10:17 | 2025-09-09 16:18
19735 | STRIVE.R2.MC1.2384.1277.1.287.20.4 | N | N | N | Planned |  | Purchase Info Record Post-Load Validation and Sign-off DE - S/4 File | 9 hrs | 2025-09-09 16:18 | 2025-09-10 01:20 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Jark Hinrichsen; Jörn Schacher; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19734 |  |  |  | 2025-09-04 08:08 | 2025-09-09 16:18 | 2025-09-10 01:20
21294 | STRIVE.R2.MC1.2384.1277.1.287.20.12 | N | N | N | Planned |  | Purchase Info Record Post-Load Validation and Sign-off SK - S/4 File | 9 hrs | 2025-09-09 16:18 | 2025-09-10 01:20 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19734 |  |  |  | 2025-09-04 08:08 | 2025-09-09 16:18 | 2025-09-10 01:20
40153 | STRIVE.R2.MC1.2384.1277.1.287.87 | [5 empty] | Supplier Item | 1824.71 hrs | 2025-08-15 08:00 | 2025-10-30 13:47 | [8 empty] | * | NA | 2025-08-15 08:00 | 2025-10-30 13:47
40151 | STRIVE.R2.MC1.2384.1277.1.287.87.15 | N | N | N | Planned |  | Supplier Item Transformation and share Pre-Load | 7 hrs | 2025-09-09 21:26 | 2025-09-10 04:28 | Saketh | sasaketh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; ; Liviana Scaricabarozzi; ; Maria Luisa Geremicca; Roman Mäkilä; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ; liviana.scaricabarozzi@it.sasol.com; ; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19734,40147 |  |  |  | 2025-09-05 08:08 | 2025-09-09 21:26 | 2025-09-10 04:28
40152 | STRIVE.R2.MC1.2384.1277.1.287.87.16 | N | N | N | Planned |  | Supplier Item Pre-Load Validation and Sign-off | 9 hrs | 2025-09-10 04:28 | 2025-09-10 13:30 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Jark Hinrichsen; Jörn Schacher; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 40151 |  |  | * | NA | 2025-09-10 04:28 | 2025-09-10 13:30
40150 | STRIVE.R2.MC1.2384.1277.1.287.87.14 | N | N | N | Planned |  | Supplier Item Load into Coupa and share Post-Load | 6 hrs | 2025-09-10 13:30 | 2025-09-10 19:30 | Aparajita Mukherjee | apamukherjee@deloitte.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Kathrin Lourenço Sarmiento; Jörn Schacher; Firat; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Kathrin.Lourenco-Sarmiento@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; edivljanovic@deloitte.de | S2P | 40152 |  |  |  | 2025-09-08 08:11 | 2025-09-10 13:30 | 2025-09-10 19:30
40149 | STRIVE.R2.MC1.2384.1277.1.287.87.13 | N | N | N | Planned |  | Supplier Item Post-Load Validation and Sign-off | 9 hrs | 2025-09-10 19:30 | 2025-09-11 04:32 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Sabrina Agueli; Jark Hinrichsen; Jörn Schacher; Firat; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; sabrina.agueli@de.sasol.com; Jark.Hinrichsen@de.sasol.com; Joern.Schacher@de.sasol.com; firat.cetin@consultary.de; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 40150 |  |  | * | NA | 2025-09-10 19:30 | 2025-09-11 04:32
19741 | STRIVE.R2.MC1.2384.1277.1.287.87.10 | N | N | N | Ready |  | Validate All Coupa XREFs - UOM, Material Number, Service number, WBS, GL, Cost Center, Supplier, location code, company Code, payment Terms, shipping terms, users etc. | 8 hrs | 2025-08-15 08:00 | 2025-08-15 16:01 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa |  |  |  | * | NA | 2025-08-15 08:00 | 2025-08-15 16:01
19742 | STRIVE.R2.MC1.2384.1277.1.287.31 | [5 empty] | Maintenance plan | 56.85 hrs | 2025-07-14 08:00 | 2025-07-16 17:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-16 17:00
19743 | STRIVE.R2.MC1.2384.1277.1.287.31.1 | N | N | N | Planned |  | Maintenance plan Transformation and share Pre-Load | 2 hrs | 2025-09-09 16:02 | 2025-09-09 18:02 | Vahini | vgudisetti@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19662,19768 |  |  |  | 2025-09-05 08:01 | 2025-09-09 16:02 | 2025-09-09 18:02
19744 | STRIVE.R2.MC1.2384.1277.1.287.31.2 | N | N | N | Planned |  | Maintenance plan Pre-Load Validation and Sign-off - BB | 2 hrs | 2025-09-09 18:02 | 2025-09-09 20:02 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19743 |  |  | * | NA | 2025-09-09 18:02 | 2025-09-09 20:02
21296 | STRIVE.R2.MC1.2384.1277.1.287.31.7 | N | N | N | Planned |  | Maintenance plan Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-09 18:02 | 2025-09-10 03:04 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19743 |  |  | * | NA | 2025-09-09 18:02 | 2025-09-10 03:04
21295 | STRIVE.R2.MC1.2384.1277.1.287.31.6 | N | N | N | Planned |  | Maintenance plan Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-09 18:02 | 2025-09-10 03:04 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19743 |  |  | * | NA | 2025-09-09 18:02 | 2025-09-10 03:04
19745 | STRIVE.R2.MC1.2384.1277.1.287.31.3 | N | N | N | Planned |  | Maintenance plan Load into S/4 and share Post-Load | 2 hrs | 2025-09-10 03:04 | 2025-09-10 05:04 | Vahini | vgudisetti@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19744,21295,21296 |  |  |  | 2025-09-08 08:02 | 2025-09-10 03:04 | 2025-09-10 05:04
19746 | STRIVE.R2.MC1.2384.1277.1.287.31.4 | N | N | N | Planned |  | Maintenance plan Post-Load Validation and Sign-off - BB | 2 hrs | 2025-09-10 05:04 | 2025-09-10 07:04 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19745 |  |  | * | NA | 2025-09-10 05:04 | 2025-09-10 07:04
21298 | STRIVE.R2.MC1.2384.1277.1.287.31.9 | N | N | N | Planned |  | Maintenance plan Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-10 05:04 | 2025-09-10 14:06 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19745 |  |  | * | NA | 2025-09-10 05:04 | 2025-09-10 14:06
21297 | STRIVE.R2.MC1.2384.1277.1.287.31.8 | N | N | N | Planned |  | Maintenance plan Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-10 05:04 | 2025-09-10 14:06 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19745 |  |  | * | NA | 2025-09-10 05:04 | 2025-09-10 14:06
19747 | STRIVE.R2.MC1.2384.1277.1.287.31.5 | N | N | N | Planned |  | Schedule Maintenance Plan (first time schedule) | 8 hrs | 2025-09-10 07:04 | 2025-09-10 15:06 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; Amit Jha; suyash Chhawala; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Chaitnya; Abhishek Sharma; Firat | jaypatel6@deloitte.com; ajha2@deloitte.no; schhawala@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; firat.cetin@consultary.de | MOR | 19746 |  |  | * | NA | 2025-09-10 07:04 | 2025-09-10 15:06
19753 | STRIVE.R2.MC1.2384.1277.1.287.42 | [5 empty] | Quality Certificate Profile | 222.26 hrs | 2025-07-14 08:00 | 2025-07-23 14:53 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-23 14:53
19754 | STRIVE.R2.MC1.2384.1277.1.287.42.1 | N | N | N | Planned |  | Quality Certificate Profile Simulate file and share findings | 0.02 hrs | 2025-09-12 17:04 | 2025-09-12 17:05 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Jay Saini; Nilesh Deshpande; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; nideshpande@deloitte.com; firat.cetin@consultary.de | DM | 21253 |  |  | * | NA | 2025-09-12 17:04 | 2025-09-12 17:05
19755 | STRIVE.R2.MC1.2384.1277.1.287.42.2 | N | N | N | Planned |  | Quality Certificate Profile - Pre-Load Validation and Sign-off - BB | 8 hrs | 2025-09-12 17:05 | 2025-09-13 01:07 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Amit das; Nilesh Deshpande; Jay Saini; Firat; Savri Sumeet Jagatap; Torsten Freydt; Jörg Hauf; Manfred Sprung; Michael Claußen | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; firat.cetin@consultary.de; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com | R2P | 19754 |  |  | * | NA | 2025-09-12 17:05 | 2025-09-13 01:07
40158 | STRIVE.R2.MC1.2384.1277.1.287.42.6 | N | N | N | Planned |  | Quality Certificate Profile - Pre-Load Validation and Sign-off - Marl | 8 hrs | 2025-09-12 17:05 | 2025-09-13 01:07 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Amit das; Nilesh Deshpande; Jay Saini; Firat; Savri Sumeet Jagatap; Torsten Freydt; Medy Schröder; Cornelia Baretti; Marcus Wallmann | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; firat.cetin@consultary.de; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Baretti@de.sasol.com; Marcus.Wallmann@de.sasol.com | R2P | 19754 |  |  | * | NA | 2025-09-12 17:05 | 2025-09-13 01:07
40157 | STRIVE.R2.MC1.2384.1277.1.287.42.5 | N | N | N | Planned |  | Quality Certificate Profile - Pre-Load Validation and Sign-off - SK | 8 hrs | 2025-09-12 17:05 | 2025-09-13 01:07 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Amit das; Nilesh Deshpande; Jay Saini; Firat; Savri Sumeet Jagatap; Torsten Freydt; Stella Hatkova | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; firat.cetin@consultary.de; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; stella.hatkova@sk.sasol.com | R2P | 19754 |  |  | * | NA | 2025-09-12 17:05 | 2025-09-13 01:07
19756 | STRIVE.R2.MC1.2384.1277.1.287.42.3 | N | N | N | Planned |  | Quality Certificate Profile - Load into S/4 and share Post-Load | 8 hrs | 2025-09-13 01:07 | 2025-09-13 09:08 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Hans Jorg; Roman Mäkilä; Jay Saini; Nilesh Deshpande; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; nideshpande@deloitte.com; firat.cetin@consultary.de | DM | 19755,40158,40157 |  |  | * | NA | 2025-09-13 01:07 | 2025-09-13 09:08
19757 | STRIVE.R2.MC1.2384.1277.1.287.42.4 | N | N | N | Planned |  | Quality Certificate Profile - Post-Load Validation and Sign-off - BB | 8 hrs | 2025-09-13 09:08 | 2025-09-13 17:09 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Amit das; Nilesh Deshpande; Jay Saini; Firat; Savri Sumeet Jagatap; Torsten Freydt; Jörg Hauf; Manfred Sprung; Michael Claußen | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; firat.cetin@consultary.de; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com | R2P | 19756 |  |  | * | NA | 2025-09-13 09:08 | 2025-09-13 17:09
40160 | STRIVE.R2.MC1.2384.1277.1.287.42.8 | N | N | N | Planned |  | Quality Certificate Profile - Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-13 09:08 | 2025-09-13 18:09 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Amit das; Nilesh Deshpande; Jay Saini; Firat; Savri Sumeet Jagatap; Torsten Freydt; Medy Schröder; Cornelia Baretti; Marcus Wallmann | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; firat.cetin@consultary.de; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; medy.schroeder@de.sasol.com; Cornelia.Baretti@de.sasol.com; Marcus.Wallmann@de.sasol.com | R2P | 19756 |  |  | * | NA | 2025-09-13 09:08 | 2025-09-13 18:09
40159 | STRIVE.R2.MC1.2384.1277.1.287.42.7 | N | N | N | Planned |  | Quality Certificate Profile - Post-Load Validation and Sign-off - Marl - SK | 9 hrs | 2025-09-13 09:08 | 2025-09-13 18:09 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Amit das; Nilesh Deshpande; Jay Saini; Firat; Savri Sumeet Jagatap; Torsten Freydt; Stella Hatkova | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; firat.cetin@consultary.de; ssumeetjagatap@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; stella.hatkova@sk.sasol.com | R2P | 19756 |  |  | * | NA | 2025-09-13 09:08 | 2025-09-13 18:09
19758 | STRIVE.R2.MC1.2384.1277.1.287.47 | [5 empty] | Sales Pricing Conditions | 72.77 hrs | 2025-07-14 08:00 | 2025-07-17 08:58 | [6 empty] | 2025-09-03 12:49 |  | * | NA | 2025-07-14 08:00 | 2025-07-17 08:58
19759 | STRIVE.R2.MC1.2384.1277.1.287.47.1 | Y | Y | Y | Complete |  | Sales Pricing Conditions Transformation and share Pre-Load | 53.48 hrs | 2025-09-03 12:49 | 2025-09-05 18:26 | Avinash Puranik | avpuranik@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Jessica Goffi; Mousikta chanda; Firat; Roman Mäkilä | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; Jessica.Goffi@it.sasol.com; mouchanda@deloitte.com; firat.cetin@consultary.de; roman.makila@deloitte.fi | DM | 19562 | 2025-09-03 12:49 | 2025-09-05 18:26 |  | 2025-09-01 17:02 | 2025-09-03 12:49 | 2025-09-05 18:26
19760 | STRIVE.R2.MC1.2384.1277.1.287.47.2 | Y | N | N | Sent |  | Sales Pricing Conditions Pre-Load Validation and Sign-off | 4 hrs | 2025-09-05 18:26 | 2025-09-05 22:26 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Firat; Mousikta chanda; Ramesh SathishKumar; Satyajit; Roman Mäkilä; Lueder Nonnenkamp; Stefanie Groenmeyer | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; firat.cetin@consultary.de; mouchanda@deloitte.com; satramesh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Lueder.Nonnenkamp@de.sasol.com; Stefanie.Groenmeyer@de.sasol.com | P2C | 19759 |  |  |  | 2025-09-02 11:02 | 2025-09-05 18:26 | 2025-09-05 22:26
19761 | STRIVE.R2.MC1.2384.1277.1.287.47.3 | N | N | N | Planned |  | Sales Pricing Conditions Load into S/4 and share Post-Load | 6 hrs | 2025-09-05 22:26 | 2025-09-06 04:28 | Avinash Puranik | avpuranik@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Jessica Goffi; Mousikta chanda; Firat; Roman Mäkilä | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; Jessica.Goffi@it.sasol.com; mouchanda@deloitte.com; firat.cetin@consultary.de; roman.makila@deloitte.fi | DM | 19760 |  |  |  | 2025-09-03 08:03 | 2025-09-05 22:26 | 2025-09-06 04:28
19762 | STRIVE.R2.MC1.2384.1277.1.287.47.4 | N | N | N | Planned |  | Sales Pricing Conditions Post-Load Validation and Sign-off | 4 hrs | 2025-09-06 04:28 | 2025-09-06 08:29 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Firat; Mousikta chanda; Ramesh SathishKumar; Satyajit; Roman Mäkilä; Lueder Nonnenkamp; Cornelia Baretti; Stefanie Groenmeyer | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; firat.cetin@consultary.de; mouchanda@deloitte.com; satramesh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Lueder.Nonnenkamp@de.sasol.com; Cornelia.Baretti@de.sasol.com; Stefanie.Groenmeyer@de.sasol.com | P2C | 19761 |  |  |  | 2025-09-04 08:04 | 2025-09-06 04:28 | 2025-09-06 08:29
19763 | STRIVE.R2.MC1.2384.1277.1.287.52 | [5 empty] | General maintenance task | 240.23 hrs | 2025-07-14 08:00 | 2025-07-24 08:54 | [6 empty] | 2025-09-03 13:05 |  | * | NA | 2025-07-14 08:00 | 2025-07-24 08:54
19764 | STRIVE.R2.MC1.2384.1277.1.287.52.1 | Y | Y | Y | Complete |  | General maintenance task list Transformation and share Pre-Load | 2.29 hrs | 2025-09-03 13:05 | 2025-09-03 15:22 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19648,19634,19728 | 2025-09-03 13:05 | 2025-09-03 15:22 |  | 2025-08-28 08:51 | 2025-09-03 13:05 | 2025-09-03 15:22
19765 | STRIVE.R2.MC1.2384.1277.1.287.52.2 | Y | Y | Y | Complete |  | General maintenance task list Pre-Load Validation and Sign-off - BB | 26.26 hrs | 2025-09-09 13:15 | 2025-09-10 15:34 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19764,77619 | 2025-09-09 13:15 | 2025-09-10 15:34 |  | 2025-08-29 08:04 | 2025-09-09 13:15 | 2025-09-10 15:34
21300 | STRIVE.R2.MC1.2384.1277.1.287.52.6 | Y | Y | Y | Complete |  | General maintenance task list Pre-Load Validation and Sign-off - Marl | 50.98 hrs | 2025-09-08 12:25 | 2025-09-10 15:32 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19764,77619 | 2025-09-08 12:25 | 2025-09-10 15:32 |  | 2025-08-29 08:04 | 2025-09-08 12:25 | 2025-09-10 15:32
21299 | STRIVE.R2.MC1.2384.1277.1.287.52.5 | Y | N | N | Sent |  | General maintenance task list Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-03 15:22 | 2025-09-04 00:24 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19764,77619 |  |  |  | 2025-08-29 08:04 | 2025-09-03 15:22 | 2025-09-04 00:24
19766 | STRIVE.R2.MC1.2384.1277.1.287.52.3 | N | N | N | Planned |  | General maintenance task list Load into S/4 and share Post-Load | 5 hrs | 2025-09-10 15:34 | 2025-09-10 20:34 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19765,21299,21300 |  |  |  | 2025-09-01 08:05 | 2025-09-10 15:34 | 2025-09-10 20:34
19767 | STRIVE.R2.MC1.2384.1277.1.287.52.4 | N | N | N | Planned |  | General maintenance task list Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-10 20:34 | 2025-09-11 05:36 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19766 |  |  |  | 2025-09-02 08:06 | 2025-09-10 20:34 | 2025-09-11 05:36
21302 | STRIVE.R2.MC1.2384.1277.1.287.52.8 | N | N | N | Planned |  | General maintenance task list Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-10 20:34 | 2025-09-11 05:36 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19766 |  |  |  | 2025-09-02 08:06 | 2025-09-10 20:34 | 2025-09-11 05:36
21301 | STRIVE.R2.MC1.2384.1277.1.287.52.7 | N | N | N | Planned |  | General maintenance task list Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-10 20:34 | 2025-09-11 05:36 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19766 |  |  |  | 2025-09-02 08:06 | 2025-09-10 20:34 | 2025-09-11 05:36
19768 | STRIVE.R2.MC1.2384.1277.1.287.57 | [5 empty] | Maintenance item | 98.66 hrs | 2025-07-14 08:00 | 2025-07-18 10:56 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-18 10:56
19769 | STRIVE.R2.MC1.2384.1277.1.287.57.1 | N | N | N | Planned |  | Maintenance item Transformation and share Pre-Load | 4 hrs | 2025-09-11 08:19 | 2025-09-11 12:20 | Avinash Puranik | avpuranik@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19688,19715,19766,19789 |  |  |  | 2025-09-03 07:57 | 2025-09-11 08:19 | 2025-09-11 12:20
19770 | STRIVE.R2.MC1.2384.1277.1.287.57.2 | N | N | N | Planned |  | Maintenance item Pre-Load Validation and Sign-off - BB | 9 hrs | 2025-09-11 12:20 | 2025-09-11 21:20 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19769 |  |  | * | NA | 2025-09-11 12:20 | 2025-09-11 21:20
21304 | STRIVE.R2.MC1.2384.1277.1.287.57.6 | N | N | N | Planned |  | Maintenance item Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-11 12:20 | 2025-09-11 21:20 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19769 |  |  | * | NA | 2025-09-11 12:20 | 2025-09-11 21:20
21303 | STRIVE.R2.MC1.2384.1277.1.287.57.5 | N | N | N | Planned |  | Maintenance item Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-11 12:20 | 2025-09-11 21:20 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19769 |  |  | * | NA | 2025-09-11 12:20 | 2025-09-11 21:20
19771 | STRIVE.R2.MC1.2384.1277.1.287.57.3 | N | N | N | Planned |  | Maintenance item Load into S/4 and share Post-Load | 5 hrs | 2025-09-11 21:20 | 2025-09-12 02:22 | Avinash Puranik | avpuranik@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19770,21303,21304 |  |  | * | NA | 2025-09-11 21:20 | 2025-09-12 02:22
19772 | STRIVE.R2.MC1.2384.1277.1.287.57.4 | N | N | N | Planned |  | Maintenance item Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-12 02:22 | 2025-09-12 11:23 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19771 |  |  | * | NA | 2025-09-12 02:22 | 2025-09-12 11:23
21306 | STRIVE.R2.MC1.2384.1277.1.287.57.8 | N | N | N | Planned |  | Maintenance item Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-12 02:22 | 2025-09-12 11:23 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19771 |  |  | * | NA | 2025-09-12 02:22 | 2025-09-12 11:23
21305 | STRIVE.R2.MC1.2384.1277.1.287.57.7 | N | N | N | Planned |  | Maintenance item Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-12 02:22 | 2025-09-12 11:23 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19771 |  |  | * | NA | 2025-09-12 02:22 | 2025-09-12 11:23
19773 | STRIVE.R2.MC1.2384.1277.1.287.62 | [5 empty] | Classification Assignment | 75.75 hrs | 2025-07-14 08:00 | 2025-07-17 11:57 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-17 11:57
19774 | STRIVE.R2.MC1.2384.1277.1.287.62.1 | N | N | N | Planned |  | Classification Assignment Simulate file and share findings | 4 hrs | 2025-09-02 04:31 | 2025-09-02 08:32 | Vahini | vgudisetti@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19667,19672 |  |  |  | 2025-08-28 08:02 | 2025-09-02 04:31 | 2025-09-02 08:32
40161 | STRIVE.R2.MC1.2384.1277.1.287.62.9 | N | N | N | Planned |  | Classification Assignment Transformation and share Pre-Load | 4 hrs | 2025-09-17 01:22 | 2025-09-17 05:22 | Vahini | vgudisetti@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19667,19672,77606 |  |  |  | 2025-08-28 08:02 | 2025-09-17 01:22 | 2025-09-17 05:22
19775 | STRIVE.R2.MC1.2384.1277.1.287.62.2 | N | N | N | Planned |  | Classification Assignment to Technical Object Pre-Load Validation and Sign-off -BB | 4 hrs | 2025-09-17 05:22 | 2025-09-17 09:23 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19774,40161 |  |  | * | NA | 2025-09-17 05:22 | 2025-09-17 09:23
21308 | STRIVE.R2.MC1.2384.1277.1.287.62.6 | N | N | N | Planned |  | Classification Assignment to Technical Object Pre-Load Validation and Sign-off -Marl | 4 hrs | 2025-09-17 05:22 | 2025-09-17 09:23 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19774,40161 |  |  | * | NA | 2025-09-17 05:22 | 2025-09-17 09:23
21307 | STRIVE.R2.MC1.2384.1277.1.287.62.5 | N | N | N | Planned |  | Classification Assignment to Technical Object Pre-Load Validation and Sign-off -SK | 4 hrs | 2025-09-17 05:22 | 2025-09-17 09:23 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19774,40161 |  |  | * | NA | 2025-09-17 05:22 | 2025-09-17 09:23
19776 | STRIVE.R2.MC1.2384.1277.1.287.62.3 | N | N | N | Planned |  | Classification Assignment to Technical Object Load into S/4 | 4 hrs | 2025-09-17 09:23 | 2025-09-17 13:24 | Vahini | vgudisetti@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19775,19672,19667,21307,21308 |  |  |  | 2025-08-29 08:03 | 2025-09-17 09:23 | 2025-09-17 13:24
19777 | STRIVE.R2.MC1.2384.1277.1.287.62.4 | N | N | N | Planned |  | Classification Assignment to Technical Object Post-Load Validation and Sign-off- BB | 4 hrs | 2025-09-17 13:24 | 2025-09-17 17:24 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19776 |  |  |  | 2025-09-01 08:04 | 2025-09-17 13:24 | 2025-09-17 17:24
21310 | STRIVE.R2.MC1.2384.1277.1.287.62.8 | N | N | N | Planned |  | Classification Assignment to Technical Object Post-Load Validation and Sign-off- Marl | 4 hrs | 2025-09-17 13:24 | 2025-09-17 17:24 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19776 |  |  |  | 2025-09-01 08:04 | 2025-09-17 13:24 | 2025-09-17 17:24
21309 | STRIVE.R2.MC1.2384.1277.1.287.62.7 | N | N | N | Planned |  | Classification Assignment to Technical Object Post-Load Validation and Sign-off- SK | 4 hrs | 2025-09-17 13:24 | 2025-09-17 17:24 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19776 |  |  |  | 2025-09-01 08:04 | 2025-09-17 13:24 | 2025-09-17 17:24
19778 | STRIVE.R2.MC1.2384.1277.1.287.67 |  |  |  | Complete |  | Upload Phrases | 1128.32 hrs | 2025-08-13 08:00 | 2025-09-29 11:27 | [6 empty] | 2025-09-02 12:17 |  | * | NA | 2025-08-13 08:00 | 2025-09-29 11:27
19779 | STRIVE.R2.MC1.2384.1277.1.287.67.1 | Y | Y | Y | Complete |  | Upload Phrases into S/4 | 0 hrs | 2025-09-02 12:17 | 2025-09-02 12:17 | Sheena Gour | shgour@deloitte.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Amit das; Mousikta chanda; Klaus Heitkamp; Nita Moniaga; Nilesh Deshpande; Torsten Freydt; Firat; Jay Saini; Hans Jorg; Priyanka Singhal | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; amitdas3@deloitte.com; mouchanda@deloitte.com; klaus.heitkamp@de.sasol.com; nita.moniaga@us.sasol.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de; jaysaini4@deloitte.com; hansjorg.becker@de.sasol.com; priyasinghal@deloitte.com | R2P |  | 2025-09-02 12:17 |  |  | 2025-08-11 08:00 | 2025-09-02 12:17 | 2025-09-02 12:17
19780 | STRIVE.R2.MC1.2384.1277.1.287.67.2 | Y | Y | Y | Complete |  | Phrases Post-Load Report Generation and Distribution to Validator | 0.03 hrs | 2025-09-03 22:01 | 2025-09-03 22:03 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Klaus Heitkamp; Amit das; Nita Moniaga; Nilesh Deshpande; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; klaus.heitkamp@de.sasol.com; amitdas3@deloitte.com; nita.moniaga@us.sasol.com; nideshpande@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19779 | 2025-09-03 22:01 | 2025-09-03 22:03 |  | 2025-08-11 08:00 | 2025-09-03 22:01 | 2025-09-03 22:03
19781 | STRIVE.R2.MC1.2384.1277.1.287.70 | [5 empty] | Master Inspection Characteristic | 145.53 hrs | 2025-08-13 08:00 | 2025-08-19 09:56 | [8 empty] | * | NA | 2025-08-13 08:00 | 2025-08-19 09:56
21311 | STRIVE.R2.MC1.2384.1277.1.287.70.5 | N | N | N | Planned |  | Master Inspection Characteristic Transformation and share Pre-Load | 9 hrs | 2025-09-10 20:56 | 2025-09-11 05:58 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Nilesh Deshpande; Jay Saini; Hans Jorg; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; nideshpande@deloitte.com; jaysaini4@deloitte.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | DM | 21204 |  |  |  | 2025-09-02 20:01 | 2025-09-10 20:56 | 2025-09-11 05:58
19782 | STRIVE.R2.MC1.2384.1277.1.287.70.1 | N | N | N | Planned |  | Master Inspection Characteristic Simulate file and share findings | 8 hrs | 2025-09-10 20:56 | 2025-09-11 04:58 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Nilesh Deshpande; Jay Saini; Hans Jorg; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; nideshpande@deloitte.com; jaysaini4@deloitte.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | DM | 21204 |  |  | * | NA | 2025-09-10 20:56 | 2025-09-11 04:58
19783 | STRIVE.R2.MC1.2384.1277.1.287.70.2 | N | N | N | Planned |  | Master Inspection Characteristic Pre-Load Validation and Sign-off - BB | 8 hrs | 2025-09-11 04:58 | 2025-09-11 13:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Jörg Hauf; Manfred Sprung; Michael Claußen; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; Joerg.Hauf@de.sasol.com; Manfred.Sprung@de.sasol.com; Michael.Claussen@de.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19782 |  |  | * | NA | 2025-09-11 04:58 | 2025-09-11 13:00
21313 | STRIVE.R2.MC1.2384.1277.1.287.70.7 | N | N | N | Planned |  | Master Inspection Characteristic Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-11 04:58 | 2025-09-11 14:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19782 |  |  | * | NA | 2025-09-11 04:58 | 2025-09-11 14:00
21312 | STRIVE.R2.MC1.2384.1277.1.287.70.6 | N | N | N | Planned |  | Master Inspection Characteristic Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-11 04:58 | 2025-09-11 14:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Stella Hatkova; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; stella.hatkova@sk.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19782 |  |  | * | NA | 2025-09-11 04:58 | 2025-09-11 14:00
19784 | STRIVE.R2.MC1.2384.1277.1.287.70.3 | N | N | N | Planned |  | Master Inspection Characteristic Load into S/4 and share Post-Load | 4 hrs | 2025-09-11 14:00 | 2025-09-11 18:00 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Nilesh Deshpande; Jay Saini; Hans Jorg; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; nideshpande@deloitte.com; jaysaini4@deloitte.com; hansjorg.becker@de.sasol.com; firat.cetin@consultary.de | DM | 19783,21312,21313 |  |  | * | NA | 2025-09-11 14:00 | 2025-09-11 18:00
19785 | STRIVE.R2.MC1.2384.1277.1.287.70.4 | N | N | N | Planned |  | Master Inspection Characteristic Post-Load Validation and Sign-off - BB | 8 hrs | 2025-09-11 18:00 | 2025-09-12 02:02 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Carlo Lombardini; Alessandro Mase; Concetta Ternullo; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; Carlo.Lombardini@it.sasol.com; Alessandro.Mase@it.sasol.com; Concetta.Ternullo@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19784 |  |  | * | NA | 2025-09-11 18:00 | 2025-09-12 02:02
21315 | STRIVE.R2.MC1.2384.1277.1.287.70.9 | N | N | N | Planned |  | Master Inspection Characteristic Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-11 18:00 | 2025-09-12 03:02 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Medy Schröder; Cornelia Kalfhues; Marcus Wallmann; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; medy.schroeder@de.sasol.com; Cornelia.Kalfhues@de.sasol.com; Marcus.Wallmann@de.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19784 |  |  | * | NA | 2025-09-11 18:00 | 2025-09-12 03:02
21314 | STRIVE.R2.MC1.2384.1277.1.287.70.8 | N | N | N | Planned |  | Master Inspection Characteristic Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-11 18:00 | 2025-09-12 03:02 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Stella Hatkova; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; stella.hatkova@sk.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19784 |  |  | * | NA | 2025-09-11 18:00 | 2025-09-12 03:02
19786 | STRIVE.R2.MC1.2384.1277.1.287.75 | [5 empty] | Equipment Task List | 511.33 hrs | 2025-08-13 08:00 | 2025-09-03 16:45 | [6 empty] | 2025-09-03 21:14 |  | * | NA | 2025-08-13 08:00 | 2025-09-03 16:45
19787 | STRIVE.R2.MC1.2384.1277.1.287.75.1 | Y | Y | Y | Complete |  | Equipment Task List Transformation and share Pre-Load | 0 hrs | 2025-09-03 21:14 | 2025-09-03 22:30 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19776,19728 | 2025-09-03 21:14 | 2025-09-03 22:30 |  | 2025-08-28 12:04 | 2025-09-03 21:14 | 2025-09-03 22:30
19788 | STRIVE.R2.MC1.2384.1277.1.287.75.2 | Y | Y | N | In-Progress |  | Equipment Task List Pre-Load Validation and Sign-off - BB | 9 hrs | 2025-09-10 17:16 | 2025-09-11 02:18 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19787 | 2025-09-10 17:16 |  | * | NA | 2025-09-10 17:16 | 2025-09-11 02:18
21317 | STRIVE.R2.MC1.2384.1277.1.287.75.6 | Y | Y | N | In-Progress |  | Equipment Task List Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-10 17:15 | 2025-09-11 02:17 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19787 | 2025-09-10 17:15 |  | * | NA | 2025-09-10 17:15 | 2025-09-11 02:17
21316 | STRIVE.R2.MC1.2384.1277.1.287.75.5 | Y | N | N | Sent |  | Equipment Task List Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-03 22:30 | 2025-09-04 07:32 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19787 |  |  | * | NA | 2025-09-03 22:30 | 2025-09-04 07:32
19789 | STRIVE.R2.MC1.2384.1277.1.287.75.3 | N | N | N | Planned |  | Equipment Task List Load into S/4 and share Post-Load | 6 hrs | 2025-09-11 02:18 | 2025-09-11 08:19 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19788,21316,21317 |  |  |  | 2025-09-01 08:06 | 2025-09-11 02:18 | 2025-09-11 08:19
19790 | STRIVE.R2.MC1.2384.1277.1.287.75.4 | N | N | N | Planned |  | Equipment Task List Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-11 08:19 | 2025-09-11 17:20 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19789 |  |  |  | 2025-09-02 08:07 | 2025-09-11 08:19 | 2025-09-11 17:20
21319 | STRIVE.R2.MC1.2384.1277.1.287.75.8 | N | N | N | Planned |  | Equipment Task List Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-11 08:19 | 2025-09-11 17:20 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19789 |  |  |  | 2025-09-02 08:07 | 2025-09-11 08:19 | 2025-09-11 17:20
21318 | STRIVE.R2.MC1.2384.1277.1.287.75.7 | N | N | N | Planned |  | Equipment Task List Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-11 08:19 | 2025-09-11 17:20 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19789 |  |  |  | 2025-09-02 08:07 | 2025-09-11 08:19 | 2025-09-11 17:20
19791 | STRIVE.R2.MC1.2384.1277.1.287.80 | [5 empty] | PCN Tables | 30.92 hrs | 2025-07-14 08:00 | 2025-07-15 15:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-15 15:00
19792 | STRIVE.R2.MC1.2384.1277.1.287.80.1 | N | N | N | Planned |  | PCN Tables Transformation and share Pre-Load | 8 hrs | 2025-09-09 10:58 | 2025-09-09 18:59 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19471 |  |  |  | 2025-09-09 10:58 | 2025-09-09 10:58 | 2025-09-09 18:59
19793 | STRIVE.R2.MC1.2384.1277.1.287.80.2 | N | N | N | Planned |  | PCN Tables Pre-Load Validation and Sign-off | 8 hrs | 2025-09-10 09:59 | 2025-09-10 18:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Klaus Heitkamp; Kira Willeke; Manfred Sprung; Amit das; Nilesh Deshpande; Michael Claußen; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; klaus.heitkamp@de.sasol.com; Kira.Willeke@de.sasol.com; Manfred.Sprung@de.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; Michael.Claussen@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19792 |  |  |  | 2025-09-10 09:59 | 2025-09-10 09:59 | 2025-09-10 18:00
19794 | STRIVE.R2.MC1.2384.1277.1.287.80.3 | N | N | N | Planned |  | PCN Tables Load into S/4 and share Post-Load | 8 hrs | 2025-09-11 08:00 | 2025-09-11 16:01 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Hans Jorg; Roman Mäkilä; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 19793 |  |  |  | 2025-09-11 08:00 | 2025-09-11 08:00 | 2025-09-11 16:01
19795 | STRIVE.R2.MC1.2384.1277.1.287.80.4 | N | N | N | Planned |  | PCN Tables Post-Load Validation and Sign-off | 8 hrs | 2025-09-12 08:01 | 2025-09-12 16:02 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Satyajit; Mousikta chanda; Roman Mäkilä; Klaus Heitkamp; Kira Willeke; Manfred Sprung; Amit das; Nilesh Deshpande; Michael Claußen; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; klaus.heitkamp@de.sasol.com; Kira.Willeke@de.sasol.com; Manfred.Sprung@de.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; Michael.Claussen@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19794 |  |  |  | 2025-09-12 08:01 | 2025-09-12 08:01 | 2025-09-12 16:02
40167 | STRIVE.R2.MC1.2384.1277.1.287.88 | [5 empty] | Rebate Contracts | 271.33 hrs | 2025-08-20 08:00 | 2025-08-31 16:05 | [6 empty] | 2025-09-09 15:09 |  | * | NA | 2025-08-20 08:00 | 2025-08-31 16:05
40168 | STRIVE.R2.MC1.2384.1277.1.287.88.26 | Y | Y | Y | Complete |  | Rebate Contracts - Provide enrichment file to DM team | 6.63 hrs | 2025-09-09 15:09 | 2025-09-09 21:47 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Satyajit; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Mousikta chanda; Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Viktoria Kormanikova; Anna Sifrova; Viera Chobotova; Firat | sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; mouchanda@deloitte.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; Viera.Chobotova@sk.sasol.com; firat.cetin@consultary.de | P2C |  | 2025-09-09 15:09 | 2025-09-09 21:47 | * | NA | 2025-09-09 15:09 | 2025-09-09 21:47
40169 | STRIVE.R2.MC1.2384.1277.1.287.88.27 | Y | Y | Y | Complete |  | Rebate Contracts - Simulate file and share findings | 3.39 hrs | 2025-09-09 15:24 | 2025-09-09 18:47 | Saketh | sasaketh@deloitte.com | Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Firat; Jessica Goffi; Andrea Ludeke; Tobias Wilmering; Thomas Lamp | sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; thomas.lamp@de.sasol.com | DM | 40168,19547,19634 | 2025-09-09 15:24 | 2025-09-09 18:47 | * | NA | 2025-09-09 15:24 | 2025-09-09 18:47
40164 | STRIVE.R2.MC1.2384.1277.1.287.88.22 | Y | N | N | Sent |  | Rebate Contracts - Pre-Load Validation and Sign-off | 4 hrs | 2025-09-09 18:47 | 2025-09-09 22:47 | Andrea Ludeke | Andrea.Luedeke@de.sasol.com | Tobias Wilmering; R. Schmidt-Biedenkopf; Viktoria Kormanikova; Anna Sifrova; Viera Chobotova; Jessica Goffi; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jens Nissen; Ines Tesch; Satyajit; Alex Miles; Roman Mäkilä; Firat | tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; Viera.Chobotova@sk.sasol.com; Jessica.Goffi@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; firat.cetin@consultary.de | P2C | 40169 |  |  | * | NA | 2025-09-09 18:47 | 2025-09-09 22:47
40165 | STRIVE.R2.MC1.2384.1277.1.287.88.23 | N | N | N | Planned |  | Rebate Contracts - Load into S/4 and share Post-Load | 4 hrs | 2025-09-09 22:47 | 2025-09-10 02:49 | Saketh | sasaketh@deloitte.com | Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Firat | sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM | 40164 |  |  | * | NA | 2025-09-09 22:47 | 2025-09-10 02:49
95075 | STRIVE.R2.MC1.2384.1277.1.287.88.1 | N | N | N | Planned |  | Rebate Contract - Releasing the condition contracts using WCOCOALL report | 4 hrs | 2025-09-10 02:49 | 2025-09-10 06:49 | Ramesh SathishKumar | satramesh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 40165 |  |  | * | NA | 2025-09-10 02:49 | 2025-09-10 06:49
40163 | STRIVE.R2.MC1.2384.1277.1.287.88.21 | N | N | N | Planned |  | Rebate Contracts - Post-Load Validation and Sign-off | 4 hrs | 2025-09-10 02:49 | 2025-09-10 06:49 | Andrea Ludeke | Andrea.Luedeke@de.sasol.com | Tobias Wilmering; R. Schmidt-Biedenkopf; Viktoria Kormanikova; Anna Sifrova; Viera Chobotova; Jessica Goffi; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Jens Nissen; Ines Tesch; Satyajit; Alex Miles; Roman Mäkilä; Firat | tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; Viera.Chobotova@sk.sasol.com; Jessica.Goffi@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; firat.cetin@consultary.de | P2C | 40165 |  |  | * | NA | 2025-09-10 02:49 | 2025-09-10 06:49
21328 | STRIVE.R2.MC1.2384.1277.1.287.85 |  |  |  | Complete |  | Sales BOM | 9 hrs | 2025-08-20 08:00 | 2025-08-20 17:01 | [6 empty] | 2025-08-25 13:35 | 2025-09-04 20:08 | * | NA | 2025-08-20 08:00 | 2025-08-20 17:01
21329 | STRIVE.R2.MC1.2384.1277.1.287.85.14 | Y | Y | Y | Complete |  | Sales BOM Transformation and share findings | 4.55 hrs | 2025-08-25 13:35 | 2025-08-25 18:07 | Avinash Puranik | avpuranik@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Firat; Jessica Goffi; Thomas Kokkindis; Ines Tesch; Jens Nissen | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; Thomas.Kokkinidis@de.sasol.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com | DM |  | 2025-08-25 13:35 | 2025-08-25 18:07 |  | 2025-08-25 08:00 | 2025-08-25 13:35 | 2025-08-25 18:07
21330 | STRIVE.R2.MC1.2384.1277.1.287.85.15 | Y | Y | Y | Complete |  | Sales BOM Pre-Load Validation and Sign-off | 97.14 hrs | 2025-08-25 22:04 | 2025-08-29 23:28 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Thomas; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Firat; Ines Tesch; Jens Nissen; Alex Miles; Satyajit | Thomas.Kokkinidis@de.sasol.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com | P2C | 21329 | 2025-08-25 22:04 | 2025-08-29 23:28 |  | 2025-08-26 08:00 | 2025-08-25 22:04 | 2025-08-29 23:28
21331 | STRIVE.R2.MC1.2384.1277.1.287.85.16 | Y | Y | Y | Complete |  | Sales BOM Load into S/4 and share Post-Load | 7.68 hrs | 2025-09-01 11:21 | 2025-09-01 19:03 | Avinash Puranik | avpuranik@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Firat; Jessica Goffi; Thomas Kokkindis; Ines Tesch; Jens Nissen | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; Thomas.Kokkinidis@de.sasol.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com | DM | 21330 | 2025-09-01 11:21 | 2025-09-01 19:03 |  | 2025-08-28 08:00 | 2025-09-01 11:21 | 2025-09-01 19:03
21332 | STRIVE.R2.MC1.2384.1277.1.287.85.17 | Y | Y | Y | Complete |  | Sales BOM Post-Load Validation and Sign-off | 71.63 hrs | 2025-09-01 20:18 | 2025-09-04 20:08 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Thomas; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Firat; Ines Tesch; Jens Nissen; Alex Miles; Satyajit | Thomas.Kokkinidis@de.sasol.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; firat.cetin@consultary.de; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com | P2C | 21331 | 2025-09-01 20:18 | 2025-09-04 20:08 |  | 2025-08-29 08:00 | 2025-09-01 20:18 | 2025-09-04 20:08
21337 | STRIVE.R2.MC1.2384.1277.1.287.86 | [5 empty] | Document Links - SDS | 391.07 hrs | 2025-08-20 08:00 | 2025-09-05 16:09 | [8 empty] | * | NA | 2025-08-20 08:00 | 2025-09-05 16:09
77602 | STRIVE.R2.MC1.2384.1277.1.287.86.1 |  |  |  | Complete |  | Document Links SDS - Create Document Info Record | 9 hrs | 2025-09-15 08:00 | 2025-09-15 17:01 | [9 empty] | 2025-09-15 08:00 | 2025-09-15 08:00 | 2025-09-15 17:01
21339 | STRIVE.R2.MC1.2384.1277.1.287.86.21 | N | N | N | Planned |  | Document Links SDS - Transformation and share Pre-Load | 9 hrs | 2025-09-15 08:03 | 2025-09-15 17:04 | Sampath | sampaupadhya@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satyajit; Roman Mäkilä; Alex Miles; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; firat.cetin@consultary.de | DM | 19473 |  |  |  | 2025-09-15 08:03 | 2025-09-15 08:03 | 2025-09-15 17:04
21340 | STRIVE.R2.MC1.2384.1277.1.287.86.22 | N | N | N | Planned |  | Document Links SDS - Pre-Load Validation and Sign-off | 9 hrs | 2025-09-16 08:05 | 2025-09-16 17:06 | Alex Miles | almiles@deloitte.de | Dhruv Kansal; Satyajit; Roman Mäkilä; USI STRIVE CUTOVER; Mousikta chanda; Firat | dhkansal@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 21339 |  |  |  | 2025-09-16 08:05 | 2025-09-16 08:05 | 2025-09-16 17:06
21341 | STRIVE.R2.MC1.2384.1277.1.287.86.23 | N | N | N | Planned |  | Document Links SDS - Load into S/4 and share Post-Load | 9 hrs | 2025-09-17 08:06 | 2025-09-17 17:07 | Sampath | sampaupadhya@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satyajit; Roman Mäkilä; Alex Miles; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; firat.cetin@consultary.de | DM | 21340 |  |  |  | 2025-09-17 08:06 | 2025-09-17 08:06 | 2025-09-17 17:07
21338 | STRIVE.R2.MC1.2384.1277.1.287.86.20 | N | N | N | Planned |  | Document Links SDS - Post-Load Validation and Sign-off | 9 hrs | 2025-09-18 08:07 | 2025-09-18 17:08 | Alex Miles | almiles@deloitte.de | Dhruv Kansal; Satyajit; Roman Mäkilä; USI STRIVE CUTOVER; Mousikta chanda; Firat | dhkansal@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 21341 |  |  |  | 2025-09-18 08:07 | 2025-09-18 08:07 | 2025-09-18 17:08
77608 | STRIVE.R2.MC1.2384.1277.1.287.89 | [5 empty] | Document Links - MOR | 400 hrs | 2025-08-20 08:00 | 2025-09-06 01:07 | [8 empty] | * | NA | 2025-08-20 08:00 | 2025-09-06 01:07
77609 | STRIVE.R2.MC1.2384.1277.1.287.89.30 |  |  |  | Complete |  | Document Links - MOR - Create Document Info Record | 9 hrs | 2025-08-20 08:00 | 2025-08-20 17:01 | [8 empty] | * | NA | 2025-08-20 08:00 | 2025-08-20 17:01
77610 | STRIVE.R2.MC1.2384.1277.1.287.89.31 | N | N | N | Planned |  | Document Links - MOR Transformation and share Pre-Load | 9 hrs | 2025-09-15 22:16 | 2025-09-16 07:18 | Sampath | sampaupadhya@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satyajit; Roman Mäkilä; Alex Miles; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; firat.cetin@consultary.de | DM | 19662,19688 |  |  |  | 2025-09-15 22:16 | 2025-09-15 22:16 | 2025-09-16 07:18
77605 | STRIVE.R2.MC1.2384.1277.1.287.89.26 | N | N | N | Planned |  | Document Links - MOR Pre-Load Validation and Sign-off | 9 hrs | 2025-09-16 07:18 | 2025-09-16 16:20 | Alex Miles | almiles@deloitte.de | Dhruv Kansal; Satyajit; Roman Mäkilä; USI STRIVE CUTOVER; Mousikta chanda; Firat | dhkansal@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 77610 |  |  | * | NA | 2025-09-16 07:18 | 2025-09-16 16:20
77606 | STRIVE.R2.MC1.2384.1277.1.287.89.27 | N | N | N | Planned |  | Document Links - MOR Load into S/4 and share Post-Load | 9 hrs | 2025-09-16 16:20 | 2025-09-17 01:22 | Sampath | sampaupadhya@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satyajit; Roman Mäkilä; Alex Miles; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; firat.cetin@consultary.de | DM | 77605 |  |  | * | NA | 2025-09-16 16:20 | 2025-09-17 01:22
77604 | STRIVE.R2.MC1.2384.1277.1.287.89.25 | N | N | N | Planned |  | Document Links - MOR Post-Load Validation and Sign-off | 9 hrs | 2025-09-17 01:22 | 2025-09-17 10:23 | Alex Miles | almiles@deloitte.de | Dhruv Kansal; Satyajit; Roman Mäkilä; USI STRIVE CUTOVER; Mousikta chanda; Firat | dhkansal@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de | DM | 77606 |  |  | * | NA | 2025-09-17 01:22 | 2025-09-17 10:23
19796 | STRIVE.R2.MC1.2384.1277.1.372 | [5 empty] | Tier Delta Loads (UAT & PRODUCTION) | 412.63 hrs | 2025-09-15 08:00 | 2025-10-02 13:47 | [6 empty] | 2025-08-08 18:15 |  | * | NA | 2025-09-15 08:00 | 2025-10-02 13:47
19797 | STRIVE.R2.MC1.2384.1277.1.372.1 | [5 empty] | Delta Material Master | 270.1 hrs | 2025-09-15 08:00 | 2025-09-26 14:51 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-26 14:51
19798 | STRIVE.R2.MC1.2384.1277.1.372.1.1 | N | N | N | Planned |  | Delta Material Master Transformation and share Pre-Load | 8 hrs | 2025-09-15 08:00 | 2025-09-15 16:01 | Savri Sumeet Jagatap | ssumeetjagatap@deloitte.com | Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Roman Mäkilä; Firat | sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 16:01
19799 | STRIVE.R2.MC1.2384.1277.1.372.1.2 | N | N | N | Planned |  | Delta Material Master Pre-Load Validation and Sign-off | 2 hrs | 2025-09-15 16:01 | 2025-09-15 18:01 | Ines Tesch | ines.tesch@de.sasol.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Satyajit; Roman Mäkilä; Firat | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | Cross-team | 19798 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 18:01
19800 | STRIVE.R2.MC1.2384.1277.1.372.1.3 | N | N | N | Planned |  | Delta Material Master Load into MDG | 2 hrs | 2025-09-15 18:01 | 2025-09-15 20:01 | Ines Tesch | ines.tesch@de.sasol.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Firat; Satyajit; Roman Mäkilä | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; firat.cetin@consultary.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | Cross-team | 19799 |  |  | * | NA | 2025-09-15 18:01 | 2025-09-15 20:01
19801 | STRIVE.R2.MC1.2384.1277.1.372.1.4 | N | N | N | Planned |  | Delta Material Master Replication to S/4 | 4 hrs | 2025-09-15 20:01 | 2025-09-16 00:03 | Vinit Raverkar | vnitinraverkar@deloitte.com | Tulika Pal; Tushar; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Amol Paswan; Firat | tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com; firat.cetin@consultary.de | MDG | 19800 |  |  | * | NA | 2025-09-15 20:01 | 2025-09-16 00:03
19802 | STRIVE.R2.MC1.2384.1277.1.372.1.5 | N | N | N | Planned |  | Delta Material Master Post-Load Validation and Sign-off | 2 hrs | 2025-09-16 00:03 | 2025-09-16 02:03 | Ines Tesch | ines.tesch@de.sasol.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Alex Miles; Satyajit; Roman Mäkilä; Firat | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | Cross-team | 19801 |  |  | * | NA | 2025-09-16 00:03 | 2025-09-16 02:03
19803 | STRIVE.R2.MC1.2384.1277.1.372.7 | [5 empty] | Delta Customer Master | 270.1 hrs | 2025-09-15 08:00 | 2025-09-26 14:51 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-26 14:51
19804 | STRIVE.R2.MC1.2384.1277.1.372.7.1 | N | N | N | Planned |  | Delta Customer Master Transformation and share Pre-Load | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Avinash Puranik | avpuranik@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Jessica Goffi; Roman Mäkilä | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; roman.makila@deloitte.fi | DM |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19805 | STRIVE.R2.MC1.2384.1277.1.372.7.2 | N | N | N | Planned |  | Delta Customer Master Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat; Satyajit; Roman Mäkilä | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | P2C | 19804 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19806 | STRIVE.R2.MC1.2384.1277.1.372.7.3 | N | N | N | Planned |  | Delta Customer Master Load into MDG and share Post-Load | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Avinash Puranik | avpuranik@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Jessica Goffi; Roman Mäkilä | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; roman.makila@deloitte.fi | DM | 19805 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19807 | STRIVE.R2.MC1.2384.1277.1.372.7.4 | N | N | N | Planned |  | Delta Customer Master Replication to S/4 | 4 hrs | 2025-09-15 20:01 | 2025-09-16 00:03 | Vinit Raverkar | vnitinraverkar@deloitte.com | Tulika Pal; Tushar; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Amol Paswan; Firat | tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com; firat.cetin@consultary.de | MDG | 19806 |  |  | * | NA | 2025-09-15 20:01 | 2025-09-16 00:03
19808 | STRIVE.R2.MC1.2384.1277.1.372.7.5 | N | N | N | Planned |  | Delta Customer Master Post-Load Validation and Sign-off | 4 hrs | 2025-09-16 00:03 | 2025-09-16 04:03 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat; Satyajit; Roman Mäkilä | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | P2C | 19807 |  |  | * | NA | 2025-09-16 00:03 | 2025-09-16 04:03
19809 | STRIVE.R2.MC1.2384.1277.1.372.13 | [5 empty] | Delta Vendor Master | 270.1 hrs | 2025-09-15 08:00 | 2025-09-26 14:51 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-26 14:51
19810 | STRIVE.R2.MC1.2384.1277.1.372.13.1 | N | N | N | Planned |  | Delta Vendor Master Transformation and share Pre-Load | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Rishi Tirthani | rtirthani@deloitte.com | Simonetta Confalonieri; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; ; ; ; Maria Luisa Geremicca; Roman Mäkilä | Simonetta.Confalonieri@it.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; ; ; ; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi | DM |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19811 | STRIVE.R2.MC1.2384.1277.1.372.13.2 | N | N | N | Planned |  | Delta Vendor Master Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Simonetta Confalonieri; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19810 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19812 | STRIVE.R2.MC1.2384.1277.1.372.13.3 | N | N | N | Planned |  | Delta Vendor Master Load into Coupa | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Manoj kovilpillai | mmanickrajkovilpi@deloitte.com | Aparajita Mukherjee; Milton; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19811 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19813 | STRIVE.R2.MC1.2384.1277.1.372.13.4 | N | N | N | Planned |  | Delta Vendor Master Replication to S/4 | 4 hrs | 2025-09-15 20:01 | 2025-09-16 00:03 | Vinit Raverkar | vnitinraverkar@deloitte.com | Tulika Pal; Tushar; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Amol Paswan; Firat | tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com; firat.cetin@consultary.de | MDG | 19812 |  |  | * | NA | 2025-09-15 20:01 | 2025-09-16 00:03
19814 | STRIVE.R2.MC1.2384.1277.1.372.13.5 | N | N | N | Planned |  | Delta Vendor Master Post-Load Validation and Sign-off | 4 hrs | 2025-09-16 00:03 | 2025-09-16 04:03 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Simonetta Confalonieri; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19813 |  |  | * | NA | 2025-09-16 00:03 | 2025-09-16 04:03
19815 | STRIVE.R2.MC1.2384.1277.1.372.19 | [5 empty] | Delta Service Master | 78.73 hrs | 2025-09-15 08:00 | 2025-09-18 14:57 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-18 14:57
19816 | STRIVE.R2.MC1.2384.1277.1.372.19.1 | N | N | N | Planned |  | Delta Service Master Transformation and share Pre-Load | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Rishi Tirthani | rtirthani@deloitte.com | Simonetta Confalonieri; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; ; ; ; Maria Luisa Geremicca; Roman Mäkilä | Simonetta.Confalonieri@it.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; ; ; ; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi | DM |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19817 | STRIVE.R2.MC1.2384.1277.1.372.19.2 | N | N | N | Planned |  | Delta Service Master Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Simonetta Confalonieri; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19816 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19818 | STRIVE.R2.MC1.2384.1277.1.372.19.3 | N | N | N | Planned |  | Delta Service Master Load into MDG and share Post-Load | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Rishi Tirthani | rtirthani@deloitte.com | Simonetta Confalonieri; Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; ; ; ; Maria Luisa Geremicca; Roman Mäkilä | Simonetta.Confalonieri@it.sasol.com; ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; ; ; ; marialuisa.geremicca@it.sasol.com; roman.makila@deloitte.fi | DM | 19817 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19819 | STRIVE.R2.MC1.2384.1277.1.372.19.4 | N | N | N | Planned |  | Delta Service Master Replication to S/4 | 4 hrs | 2025-09-15 20:01 | 2025-09-16 00:03 | Vinit Raverkar | vnitinraverkar@deloitte.com | Tulika Pal; Tushar; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Amol Paswan; Firat | tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ampaswan@deloitte.com; firat.cetin@consultary.de | MDG | 19818 |  |  | * | NA | 2025-09-15 20:01 | 2025-09-16 00:03
19820 | STRIVE.R2.MC1.2384.1277.1.372.19.5 | N | N | N | Planned |  | Delta Service Master Post-Load Validation and Sign-off | 4 hrs | 2025-09-16 00:03 | 2025-09-16 04:03 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat; Simonetta Confalonieri; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de; Simonetta.Confalonieri@it.sasol.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19819 |  |  | * | NA | 2025-09-16 00:03 | 2025-09-16 04:03
19821 | STRIVE.R2.MC1.2384.1277.1.372.25 |  |  |  | Complete |  | Delta Bank Master (Not Applicable for MC1) | 29.9 hrs | 2025-09-15 08:00 | 2025-09-16 13:59 | [6 empty] | 2025-08-08 18:15 |  | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19822 | STRIVE.R2.MC1.2384.1277.1.372.25.1 | Y | Y | Y | Complete |  | Delta Bank Master Pre-Load Validation and Sign-off (Not Applicable for MC1) | 4 hrs | 2025-08-08 18:15 | 2025-09-15 12:00 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Maria Lusardi; ; Patrizia; Tatiana; Roshanlal; Satyajit; Roman Mäkilä; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; maria.lusardi@it.sasol.com; ; patrizia.vergani@it.sasol.com; tvinogradova@deloitte.de; rohemwani@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | R2D |  | 2025-08-08 18:15 |  | * | NA | 2025-08-08 18:15 | 2025-09-15 12:00
19823 | STRIVE.R2.MC1.2384.1277.1.372.25.2 | Y | Y | Y | Complete |  | Delta Bank Master - Manual Adjustments into S/4 (Not Applicable for MC1) | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Maria Lusardi; Firat; Patrizia; Tatiana; Roshanlal | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; maria.lusardi@it.sasol.com; firat.cetin@consultary.de; patrizia.vergani@it.sasol.com; tvinogradova@deloitte.de; rohemwani@deloitte.com | R2D | 19822 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19824 | STRIVE.R2.MC1.2384.1277.1.372.25.3 | Y | Y | Y | Complete |  | Delta Bank Master Post-Load Validation and Sign-off (Not Applicable for MC1) | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Maria Lusardi; Firat; Patrizia; Tatiana; Roshanlal; Satyajit; Roman Mäkilä | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; maria.lusardi@it.sasol.com; firat.cetin@consultary.de; patrizia.vergani@it.sasol.com; tvinogradova@deloitte.de; rohemwani@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi | R2D | 19823 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19825 | STRIVE.R2.MC1.2384.1277.1.372.29 | [5 empty] | Delta Project& WBS | 101.65 hrs | 2025-09-15 08:00 | 2025-09-19 13:56 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-19 13:56
19826 | STRIVE.R2.MC1.2384.1277.1.372.29.1 | N | N | N | Planned |  | Delta Project/WBS - Handover of Change Log from new system to DM Team | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Krishna Teja; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sergio; Elisa Latona; Amit Jha; Firat; ; ; Chaitnya; Abhishek Sharma; Moonalisa; Satyajit Patnaik; Roman Mäkilä; Alex Miles | joseph.barber@us.sasol.com; krishn@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; firat.cetin@consultary.de; ; ; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; mooghosh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19827 | STRIVE.R2.MC1.2384.1277.1.372.29.2 | N | N | N | Planned |  | Delta Project& WBS Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Krishna Teja; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sergio; Elisa Latona; Amit Jha; Firat; ; ; Chaitnya; Abhishek Sharma; Moonalisa; Satyajit Patnaik; Roman Mäkilä; Alex Miles | joseph.barber@us.sasol.com; krishn@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; firat.cetin@consultary.de; ; ; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; mooghosh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de | MOR | 19826 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19828 | STRIVE.R2.MC1.2384.1277.1.372.29.3 | N | N | N | Planned |  | Delta Project& WBS Load into S/4 and share Post-Load | 1.5 hrs | 2025-09-15 16:01 | 2025-09-15 17:31 | Moonalisa | mooghosh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Firat; Sven Gelking; Joseph Barber; Elisa Latona; Roman Mäkilä; Nikhil Gupta; Mythili | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de; sven.gelking@de.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; roman.makila@deloitte.fi; mrgupta3@deloitte.com; myboyapati@deloitte.com | DM | 19827 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 17:31
19829 | STRIVE.R2.MC1.2384.1277.1.372.29.4 | N | N | N | Planned |  | Delta Project& WBS Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 17:31 | 2025-09-15 21:31 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Krishna Teja; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sergio; Elisa Latona; Amit Jha; Firat; ; ; Chaitnya; Abhishek Sharma; Moonalisa; Satyajit Patnaik; Roman Mäkilä; Alex Miles | joseph.barber@us.sasol.com; krishn@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; ajha2@deloitte.no; firat.cetin@consultary.de; ; ; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; mooghosh@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de | MOR | 19828 |  |  | * | NA | 2025-09-15 17:31 | 2025-09-15 21:31
19830 | STRIVE.R2.MC1.2384.1277.1.372.29.5 | N | N | N | Planned |  | Delta WBS - Share WBS Details with coupa Team | 4 hrs | 2025-09-15 21:31 | 2025-09-16 01:33 | Mythili | myboyapati@deloitte.com | Nikhil Gupta; Vinod Kumar; Jay Patel; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Amit Jha; Firat | mrgupta3@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; ajha2@deloitte.no; firat.cetin@consultary.de | MOR | 19829 |  |  | * | NA | 2025-09-15 21:31 | 2025-09-16 01:33
19831 | STRIVE.R2.MC1.2384.1277.1.372.29.6 | N | N | N | Planned |  | Delta WBS - Populate WBS in a Coupa Acceptable Format | 4 hrs | 2025-09-16 01:33 | 2025-09-16 05:33 | Supriya | supriychakraborty@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19830 |  |  | * | NA | 2025-09-16 01:33 | 2025-09-16 05:33
19832 | STRIVE.R2.MC1.2384.1277.1.372.29.7 | N | N | N | Planned |  | Delta WBS - Coupa- Pre Load Validation and sign off | 4 hrs | 2025-09-16 05:33 | 2025-09-16 09:34 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19831 |  |  | * | NA | 2025-09-16 05:33 | 2025-09-16 09:34
19833 | STRIVE.R2.MC1.2384.1277.1.372.29.8 | N | N | N | Planned |  | Delta Load WBS in Coupa | 4 hrs | 2025-09-16 09:34 | 2025-09-16 13:35 | Supriya | supriychakraborty@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19832 |  |  | * | NA | 2025-09-16 09:34 | 2025-09-16 13:35
19834 | STRIVE.R2.MC1.2384.1277.1.372.29.9 | N | N | N | Planned |  | Delta WBS - Coupa - Post Load Validation and sign off | 4 hrs | 2025-09-16 13:35 | 2025-09-16 17:35 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Supriya; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Mousikta chanda; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; supriychakraborty@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19833 |  |  | * | NA | 2025-09-16 13:35 | 2025-09-16 17:35
19835 | STRIVE.R2.MC1.2384.1277.1.372.39 | [5 empty] | Delta Sales Pricing Conditions | 29.9 hrs | 2025-09-15 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19836 | STRIVE.R2.MC1.2384.1277.1.372.39.1 | N | N | N | Planned |  | Delta Sales Pricing Conditions Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat; Satyajit; Roman Mäkilä | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19837 | STRIVE.R2.MC1.2384.1277.1.372.39.2 | N | N | N | Planned |  | Delta Sales Pricing Conditions - Manual Adjustment in S/4 | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat; | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de; | P2C | 19836 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19838 | STRIVE.R2.MC1.2384.1277.1.372.39.3 | N | N | N | Planned |  | Delta Sales Pricing Conditions Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat; Satyajit; Roman Mäkilä | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | P2C | 19837 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19839 | STRIVE.R2.MC1.2384.1277.1.372.43 | [5 empty] | Delta CMIR | 29.9 hrs | 2025-09-15 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19840 | STRIVE.R2.MC1.2384.1277.1.372.43.1 | N | N | N | Planned |  | Delta CMIR Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat; Satyajit; Roman Mäkilä | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19841 | STRIVE.R2.MC1.2384.1277.1.372.43.2 | N | N | N | Planned |  | Delta CMIR - Manual Adjustment in S/4 | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de | P2C | 19840 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19842 | STRIVE.R2.MC1.2384.1277.1.372.43.3 | N | N | N | Planned |  | Delta CMIR Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Ramesh SathishKumar; Firat; Satyajit; Roman Mäkilä | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; satramesh@deloitte.com; firat.cetin@consultary.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi | P2C | 19841 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19843 | STRIVE.R2.MC1.2384.1277.1.372.47 | [5 empty] | Delta Material BOM | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19844 | STRIVE.R2.MC1.2384.1277.1.372.47.1 | N | N | N | Planned |  | Delta Material BOM Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Gianluigi Loru; Giovanni Merendino; Antonio Zinzalini; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; gianluigi.loru@it.sasol.com; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19845 | STRIVE.R2.MC1.2384.1277.1.372.47.2 | N | N | N | Planned |  | Delta Material BOM - Manual Adjustment in S/4 | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19844 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19846 | STRIVE.R2.MC1.2384.1277.1.372.47.3 | N | N | N | Planned |  | Delta Material BOM Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Gianluigi Loru; Giovanni Merendino; Antonio Zinzalini; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; gianluigi.loru@it.sasol.com; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19845 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19847 | STRIVE.R2.MC1.2384.1277.1.372.51 | [5 empty] | Delta Production Version | 29.9 hrs | 2025-09-15 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19848 | STRIVE.R2.MC1.2384.1277.1.372.51.1 | N | N | N | Planned |  | Delta Production Version Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19849 | STRIVE.R2.MC1.2384.1277.1.372.51.2 | N | N | N | Planned |  | Delta Production Version - Manual Adjustment in S/4 | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19848 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19850 | STRIVE.R2.MC1.2384.1277.1.372.51.3 | N | N | N | Planned |  | Delta Production Version Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19849 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19851 | STRIVE.R2.MC1.2384.1277.1.372.55 | [5 empty] | Delta Batch | 29.9 hrs | 2025-09-15 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19852 | STRIVE.R2.MC1.2384.1277.1.372.55.1 | N | N | N | Planned |  | Delta Batch Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19853 | STRIVE.R2.MC1.2384.1277.1.372.55.2 | N | N | N | Planned |  | Delta Batch - Manual Adjustment in S/4 | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19852 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19854 | STRIVE.R2.MC1.2384.1277.1.372.55.3 | N | N | N | Planned |  | Delta Batch Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19853 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19855 | STRIVE.R2.MC1.2384.1277.1.372.59 | [5 empty] | Delta Master Recipes | 29.9 hrs | 2025-09-15 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19856 | STRIVE.R2.MC1.2384.1277.1.372.59.1 | N | N | N | Planned |  | Delta Master Recipes Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19857 | STRIVE.R2.MC1.2384.1277.1.372.59.2 | N | N | N | Planned |  | Delta Master Recipes - Manual Adjustment in S/4 | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19856 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19858 | STRIVE.R2.MC1.2384.1277.1.372.59.3 | N | N | N | Planned |  | Delta Master Recipes Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Giovanni Merendino; Antonio Zinzalini; Gianluigi Loru; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; gianluigi.loru@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19857 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19859 | STRIVE.R2.MC1.2384.1277.1.372.63 | [5 empty] | Delta Substance / Specification | 29.9 hrs | 2025-09-15 08:00 | 2025-09-16 13:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 13:59
19860 | STRIVE.R2.MC1.2384.1277.1.372.63.1 | N | N | N | Planned |  | Delta Substance / Specification Pre-Load Validation and Sign-off | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Gianluigi Loru; Giovanni Merendino; Antonio Zinzalini; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; gianluigi.loru@it.sasol.com; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19861 | STRIVE.R2.MC1.2384.1277.1.372.63.2 | N | N | N | Planned |  | Delta Substance / Specification - Manual Adjustment in S/4 | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Gianluigi Loru; Giovanni Merendino; Antonio Zinzalini; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; gianluigi.loru@it.sasol.com; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19860 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19862 | STRIVE.R2.MC1.2384.1277.1.372.63.3 | N | N | N | Planned |  | Delta Substance / Specification Post-Load Validation and Sign-off | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Hans-Jörg Becker | hansjorg.becker@de.sasol.com | Alex Pradeep; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Satyajit; Roman Mäkilä; Gianluigi Loru; Giovanni Merendino; Antonio Zinzalini; Amit das; Nilesh Deshpande; Jay Saini; Torsten Freydt; Firat | alex.pradeep@us.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; gianluigi.loru@it.sasol.com; Giovanni.Merendino@it.sasol.com; antonio.zinzalini@it.sasol.com; amitdas3@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; firat.cetin@consultary.de | R2P | 19861 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19863 | STRIVE.R2.MC1.2384.1277.1.372.67 |  |  |  | Complete |  | Costing Preparation for Delta Materials (Not Applicable for MC1) | 99.73 hrs | 2025-09-15 08:00 | 2025-09-19 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-19 12:00
19864 | STRIVE.R2.MC1.2384.1277.1.372.67.1 | Y | Y | Y | Complete |  | If needed for delta materials, preparation of plan prices for purchased materials (components) forecast prices for March (Not Applicable for MC1) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal Hemwani; Tatiana; Firat | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; firat.cetin@consultary.de | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19865 | STRIVE.R2.MC1.2384.1277.1.372.67.2 | Y | Y | Y | Complete |  | If needed for delta, Validate the activity rates (Not Applicable for MC1) | 4 hrs | 2025-09-15 12:01 | 2025-09-15 16:01 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal Hemwani; Tatiana; Firat | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; firat.cetin@consultary.de | R2D | 19864 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 16:01
19866 | STRIVE.R2.MC1.2384.1277.1.372.67.3 | Y | Y | Y | Complete |  | If needed for delta materials, Upload conditions for profit center valuation (Not Applicable for MC1) | 4 hrs | 2025-09-15 16:01 | 2025-09-15 20:01 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal Hemwani; Tatiana; Firat | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; firat.cetin@consultary.de | R2D | 19865 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 20:01
19867 | STRIVE.R2.MC1.2384.1277.1.372.67.4 | Y | Y | Y | Complete |  | If needed for delta materials, Run standard cost estimates with validity 01.04.2025 (Not Applicable for MC1) | 4 hrs | 2025-09-15 20:01 | 2025-09-16 00:03 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal Hemwani; Tatiana; Firat | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; firat.cetin@consultary.de | R2D | 19866 |  |  | * | NA | 2025-09-15 20:01 | 2025-09-16 00:03
19868 | STRIVE.R2.MC1.2384.1277.1.372.72 | [5 empty] | Delta Coupa Item | 27.3 hrs | 2025-09-15 08:00 | 2025-09-16 11:22 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 11:22
19869 | STRIVE.R2.MC1.2384.1277.1.372.72.1 | N | N | N | Planned |  | Delta Coupa Item - Share the S/4 Postload file | 4 hrs | 2025-09-16 00:03 | 2025-09-16 04:03 | Priyadharshani | pkandan@deloitte.com | Prasanth; S2P Team; Rishi Tirthani; Alex Miles; Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; usisasols2p@deloitte.com; rtirthani@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19801,19819 |  |  | * | NA | 2025-09-16 00:03 | 2025-09-16 04:03
19870 | STRIVE.R2.MC1.2384.1277.1.372.72.2 | N | N | N | Planned |  | Delta Coupa Item - Prepare the Coupa file | 4 hrs | 2025-09-16 04:03 | 2025-09-16 08:04 | Rahul Sengupta | rahusengupta@deloitte.com | Aparajita Mukherjee; S2P Team; Rishi Tirthani; Alex Miles; Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usisasols2p@deloitte.com; rtirthani@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19869 |  |  | * | NA | 2025-09-16 04:03 | 2025-09-16 08:04
19871 | STRIVE.R2.MC1.2384.1277.1.372.72.3 | N | N | N | Planned |  | Delta Coupa Item Pre-Load Validation and Sign-off | 4 hrs | 2025-09-16 08:04 | 2025-09-16 12:05 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19870 |  |  | * | NA | 2025-09-16 08:04 | 2025-09-16 12:05
19872 | STRIVE.R2.MC1.2384.1277.1.372.72.4 | N | N | N | Planned |  | Delta Coupa Item - Load in Coupa | 4 hrs | 2025-09-16 12:05 | 2025-09-16 16:05 | Rahul Sengupta | rahusengupta@deloitte.com | Prasanth; S2P Team; Sandeep Galhotra; Alex Miles; Satyajit Patnaik; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; usisasols2p@deloitte.com; sagalhotra@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19871 |  |  | * | NA | 2025-09-16 12:05 | 2025-09-16 16:05
19873 | STRIVE.R2.MC1.2384.1277.1.372.72.5 | N | N | N | Planned |  | Delta Coupa Item Post-Load Validation and Sign-off | 4 hrs | 2025-09-16 16:05 | 2025-09-16 20:05 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19872 |  |  | * | NA | 2025-09-16 16:05 | 2025-09-16 20:05
19874 | STRIVE.R2.MC1.2384.1277.1.372.78 | [5 empty] | Delta Supplier Item | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19875 | STRIVE.R2.MC1.2384.1277.1.372.78.1 | N | N | N | Planned |  | Delta Supplier Item - Share the S/4 Postload file | 4 hrs | 2025-09-16 20:05 | 2025-09-17 00:07 | Priyadharshani | pkandan@deloitte.com | Prasanth; S2P Team; Rishi Tirthani; Alex Miles; Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; usisasols2p@deloitte.com; rtirthani@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19885,19891 |  |  | * | NA | 2025-09-16 20:05 | 2025-09-17 00:07
19876 | STRIVE.R2.MC1.2384.1277.1.372.78.2 | N | N | N | Planned |  | Delta Supplier Item - Prepare the Coupa supplier item file | 4 hrs | 2025-09-17 00:07 | 2025-09-17 04:07 | Supriya | supriychakraborty@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; S2P Team; Rishi Tirthani; Alex Miles; Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Esmir Divljanovic; Firat | rahusengupta@deloitte.com; apamukherjee@deloitte.com; usisasols2p@deloitte.com; rtirthani@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19875 |  |  | * | NA | 2025-09-17 00:07 | 2025-09-17 04:07
19877 | STRIVE.R2.MC1.2384.1277.1.372.78.3 | N | N | N | Planned |  | Delta Supplier Item Pre-Load Validation and Sign-off | 4 hrs | 2025-09-17 04:07 | 2025-09-17 08:08 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19876 |  |  | * | NA | 2025-09-17 04:07 | 2025-09-17 08:08
19878 | STRIVE.R2.MC1.2384.1277.1.372.78.4 | N | N | N | Planned |  | Delta Supplier Item - Load in Coupa | 4 hrs | 2025-09-17 08:08 | 2025-09-17 12:09 | Supriya | supriychakraborty@deloitte.com | Rahul Sengupta; Aparajita Mukherjee; S2P Team; Rishi Tirthani; Alex Miles; Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Esmir Divljanovic; Firat | rahusengupta@deloitte.com; apamukherjee@deloitte.com; usisasols2p@deloitte.com; rtirthani@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19877 |  |  | * | NA | 2025-09-17 08:08 | 2025-09-17 12:09
19879 | STRIVE.R2.MC1.2384.1277.1.372.78.5 | N | N | N | Planned |  | Delta Supplier Item Post-Load Validation and Sign-off | 4 hrs | 2025-09-17 12:09 | 2025-09-17 16:09 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19878 |  |  | * | NA | 2025-09-17 12:09 | 2025-09-17 16:09
19880 | STRIVE.R2.MC1.2384.1277.1.372.84 | [5 empty] | Delta Purchase Info Record | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19881 | STRIVE.R2.MC1.2384.1277.1.372.84.1 | N | N | N | Planned |  | Delta Purchase Info Record - Transform and share the pre-load | 4 hrs | 2025-09-16 00:03 | 2025-09-16 04:03 | Rishi Tirthani | rtirthani@deloitte.com | Alex Miles; Roman Mäkilä; Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Firat | almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; firat.cetin@consultary.de | DM | 19801,19813 |  |  | * | NA | 2025-09-16 00:03 | 2025-09-16 04:03
19882 | STRIVE.R2.MC1.2384.1277.1.372.84.2 | N | N | N | Planned |  | Delta Purchase Info Record Pre-Load Validation and Sign-off | 4 hrs | 2025-09-16 04:03 | 2025-09-16 08:04 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19881 |  |  | * | NA | 2025-09-16 04:03 | 2025-09-16 08:04
19883 | STRIVE.R2.MC1.2384.1277.1.372.84.3 | N | N | N | Planned |  | Delta Purchase Info Record - Manual Adjustment in S/4 | 4 hrs | 2025-09-16 08:04 | 2025-09-16 12:05 | Priyadharshani | pkandan@deloitte.com | Prasanth; S2P Team; Sandeep Galhotra; Alex Miles; Satyajit Patnaik; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; usisasols2p@deloitte.com; sagalhotra@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19882 |  |  | * | NA | 2025-09-16 08:04 | 2025-09-16 12:05
19884 | STRIVE.R2.MC1.2384.1277.1.372.84.4 | N | N | N | Planned |  | Delta Purchase Info Record - share the post load with Sasol | 4 hrs | 2025-09-16 12:05 | 2025-09-16 16:05 | Rishi Tirthani | rtirthani@deloitte.com | Alex Miles; Roman Mäkilä; Satyajit; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Firat | almiles@deloitte.de; roman.makila@deloitte.fi; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; firat.cetin@consultary.de | DM | 19883 |  |  | * | NA | 2025-09-16 12:05 | 2025-09-16 16:05
19885 | STRIVE.R2.MC1.2384.1277.1.372.84.5 | N | N | N | Planned |  | Delta Purchase Info Record Post-Load Validation and Sign-off | 4 hrs | 2025-09-16 16:05 | 2025-09-16 20:05 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19884 |  |  | * | NA | 2025-09-16 16:05 | 2025-09-16 20:05
19886 | STRIVE.R2.MC1.2384.1277.1.372.90 | [5 empty] | Delta Purchasing Contracts | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19887 | STRIVE.R2.MC1.2384.1277.1.372.90.1 | N | N | N | Planned |  | Delta Purchasing Contracts - Transform and share the pre-load | 4 hrs | 2025-09-16 00:03 | 2025-09-16 04:03 | Rishi Tirthani | rtirthani@deloitte.com | Satyajit; Alex Miles; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aparajita Mukherjee; S2P Team; Firat | sapatnaik@deloitte.com; almiles@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; apamukherjee@deloitte.com; usisasols2p@deloitte.com; firat.cetin@consultary.de | DM | 19801,19813,19819 |  |  | * | NA | 2025-09-16 00:03 | 2025-09-16 04:03
19888 | STRIVE.R2.MC1.2384.1277.1.372.90.2 | N | N | N | Planned |  | Delta Purchasing Contracts - Prepare the coupa load file | 4 hrs | 2025-09-16 04:03 | 2025-09-16 08:04 | Aparajita Mukherjee | apamukherjee@deloitte.com | Rahul Sengupta; Prasanth; S2P Team; Sandeep Galhotra; Alex Miles; Satyajit Patnaik; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Esmir Divljanovic; Firat | rahusengupta@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; sagalhotra@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19887 |  |  | * | NA | 2025-09-16 04:03 | 2025-09-16 08:04
19889 | STRIVE.R2.MC1.2384.1277.1.372.90.3 | N | N | N | Planned |  | Delta Purchasing Contracts Pre-Load Validation and Sign-off | 4 hrs | 2025-09-16 08:04 | 2025-09-16 12:05 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19888 |  |  | * | NA | 2025-09-16 08:04 | 2025-09-16 12:05
19890 | STRIVE.R2.MC1.2384.1277.1.372.90.4 | N | N | N | Planned |  | Delta Purchasing Contracts - Load in Coupa | 4 hrs | 2025-09-16 12:05 | 2025-09-16 16:05 | Aparajita Mukherjee | apamukherjee@deloitte.com | Rahul Sengupta; Prasanth; S2P Team; Sandeep Galhotra; Alex Miles; Satyajit Patnaik; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Esmir Divljanovic; Firat | rahusengupta@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; sagalhotra@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19889 |  |  | * | NA | 2025-09-16 12:05 | 2025-09-16 16:05
19891 | STRIVE.R2.MC1.2384.1277.1.372.90.5 | N | N | N | Planned |  | Delta Purchasing Contracts Post-Load Validation and Sign-off | 4 hrs | 2025-09-16 16:05 | 2025-09-16 20:05 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Tina Vidrine; Frank Toedter ; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19890 |  |  | * | NA | 2025-09-16 16:05 | 2025-09-16 20:05
19892 | STRIVE.R2.MC1.2384.1277.1.468 | [5 empty] | Tier 4 Blackout Window | 438.56 hrs | 2025-08-25 08:00 | 2025-09-12 15:47 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-08-25 08:00 | 2025-09-12 15:47
19893 | STRIVE.R2.MC1.2384.1277.1.468.1 | N | N | N | Ready |  | Start Blackout Window - Notification Task | 1 hrs | 2025-08-25 08:00 | 2025-08-25 09:00 | Dhruv Kansal | dhkansal@deloitte.com | Mousikta chanda; Alex Miles; Satyajit Patnaik; USI STRIVE CUTOVER | mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; usistrivecutover@deloitte.com | Cutover |  |  |  | * | NA | 2025-08-25 08:00 | 2025-08-25 09:00
19894 | STRIVE.R2.MC1.2384.1277.1.468.2 | [5 empty] | Maintenance notification | 56.85 hrs | 2025-07-14 08:00 | 2025-07-16 17:00 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-16 17:00
19895 | STRIVE.R2.MC1.2384.1277.1.468.2.1 | N | N | N | Ready |  | Maintenance notification Extraction (Production Only) | 4 hrs | 2025-09-08 08:00 | 2025-09-08 12:00 | Moonalisa | mooghosh@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Sven Gelking; Elisa Latona; Joseph Barber; Roman Mäkilä; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | DM |  |  |  |  | 2025-09-08 08:00 | 2025-09-08 08:00 | 2025-09-08 12:00
19897 | STRIVE.R2.MC1.2384.1277.1.468.2.3 | N | N | N | Planned |  | Maintenance notification Transformation and share Pre-Load | 4 hrs | 2025-09-09 09:00 | 2025-09-09 13:01 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19893 |  |  |  | 2025-09-09 09:00 | 2025-09-09 09:00 | 2025-09-09 13:01
19898 | STRIVE.R2.MC1.2384.1277.1.468.2.4 | N | N | N | Planned |  | Maintenance notification Pre-Load Validation and Sign-off - BB | 9 hrs | 2025-09-10 08:01 | 2025-09-10 17:02 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19897 |  |  |  | 2025-09-10 08:01 | 2025-09-10 08:01 | 2025-09-10 17:02
21343 | STRIVE.R2.MC1.2384.1277.1.468.2.9 | N | N | N | Planned |  | Maintenance notification Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-10 08:01 | 2025-09-10 17:02 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19897 |  |  |  | 2025-09-10 08:01 | 2025-09-10 08:01 | 2025-09-10 17:02
21342 | STRIVE.R2.MC1.2384.1277.1.468.2.8 | N | N | N | Planned |  | Maintenance notification Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-10 08:01 | 2025-09-10 17:02 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19897 |  |  |  | 2025-09-10 08:01 | 2025-09-10 08:01 | 2025-09-10 17:02
19899 | STRIVE.R2.MC1.2384.1277.1.468.2.5 | N | N | N | Planned |  | Maintenance notification Load into S/4 and share Post-Load | 9 hrs | 2025-09-12 08:02 | 2025-09-12 17:03 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19898,21342,21343 |  |  |  | 2025-09-12 08:02 | 2025-09-12 08:02 | 2025-09-12 17:03
19900 | STRIVE.R2.MC1.2384.1277.1.468.2.6 | N | N | N | Planned |  | Maintenance notification Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-15 08:03 | 2025-09-15 17:04 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19899 |  |  |  | 2025-09-15 08:03 | 2025-09-15 08:03 | 2025-09-15 17:04
21345 | STRIVE.R2.MC1.2384.1277.1.468.2.11 | N | N | N | Planned |  | Maintenance notification Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-15 08:03 | 2025-09-15 17:04 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19899 |  |  |  | 2025-09-15 08:03 | 2025-09-15 08:03 | 2025-09-15 17:04
21344 | STRIVE.R2.MC1.2384.1277.1.468.2.10 | N | N | N | Planned |  | Maintenance notification Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-15 08:03 | 2025-09-15 17:04 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19899 |  |  |  | 2025-09-15 08:03 | 2025-09-15 08:03 | 2025-09-15 17:04
19901 | STRIVE.R2.MC1.2384.1277.1.468.2.7 | N | N | N | Planned |  | Change the notification status from CRTD status to NOPR and NOCO | 8 hrs | 2025-09-15 17:04 | 2025-09-16 01:06 | Abhishek Sharma | abhisheksharma59@deloitte.com | Vinod Kumar; suyash Chhawala; Jay Patel; Amit Jha; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Chaitnya; Firat | vinodkumar692@deloitte.com; schhawala@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; csudhakarraut@deloitte.com; firat.cetin@consultary.de | MOR | 19900 |  |  | * | NA | 2025-09-15 17:04 | 2025-09-16 01:06
19902 | STRIVE.R2.MC1.2384.1277.1.468.10 | [5 empty] | Maintenance Work Orders | 71.84 hrs | 2025-08-25 08:00 | 2025-08-28 08:02 | [8 empty] | * | NA | 2025-08-25 08:00 | 2025-08-28 08:02
19907 | STRIVE.R2.MC1.2384.1277.1.468.10.5 | N | N | N | Planned |  | Maintenance Work Orders Transformation and share Pre-Load | 6 hrs | 2025-09-12 17:03 | 2025-09-12 23:03 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19899 |  |  |  | 2025-09-10 20:03 | 2025-09-12 17:03 | 2025-09-12 23:03
19908 | STRIVE.R2.MC1.2384.1277.1.468.10.6 | N | N | N | Planned |  | Maintenance Work Orders Pre-Load Validation and Sign-off - BB | 9 hrs | 2025-09-12 23:03 | 2025-09-13 08:06 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19907 |  |  | * | NA | 2025-09-12 23:03 | 2025-09-13 08:06
21346 | STRIVE.R2.MC1.2384.1277.1.468.10.14 | N | N | N | Planned |  | Maintenance Work Orders Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-12 23:03 | 2025-09-13 08:06 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19907 |  |  | * | NA | 2025-09-12 23:03 | 2025-09-13 08:06
19909 | STRIVE.R2.MC1.2384.1277.1.468.10.7 | N | N | N | Planned |  | Maintenance Work Orders Load into S/4 and share Post-Load | 9 hrs | 2025-09-15 08:06 | 2025-09-15 17:07 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19908,21346 |  |  |  | 2025-09-15 08:06 | 2025-09-15 08:06 | 2025-09-15 17:07
19910 | STRIVE.R2.MC1.2384.1277.1.468.10.8 | N | N | N | Planned |  | Maintenance Work Orders Post-Load Validation and Sign-off - BB | 9 hrs | 2025-09-16 08:07 | 2025-09-16 17:08 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19909 |  |  |  | 2025-09-16 08:07 | 2025-09-16 08:07 | 2025-09-16 17:08
21347 | STRIVE.R2.MC1.2384.1277.1.468.10.15 | N | N | N | Planned |  | Maintenance Work Orders Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-16 08:07 | 2025-09-16 17:08 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19909 |  |  |  | 2025-09-16 08:07 | 2025-09-16 08:07 | 2025-09-16 17:08
19911 | STRIVE.R2.MC1.2384.1277.1.468.10.9 | N | N | N | Planned |  | Change the Work Order status from CRTD status to REL and TECO status | 8 hrs | 2025-09-16 17:08 | 2025-09-17 01:10 | Abhishek Sharma | abhisheksharma59@deloitte.com | Chaitnya; Vinod Kumar; Jay Patel; suyash Chhawala; Amit Jha; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Firat | csudhakarraut@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; schhawala@deloitte.com; ajha2@deloitte.no; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; firat.cetin@consultary.de | MOR | 19910 |  |  | * | NA | 2025-09-16 17:08 | 2025-09-17 01:10
19912 | STRIVE.R2.MC1.2384.1277.1.468.10.10 | N | N | N | Planned |  | Maintenance Work Order Coupa formatting | 4 hrs | 2025-09-17 01:10 | 2025-09-17 05:10 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19911 |  |  | * | NA | 2025-09-17 01:10 | 2025-09-17 05:10
19913 | STRIVE.R2.MC1.2384.1277.1.468.10.11 | N | N | N | Planned |  | Maintenance Work Order Coupa Pre-Load Validation | 4 hrs | 2025-09-17 05:10 | 2025-09-17 09:11 | Tina Vidrine | tina.vidrine@us.sasol.com | Aparajita Mukherjee; Milton; Pournami Nair; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Myriam; Frank Toedter ; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19912 |  |  | * | NA | 2025-09-17 05:10 | 2025-09-17 09:11
19914 | STRIVE.R2.MC1.2384.1277.1.468.10.12 | N | N | N | Planned |  | Maintenance Work Order Coupa Load | 4 hrs | 2025-09-17 09:11 | 2025-09-17 13:12 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19913 |  |  | * | NA | 2025-09-17 09:11 | 2025-09-17 13:12
19915 | STRIVE.R2.MC1.2384.1277.1.468.10.13 | N | N | N | Planned |  | Maintenance Work Order Coupa Post-Load Validation | 4 hrs | 2025-09-17 13:12 | 2025-09-17 17:12 | Tina Vidrine | tina.vidrine@us.sasol.com | Aparajita Mukherjee; Milton; Pournami Nair; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; S2P Team; Alex Miles; Satyajit; Roman Mäkilä; Myriam; Frank Toedter ; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; miltjones@deloitte.com; pounair@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; usisasols2p@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P | 19914 |  |  | * | NA | 2025-09-17 13:12 | 2025-09-17 17:12
19916 | STRIVE.R2.MC1.2384.1277.1.468.24 |  |  |  | Complete |  | Historical Work Orders - Not Relevant for MC1, Applicable for UAT | 99.48 hrs | 2025-08-25 08:00 | 2025-08-29 11:45 | [8 empty] | * | NA | 2025-08-25 08:00 | 2025-08-29 11:45
19919 | STRIVE.R2.MC1.2384.1277.1.468.24.3 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Transformation and share Pre-Load - Not relevant for MC1 | 4 hrs | 2025-09-15 17:07 | 2025-09-15 21:07 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19909 |  |  | * | NA | 2025-09-15 17:07 | 2025-09-15 21:07
19920 | STRIVE.R2.MC1.2384.1277.1.468.24.4 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Pre-Load Validation and Sign-off - BB - Not relevant for MC1 | 9 hrs | 2025-09-15 21:07 | 2025-09-16 06:09 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19919 |  |  | * | NA | 2025-09-15 21:07 | 2025-09-16 06:09
21349 | STRIVE.R2.MC1.2384.1277.1.468.24.8 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Pre-Load Validation and Sign-off - Marl - Not relevant for MC1 | 9 hrs | 2025-09-15 21:07 | 2025-09-16 06:09 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19919 |  |  | * | NA | 2025-09-15 21:07 | 2025-09-16 06:09
21348 | STRIVE.R2.MC1.2384.1277.1.468.24.7 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Pre-Load Validation and Sign-off - SK - Not relevant for MC1 | 9 hrs | 2025-09-15 21:07 | 2025-09-16 06:09 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19919 |  |  | * | NA | 2025-09-15 21:07 | 2025-09-16 06:09
19921 | STRIVE.R2.MC1.2384.1277.1.468.24.5 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Load into S/4 and share Post-Load - Not relevant for MC1 | 5 hrs | 2025-09-16 06:09 | 2025-09-16 11:10 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sven Gelking; Elisa Latona; Joseph Barber; Vieroslav Kratky; Branislav Drienovsky; Daniel Bunge; Andre Harders; Matthias Rudolph; Firat | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com; Vieroslav.Kratky@sk.sasol.com; Branislav.Drienovsky@sk.sasol.com; Daniel.Bunge@de.sasol.com; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com; firat.cetin@consultary.de | DM | 19920,21349,21348 |  |  | * | NA | 2025-09-16 06:09 | 2025-09-16 11:10
19922 | STRIVE.R2.MC1.2384.1277.1.468.24.6 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Post-Load Validation and Sign-off - S/4 - BB - Not relevant for MC1 | 9 hrs | 2025-09-16 11:10 | 2025-09-16 20:11 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19921 |  |  | * | NA | 2025-09-16 11:10 | 2025-09-16 20:11
21351 | STRIVE.R2.MC1.2384.1277.1.468.24.10 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Post-Load Validation and Sign-off - S/4 - Marl - Not relevant for MC1 | 9 hrs | 2025-09-16 11:10 | 2025-09-16 20:11 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19921 |  |  | * | NA | 2025-09-16 11:10 | 2025-09-16 20:11
21350 | STRIVE.R2.MC1.2384.1277.1.468.24.9 | Y | Y | Y | Complete |  | Historical Maintenance Work Orders Post-Load Validation and Sign-off - S/4 - SK - Not relevant for MC1 | 9 hrs | 2025-09-16 11:10 | 2025-09-16 20:11 | Sven Gelking | sven.gelking@de.sasol.com | Joseph Barber; Elisa Latona; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Krishna Teja; Jay Patel; Amit Jha; Chaitnya; Abhishek Sharma; Alex Miles; Satyajit; Roman Mäkilä; Firat; Andre Harders; Matthias Rudolph | joseph.barber@us.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; krishn@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Andre.Harders@de.sasol.com; Matthias.Rudolph@de.sasol.com | MOR | 19921 |  |  | * | NA | 2025-09-16 11:10 | 2025-09-16 20:11
19926 | STRIVE.R2.MC1.2384.1277.1.468.34 | [5 empty] | Purchase Order | 199.38 hrs | 2025-08-25 08:00 | 2025-09-02 15:56 | [8 empty] | * | NA | 2025-08-25 08:00 | 2025-09-02 15:56
19927 | STRIVE.R2.MC1.2384.1277.1.468.34.1 | N | N | N | Planned |  | PO Extraction (PRODUCTION ONLY) | 5 hrs | 2025-09-15 08:00 | 2025-09-15 13:01 | Rishi Tirthani | rtirthani@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; ; ; ; Liviana Scaricabarozzi; ; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ; ; ; liviana.scaricabarozzi@it.sasol.com; ; firat.cetin@consultary.de | DM |  |  |  |  | 2025-09-15 08:00 | 2025-09-15 08:00 | 2025-09-15 13:01
77621 | STRIVE.R2.MC1.2384.1277.1.468.34.28 | N | N | N | Planned |  | Purchase Order Inclusion list provided to DM | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Sabrina Agueli; Jörn Schacher; Sandra Kaczor; Firat; Frank Toedter ; ; ; ; Liviana Scaricabarozzi; ; Savri Sumeet Jagatap | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; sabrina.agueli@de.sasol.com; Joern.Schacher@de.sasol.com; Sandra.Kaczor@de.sasol.com; firat.cetin@consultary.de; ft@toedter-consult.de; ; ; ; liviana.scaricabarozzi@it.sasol.com; ; ssumeetjagatap@deloitte.com | [5 empty] | 2025-09-15 08:00 | 2025-09-15 08:00 | 2025-09-15 09:00
19928 | STRIVE.R2.MC1.2384.1277.1.468.34.2 | N | N | N | Planned |  | Purchase Order Transformation, Create Pre Load and share Pre Load file (Coupa and SAP Format) | 10 hrs | 2025-09-15 17:07 | 2025-09-16 03:09 | Rishi Tirthani | rtirthani@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; ; ; ; Liviana Scaricabarozzi; ; Maria Luisa Geremicca; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ; ; ; liviana.scaricabarozzi@it.sasol.com; ; marialuisa.geremicca@it.sasol.com; firat.cetin@consultary.de | DM | 19909 |  |  |  | 2025-09-09 17:07 | 2025-09-15 17:07 | 2025-09-16 03:09
19929 | STRIVE.R2.MC1.2384.1277.1.468.34.3 | N | N | N | Planned |  | Purchase Order Convert Excel to CSV of Coupa Pre load file and Send the file to Business | 6 hrs | 2025-09-16 03:09 | 2025-09-16 09:10 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19928 |  |  | * | NA | 2025-09-16 03:09 | 2025-09-16 09:10
19930 | STRIVE.R2.MC1.2384.1277.1.468.34.4 | N | N | N | Planned |  | Purchase Order Extract the unique users and their email IDs, Upload these users to Coupa with N Approval Limit | 3 hrs | 2025-09-16 09:10 | 2025-09-16 12:11 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19929 |  |  | * | NA | 2025-09-16 09:10 | 2025-09-16 12:11
19931 | STRIVE.R2.MC1.2384.1277.1.468.34.5 | N | N | N | Planned |  | Purchase Order Pre-Load Validation and Sign-off - DE | 8 hrs | 2025-09-16 09:10 | 2025-09-16 17:11 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Sabrina Agueli; Jörn Schacher; Sandra Kaczor; Firat; Frank Toedter | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; sabrina.agueli@de.sasol.com; Joern.Schacher@de.sasol.com; Sandra.Kaczor@de.sasol.com; firat.cetin@consultary.de; ft@toedter-consult.de | S2P | 19929 |  |  | * | NA | 2025-09-16 09:10 | 2025-09-16 17:11
21352 | STRIVE.R2.MC1.2384.1277.1.468.34.17 | N | N | N | Planned |  | Purchase Order Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 09:10 | 2025-09-16 18:11 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Firat; Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Jozef Sedlak; Zuzana Hlucha; Eva Bani; Frank Toedter | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; firat.cetin@consultary.de; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; jozef.sedlak@sk.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; ft@toedter-consult.de | S2P | 19929 |  |  | * | NA | 2025-09-16 09:10 | 2025-09-16 18:11
19932 | STRIVE.R2.MC1.2384.1277.1.468.34.6 | N | N | N | Planned |  | Purchase Order Coupa Load | 6 hrs | 2025-09-16 18:11 | 2025-09-17 00:13 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19931,21352 |  |  | * | NA | 2025-09-16 18:11 | 2025-09-17 00:13
19933 | STRIVE.R2.MC1.2384.1277.1.468.34.7 | N | N | N | Planned |  | Purchase Order Integration from Coupa to S/4 | 8 hrs | 2025-09-17 00:13 | 2025-09-17 08:14 | Pournami Nair | pounair@deloitte.com | Prasanth; Rahul Sengupta; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Esmir Divljanovic; Firat | kalprasanth@deloitte.com; rahusengupta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19932 |  |  | * | NA | 2025-09-17 00:13 | 2025-09-17 08:14
19934 | STRIVE.R2.MC1.2384.1277.1.468.34.8 | N | N | N | Planned |  | Purchase Order Manually create POs with lines more than 100 | 1 hrs | 2025-09-16 17:11 | 2025-09-16 18:11 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19931 |  |  | * | NA | 2025-09-16 17:11 | 2025-09-16 18:11
19935 | STRIVE.R2.MC1.2384.1277.1.468.34.9 | N | N | N | Planned |  | Purchase Orders Coupa Error Report Creation and share with Business | 2 hrs | 2025-09-17 08:14 | 2025-09-17 10:14 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19933,19932,19934 |  |  | * | NA | 2025-09-17 08:14 | 2025-09-17 10:14
19936 | STRIVE.R2.MC1.2384.1277.1.468.34.10 | N | N | N | Planned |  | Purchase Order Post Load XREF preparation and share with DM team | 2 hrs | 2025-09-17 10:14 | 2025-09-17 12:15 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19935 |  |  | * | NA | 2025-09-17 10:14 | 2025-09-17 12:15
19937 | STRIVE.R2.MC1.2384.1277.1.468.34.11 | N | N | N | Planned |  | Purchase Order Post Load Validation Report Creation and share with Business | 7 hrs | 2025-09-17 12:15 | 2025-09-17 19:15 | Rishi Tirthani | rtirthani@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; ; ; ; Liviana Scaricabarozzi; ; Maria Luisa Geremicca; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; ; ; ; liviana.scaricabarozzi@it.sasol.com; ; marialuisa.geremicca@it.sasol.com; firat.cetin@consultary.de | DM | 19936 |  |  | * | NA | 2025-09-17 12:15 | 2025-09-17 19:15
19938 | STRIVE.R2.MC1.2384.1277.1.468.34.12 | N | N | N | Planned |  | Purchase Order Update the contract full amount | 3 hrs | 2025-09-16 18:11 | 2025-09-16 21:11 | Aparajita Mukherjee | apamukherjee@deloitte.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Supriya; Esmir Divljanovic; Firat | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; supriychakraborty@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19934 |  |  | * | NA | 2025-09-16 18:11 | 2025-09-16 21:11
19939 | STRIVE.R2.MC1.2384.1277.1.468.34.13 | N | N | N | Planned |  | Purchase Order Post-Load Validation and Sign-off Coupa - DE | 5 hrs | 2025-09-17 19:15 | 2025-09-18 00:17 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Sabrina Agueli; Jörn Schacher; Sandra Kaczor; Firat; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; sabrina.agueli@de.sasol.com; Joern.Schacher@de.sasol.com; Sandra.Kaczor@de.sasol.com; firat.cetin@consultary.de; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19937 |  |  | * | NA | 2025-09-17 19:15 | 2025-09-18 00:17
21353 | STRIVE.R2.MC1.2384.1277.1.468.34.18 | N | N | N | Planned |  | Purchase Order Post-Load Validation and Sign-off Coupa - SK | 9 hrs | 2025-09-17 19:15 | 2025-09-18 04:17 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Firat; Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Jozef Sedlak; Zuzana Hlucha; Eva Bani; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; firat.cetin@consultary.de; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; jozef.sedlak@sk.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19937 |  |  | * | NA | 2025-09-17 19:15 | 2025-09-18 04:17
19940 | STRIVE.R2.MC1.2384.1277.1.468.34.14 | N | N | N | Planned |  | Purchase Order Post-Load Validation and Sign-off S/4 - DE | 4 hrs | 2025-09-17 19:15 | 2025-09-17 23:15 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Sabrina Agueli; Jörn Schacher; Sandra Kaczor; Firat; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; sabrina.agueli@de.sasol.com; Joern.Schacher@de.sasol.com; Sandra.Kaczor@de.sasol.com; firat.cetin@consultary.de; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19937 |  |  | * | NA | 2025-09-17 19:15 | 2025-09-17 23:15
21354 | STRIVE.R2.MC1.2384.1277.1.468.34.19 | N | N | N | Planned |  | Purchase Order Post-Load Validation and Sign-off S/4 - SK | 9 hrs | 2025-09-17 19:15 | 2025-09-18 04:17 | Maria Luisa Geremicca | marialuisa.geremicca@it.sasol.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; S2P Team; Satyajit; Roman Mäkilä; Tina Vidrine; Firat; Jana Valíková; Liviana Scaricabarozzi; Simonetta Confalonieri; Jozef Sedlak; Zuzana Hlucha; Eva Bani; Frank Toedter ; Esmir Divljanovic | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; usisasols2p@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; tina.vidrine@us.sasol.com; firat.cetin@consultary.de; jana.valikova@sk.sasol.com; liviana.scaricabarozzi@it.sasol.com; Simonetta.Confalonieri@it.sasol.com; jozef.sedlak@sk.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; ft@toedter-consult.de; edivljanovic@deloitte.de | S2P | 19937 |  |  | * | NA | 2025-09-17 19:15 | 2025-09-18 04:17
19941 | STRIVE.R2.MC1.2384.1277.1.468.34.15 | N | N | N | Planned |  | Purchase Order Validate the users loaded in Coupa and change their settings to original | 2 hrs | 2025-09-18 04:17 | 2025-09-18 06:17 | Adelin Apotsu | aapostu@deloittece.com | S2P Team; Supriya; Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; Esmir Divljanovic; Firat | usisasols2p@deloitte.com; supriychakraborty@deloitte.com; apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19940,21354 |  |  | * | NA | 2025-09-18 04:17 | 2025-09-18 06:17
19942 | STRIVE.R2.MC1.2384.1277.1.468.34.16 | N | N | N | Planned |  | Purchase Order Revert the company information settings and approval change settings in Coupa | 1 hrs | 2025-09-18 04:17 | 2025-09-18 05:17 | Supriya | supriychakraborty@deloitte.com | Aparajita Mukherjee; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Prasanth; S2P Team; Esmir Divljanovic; Firat | apamukherjee@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; kalprasanth@deloitte.com; usisasols2p@deloitte.com; edivljanovic@deloitte.de; firat.cetin@consultary.de | S2P_Coupa | 19940,21354 |  |  | * | NA | 2025-09-18 04:17 | 2025-09-18 05:17
21361 | STRIVE.R2.MC1.2384.1277.1.468.82 | [5 empty] | Sales Contracts | 248.43 hrs | 2025-09-05 08:03 | 2025-09-15 17:10 | [8 empty] | * | NA | 2025-09-05 08:03 | 2025-09-15 17:10
21362 | STRIVE.R2.MC1.2384.1277.1.468.82.25 | N | N | N | Planned |  | Sales Contracts - Share relevant Sales Contract list to DM Team (Inclusion) | 9 hrs | 2025-09-05 08:03 | 2025-09-05 17:04 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Riepe Joëlle | Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | P2C | 19893 |  |  |  | 2025-09-05 08:03 | 2025-09-05 08:03 | 2025-09-05 17:04
77622 | STRIVE.R2.MC1.2384.1277.1.468.82.1 | N | N | N | Planned |  | Sales Contracts - Extract Sales Contracts based upon inclusion list | 9 hrs | 2025-09-05 17:04 | 2025-09-06 02:06 | Sampath | sampaupadhya@deloitte.com | Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Jessica Goffi; Riepe Joëlle | Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Jessica.Goffi@it.sasol.com; Joelle.Riepe@de.sasol.com | DM | 21362 |  |  |  | 2025-09-05 08:03 | 2025-09-05 17:04 | 2025-09-06 02:06
21363 | STRIVE.R2.MC1.2384.1277.1.468.82.26 | N | N | N | Planned |  | Sales Contracts Transformation and share Pre-Load | 9 hrs | 2025-09-08 08:06 | 2025-09-08 17:07 | Sampath | sampaupadhya@deloitte.com | Jessica Goffi; Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Avinash Puranik; Riepe Joëlle | Jessica.Goffi@it.sasol.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; avpuranik@deloitte.com; Joelle.Riepe@de.sasol.com | DM | 77622 |  |  |  | 2025-09-08 08:06 | 2025-09-08 08:06 | 2025-09-08 17:07
21364 | STRIVE.R2.MC1.2384.1277.1.468.82.27 | N | N | N | Planned |  | Sales Contracts Pre-Load Validation and Sign-off | 9 hrs | 2025-09-09 08:07 | 2025-09-09 17:08 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Riepe Joëlle | Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | P2C | 21363 |  |  |  | 2025-09-09 08:07 | 2025-09-09 08:07 | 2025-09-09 17:08
21359 | STRIVE.R2.MC1.2384.1277.1.468.82.22 | N | N | N | Planned |  | Sales Contracts Load into S/4 and share Post-Load | 9 hrs | 2025-09-11 08:08 | 2025-09-11 17:09 | Sampath | sampaupadhya@deloitte.com | Jessica Goffi; Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Avinash Puranik; Riepe Joëlle | Jessica.Goffi@it.sasol.com; Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; avpuranik@deloitte.com; Joelle.Riepe@de.sasol.com | DM | 21364 |  |  |  | 2025-09-11 08:08 | 2025-09-11 08:08 | 2025-09-11 17:09
21360 | STRIVE.R2.MC1.2384.1277.1.468.82.23 | N | N | N | Planned |  | Sales Contracts Post-Load Validation and Sign-off | 9 hrs | 2025-09-15 08:09 | 2025-09-15 17:10 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Riepe Joëlle | Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | P2C | 21359 |  |  |  | 2025-09-15 08:09 | 2025-09-15 08:09 | 2025-09-15 17:10
19943 | STRIVE.R2.MC1.2384.1277.1.468.51 | [5 empty] | Sales Orders (Open) | 79.75 hrs | 2025-08-25 08:00 | 2025-08-28 15:58 | [8 empty] | * | NA | 2025-08-25 08:00 | 2025-08-28 15:58
19944 | STRIVE.R2.MC1.2384.1277.1.468.51.1 | N | N | N | Planned |  | Sales Orders (Open) Extraction (PRODUCTION ONLY) | 3 hrs | 2025-09-16 09:00 | 2025-09-16 12:00 | Avinash Puranik | avpuranik@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Jessica Goffi; Roman Mäkilä; Firat; Riepe Joëlle | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | DM | 19893 |  |  |  | 2025-09-16 09:00 | 2025-09-16 09:00 | 2025-09-16 12:00
19945 | STRIVE.R2.MC1.2384.1277.1.468.51.2 | N | N | N | Planned |  | Sales Orders (Open) Transformation and share Pre-Load | 4 hrs | 2025-09-17 08:01 | 2025-09-17 12:02 | Avinash Puranik | avpuranik@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Jessica Goffi; Roman Mäkilä; Firat; Riepe Joëlle | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | DM | 19944 |  |  |  | 2025-09-17 08:01 | 2025-09-17 08:01 | 2025-09-17 12:02
19946 | STRIVE.R2.MC1.2384.1277.1.468.51.3 | N | N | N | Planned |  | Sales Orders (Open) Pre-Load Validation and Sign-off - DE | 8 hrs | 2025-09-18 08:02 | 2025-09-18 16:03 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Riepe Joëlle | Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | P2C | 19945 |  |  |  | 2025-09-18 08:02 | 2025-09-18 08:02 | 2025-09-18 16:03
40021 | STRIVE.R2.MC1.2384.1277.1.468.51.6 | N | N | N | Planned |  | Sales Orders (Open) Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-18 08:02 | 2025-09-18 17:03 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Viktoria Kormanikova; Anna Sifrova; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Riepe Joëlle | viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | P2C | 19945 |  |  |  | 2025-09-18 08:02 | 2025-09-18 08:02 | 2025-09-18 17:03
19947 | STRIVE.R2.MC1.2384.1277.1.468.51.4 | N | N | N | Planned |  | Sales Orders (Open) Load into S/4 and share Post-Load | 3 hrs | 2025-09-22 08:03 | 2025-09-22 11:03 | Avinash Puranik | avpuranik@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Firat; Mousikta chanda; Jessica Goffi; Roman Mäkilä; Riepe Joëlle | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; firat.cetin@consultary.de; mouchanda@deloitte.com; Jessica.Goffi@it.sasol.com; roman.makila@deloitte.fi; Joelle.Riepe@de.sasol.com | DM | 19946,40021 |  |  |  | 2025-09-22 08:03 | 2025-09-22 08:03 | 2025-09-22 11:03
40022 | STRIVE.R2.MC1.2384.1277.1.468.51.7 | N | N | N | Planned |  | Sales Orders (Open) Post-Load Validation and Sign-off - DE | 9 hrs | 2025-09-23 11:03 | 2025-09-23 20:04 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Andrea Ludeke; Tobias Wilmering; R. Schmidt-Biedenkopf; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Riepe Joëlle | Andrea.Luedeke@de.sasol.com; tobias.wilmering@de.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | P2C | 19947 |  |  |  | 2025-09-23 11:03 | 2025-09-23 11:03 | 2025-09-23 20:04
19948 | STRIVE.R2.MC1.2384.1277.1.468.51.5 | N | N | N | Planned |  | Sales Orders (Open) Post-Load Validation and Sign-off - SK | 6 hrs | 2025-09-23 11:03 | 2025-09-23 17:04 | Jessica Goffi | Jessica.Goffi@it.sasol.com | Viktoria Kormanikova; Anna Sifrova; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Satyajit; Roman Mäkilä; Alex Miles; Savri Sumeet Jagatap; Ines Tesch; Jens Nissen; Firat; Riepe Joëlle | viktoria.kormanikova@sk.sasol.com; anna.sifrova@sk.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; almiles@deloitte.de; ssumeetjagatap@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Joelle.Riepe@de.sasol.com | P2C | 19947 |  |  |  | 2025-09-23 11:03 | 2025-09-23 11:03 | 2025-09-23 17:04
19949 | STRIVE.R2.MC1.2384.1277.1.468.57 | [5 empty] | Inventory Balances (Unit counts) | 71.93 hrs | 2025-08-25 08:00 | 2025-08-28 08:08 | [8 empty] | * | NA | 2025-08-25 08:00 | 2025-08-28 08:08
19950 | STRIVE.R2.MC1.2384.1277.1.468.57.1 | N | N | N | Planned |  | Inventory Balances (Unit counts) Extraction (PRODUCTION ONLY) | 1 hrs | 2025-09-12 08:00 | 2025-09-12 09:00 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Hans Jorg; Roman Mäkilä; Alex Pradeep; Jay Saini; Aniket Kulkarni; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; roman.makila@deloitte.fi; alex.pradeep@us.sasol.com; jaysaini4@deloitte.com; anikulkarni@deloitte.com; firat.cetin@consultary.de | DM |  |  |  |  | 2025-09-12 08:00 | 2025-09-12 08:00 | 2025-09-12 09:00
19951 | STRIVE.R2.MC1.2384.1277.1.468.57.2 | N | N | N | Planned |  | Inventory Balances (Unit counts) - R2D Upload V prices ZTEQ, ZMAG, ZOPS | 1 hrs | 2025-09-12 08:00 | 2025-09-12 09:00 | Christian Canale | christian.canale@it.sasol.com | Hendrik Kamsteeg; Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Alex Miles; Mousikta chanda; Satyajit Patnaik; Roman Mäkilä; Jay Saini; Aniket Kulkarni; Firat | hendrik.kamsteeg@de.sasol.com; aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; almiles@deloitte.de; mouchanda@deloitte.com; sapatnaik@deloitte.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; anikulkarni@deloitte.com; firat.cetin@consultary.de | DM |  |  |  |  | 2025-09-12 08:00 | 2025-09-12 08:00 | 2025-09-12 09:00
19952 | STRIVE.R2.MC1.2384.1277.1.468.57.3 | N | N | N | Planned |  | Inventory Balances (Unit counts) - R2D Releases Price Estimates | 1 hrs | 2025-09-12 08:00 | 2025-09-12 09:00 | Christian Canale | christian.canale@it.sasol.com | Hendrik Kamsteeg; Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Miles; Satyajit Patnaik; Roman Mäkilä; Jay Saini; Aniket Kulkarni; Firat | hendrik.kamsteeg@de.sasol.com; aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; jaysaini4@deloitte.com; anikulkarni@deloitte.com; firat.cetin@consultary.de | DM |  |  |  |  | 2025-09-12 08:00 | 2025-09-12 08:00 | 2025-09-12 09:00
19953 | STRIVE.R2.MC1.2384.1277.1.468.57.4 | N | N | N | Planned |  | Inventory Balances (Unit counts) Transformation and share Pre-Load | 2 hrs | 2025-09-15 09:00 | 2025-09-15 11:00 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Hans Jorg; Mousikta chanda; Roman Mäkilä; Alex Pradeep; Jay Saini; Aniket Kulkarni; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; hansjorg.becker@de.sasol.com; mouchanda@deloitte.com; roman.makila@deloitte.fi; alex.pradeep@us.sasol.com; jaysaini4@deloitte.com; anikulkarni@deloitte.com; firat.cetin@consultary.de | DM | 19893 |  |  |  | 2025-09-15 09:00 | 2025-09-15 09:00 | 2025-09-15 11:00
19954 | STRIVE.R2.MC1.2384.1277.1.468.57.5 | N | N | N | Planned |  | Inventory Balances (Unit counts) Pre-Load Validation and Sign-off - BB | 8 hrs | 2025-09-16 11:00 | 2025-09-16 19:01 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19953 |  |  |  | 2025-09-16 11:00 | 2025-09-16 11:00 | 2025-09-16 19:01
40024 | STRIVE.R2.MC1.2384.1277.1.468.57.9 | N | N | N | Planned |  | Inventory Balances (Unit counts) Pre-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-16 11:00 | 2025-09-16 20:01 | Hans Jorg | hansjorg.becker@de.sasol.com | Bruno van der Valk; Dominik Rowek; Thomas; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Bruno.vanderValk@de.sasol.com; Dominik.Rowek@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19953 |  |  |  | 2025-09-16 11:00 | 2025-09-16 11:00 | 2025-09-16 20:01
40023 | STRIVE.R2.MC1.2384.1277.1.468.57.8 | N | N | N | Planned |  | Inventory Balances (Unit counts) Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 11:00 | 2025-09-16 20:01 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Zuzana Hlucha; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19953 |  |  |  | 2025-09-16 11:00 | 2025-09-16 11:00 | 2025-09-16 20:01
19955 | STRIVE.R2.MC1.2384.1277.1.468.57.6 | N | N | N | Planned |  | Inventory Balances (Unit counts) Load into S/4 and share Post-Load | 2 hrs | 2025-09-18 08:01 | 2025-09-18 10:01 | Manikanta Manikanta | manikmanikanta@deloitte.com | Satyajit Patnaik; Savri Sumeet Jagatap; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Hans Jorg; Roman Mäkilä; Alex Pradeep; Aniket Kulkarni; Jay Saini; Nilesh Deshpande; Firat | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; hansjorg.becker@de.sasol.com; roman.makila@deloitte.fi; alex.pradeep@us.sasol.com; anikulkarni@deloitte.com; jaysaini4@deloitte.com; nideshpande@deloitte.com; firat.cetin@consultary.de | DM | 19954,19952,19951,40023,40024 |  |  |  | 2025-09-18 08:01 | 2025-09-18 08:01 | 2025-09-18 10:01
19956 | STRIVE.R2.MC1.2384.1277.1.468.57.7 | N | N | N | Planned |  | Inventory Balances (Unit counts) Post-Load Validation and Sign-off - BB | 2 hrs | 2025-09-19 10:01 | 2025-09-19 12:02 | Hans Jorg | hansjorg.becker@de.sasol.com | Andreas Biernath; Jonas Dohrn; Daniel Dierenfeld; Michael Robertshaw; Birte Schumacher; Steffen Erichson; Niclas Meyer; Jens Timmermann; T. Junge; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Andreas.Biernath@de.sasol.com; jonas.dohrn@de.sasol.com; Daniel.Dierenfeld@de.sasol.com; Michael.Robertshaw@de.sasol.com; Birte.Schumacher@de.sasol.com; steffen.erichson@de.sasol.com; Niclas.Meyer@de.sasol.com; Jens.Timmermann@de.sasol.com; Tim.Junge@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19955 |  |  |  | 2025-09-19 10:01 | 2025-09-19 10:01 | 2025-09-19 12:02
40026 | STRIVE.R2.MC1.2384.1277.1.468.57.11 | N | N | N | Planned |  | Inventory Balances (Unit counts) Post-Load Validation and Sign-off - Marl | 9 hrs | 2025-09-19 10:01 | 2025-09-19 19:02 | Hans Jorg | hansjorg.becker@de.sasol.com | Bruno van der Valk; Dominik Rowek; Thomas; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | Bruno.vanderValk@de.sasol.com; Dominik.Rowek@de.sasol.com; Thomas.Kokkinidis@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19955 |  |  |  | 2025-09-19 10:01 | 2025-09-19 10:01 | 2025-09-19 19:02
40025 | STRIVE.R2.MC1.2384.1277.1.468.57.10 | N | N | N | Planned |  | Inventory Balances (Unit counts) Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-19 10:01 | 2025-09-19 19:02 | Hans Jorg | hansjorg.becker@de.sasol.com | Timotej Šándor; Eva Bani; Zuzana Hlucha; Alex Miles; Satyajit; Roman Mäkilä; Savri Sumeet Jagatap; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Firat; Torsten Freydt | timotej.sandor@sk.sasol.com; eva.bani@sk.sasol.com; zuzana.hlucha@sk.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; ssumeetjagatap@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; firat.cetin@consultary.de; Torsten.Freydt-Olek@de.sasol.com | R2P | 19955 |  |  |  | 2025-09-19 10:01 | 2025-09-19 10:01 | 2025-09-19 19:02
40092 | STRIVE.R2.MC1.2384.1277.1.468.83 |  |  |  | Complete |  | NC Withdrawal / TR Clean Up (Applicable for UAT & PROD cycles only) - After Transactional Loads | 4 hrs | 2025-09-30 08:00 | 2025-09-30 12:00 | [6 empty] | 2025-09-03 23:54 |  | * | NA | 2025-09-30 08:00 | 2025-09-30 12:00
40093 | STRIVE.R2.MC1.2384.1277.1.468.83.25 | Y | Y | Y | Complete |  | Take an extarct of all NCs / TR that needs to be cleaned up | 0 hrs | 2025-09-03 23:54 | 2025-09-03 23:54 | Manasa | mha@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Analytics |  | 2025-09-03 23:54 | 2025-09-03 23:54 | * | NA | 2025-09-03 23:54 | 2025-09-03 23:54
40094 | STRIVE.R2.MC1.2384.1277.1.468.83.26 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - R2P | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Amit das | amitdas3@deloitte.com | Claudiu; Aniket Kulkarni; Pamela Mihali; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Nilesh Deshpande; Manasa | cljipa@deloitte.de; anikulkarni@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com; mha@deloitte.com | R2P |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40095 | STRIVE.R2.MC1.2384.1277.1.468.83.27 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - S2P | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Prasanth Kallakuri | kalprasanth@deloitte.com | Sandeep Galhotra; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team; Milton; Manasa | sagalhotra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com; miltjones@deloitte.com; mha@deloitte.com | S2P |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40096 | STRIVE.R2.MC1.2384.1277.1.468.83.28 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - P2C | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Malta; Tripti mehta; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Manasa | dzarate@deloitte.com; mawilhelm@deloitte.de; trimehta@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; mha@deloitte.com | P2C |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40097 | STRIVE.R2.MC1.2384.1277.1.468.83.29 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - R2D | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Roshanlal Hemwani | rohemwani@deloitte.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Daniel Lohmann; ; Manasa | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dlohmann@deloitte.de; ; mha@deloitte.com | R2D |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40098 | STRIVE.R2.MC1.2384.1277.1.468.83.30 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - MOR | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Vinod Kumar | vinodkumar692@deloitte.com | Krishna Teja; Nikhil Gupta; Vinod; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Mythili; Manasa | krishn@deloitte.com; mrgupta3@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; myboyapati@deloitte.com; mha@deloitte.com | MOR |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40099 | STRIVE.R2.MC1.2384.1277.1.468.83.31 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - ABAP | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Ashish patil | ashishspatil@deloitte.com | Shivraj; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Satish rahangadale; Manasa | shivrsinha@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; srahangdale@deloitte.com; mha@deloitte.com | ABAP |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40101 | STRIVE.R2.MC1.2384.1277.1.468.83.33 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - DM | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Alex Miles | almiles@deloitte.de | Roman Mäkilä; Satyajit Patnaik; Savri Sumeet Jagatap; Jens Nissen; Ines Tesch; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rushikesh Mahendrakar; Manasa | roman.makila@deloitte.fi; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rumahendrakar@deloitte.com; mha@deloitte.com | DM |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40102 | STRIVE.R2.MC1.2384.1277.1.468.83.34 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - GRC | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Sasol GRC | dttsasolsecuritygrcteam@deloitte.com | Shubham Thakur; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Manasa | Shubhathakur@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; mha@deloitte.com | GRC |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40103 | STRIVE.R2.MC1.2384.1277.1.468.83.35 | Y | Y | Y | Complete |  | NC Withdrawal / TR Clean Up - MDG | 2 hrs | 2025-09-30 08:00 | 2025-09-30 10:00 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Manasa | tupal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; mha@deloitte.com | MDG |  |  |  | * | NA | 2025-09-30 08:00 | 2025-09-30 10:00
40104 | STRIVE.R2.MC1.2384.1277.1.468.83.1 | Y | Y | Y | Complete |  | Take an extarct of all NCs / TR that needs to be cleaned up (post clean up by teams) | 2 hrs | 2025-09-30 10:00 | 2025-09-30 12:00 | Manasa | mha@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Analytics | 40094,40095,40096,40097,40098,40099,40101,40102,40103 |  |  | * | NA | 2025-09-30 10:00 | 2025-09-30 12:00
19968 | STRIVE.R2.MC1.2384.1277.1.468.76 | [5 empty] | MOR | 24.93 hrs | 2025-09-15 08:00 | 2025-09-16 09:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 09:00
19969 | STRIVE.R2.MC1.2384.1277.1.468.76.1 | N | N | N | Planned |  | Validate Number range for notification-Black out | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Abhishek Sharma | abhisheksharma59@deloitte.com | Chaitnya; Jay Patel; Amit Jha; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | csudhakarraut@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19970 | STRIVE.R2.MC1.2384.1277.1.468.76.2 | N | N | N | Planned |  | Validate Number range for Work Order -Black out | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Abhishek Sharma | abhisheksharma59@deloitte.com | Chaitnya; Jay Patel; Amit Jha; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | csudhakarraut@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19971 | STRIVE.R2.MC1.2384.1277.1.468.76.3 | N | N | N | Planned |  | Copies of LSMW should be made in advance to avoid re-work | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Abhishek Sharma | abhisheksharma59@deloitte.com | Chaitnya; Jay Patel; Amit Jha; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | csudhakarraut@deloitte.com; jaypatel6@deloitte.com; ajha2@deloitte.no; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19972 | STRIVE.R2.MC1.2384.1277.1.468.76.4 | N | N | N | Planned |  | Create Organization Responsible to map the company Code | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Mythili | myboyapati@deloitte.com | Jay Patel; Amit Jha; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Krishna Teja; Nikhil Gupta | jaypatel6@deloitte.com; ajha2@deloitte.no; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; krishn@deloitte.com; mrgupta3@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
19973 | STRIVE.R2.MC1.2384.1277.1.549 | [5 empty] | Smoke Testing | 5783.55 hrs | 2025-09-20 08:00 | 2026-07-22 15:19 | [8 empty] | * | NA | 2025-09-20 08:00 | 2026-07-22 15:19
19974 | STRIVE.R2.MC1.2384.1277.1.549.1 | [5 empty] | MOR - Smoke Testing | 0.67 hrs | 2025-09-20 08:00 | 2025-09-20 08:40 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 08:40
19975 | STRIVE.R2.MC1.2384.1277.1.549.1.1 | N | N | N | Planned |  | Create work order in s/4 to for safe work | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19976 | STRIVE.R2.MC1.2384.1277.1.549.1.2 | Y | Y | Y | Complete |  | Validate the work order in safe work (Not relevant for MC1) | 0.25 hrs | 2025-09-20 08:15 | 2025-09-20 08:30 | Orazio Modica | orazio.modica@it.sasol.com | Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 19975 |  |  | * | NA | 2025-09-20 08:15 | 2025-09-20 08:30
19977 | STRIVE.R2.MC1.2384.1277.1.549.1.3 | Y | Y | Y | Complete |  | send permit details from safe work to s/4 (Not relevant for MC1) | 0.25 hrs | 2025-09-20 08:30 | 2025-09-20 08:45 | Orazio Modica | orazio.modica@it.sasol.com | Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 19976 |  |  | * | NA | 2025-09-20 08:30 | 2025-09-20 08:45
19978 | STRIVE.R2.MC1.2384.1277.1.549.1.4 | N | N | N | Planned |  | validate if permit details available in s/4 | 0.25 hrs | 2025-09-20 08:45 | 2025-09-20 09:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 19977 |  |  | * | NA | 2025-09-20 08:45 | 2025-09-20 09:00
19979 | STRIVE.R2.MC1.2384.1277.1.549.1.5 | N | N | N | Planned |  | Validate create mainteance request is working as per expected | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19980 | STRIVE.R2.MC1.2384.1277.1.549.1.6 | N | N | N | Planned |  | Create work order to perform add materaial and service via coupa catalog | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19981 | STRIVE.R2.MC1.2384.1277.1.549.1.7 | N | N | N | Planned |  | Execute migrated work order | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19982 | STRIVE.R2.MC1.2384.1277.1.549.1.8 | N | N | N | Planned |  | Create Planning Bucket | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19983 | STRIVE.R2.MC1.2384.1277.1.549.1.9 | N | N | N | Planned |  | Validate Manage backlog app using created planning bucket | 0.25 hrs | 2025-09-20 08:15 | 2025-09-20 08:30 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Sven Gelking; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; sven.gelking@de.sasol.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 19982 |  |  | * | NA | 2025-09-20 08:15 | 2025-09-20 08:30
19984 | STRIVE.R2.MC1.2384.1277.1.549.11 | [5 empty] | P2C - Smoke Testing | 3.92 hrs | 2025-09-20 08:00 | 2025-09-20 11:55 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 11:55
19985 | STRIVE.R2.MC1.2384.1277.1.549.11.1 | N | N | N | Planned |  | Check sales order for customer, material, plant combination (no transacting - smoke test) | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Maria teresa | mariateresa.denti@it.sasol.com | Jessica Goffi; Rob Hall; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | Jessica.Goffi@it.sasol.com; rob.hall@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19986 | STRIVE.R2.MC1.2384.1277.1.549.11.2 | N | N | N | Planned |  | Create delivery, freight unit, freight order for migrated sales order (no transacting - smoke test) | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Manuel | Manuel.Roellinghoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rob Hall | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rob.hall@sasol.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19987 | STRIVE.R2.MC1.2384.1277.1.549.11.3 | N | N | N | Planned |  | Check initiation of key interfaces: no transacting - smoke test | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Manuel | Manuel.Roellinghoff@de.sasol.com | Christina Tomascu; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rob Hall | cristina.tomascu@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rob.hall@sasol.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
95096 | STRIVE.R2.MC1.2384.1277.1.549.11.10 | N | N | N | Planned |  | Perform smoke test - P2C_I_200 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Ilja | iholub@deloitte.it | Siddhesh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tripti mehta; Ramesh SathishKumar | sibaraskar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; trimehta@deloitte.com; satramesh@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
95095 | STRIVE.R2.MC1.2384.1277.1.549.11.9 | N | N | N | Planned |  | Perform smoke test - P2C_I_201 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Rajeev Mishra | rajeemishra@deloitte.com | Siddhesh; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Tripti mehta; Ramesh SathishKumar | sibaraskar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; trimehta@deloitte.com; satramesh@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
95088 | STRIVE.R2.MC1.2384.1277.1.549.11.8 | N | N | N | Planned |  | Perform smoke test - P2C_I_204 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Rajeev Mishra | rajeemishra@deloitte.com | Siddhesh; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Tripti mehta; Ramesh SathishKumar | sibaraskar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; trimehta@deloitte.com; satramesh@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
95083 | STRIVE.R2.MC1.2384.1277.1.549.11.7 | N | N | N | Planned |  | Perform Smoke testing for P2C_I_400 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Shubham Mishra | spratapmishra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
95082 | STRIVE.R2.MC1.2384.1277.1.549.11.6 | N | N | N | Planned |  | Perform Smoke testing for P2C_I_401 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Shubham Mishra | spratapmishra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
95081 | STRIVE.R2.MC1.2384.1277.1.549.11.5 | N | N | N | Planned |  | Perform Smoke testing for P2C_I_415 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Shubham Mishra | spratapmishra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
95080 | STRIVE.R2.MC1.2384.1277.1.549.11.4 | N | N | N | Planned |  | Perform Smoke testing for P2C_I_416 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Shubham Mishra | spratapmishra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
19988 | STRIVE.R2.MC1.2384.1277.1.549.15 | [5 empty] | S2P - Smoke Testing | 1294.68 hrs | 2025-09-20 08:00 | 2025-11-13 10:17 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-11-13 10:17
19989 | STRIVE.R2.MC1.2384.1277.1.549.15.1 | N | N | N | Planned |  | Coupa docusign interface - Smoke Test | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19990 | STRIVE.R2.MC1.2384.1277.1.549.15.2 | N | N | N | Planned |  | Create penny contract and take it up to signature stage | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19991 | STRIVE.R2.MC1.2384.1277.1.549.15.3 | [5 empty] | S2P_I_018 | 0.17 hrs | 2025-09-20 08:00 | 2025-09-20 08:10 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 08:10
19992 | STRIVE.R2.MC1.2384.1277.1.549.15.3.1 | N | N | N | Planned |  | Creation of PR in Coupa, PO generated in Coupa | 0.25 hrs | 2025-09-20 08:00 | 2025-09-20 08:15 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:15
19993 | STRIVE.R2.MC1.2384.1277.1.549.15.3.2 | N | N | N | Planned |  | Validate PO in S4 | 0.25 hrs | 2025-09-20 08:15 | 2025-09-20 08:30 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 19992 |  |  | * | NA | 2025-09-20 08:15 | 2025-09-20 08:30
19994 | STRIVE.R2.MC1.2384.1277.1.549.15.6 | [5 empty] | S2P_I_024 | 0.08 hrs | 2025-09-20 08:00 | 2025-09-20 08:05 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 08:05
19995 | STRIVE.R2.MC1.2384.1277.1.549.15.6.1 | N | N | N | Planned |  | Create GR in S4 | 151.88 hrs | 2025-09-20 08:30 | 2025-09-26 16:48 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 19993 |  |  | * | NA | 2025-09-20 08:30 | 2025-09-26 16:48
19996 | STRIVE.R2.MC1.2384.1277.1.549.15.8 | [5 empty] | S2P_I_019 | 0.17 hrs | 2025-09-20 08:00 | 2025-09-20 08:10 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 08:10
19997 | STRIVE.R2.MC1.2384.1277.1.549.15.8.1 | N | N | N | Planned |  | Create Invoice for full amount in Coupa | 0 hrs | 2025-09-26 16:48 | 2025-09-26 16:48 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 19995 |  |  | * | NA | 2025-09-26 16:48 | 2025-09-26 16:48
19998 | STRIVE.R2.MC1.2384.1277.1.549.15.8.2 | N | N | N | Planned |  | Validate Invoice in S4 , ok to pay status from Coupa | 0 hrs | 2025-09-26 16:48 | 2025-09-26 16:48 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 19997 |  |  | * | NA | 2025-09-26 16:48 | 2025-09-26 16:48
19999 | STRIVE.R2.MC1.2384.1277.1.549.15.11 | [5 empty] | S2P_I_022 | 0.17 hrs | 2025-09-20 08:00 | 2025-09-20 08:10 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 08:10
20000 | STRIVE.R2.MC1.2384.1277.1.549.15.11.1 | N | N | N | Planned |  | Work Order Created in S4 | 2.78 hrs | 2025-09-20 08:00 | 2025-09-20 10:47 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:47
20001 | STRIVE.R2.MC1.2384.1277.1.549.15.11.2 | N | N | N | Planned |  | Validate WO Lookup Value in Coupa | 50.1 hrs | 2025-09-20 10:47 | 2025-09-22 13:02 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 20000 |  |  | * | NA | 2025-09-20 10:47 | 2025-09-22 13:02
20002 | STRIVE.R2.MC1.2384.1277.1.549.15.14 | [5 empty] | S2P_I_009 | 0.17 hrs | 2025-09-20 08:00 | 2025-09-20 08:10 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 08:10
20003 | STRIVE.R2.MC1.2384.1277.1.549.15.14.1 | N | N | N | Planned |  | Create MOR Service PR in S4 | 54.93 hrs | 2025-09-22 13:02 | 2025-09-24 20:06 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Luca Burgio; Sergio; Elisa Latona; Jay Patel; Amit Jha; Abhishek Sharma; Chaitnya; Vinod Kumar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | luca.burgio@it.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; abhisheksharma59@deloitte.com; csudhakarraut@deloitte.com; vinodkumar692@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 20001 |  |  | * | NA | 2025-09-22 13:02 | 2025-09-24 20:06
20004 | STRIVE.R2.MC1.2384.1277.1.549.15.14.2 | N | N | N | Planned |  | Validate PR created in Coupa | 0.17 hrs | 2025-09-24 20:06 | 2025-09-24 20:16 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 20003 |  |  | * | NA | 2025-09-24 20:06 | 2025-09-24 20:16
20005 | STRIVE.R2.MC1.2384.1277.1.549.15.17 | [5 empty] | S2P_I_016 | 0.17 hrs | 2025-09-20 08:00 | 2025-09-20 08:10 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 08:10
20006 | STRIVE.R2.MC1.2384.1277.1.549.15.17.1 | N | N | N | Planned |  | Approve PR | 0.17 hrs | 2025-09-24 20:16 | 2025-09-24 20:26 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 20004 |  |  | * | NA | 2025-09-24 20:16 | 2025-09-24 20:26
20007 | STRIVE.R2.MC1.2384.1277.1.549.15.17.2 | N | N | N | Planned |  | Validate PO in S4 | 0.17 hrs | 2025-09-24 20:26 | 2025-09-24 20:36 | Tina Vidrine | tina.vidrine@us.sasol.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Myriam; Frank Toedter | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; marialuisa.geremicca@it.sasol.com; ft@toedter-consult.de | S2P | 20006 |  |  | * | NA | 2025-09-24 20:26 | 2025-09-24 20:36
20008 | STRIVE.R2.MC1.2384.1277.1.549.35 | [5 empty] | R2D - Smoke Testing | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20009 | STRIVE.R2.MC1.2384.1277.1.549.35.1 | Y | Y | Y | Complete |  | MBC and penny testing for payments (Not Applicable for MC1) | 0 hrs | 2025-09-20 08:00 | 2025-09-20 08:00 | Patrizia | patrizia.vergani@it.sasol.com | Roshanlal; Tatiana; Francois Conradie; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | rohemwani@deloitte.com; tvinogradova@deloitte.de; francois.conradie@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:00
20010 | STRIVE.R2.MC1.2384.1277.1.549.35.2 | N | N | N | Planned |  | Park Post Functionality | 0 hrs | 2025-09-20 08:00 | 2025-09-20 08:00 | Patrizia | patrizia.vergani@it.sasol.com | ; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Tatiana; Roshanlal; Francois Conradie | ; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; tvinogradova@deloitte.de; rohemwani@deloitte.com; francois.conradie@de.sasol.com | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:00
20011 | STRIVE.R2.MC1.2384.1277.1.549.38 | [5 empty] | MDG - Smoke Testing | 1.79 hrs | 2025-09-20 08:00 | 2025-09-20 09:47 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 09:47
20012 | STRIVE.R2.MC1.2384.1277.1.549.38.1 | N | N | N | Planned |  | MDG: Smoke Testing for BP | 1.79 hrs | 2025-09-20 08:00 | 2025-09-20 09:47 | Antonio Sciullodi | antonio.sciullodi@de.sasol.com | ; Amol; Tulika Pal; Tushar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; ampaswan@deloitte.com; tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:47
20013 | STRIVE.R2.MC1.2384.1277.1.549.38.2 | N | N | N | Planned |  | MDG: Smoke Testing for MM | 0.02 hrs | 2025-09-20 08:00 | 2025-09-20 08:01 | Thomas | Thomas.Kokkinidis@de.sasol.com | ; Vinit Raverkar; Tulika Pal; Tushar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rajat Sharma | ; vnitinraverkar@deloitte.com; tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rajatsharma67@deloitte.com | MDG |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:01
20014 | STRIVE.R2.MC1.2384.1277.1.549.38.3 | N | N | N | Planned |  | MDG: Smoke Testing for SM | 1.16 hrs | 2025-09-20 08:00 | 2025-09-20 09:10 | Japie | japie.herbst@sasol.com | ; Amol Paswan; Tulika Pal; Tushar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; ampaswan@deloitte.com; tupal@deloitte.com; tamrutkar@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:10
20015 | STRIVE.R2.MC1.2384.1277.1.549.42 | [5 empty] | R2P - Smoke Testing | 56.85 hrs | 2025-09-20 08:00 | 2025-09-22 17:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 17:00
20016 | STRIVE.R2.MC1.2384.1277.1.549.42.1 | N | N | N | Planned |  | Create Planned Orders for Terranova | 2.99 hrs | 2025-09-20 08:00 | 2025-09-20 10:59 | Claudiu | cljipa@deloitte.de | Amit das; Jay Saini; Meriem; Varsha Gupta; Shivani Kulkarni; Vincenzo; Francesco Geradi; Hans Jorg; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | amitdas3@deloitte.com; jaysaini4@deloitte.com; mebenslimane@deloitte.de; varshagupta7@deloitte.com; shivankulkarni@deloitte.com; vincenzo.demarco@it.sasol.com; francesco.geradi@it.sasol.com; hansjorg.becker@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P | 19952 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:59
20017 | STRIVE.R2.MC1.2384.1277.1.549.42.2 | N | N | N | Planned |  | Convert planned orders to process orders | 2 hrs | 2025-09-20 10:59 | 2025-09-20 13:01 | Claudiu | cljipa@deloitte.de | Amit das; Jay Saini; Meriem; Varsha Gupta; Shivani Kulkarni; Vincenzo; Francesco Geradi; Hans Jorg; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | amitdas3@deloitte.com; jaysaini4@deloitte.com; mebenslimane@deloitte.de; varshagupta7@deloitte.com; shivankulkarni@deloitte.com; vincenzo.demarco@it.sasol.com; francesco.geradi@it.sasol.com; hansjorg.becker@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P | 20016 |  |  | * | NA | 2025-09-20 10:59 | 2025-09-20 13:01
20019 | STRIVE.R2.MC1.2384.1277.1.549.42.4 | N | N | N | Planned |  | MSDS - Material Safety Data Sheet | 26.43 hrs | 2025-09-20 08:00 | 2025-09-21 10:30 | Klaus | klaus.heitkamp@de.sasol.com | Amit das; Peeyush Kumar; Denise; Sheena Gour; Shahid Sheikh; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Priyanka Singhal; Alex Larionov | amitdas3@deloitte.com; peekumar@deloitte.com; Denise.Koetter@de.sasol.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; priyasinghal@deloitte.com; allarionov@deloitte.de | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-21 10:30
20020 | STRIVE.R2.MC1.2384.1277.1.549.42.5 | N | N | N | Planned |  | PDB& German Portal - Key Files | 25.93 hrs | 2025-09-21 10:30 | 2025-09-22 12:31 | Klaus | klaus.heitkamp@de.sasol.com | Amit das; Peeyush Kumar; Denise; Sheena Gour; Shahid Sheikh; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Priyanka Singhal; Alex Larionov | amitdas3@deloitte.com; peekumar@deloitte.com; Denise.Koetter@de.sasol.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; priyasinghal@deloitte.com; allarionov@deloitte.de | R2P | 20019 |  |  | * | NA | 2025-09-21 10:30 | 2025-09-22 12:31
20021 | STRIVE.R2.MC1.2384.1277.1.549.48 | [5 empty] | IBP - Smoke Testing | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20022 | STRIVE.R2.MC1.2384.1277.1.549.48.1 | N | N | N | Planned |  | Create PLO in OMP and trigger conversion into PRO in S/4 | 1.17 hrs | 2025-09-20 08:00 | 2025-09-20 09:10 | Marcello Trapani | marcello.trapani@it.sasol.com | Salvatore Noto; Elle Sempels; Rajat Sahgal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | salvatore.noto@it.sasol.com; esempels@deloitte.com ; rasahgal@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:10
20023 | STRIVE.R2.MC1.2384.1277.1.549.48.2 | N | N | N | Planned |  | Create STR in OMP and interface it to S/4 | 74.66 hrs | 2025-09-20 08:00 | 2025-09-23 10:52 | Marcello Trapani | marcello.trapani@it.sasol.com | Salvatore Noto; Elle Sempels; Rajat Sahgal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | salvatore.noto@it.sasol.com; esempels@deloitte.com ; rasahgal@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-23 10:52
20024 | STRIVE.R2.MC1.2384.1277.1.549.51 | [5 empty] | Tier 5 Finance Transactional Objects | 1198.04 hrs | 2025-09-15 08:00 | 2025-11-04 09:22 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-11-04 09:22
20025 | STRIVE.R2.MC1.2384.1277.1.549.51.1 | N | N | N | Planned |  | Handover of Profit Center Enrichment File for A/R and A/P to DM team | 1.99 hrs | 2025-09-15 08:00 | 2025-09-15 09:59 | Michaela | michaela.schulz@de.sasol.com | Moonalisa; Satyajit Patnaik; Alex Miles; Roshni; Hendrik Kamsteeg; Roshanlal; Tatiana; Roman Mäkilä; Firat | mooghosh@deloitte.com; sapatnaik@deloitte.com; almiles@deloitte.de; roshsingh@deloitte.com; hendrik.kamsteeg@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; roman.makila@deloitte.fi; firat.cetin@consultary.de | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:59
20026 | STRIVE.R2.MC1.2384.1277.1.549.51.2 | [5 empty] | GL Balances | 194.35 hrs | 2025-09-15 08:00 | 2025-09-23 10:53 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-23 10:53
20027 | STRIVE.R2.MC1.2384.1277.1.549.51.2.1 | N | N | N | Planned |  | GL Balances Extraction from A01 by Process Streams and Handover to DM | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Oluf baren | oluf.braren@de.sasol.com | Hendrik Kamsteeg; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Firat | hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; firat.cetin@consultary.de | R2D | 19893 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20028 | STRIVE.R2.MC1.2384.1277.1.549.51.2.2 | N | N | N | Planned |  | GL Balances Transformation and share Pre-Load | 4 hrs | 2025-09-16 11:09 | 2025-09-16 15:10 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Hendrik Kamsteeg; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; firat.cetin@consultary.de | DM | 20027,20035,20040,20049 |  |  | * | NA | 2025-09-16 11:09 | 2025-09-16 15:10
20029 | STRIVE.R2.MC1.2384.1277.1.549.51.2.3 | N | N | N | Planned |  | GL Balances Pre-Load Validation and Sign-off - DE | 8 hrs | 2025-09-16 15:10 | 2025-09-16 23:10 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; T. Hagen; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com | R2D | 20028 |  |  | * | NA | 2025-09-16 15:10 | 2025-09-16 23:10
40030 | STRIVE.R2.MC1.2384.1277.1.549.51.2.7 | N | N | N | Planned |  | GL Balances Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 15:10 | 2025-09-17 00:12 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; Viera Chobotova; Eva Bani | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com | R2D | 20028 |  |  | * | NA | 2025-09-16 15:10 | 2025-09-17 00:12
40029 | STRIVE.R2.MC1.2384.1277.1.549.51.2.6 | N | N | N | Planned |  | GL Balances Pre-Load Validation and Sign-off - UK | 9 hrs | 2025-09-16 15:10 | 2025-09-17 00:12 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; L. Theakston | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Laraine.Theakston@eu.sasol.com | R2D | 20028 |  |  | * | NA | 2025-09-16 15:10 | 2025-09-17 00:12
20030 | STRIVE.R2.MC1.2384.1277.1.549.51.2.4 | N | N | N | Planned |  | GL Balances Load into S/4 and share Post-Load | 8 hrs | 2025-09-17 00:12 | 2025-09-17 08:13 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Hendrik Kamsteeg; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; firat.cetin@consultary.de | DM | 20029,40029,40030 |  |  | * | NA | 2025-09-17 00:12 | 2025-09-17 08:13
20031 | STRIVE.R2.MC1.2384.1277.1.549.51.2.5 | N | N | N | Planned |  | GL Balances Post-Load Validation and Sign-off - DE | 8 hrs | 2025-09-17 08:13 | 2025-09-17 16:14 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; T. Hagen; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com | R2D | 20030 |  |  | * | NA | 2025-09-17 08:13 | 2025-09-17 16:14
40032 | STRIVE.R2.MC1.2384.1277.1.549.51.2.9 | N | N | N | Planned |  | GL Balances Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-17 08:13 | 2025-09-17 17:14 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; Viera Chobotova; Eva Bani | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com | R2D | 20030 |  |  | * | NA | 2025-09-17 08:13 | 2025-09-17 17:14
40031 | STRIVE.R2.MC1.2384.1277.1.549.51.2.8 | N | N | N | Planned |  | GL Balances Post-Load Validation and Sign-off - UK | 9 hrs | 2025-09-17 08:13 | 2025-09-17 17:14 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; L. Theakston | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Laraine.Theakston@eu.sasol.com | R2D | 20030 |  |  | * | NA | 2025-09-17 08:13 | 2025-09-17 17:14
20032 | STRIVE.R2.MC1.2384.1277.1.549.51.8 | [5 empty] | GL Open Items | 699.68 hrs | 2025-09-15 08:00 | 2025-10-14 13:38 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-14 13:38
20033 | STRIVE.R2.MC1.2384.1277.1.549.51.8.1 | N | N | N | Planned |  | GL Open Items Transformation and share Pre-Load | 9 hrs | 2025-09-15 08:00 | 2025-09-15 17:01 | Avinash Puranik | avpuranik@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Hendrik Kamsteeg; T. Hagen; M. Jomrich; Viera Chobotova; Eva Bani; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; firat.cetin@consultary.de | DM |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 17:01
20034 | STRIVE.R2.MC1.2384.1277.1.549.51.8.2 | N | N | N | Planned |  | GL Open Items Pre-Load Validation and Sign-off - DE | 9 hrs | 2025-09-15 17:01 | 2025-09-16 02:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; T. Hagen; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com | R2D | 20033 |  |  | * | NA | 2025-09-15 17:01 | 2025-09-16 02:03
40034 | STRIVE.R2.MC1.2384.1277.1.549.51.8.6 | N | N | N | Planned |  | GL Open Items Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-15 17:01 | 2025-09-16 02:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; Viera Chobotova; Eva Bani | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com | R2D | 20033 |  |  | * | NA | 2025-09-15 17:01 | 2025-09-16 02:03
40033 | STRIVE.R2.MC1.2384.1277.1.549.51.8.5 | N | N | N | Planned |  | GL Open Items Pre-Load Validation and Sign-off - UK | 9 hrs | 2025-09-15 17:01 | 2025-09-16 02:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; L. Theakston | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Laraine.Theakston@eu.sasol.com | R2D | 20033 |  |  | * | NA | 2025-09-15 17:01 | 2025-09-16 02:03
20035 | STRIVE.R2.MC1.2384.1277.1.549.51.8.3 | N | N | N | Planned |  | GL Open Items Load into S/4 and share Post-Load | 9 hrs | 2025-09-16 02:03 | 2025-09-16 11:04 | Avinash Puranik | avpuranik@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat; Hendrik Kamsteeg; T. Hagen; M. Jomrich; Viera Chobotova; Eva Bani | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de; hendrik.kamsteeg@de.sasol.com; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com | DM | 20034,40033,40034 |  |  | * | NA | 2025-09-16 02:03 | 2025-09-16 11:04
20036 | STRIVE.R2.MC1.2384.1277.1.549.51.8.4 | N | N | N | Planned |  | GL Open Items Post-Load Validation and Sign-off - DE | 8 hrs | 2025-09-16 11:04 | 2025-09-16 19:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; T. Hagen; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com | R2D | 20035 |  |  | * | NA | 2025-09-16 11:04 | 2025-09-16 19:05
40036 | STRIVE.R2.MC1.2384.1277.1.549.51.8.8 | N | N | N | Planned |  | GL Open Items Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 11:04 | 2025-09-16 20:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; Viera Chobotova; Eva Bani | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com | R2D | 20035 |  |  | * | NA | 2025-09-16 11:04 | 2025-09-16 20:05
40035 | STRIVE.R2.MC1.2384.1277.1.549.51.8.7 | N | N | N | Planned |  | GL Open Items Post-Load Validation and Sign-off - UK | 9 hrs | 2025-09-16 11:04 | 2025-09-16 20:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; L. Theakston | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Laraine.Theakston@eu.sasol.com | R2D | 20035 |  |  | * | NA | 2025-09-16 11:04 | 2025-09-16 20:05
20037 | STRIVE.R2.MC1.2384.1277.1.549.51.13 | [5 empty] | Customer Open Items (AR) | 696.7 hrs | 2025-09-15 08:00 | 2025-10-14 10:38 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-14 10:38
94442 | STRIVE.R2.MC1.2384.1277.1.549.51.13.10 | N | N | N | Planned |  | Customer Open Items (AR) Provide profit center enrichment to DM team | 1 hrs | 2025-09-15 09:59 | 2025-09-15 10:59 | Michaela Schulz | michaela.schulz@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; R. Schmidt-Biedenkopf; D. Busch; Firat; Roshan | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Ruth.Schmidt-Biedenkopf@de.sasol.com; Dominik.Busch@de.sasol.com; firat.cetin@consultary.de; rohemwani@deloitte.com | R2D | 20025 |  |  | * | NA | 2025-09-15 09:59 | 2025-09-15 10:59
20038 | STRIVE.R2.MC1.2384.1277.1.549.51.13.1 | N | N | N | Planned |  | Customer Open Items (AR) Transformation and share Pre-Load | 6 hrs | 2025-09-15 10:59 | 2025-09-15 17:00 | Saketh | sasaketh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Firat; Hendrik Kamsteeg; T. Hagen; M. Jomrich; Viera Chobotova; Eva Bani; R. Schmidt-Biedenkopf; D. Busch | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; firat.cetin@consultary.de; hendrik.kamsteeg@de.sasol.com; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; Dominik.Busch@de.sasol.com | DM | 94442 |  |  | * | NA | 2025-09-15 10:59 | 2025-09-15 17:00
20039 | STRIVE.R2.MC1.2384.1277.1.549.51.13.2 | N | N | N | Planned |  | Customer Open Items (AR) Pre-Load Validation and Sign-off - DE | 9 hrs | 2025-09-15 17:00 | 2025-09-16 02:02 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; R. Schmidt-Biedenkopf; D. Busch; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Ruth.Schmidt-Biedenkopf@de.sasol.com; Dominik.Busch@de.sasol.com; firat.cetin@consultary.de | R2D | 20038 |  |  | * | NA | 2025-09-15 17:00 | 2025-09-16 02:02
40038 | STRIVE.R2.MC1.2384.1277.1.549.51.13.7 | N | N | N | Planned |  | Customer Open Items (AR) Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-15 17:00 | 2025-09-16 02:02 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; Viera Chobotova; Eva Bani | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com | R2D | 20038 |  |  | * | NA | 2025-09-15 17:00 | 2025-09-16 02:02
40037 | STRIVE.R2.MC1.2384.1277.1.549.51.13.6 | N | N | N | Planned |  | Customer Open Items (AR) Pre-Load Validation and Sign-off - UK | 9 hrs | 2025-09-15 17:00 | 2025-09-16 02:02 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | R2D | 20038 |  |  | * | NA | 2025-09-15 17:00 | 2025-09-16 02:02
20040 | STRIVE.R2.MC1.2384.1277.1.549.51.13.3 | N | N | N | Planned |  | Customer Open Items (AR) Load into S/4 and share Post-Load | 9 hrs | 2025-09-16 02:02 | 2025-09-16 11:03 | Saketh | sasaketh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roman Mäkilä; Mousikta chanda; Hendrik Kamsteeg; T. Hagen; M. Jomrich; Viera Chobotova; Eva Bani; R. Schmidt-Biedenkopf; D. Busch; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; roman.makila@deloitte.fi; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; Torsten.Hagen@de.sasol.com; Maik.Jomrich@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Ruth.Schmidt-Biedenkopf@de.sasol.com; Dominik.Busch@de.sasol.com; firat.cetin@consultary.de | DM | 20039,40038,40037 |  |  | * | NA | 2025-09-16 02:02 | 2025-09-16 11:03
20041 | STRIVE.R2.MC1.2384.1277.1.549.51.13.4 | N | N | N | Planned |  | Customer Open Items (AR) Post-Load Validation and Sign-off - DE | 9 hrs | 2025-09-16 11:03 | 2025-09-16 20:04 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; R. Schmidt-Biedenkopf; D. Busch; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Ruth.Schmidt-Biedenkopf@de.sasol.com; Dominik.Busch@de.sasol.com; firat.cetin@consultary.de | R2D | 20040 |  |  | * | NA | 2025-09-16 11:03 | 2025-09-16 20:04
40040 | STRIVE.R2.MC1.2384.1277.1.549.51.13.9 | N | N | N | Planned |  | Customer Open Items (AR) Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 11:03 | 2025-09-16 20:04 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat; Viera Chobotova; Eva Bani | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com | R2D | 20040 |  |  | * | NA | 2025-09-16 11:03 | 2025-09-16 20:04
40039 | STRIVE.R2.MC1.2384.1277.1.549.51.13.8 | N | N | N | Planned |  | Customer Open Items (AR) Post-Load Validation and Sign-off - UK | 9 hrs | 2025-09-16 11:03 | 2025-09-16 20:04 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; firat.cetin@consultary.de | R2D | 20040 |  |  | * | NA | 2025-09-16 11:03 | 2025-09-16 20:04
20043 | STRIVE.R2.MC1.2384.1277.1.549.51.19 | [5 empty] | Vendor Open Items (AP) | 696.7 hrs | 2025-09-15 08:00 | 2025-10-14 10:38 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-14 10:38
94443 | STRIVE.R2.MC1.2384.1277.1.549.51.19.15 | N | N | N | Planned |  | Vendor Open Items (AP) Provide profit center enrichment to DM team | 1 hrs | 2025-09-15 09:59 | 2025-09-15 10:59 | Michaela Schulz | michaela.schulz@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; R. Schmidt-Biedenkopf; D. Busch; Firat; Roshan | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Ruth.Schmidt-Biedenkopf@de.sasol.com; Dominik.Busch@de.sasol.com; firat.cetin@consultary.de; rohemwani@deloitte.com | R2D | 20025 |  |  | * | NA | 2025-09-15 09:59 | 2025-09-15 10:59
20044 | STRIVE.R2.MC1.2384.1277.1.549.51.19.1 | N | N | N | Planned |  | Vendor Open Items (AP) Transformation and share Pre-Load | 6 hrs | 2025-09-15 10:59 | 2025-09-15 17:00 | Saketh | sasaketh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sandra Kaczor; U. Kath; Hendrik Kamsteeg; Roman Mäkilä; Christian Witt; M. Wieters; P. Halfar; Zuzana Hlucha; Eva Bani; L. Theakston; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Sandra.Kaczor@de.sasol.com; urte.kath@de.sasol.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; christian.witt@de.sasol.com; Margitta.Wieters@de.sasol.com; patrick.halfar@de.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | DM | 94443 |  |  | * | NA | 2025-09-15 10:59 | 2025-09-15 17:00
20045 | STRIVE.R2.MC1.2384.1277.1.549.51.19.2 | N | N | N | Planned |  | Vendor Open Items (AP) Pre-Load Validation and Sign-off - DE | 9 hrs | 2025-09-15 17:00 | 2025-09-16 02:02 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Sandra Kaczor; U. Kath; C. Witt; M. Wieters; P. Halfar; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Sandra.Kaczor@de.sasol.com; urte.kath@de.sasol.com; Christian.Witt@de.sasol.com; Margitta.Wieters@de.sasol.com; patrick.halfar@de.sasol.com; firat.cetin@consultary.de | R2D | 20044 |  |  | * | NA | 2025-09-15 17:00 | 2025-09-16 02:02
40042 | STRIVE.R2.MC1.2384.1277.1.549.51.19.12 | N | N | N | Planned |  | Vendor Open Items (AP) Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-15 17:00 | 2025-09-16 02:02 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Zuzana Hlucha; Eva Bani; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; firat.cetin@consultary.de | R2D | 20044 |  |  | * | NA | 2025-09-15 17:00 | 2025-09-16 02:02
40041 | STRIVE.R2.MC1.2384.1277.1.549.51.19.11 | N | N | N | Planned |  | Vendor Open Items (AP) Pre-Load Validation and Sign-off - UK | 9 hrs | 2025-09-15 17:00 | 2025-09-16 02:02 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | R2D | 20044 |  |  | * | NA | 2025-09-15 17:00 | 2025-09-16 02:02
20046 | STRIVE.R2.MC1.2384.1277.1.549.51.19.3 | N | N | N | Planned |  | Notify R2D (Aquib, Roshanlal, Michaela, Alexandra, Tatiana) Team to update vendors with Invoice WHT code | 0.1 hrs | 2025-09-16 02:02 | 2025-09-16 02:08 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit Patnaik; Roman Mäkilä; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | DM | 20045,40042,40041 |  |  | * | NA | 2025-09-16 02:02 | 2025-09-16 02:08
20049 | STRIVE.R2.MC1.2384.1277.1.549.51.19.6 | N | N | N | Planned |  | Vendor Open Items (AP) Load into S/4 and share Post-Load | 9 hrs | 2025-09-16 02:08 | 2025-09-16 11:09 | Saketh | sasaketh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Sandra Kaczor; U. Kath; Hendrik Kamsteeg; Roman Mäkilä; Christian Witt; M. Wieters; P. Halfar; Zuzana Hlucha; Eva Bani; L. Theakston; Firat | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Sandra.Kaczor@de.sasol.com; urte.kath@de.sasol.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; christian.witt@de.sasol.com; Margitta.Wieters@de.sasol.com; patrick.halfar@de.sasol.com; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | DM | 20046 |  |  | * | NA | 2025-09-16 02:08 | 2025-09-16 11:09
20050 | STRIVE.R2.MC1.2384.1277.1.549.51.19.7 | N | N | N | Planned |  | Notify R2D (Aquib, Roshanlal, Michaela, Alexandra, Tatiana) Team to update vendors with Invoice WHT code | 0.06 hrs | 2025-09-16 11:09 | 2025-09-16 11:13 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | DM | 20049 |  |  | * | NA | 2025-09-16 11:09 | 2025-09-16 11:13
20053 | STRIVE.R2.MC1.2384.1277.1.549.51.19.10 | N | N | N | Planned |  | Vendor Open Items (AP) Post-Load Validation and Sign-off - DE | 9 hrs | 2025-09-16 11:13 | 2025-09-16 20:14 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Sandra Kaczor; U. Kath; C. Witt; M. Wieters; P. Halfar; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Sandra.Kaczor@de.sasol.com; urte.kath@de.sasol.com; Christian.Witt@de.sasol.com; Margitta.Wieters@de.sasol.com; patrick.halfar@de.sasol.com; firat.cetin@consultary.de | R2D | 20050 |  |  | * | NA | 2025-09-16 11:13 | 2025-09-16 20:14
40046 | STRIVE.R2.MC1.2384.1277.1.549.51.19.14 | N | N | N | Planned |  | Vendor Open Items (AP) Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 11:13 | 2025-09-16 20:14 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Zuzana Hlucha; Eva Bani; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; zuzana.hlucha@sk.sasol.com; eva.bani@sk.sasol.com; firat.cetin@consultary.de | R2D | 20050 |  |  | * | NA | 2025-09-16 11:13 | 2025-09-16 20:14
40045 | STRIVE.R2.MC1.2384.1277.1.549.51.19.13 | N | N | N | Planned |  | Vendor Open Items (AP) Post-Load Validation and Sign-off - UK | 9 hrs | 2025-09-16 11:13 | 2025-09-16 20:14 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | R2D | 20050 |  |  | * | NA | 2025-09-16 11:13 | 2025-09-16 20:14
20054 | STRIVE.R2.MC1.2384.1277.1.549.51.30 | N | N | N | Planned |  | Handover of Final Exchange Rates to DM Team for Asset Migration | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Daniel Lohmann | dlohmann@deloitte.de | Moonalisa; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tatiana; Alexandra Ruff; Satyajit Patnaik; Roshanlal | mooghosh@deloitte.com; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; aruff@deloitte.de; sapatnaik@deloitte.com; rohemwani@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20055 | STRIVE.R2.MC1.2384.1277.1.549.51.31 | N | N | N | Planned |  | Update Asset Exchange Rate Code in Syniti and Promote Code | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Moonalisa | mooghosh@deloitte.com | Daniel Lohmann; Roman Mäkilä; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tatiana; Alexandra Ruff; Satyajit Patnaik; Savri Sumeet Jagatap; Firat | dlohmann@deloitte.de; roman.makila@deloitte.fi; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; aruff@deloitte.de; sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | DM | 20054 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20056 | STRIVE.R2.MC1.2384.1277.1.549.51.32 | [5 empty] | Fixed Asset Master&Balances | 696.7 hrs | 2025-09-15 08:00 | 2025-10-14 10:38 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-14 10:38
20057 | STRIVE.R2.MC1.2384.1277.1.549.51.32.1 | N | N | N | Planned |  | Fixed Asset Master & Balances Transformation and share Pre-Load | 9 hrs | 2025-09-15 08:00 | 2025-09-15 17:01 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Firat; T. Hagen; T. Theede; M. Jomrich | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Theresa.Theede@de.sasol.com; Maik.Jomrich@de.sasol.com | DM | 19893 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 17:01
20058 | STRIVE.R2.MC1.2384.1277.1.549.51.32.2 | N | N | N | Planned |  | Fixed Asset Master & Balances Pre-Load Validation and Sign-off - DE | 9 hrs | 2025-09-15 17:01 | 2025-09-16 02:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; T. Hagen; T. Theede; M. Jomrich; Viera Chobotova; Eva Bani; L. Theakston; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Torsten.Hagen@de.sasol.com; Theresa.Theede@de.sasol.com; Maik.Jomrich@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | R2D | 20057 |  |  | * | NA | 2025-09-15 17:01 | 2025-09-16 02:03
40048 | STRIVE.R2.MC1.2384.1277.1.549.51.32.6 | N | N | N | Planned |  | Fixed Asset Master & Balances Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-15 17:01 | 2025-09-16 02:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Viera Chobotova; Eva Bani; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; firat.cetin@consultary.de | R2D | 20057 |  |  | * | NA | 2025-09-15 17:01 | 2025-09-16 02:03
40047 | STRIVE.R2.MC1.2384.1277.1.549.51.32.5 | N | N | N | Planned |  | Fixed Asset Master & Balances Pre-Load Validation and Sign-off - UK | 9 hrs | 2025-09-15 17:01 | 2025-09-16 02:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | R2D | 20057 |  |  | * | NA | 2025-09-15 17:01 | 2025-09-16 02:03
20059 | STRIVE.R2.MC1.2384.1277.1.549.51.32.3 | N | N | N | Planned |  | Fixed Asset Master&Balances Load into S/4 and share Post-Load | 9 hrs | 2025-09-16 02:03 | 2025-09-16 11:04 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Firat; T. Hagen; T. Theede; M. Jomrich | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Theresa.Theede@de.sasol.com; Maik.Jomrich@de.sasol.com | DM | 20058,40048,40047 |  |  | * | NA | 2025-09-16 02:03 | 2025-09-16 11:04
20060 | STRIVE.R2.MC1.2384.1277.1.549.51.32.4 | N | N | N | Planned |  | Fixed Asset Master & Balances Post-Load Validation and Sign-off - DE | 9 hrs | 2025-09-16 11:04 | 2025-09-16 20:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; T. Hagen; T. Theede; M. Jomrich; Viera Chobotova; Eva Bani; L. Theakston; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Torsten.Hagen@de.sasol.com; Theresa.Theede@de.sasol.com; Maik.Jomrich@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | R2D | 20059 |  |  | * | NA | 2025-09-16 11:04 | 2025-09-16 20:05
40050 | STRIVE.R2.MC1.2384.1277.1.549.51.32.8 | N | N | N | Planned |  | Fixed Asset Master & Balances Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 11:04 | 2025-09-16 20:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Viera Chobotova; Eva Bani; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; firat.cetin@consultary.de | R2D | 20059 |  |  | * | NA | 2025-09-16 11:04 | 2025-09-16 20:05
40049 | STRIVE.R2.MC1.2384.1277.1.549.51.32.7 | N | N | N | Planned |  | Fixed Asset Master & Balances Post-Load Validation and Sign-off - UK | 9 hrs | 2025-09-16 11:04 | 2025-09-16 20:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; firat.cetin@consultary.de | R2D | 20059 |  |  | * | NA | 2025-09-16 11:04 | 2025-09-16 20:05
20061 | STRIVE.R2.MC1.2384.1277.1.549.51.37 | [5 empty] | P&L Extraction | 103.64 hrs | 2025-09-15 08:00 | 2025-09-19 15:55 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-19 15:55
20062 | STRIVE.R2.MC1.2384.1277.1.549.51.37.1 | N | N | N | Planned |  | P&L Extraction from A01 by Process Streams and Handover to DM | 8 hrs | 2025-09-15 08:00 | 2025-09-15 16:01 | Oluf baren | oluf.braren@de.sasol.com | Hendrik Kamsteeg; Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Firat; Tatiana | hendrik.kamsteeg@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; firat.cetin@consultary.de; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 16:01
20063 | STRIVE.R2.MC1.2384.1277.1.549.51.37.2 | N | N | N | Planned |  | P&L Transformation and share Pre-Load | 3 hrs | 2025-09-15 16:01 | 2025-09-15 19:01 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Firat; T. Hagen; Viera Chobotova; Eva Bani; L. Theakston | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com | DM | 20062 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 19:01
20064 | STRIVE.R2.MC1.2384.1277.1.549.51.37.3 | N | N | N | Planned |  | P&L Pre-Load Validation and Sign-off - DE | 9 hrs | 2025-09-15 19:01 | 2025-09-16 04:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; T. Hagen; Firat; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Torsten.Hagen@de.sasol.com; firat.cetin@consultary.de; Maik.Jomrich@de.sasol.com | R2D | 20063 |  |  | * | NA | 2025-09-15 19:01 | 2025-09-16 04:03
40052 | STRIVE.R2.MC1.2384.1277.1.549.51.37.7 | N | N | N | Planned |  | P&L Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-15 19:01 | 2025-09-16 04:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Viera Chobotova; Eva Bani; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 20063 |  |  | * | NA | 2025-09-15 19:01 | 2025-09-16 04:03
40051 | STRIVE.R2.MC1.2384.1277.1.549.51.37.6 | N | N | N | Planned |  | P&L Pre-Load Validation and Sign-off - UK | 9 hrs | 2025-09-15 19:01 | 2025-09-16 04:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 20063 |  |  | * | NA | 2025-09-15 19:01 | 2025-09-16 04:03
20065 | STRIVE.R2.MC1.2384.1277.1.549.51.37.4 | N | N | N | Planned |  | P&L Load into S/4 and share Post-Load | 5 hrs | 2025-09-16 04:03 | 2025-09-16 09:04 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Firat; T. Hagen; Viera Chobotova; Eva Bani; L. Theakston | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com | DM | 20064,40052,40051 |  |  | * | NA | 2025-09-16 04:03 | 2025-09-16 09:04
20066 | STRIVE.R2.MC1.2384.1277.1.549.51.37.5 | N | N | N | Planned |  | P&L Post-Load Validation and Sign-off - DE | 9 hrs | 2025-09-16 09:04 | 2025-09-16 18:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; T. Hagen; Firat; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Torsten.Hagen@de.sasol.com; firat.cetin@consultary.de; Maik.Jomrich@de.sasol.com | R2D | 20065 |  |  | * | NA | 2025-09-16 09:04 | 2025-09-16 18:05
40061 | STRIVE.R2.MC1.2384.1277.1.549.51.37.16 | N | N | N | Planned |  | P&L Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 09:04 | 2025-09-16 18:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Viera Chobotova; Eva Bani; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 20065 |  |  | * | NA | 2025-09-16 09:04 | 2025-09-16 18:05
40062 | STRIVE.R2.MC1.2384.1277.1.549.51.37.17 | N | N | N | Planned |  | P&L Post-Load Validation and Sign-off - UK | 9 hrs | 2025-09-16 09:04 | 2025-09-16 18:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 20065 |  |  | * | NA | 2025-09-16 09:04 | 2025-09-16 18:05
40063 | STRIVE.R2.MC1.2384.1277.1.549.51.43 | [5 empty] | Historical P&L | 99.73 hrs | 2025-09-15 08:00 | 2025-09-19 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-19 12:00
40064 | STRIVE.R2.MC1.2384.1277.1.549.51.43.19 | N | N | N | Planned |  | P&L Transformation and share Pre-Load | 3 hrs | 2025-09-15 16:01 | 2025-09-15 19:01 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Firat; T. Hagen; Viera Chobotova; Eva Bani; L. Theakston | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com | DM | 20062 |  |  | * | NA | 2025-09-15 16:01 | 2025-09-15 19:01
40065 | STRIVE.R2.MC1.2384.1277.1.549.51.43.20 | N | N | N | Planned |  | P&L Pre-Load Validation and Sign-off - DE | 9 hrs | 2025-09-15 19:01 | 2025-09-16 04:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; T. Hagen; Firat; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Torsten.Hagen@de.sasol.com; firat.cetin@consultary.de; Maik.Jomrich@de.sasol.com | R2D | 40064 |  |  | * | NA | 2025-09-15 19:01 | 2025-09-16 04:03
40066 | STRIVE.R2.MC1.2384.1277.1.549.51.43.21 | N | N | N | Planned |  | P&L Pre-Load Validation and Sign-off - SK | 9 hrs | 2025-09-15 19:01 | 2025-09-16 04:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Viera Chobotova; Eva Bani; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 40064 |  |  | * | NA | 2025-09-15 19:01 | 2025-09-16 04:03
40067 | STRIVE.R2.MC1.2384.1277.1.549.51.43.22 | N | N | N | Planned |  | P&L Pre-Load Validation and Sign-off - UK | 9 hrs | 2025-09-15 19:01 | 2025-09-16 04:03 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 40064 |  |  | * | NA | 2025-09-15 19:01 | 2025-09-16 04:03
40068 | STRIVE.R2.MC1.2384.1277.1.549.51.43.23 | N | N | N | Planned |  | P&L Load into S/4 and share Post-Load | 5 hrs | 2025-09-16 04:03 | 2025-09-16 09:04 | Sampath | sampaupadhya@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Hendrik Kamsteeg; Roman Mäkilä; Firat; T. Hagen; Viera Chobotova; Eva Bani; L. Theakston | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; hendrik.kamsteeg@de.sasol.com; roman.makila@deloitte.fi; firat.cetin@consultary.de; Torsten.Hagen@de.sasol.com; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; Laraine.Theakston@eu.sasol.com | DM | 40065,40066,40067 |  |  | * | NA | 2025-09-16 04:03 | 2025-09-16 09:04
40057 | STRIVE.R2.MC1.2384.1277.1.549.51.43.12 | N | N | N | Planned |  | P&L Post-Load Validation and Sign-off - DE | 9 hrs | 2025-09-16 09:04 | 2025-09-16 18:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; T. Hagen; Firat; M. Jomrich | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Torsten.Hagen@de.sasol.com; firat.cetin@consultary.de; Maik.Jomrich@de.sasol.com | R2D | 40068 |  |  | * | NA | 2025-09-16 09:04 | 2025-09-16 18:05
40058 | STRIVE.R2.MC1.2384.1277.1.549.51.43.13 | N | N | N | Planned |  | P&L Post-Load Validation and Sign-off - SK | 9 hrs | 2025-09-16 09:04 | 2025-09-16 18:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; Viera Chobotova; Eva Bani; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Viera.Chobotova@sk.sasol.com; eva.bani@sk.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 40068 |  |  | * | NA | 2025-09-16 09:04 | 2025-09-16 18:05
40059 | STRIVE.R2.MC1.2384.1277.1.549.51.43.14 | N | N | N | Planned |  | P&L Post-Load Validation and Sign-off - UK | 9 hrs | 2025-09-16 09:04 | 2025-09-16 18:05 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Ines Tesch; Jens Nissen; Alex Miles; Roshanlal; Mousikta chanda; Tatiana; Satyajit; Roman Mäkilä; L. Theakston; Savri Sumeet Jagatap; Firat | dhkansal@deloitte.com; usistrivecutover@deloitte.com; ines.tesch@de.sasol.com; Jens.Nissen@de.sasol.com; almiles@deloitte.de; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; Laraine.Theakston@eu.sasol.com; ssumeetjagatap@deloitte.com; firat.cetin@consultary.de | R2D | 40068 |  |  | * | NA | 2025-09-16 09:04 | 2025-09-16 18:05
20067 | STRIVE.R2.MC1.2384.1277.1.549.94 | [5 empty] | Post-Migration Activities | 25.91 hrs | 2025-09-15 08:00 | 2025-09-16 09:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 09:59
20068 | STRIVE.R2.MC1.2384.1277.1.549.94.1 | N | N | N | Planned |  | Get sign-off for Test Data Load execution results | 0 hrs | 2025-09-15 08:00 | 2025-09-15 08:00 | Moonalisa | mooghosh@deloitte.com | Savri Sumeet Jagatap; Satyajit Patnaik; Jens Nissen; Ines Tesch; Alex Miles; Dhruv Kansal; USI STRIVE CUTOVER; Roman Mäkilä; Mousikta chanda | ssumeetjagatap@deloitte.com; sapatnaik@deloitte.com; Jens.Nissen@de.sasol.com; ines.tesch@de.sasol.com; almiles@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com | DM |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 08:00
20069 | STRIVE.R2.MC1.2384.1277.1.549.96 | [5 empty] | Migration End | 25.91 hrs | 2025-09-15 08:00 | 2025-09-16 09:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-16 09:59
20070 | STRIVE.R2.MC1.2384.1277.1.549.96.1 | N | N | N | Planned |  | Run program in GE-APM to send Equipment Details from S/4 to GE-APM | 150.55 hrs | 2025-09-15 08:00 | 2025-09-21 14:58 | Chaitnya | csudhakarraut@deloitte.com | Amit Jha; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Jay Patel; Mousikta chanda | ajha2@deloitte.no; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaypatel6@deloitte.com; mouchanda@deloitte.com | MOR | 19663 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-21 14:58
20071 | STRIVE.R2.MC1.2384.1277.1.549.96.2 | N | N | N | Planned |  | Run program in GE-APM to send Functional Location Details from S/4 to GE-APM | 88.53 hrs | 2025-09-15 08:00 | 2025-09-19 00:47 | Joseph Barber | joseph.barber@us.sasol.com | Sergio; Jay Patel; Amit Jha; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Elisa Latona | sergio.guzzo@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; elisa.latona@it.sasol.com | MOR | 19690 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-19 00:47
20072 | STRIVE.R2.MC1.2384.1277.1.549.96.3 | N | N | N | Planned |  | Run program in GE-APM to send Technical Object Classification Details from S/4 to GE-APM | 150.55 hrs | 2025-09-17 13:24 | 2025-09-23 20:21 | Joseph Barber | joseph.barber@us.sasol.com | Sergio; Jay Patel; Amit Jha; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Elisa Latona | sergio.guzzo@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; elisa.latona@it.sasol.com | MOR | 19776 |  |  | * | NA | 2025-09-17 13:24 | 2025-09-23 20:21
20073 | STRIVE.R2.MC1.2384.1277.1.549.96.4 | N | N | N | Planned |  | Run program in GE-APM to send task list Details from S/4 to GE-APM | 176.37 hrs | 2025-09-15 08:00 | 2025-09-22 16:51 | Joseph Barber | joseph.barber@us.sasol.com | Sergio; Jay Patel; Amit Jha; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Elisa Latona | sergio.guzzo@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; elisa.latona@it.sasol.com | MOR | 19716,19767,19790 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-22 16:51
20074 | STRIVE.R2.MC1.2384.1277.1.549.96.5 | N | N | N | Planned |  | Run program in GE-APM to send Maintenance Plan Details from S/4 to GE-APM | 85.35 hrs | 2025-09-15 08:00 | 2025-09-18 21:34 | Joseph Barber | joseph.barber@us.sasol.com | Sergio; Jay Patel; Amit Jha; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Elisa Latona | sergio.guzzo@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; elisa.latona@it.sasol.com | MOR | 19747 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-18 21:34
20075 | STRIVE.R2.MC1.2384.1277.1.549.96.6 | N | N | N | Planned |  | Run program in GE-APM to send notification Details from S/4 to GE-APM | 0 hrs | 2025-09-16 01:06 | 2025-09-16 01:06 | Joseph Barber | joseph.barber@us.sasol.com | Sergio; Jay Patel; Amit Jha; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Elisa Latona | sergio.guzzo@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; elisa.latona@it.sasol.com | MOR | 19901 |  |  | * | NA | 2025-09-16 01:06 | 2025-09-16 01:06
20076 | STRIVE.R2.MC1.2384.1277.1.549.96.7 | N | N | N | Planned |  | Run program in GE-APM to send Work Order Details from S/4 to GE-APM | 0 hrs | 2025-09-17 01:10 | 2025-09-17 01:10 | Joseph Barber | joseph.barber@us.sasol.com | Sergio; Jay Patel; Amit Jha; Nikhil Gupta; Krishna Teja; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Elisa Latona | sergio.guzzo@it.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; mrgupta3@deloitte.com; krishn@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; elisa.latona@it.sasol.com | MOR | 19911 |  |  | * | NA | 2025-09-17 01:10 | 2025-09-17 01:10
77612 | STRIVE.R2.MC1.2384.1277.1.549.104 | [5 empty] | MDG | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
77613 | STRIVE.R2.MC1.2384.1277.1.549.104.9 | N | N | N | Planned |  | Customer Master Trigger Replication from MDG to Sample manager LIMS - Not Open Client | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Ashish Sarangi | assarangi@deloitte.com | Amol Paswan; Tulika Pal; Tushar; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | ampaswan@deloitte.com; tupal@deloitte.com; tamrutkar@deloitte.de; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | MDG | 19547 |  |  |  | 2025-08-15 08:55 | 2025-09-20 08:00 | 2025-09-20 12:00
20077 | STRIVE.R2.MC1.2384.1277.1.653 | [5 empty] | P2C | 1444.36 hrs | 2025-08-11 08:00 | 2025-10-10 16:23 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-08-11 08:00 | 2025-10-10 16:23
20078 | STRIVE.R2.MC1.2384.1277.1.653.1 | [5 empty] | P2C- SD | 1872.03 hrs | 2025-07-14 08:00 | 2025-09-30 13:15 | [6 empty] | 2025-09-09 23:50 |  | * | NA | 2025-07-14 08:00 | 2025-09-30 13:15
20079 | STRIVE.R2.MC1.2384.1277.1.653.1.1 | Y | Y | Y | Complete |  | Maintenance of Workflow relevant FIORI apps for Credit / Debit memo Request : Manage Teams and Responsibilities, Manage Workflows | 0 hrs | 2025-09-09 23:50 | 2025-09-09 23:50 | Siddhesh | sibaraskar@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ramesh SathishKumar; Nirjhar Malik | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; satramesh@deloitte.com; nimalik@deloitte.com | P2C | 18262 | 2025-09-09 23:50 | 2025-09-09 23:50 |  | 2025-09-10 10:00 | 2025-09-09 23:50 | 2025-09-09 23:50
20080 | STRIVE.R2.MC1.2384.1277.1.653.1.2 | Y | Y | Y | Complete |  | Maintenance of Workflow relevant FIORI apps for Sales Order : Manage Teams and Responsibilities, Manage Workflows | 0 hrs | 2025-09-09 23:52 | 2025-09-09 23:52 | Siddhesh | sibaraskar@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ramesh SathishKumar; Nirjhar Malik | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; satramesh@deloitte.com; nimalik@deloitte.com | P2C | 18262 | 2025-09-09 23:52 | 2025-09-09 23:52 |  | 2025-09-10 10:00 | 2025-09-09 23:52 | 2025-09-09 23:52
20082 | STRIVE.R2.MC1.2384.1277.1.653.1.4 | N | N | N | Planned |  | Maintence of Custom table (CBO & TVARVC) | 4 hrs | 2025-09-15 10:00 | 2025-09-15 14:01 | Rajeev Mishra | rajeemishra@deloitte.com | Salish Santhosh Kurian; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Ramesh SathishKumar; Siddhesh | skuriansanthosh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; satramesh@deloitte.com; sibaraskar@deloitte.com | P2C |  |  |  |  | 2025-09-15 10:00 | 2025-09-15 10:00 | 2025-09-15 14:01
20092 | STRIVE.R2.MC1.2384.1277.1.653.1.14 | Y | N | N | Sent |  | Provide the list of condition records for ZT01(Freight cost), Z993 (Discount on Freight) and GRWR (Statistical Value) needed for INTRASTAT | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Michaela | michaela.schulz@de.sasol.com | Ramesh SathishKumar; Siddhesh Baraskar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | satramesh@deloitte.com; sibaraskar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20093 | STRIVE.R2.MC1.2384.1277.1.653.1.15 | N | N | N | Planned |  | Maintain condition records for ZT01(Freight cost), Z993 (Discount on Freight) and GRWR (Statistical Value) needed for INTRASTAT | 3.05 hrs | 2025-09-10 14:01 | 2025-09-10 17:04 | Siddhesh Baraskar | sibaraskar@deloitte.com | Ramesh SathishKumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | satramesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20092 |  |  |  | 2025-09-10 10:00 | 2025-09-10 14:01 | 2025-09-10 17:04
20094 | STRIVE.R2.MC1.2384.1277.1.653.1.16 | Y | N | N | Sent |  | Provide list of Commodity Codes | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Michaela | michaela.schulz@de.sasol.com | Ramesh SathishKumar; Siddhesh Baraskar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | satramesh@deloitte.com; sibaraskar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20095 | STRIVE.R2.MC1.2384.1277.1.653.1.17 | N | N | N | Planned |  | Maintain Commodity Codes | 2 hrs | 2025-09-10 14:01 | 2025-09-10 16:01 | Siddhesh Baraskar | sibaraskar@deloitte.com | Ramesh SathishKumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | satramesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20094 |  |  |  | 2025-09-05 10:00 | 2025-09-10 14:01 | 2025-09-10 16:01
20096 | STRIVE.R2.MC1.2384.1277.1.653.1.18 | Y | N | N | Sent |  | Provide list of Comodity Codes Assignment to Materials | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Michaela | michaela.schulz@de.sasol.com | Ramesh SathishKumar; Siddhesh Baraskar; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | satramesh@deloitte.com; sibaraskar@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20097 | STRIVE.R2.MC1.2384.1277.1.653.1.19 | N | N | N | Planned |  | Maintain list of Comodity Codes Assignment to Materials | 4 hrs | 2025-09-10 16:01 | 2025-09-10 20:01 | Siddhesh Baraskar | sibaraskar@deloitte.com | Ramesh SathishKumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | satramesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20096,20095 |  |  |  | 2025-08-28 17:00 | 2025-09-10 16:01 | 2025-09-10 20:01
95094 | STRIVE.R2.MC1.2384.1277.1.653.1.25 | N | N | N | Planned |  | Partner Profile (WE20) Validation for Tungsten Customers | 4 hrs | 2025-09-28 08:00 | 2025-09-28 12:00 | Rajeev Mishra | rajeemishra@deloitte.com | Siddhesh; Ramesh SathishKumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | sibaraskar@deloitte.com; satramesh@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-28 08:00 | 2025-09-28 08:00 | 2025-09-28 12:00
95093 | STRIVE.R2.MC1.2384.1277.1.653.1.24 | N | N | N | Planned |  | OPD settings for Tungsten with IDoc output in XML format | 4 hrs | 2025-09-28 08:00 | 2025-09-28 12:00 | Rajeev Mishra | rajeemishra@deloitte.com | Siddhesh; Ramesh SathishKumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | sibaraskar@deloitte.com; satramesh@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-28 08:00 | 2025-09-28 08:00 | 2025-09-28 12:00
95092 | STRIVE.R2.MC1.2384.1277.1.653.1.23 | N | N | N | Planned |  | Pricing Text ID Validation (Pricing Hub) | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Rajeev Mishra | rajeemishra@deloitte.com | Siddhesh; Ramesh SathishKumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | sibaraskar@deloitte.com; satramesh@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 09:00
95091 | STRIVE.R2.MC1.2384.1277.1.653.1.22 | N | N | N | Planned |  | ATP Validate the configuration and Set Master Date fields | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Ilja | iholub@deloitte.it | Siddhesh; Ramesh SathishKumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sibaraskar@deloitte.com; satramesh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 10:00
95090 | STRIVE.R2.MC1.2384.1277.1.653.1.21 | N | N | N | Planned |  | Output Condition Records for Packing List Form | 4 hrs | 2025-09-24 08:00 | 2025-09-24 12:00 | Manuel | Manuel.Roellinghoff@de.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Tripti mehta; Siddhesh; Ramesh SathishKumar | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; trimehta@deloitte.com; sibaraskar@deloitte.com; satramesh@deloitte.com | P2C |  |  |  |  | 2025-09-24 08:00 | 2025-09-24 08:00 | 2025-09-24 12:00
95089 | STRIVE.R2.MC1.2384.1277.1.653.1.20 | N | N | N | Planned |  | Output Condition Records for Pickup Notification Form | 4 hrs | 2025-09-24 08:00 | 2025-09-24 12:00 | Manuel | Manuel.Roellinghoff@de.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Tripti mehta; Siddhesh; Ramesh SathishKumar | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; trimehta@deloitte.com; sibaraskar@deloitte.com; satramesh@deloitte.com | P2C |  |  |  |  | 2025-09-24 08:00 | 2025-09-24 08:00 | 2025-09-24 12:00
20098 | STRIVE.R2.MC1.2384.1277.1.653.21 | [5 empty] | P2C- TM | 671.52 hrs | 2025-07-14 08:00 | 2025-08-11 09:23 | [6 empty] | 2025-09-10 10:00 |  | * | NA | 2025-07-14 08:00 | 2025-08-11 09:23
20100 | STRIVE.R2.MC1.2384.1277.1.653.21.2 | N | N | N | Ready |  | Run program /SAPAPO/CREATE_LOCATION for roles FLVN01/FLCU01 and Shipping Points, then assign Plant BP’s to the Shipping Point Locations | 1 hrs | 2025-09-10 10:00 | 2025-09-10 11:00 | Diego Zarate | dzarate@deloitte.com | Shubham Mishra; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 19551 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 11:00
20101 | STRIVE.R2.MC1.2384.1277.1.653.21.3 | Y | N | N | Sent |  | Execute transaction /SCMTMS/TRIGGER_SETUP_BGRFC | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Shubham Mishra | spratapmishra@deloitte.com | Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20104 | STRIVE.R2.MC1.2384.1277.1.653.21.6 | Y | N | N | Sent |  | Validation of Assign Logical System and Queue Type | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Shubham Mishra | spratapmishra@deloitte.com | Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20105 | STRIVE.R2.MC1.2384.1277.1.653.21.7 | N | N | N | Planned |  | Create active model&version for TM Master Data (IMG>Transportation Management>Create active version & Model) | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Valentijn | vvandriessen@deloitte.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20104 |  |  |  | 2025-09-10 10:00 | 2025-09-10 14:01 | 2025-09-10 18:01
20106 | STRIVE.R2.MC1.2384.1277.1.653.21.8 | Y | N | N | Sent |  | Pre-load validation of SAP TM Transportation Zones | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20107 | STRIVE.R2.MC1.2384.1277.1.653.21.9 | N | N | N | Planned |  | Loading of SAP TM Transportation Zones | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Diego Zarate | dzarate@deloitte.com | Vaishali Singh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Shubham Mishra | vaishsingh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; spratapmishra@deloitte.com | P2C | 20106 |  |  |  | 2025-09-05 02:39 | 2025-09-10 14:01 | 2025-09-10 18:01
20108 | STRIVE.R2.MC1.2384.1277.1.653.21.10 | N | N | N | Planned |  | Post-load validation of SAP TM Transportation Zones | 4 hrs | 2025-09-10 18:01 | 2025-09-10 22:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20107 |  |  |  | 2025-09-05 02:39 | 2025-09-10 18:01 | 2025-09-10 22:01
20109 | STRIVE.R2.MC1.2384.1277.1.653.21.11 | N | N | N | Planned |  | Pre-load validation of SAP TM Transportation Lanes | 4 hrs | 2025-09-10 22:01 | 2025-09-11 02:03 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20108,19531 |  |  |  | 2025-09-05 02:39 | 2025-09-10 22:01 | 2025-09-11 02:03
20110 | STRIVE.R2.MC1.2384.1277.1.653.21.12 | N | N | N | Planned |  | Loading of SAP TM Transportation Lanes | 4 hrs | 2025-09-11 02:03 | 2025-09-11 06:03 | Diego Zarate | dzarate@deloitte.com | Shubham Mishra; Vaishali Singh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; vaishsingh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20109 |  |  |  | 2025-09-05 02:39 | 2025-09-11 02:03 | 2025-09-11 06:03
20111 | STRIVE.R2.MC1.2384.1277.1.653.21.13 | N | N | N | Planned |  | Post-load validation of SAP TM Transportation Lanes | 4 hrs | 2025-09-11 06:03 | 2025-09-11 10:04 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20110 |  |  |  | 2025-09-05 02:39 | 2025-09-11 06:03 | 2025-09-11 10:04
20112 | STRIVE.R2.MC1.2384.1277.1.653.21.14 | Y | N | N | Sent |  | Pre-load validation of SAP TM Vehicle Resources | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20113 | STRIVE.R2.MC1.2384.1277.1.653.21.15 | N | N | N | Planned |  | Load SAP TM Vehicle Resources | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20112 |  |  |  | 2025-09-05 02:39 | 2025-09-10 14:01 | 2025-09-10 18:01
95078 | STRIVE.R2.MC1.2384.1277.1.653.21.48 | N | N | N | Planned |  | Pre-load Validation of Rail Car Resource Master | 4 hrs | 2025-09-10 18:01 | 2025-09-10 22:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20113 |  |  | * | NA | 2025-09-10 18:01 | 2025-09-10 22:01
95077 | STRIVE.R2.MC1.2384.1277.1.653.21.47 | N | N | N | Ready |  | Load Rail Car Resource Master | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
95076 | STRIVE.R2.MC1.2384.1277.1.653.21.46 | N | N | N | Ready |  | Post-load Validation of Rail Car Resource Master | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20114 | STRIVE.R2.MC1.2384.1277.1.653.21.16 | N | N | N | Planned |  | Post-load validation of SAP TM Vehicle Resources | 4 hrs | 2025-09-10 18:01 | 2025-09-10 22:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20113 |  |  |  | 2025-09-05 02:39 | 2025-09-10 18:01 | 2025-09-10 22:01
20115 | STRIVE.R2.MC1.2384.1277.1.653.21.17 | Y | N | N | Sent |  | Set up SAP TM Documents Number Ranges | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Shefali | shefaggarwal@deloitte.com | Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Shubham Mishra | dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; spratapmishra@deloitte.com | P2C | 18395,18406 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20116 | STRIVE.R2.MC1.2384.1277.1.653.21.18 | Y | Y | N | In-Progress |  | Set up of the SOAMANAGER connection for BN4L | 4 hrs | 2025-09-10 18:39 | 2025-09-10 22:39 | Leo | lvilvoi@deloittece.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 18959 | 2025-09-10 18:39 |  |  | 2025-09-10 10:00 | 2025-09-10 18:39 | 2025-09-10 22:39
20117 | STRIVE.R2.MC1.2384.1277.1.653.21.19 | Y | N | N | Sent |  | Validation of the Set up of the connection to the Optimizer | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Valentijn | vvandriessen@deloitte.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 18838 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20118 | STRIVE.R2.MC1.2384.1277.1.653.21.20 | Y | N | N | Sent |  | Pre-load validation of the Scales for Charge Calculation | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Anke Willaert; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; awillaert@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20119 | STRIVE.R2.MC1.2384.1277.1.653.21.21 | N | N | N | Planned |  | Upload of the Scales for Charge Calculation | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Anke Willaert | awillaert@deloitte.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20118 |  |  |  | 2025-09-10 10:00 | 2025-09-10 14:01 | 2025-09-10 18:01
20120 | STRIVE.R2.MC1.2384.1277.1.653.21.22 | N | N | N | Planned |  | Post-load validation of the Scales for Charge Calculation | 4 hrs | 2025-09-10 18:01 | 2025-09-10 22:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20119 |  |  |  | 2025-09-05 10:40 | 2025-09-10 18:01 | 2025-09-10 22:01
20121 | STRIVE.R2.MC1.2384.1277.1.653.21.23 | N | N | N | Planned |  | Pre-load validation of the Rate Tables for Charge Calculation | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 19531,19549 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20122 | STRIVE.R2.MC1.2384.1277.1.653.21.24 | N | N | N | Planned |  | Upload of the Rate Tables for Charge Calculation | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Anke Willaert | awillaert@deloitte.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20121 |  |  |  | 2025-09-05 10:40 | 2025-09-10 14:01 | 2025-09-10 18:01
20123 | STRIVE.R2.MC1.2384.1277.1.653.21.25 | N | N | N | Planned |  | Post-load validation of the Rate Tables for Charge Calculation | 4 hrs | 2025-09-10 18:01 | 2025-09-10 22:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 20122 |  |  |  | 2025-09-05 10:40 | 2025-09-10 18:01 | 2025-09-10 22:01
20124 | STRIVE.R2.MC1.2384.1277.1.653.21.26 | N | N | N | Planned |  | Pre-load validation of the Calculation Sheets for Charge Calculation | 4 hrs | 2025-09-10 22:01 | 2025-09-11 02:03 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 20123 |  |  |  | 2025-09-05 10:40 | 2025-09-10 22:01 | 2025-09-11 02:03
20125 | STRIVE.R2.MC1.2384.1277.1.653.21.27 | N | N | N | Planned |  | Upload of the Calculation Sheets for Charge Calculation | 4 hrs | 2025-09-11 02:03 | 2025-09-11 06:03 | Anke Willaert | awillaert@deloitte.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20124 |  |  |  | 2025-09-05 10:40 | 2025-09-11 02:03 | 2025-09-11 06:03
20126 | STRIVE.R2.MC1.2384.1277.1.653.21.28 | N | N | N | Planned |  | Post-load validation of the Calculation Sheets for Charge Calculation | 4 hrs | 2025-09-11 06:03 | 2025-09-11 10:04 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 20125 |  |  |  | 2025-09-05 10:40 | 2025-09-11 06:03 | 2025-09-11 10:04
20127 | STRIVE.R2.MC1.2384.1277.1.653.21.29 | N | N | N | Planned |  | Pre-load validation of the Freight Agreements for Charge Calculation | 4 hrs | 2025-09-11 10:04 | 2025-09-11 14:05 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 20126 |  |  |  | 2025-09-05 10:40 | 2025-09-11 10:04 | 2025-09-11 14:05
20128 | STRIVE.R2.MC1.2384.1277.1.653.21.30 | N | N | N | Planned |  | Upload of the Freight Agreements for Charge Calculation | 4 hrs | 2025-09-11 14:05 | 2025-09-11 18:05 | Anke Willaert | awillaert@deloitte.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20127 |  |  |  | 2025-09-05 10:40 | 2025-09-11 14:05 | 2025-09-11 18:05
20129 | STRIVE.R2.MC1.2384.1277.1.653.21.31 | N | N | N | Planned |  | Post-load validation of the Freight Agreements for Charge Calculation | 4 hrs | 2025-09-11 18:05 | 2025-09-11 22:05 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 20128 |  |  |  | 2025-09-02 06:43 | 2025-09-11 18:05 | 2025-09-11 22:05
20130 | STRIVE.R2.MC1.2384.1277.1.653.21.32 | N | N | N | Planned |  | Validation of Customer BPs, Vendor BPs, Org. Units BP, Carrier in TM | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 19551,19531 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
95079 | STRIVE.R2.MC1.2384.1277.1.653.21.49 | N | N | N | Planned |  | Validation of RICS code in Carrier Master | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Anke Willaert; Mousikta chanda | dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; awillaert@deloitte.com; mouchanda@deloitte.com | P2C | 20130 |  |  | * | NA | 2025-09-10 14:01 | 2025-09-10 18:01
20131 | STRIVE.R2.MC1.2384.1277.1.653.21.33 | Y | N | N | Sent |  | Pre-load validation of SAP TM Incoterm Locations | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20132 | STRIVE.R2.MC1.2384.1277.1.653.21.34 | Y | N | N | Sent |  | Mapping of SAP TM Incoterm Locations | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Diego Zarate | dzarate@deloitte.com | Shefali; Shubham Mishra; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | shefaggarwal@deloitte.com; spratapmishra@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20131 |  |  |  | 2025-09-05 06:43 | 2025-09-10 14:01 | 2025-09-10 18:01
20133 | STRIVE.R2.MC1.2384.1277.1.653.21.35 | N | N | N | Planned |  | Post-load validation of SAP TM Incoterm Locations | 4 hrs | 2025-09-10 22:01 | 2025-09-11 02:03 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20134 |  |  |  | 2025-09-05 06:43 | 2025-09-10 22:01 | 2025-09-11 02:03
20134 | STRIVE.R2.MC1.2384.1277.1.653.21.36 | N | N | N | Planned |  | Mapping of SAP TM Incoterm Locations in MDG system | 4 hrs | 2025-09-10 18:01 | 2025-09-10 22:01 | Diego Zarate | dzarate@deloitte.com | Shubham Mishra; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20132 |  |  |  | 2025-09-05 06:43 | 2025-09-10 18:01 | 2025-09-10 22:01
20135 | STRIVE.R2.MC1.2384.1277.1.653.21.37 | N | N | N | Planned |  | Maintain SAP TM TVARVC Parameters | 4 hrs | 2025-09-15 06:43 | 2025-09-15 10:44 | Shefali | shefaggarwal@deloitte.com | Shubham Mishra; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-15 06:43 | 2025-09-15 06:43 | 2025-09-15 10:44
20136 | STRIVE.R2.MC1.2384.1277.1.653.21.38 | N | N | N | Planned |  | Validation of SAP TM TVARVC Parameters | 4 hrs | 2025-09-15 10:44 | 2025-09-15 14:45 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20135 |  |  |  | 2025-09-05 06:43 | 2025-09-15 10:44 | 2025-09-15 14:45
20137 | STRIVE.R2.MC1.2384.1277.1.653.21.39 | N | N | N | Ready |  | Set up of the SAP TM Batch Jobs | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Diego Zarate | dzarate@deloitte.com | Shubham Mishra; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20138 | STRIVE.R2.MC1.2384.1277.1.653.21.40 | N | N | N | Planned |  | Validation of the loaded SAP TM Batch Jobs | 4 hrs | 2025-09-10 14:01 | 2025-09-10 18:01 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20137 |  |  |  | 2025-09-10 10:00 | 2025-09-10 14:01 | 2025-09-10 18:01
20139 | STRIVE.R2.MC1.2384.1277.1.653.21.41 | N | N | N | Planned |  | Maintenance of Z-Tables | 4 hrs | 2025-09-15 06:43 | 2025-09-15 10:44 | Shefali | shefaggarwal@deloitte.com | Shubham Mishra; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  |  | 2025-09-15 06:43 | 2025-09-15 06:43 | 2025-09-15 10:44
20140 | STRIVE.R2.MC1.2384.1277.1.653.21.42 | N | N | N | Planned |  | Validation of Z-Tables | 4 hrs | 2025-09-15 10:44 | 2025-09-15 14:45 | Manuel | Manuel.Roellinghoff@de.sasol.com | Shubham Mishra; Diego Zarate; Valentijn; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | spratapmishra@deloitte.com; dzarate@deloitte.com; vvandriessen@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20139 |  |  |  | 2025-09-05 06:43 | 2025-09-15 10:44 | 2025-09-15 14:45
20141 | STRIVE.R2.MC1.2384.1277.1.653.21.43 | N | N | N | Planned |  | Maintain BN4L ID in Carrier Business Partners | 4 hrs | 2025-09-10 22:39 | 2025-09-11 02:41 | Valentijn | vvandriessen@deloitte.com | Shefali; Shubham Mishra; Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | shefaggarwal@deloitte.com; spratapmishra@deloitte.com; dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C | 20116,19531 |  |  |  | 2025-09-05 06:43 | 2025-09-10 22:39 | 2025-09-11 02:41
20142 | STRIVE.R2.MC1.2384.1277.1.653.21.44 | N | N | N | Planned |  | Service order access to be added for user -Tanker and Road Scenario | 4 hrs | 2025-09-10 10:00 | 2025-09-10 14:01 | Anke | awillaert@deloitte.com | Diego Zarate; Shubham Mishra; Valentijn; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | dzarate@deloitte.com; spratapmishra@deloitte.com; vvandriessen@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | P2C | 19549 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 14:01
20143 | STRIVE.R2.MC1.2384.1277.1.653.21.45 | N | N | N | Planned |  | Freight Condition Record Upload -ZT01& ZT02 | 4 hrs | 2025-09-20 12:01 | 2025-09-20 16:01 | Shubham Mishra | spratapmishra@deloitte.com | Diego Zarate; Valentijn; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | dzarate@deloitte.com; vvandriessen@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C | 20312 |  |  |  | 2025-09-05 06:43 | 2025-09-20 12:01 | 2025-09-20 16:01
20144 | STRIVE.R2.MC1.2384.1277.1.653.67 | [5 empty] | R2D | 340.55 hrs | 2025-07-14 08:00 | 2025-07-28 13:30 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-07-28 13:30
20145 | STRIVE.R2.MC1.2384.1277.1.653.67.1 | N | N | N | Ready |  | P&L Extraction Historical Values – Check that no further AuC have been settled to final assets and handover to Data Migration Team | 2 hrs | 2025-09-10 08:00 | 2025-09-10 10:00 | Oluf baren | oluf.braren@de.sasol.com | Hendrik Kamsteeg; Michaela; Alex Miles; Satyajit; Roman Mäkilä; Moonalisa; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roshanlal | hendrik.kamsteeg@de.sasol.com; michaela.schulz@de.sasol.com; almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; mooghosh@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; rohemwani@deloitte.com | R2D |  |  |  |  | 2025-09-10 08:00 | 2025-09-10 08:00 | 2025-09-10 10:00
20146 | STRIVE.R2.MC1.2384.1277.1.653.67.2 | N | N | N | Planned |  | Historical P&L Open Period 12/2024 for P/L Load as per 30.06.2024 (Historical AuC) | 8 hrs | 2025-09-20 14:23 | 2025-09-20 22:23 | Alexandra Ruff | aruff@deloitte.de | Mohamed Ibrahim; Roshanlal; Daniel Lohmann; Alex Miles; Satyajit; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | mibrahimjs@deloitte.com; rohemwani@deloitte.com; dlohmann@deloitte.de; almiles@deloitte.de; sapatnaik@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D | 19489 |  |  | * | NA | 2025-09-20 14:23 | 2025-09-20 22:23
20147 | STRIVE.R2.MC1.2384.1277.1.653.67.3 | N | N | N | Planned |  | Historical P&L Simulation and share results | 2 hrs | 2025-09-20 22:23 | 2025-09-21 00:25 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Hendrik Kamsteeg; Oluf baren; Daniel Lohmann; Tatiana; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Roshanlal | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; hendrik.kamsteeg@de.sasol.com; oluf.braren@de.sasol.com; dlohmann@deloitte.de; tvinogradova@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rohemwani@deloitte.com | R2D | 20146 |  |  | * | NA | 2025-09-20 22:23 | 2025-09-21 00:25
20148 | STRIVE.R2.MC1.2384.1277.1.653.67.4 | N | N | N | Planned |  | Historical P&L Pre-Load Validation and Sign-off | 1 hrs | 2025-09-21 00:25 | 2025-09-21 01:25 | Oluf baren | oluf.braren@de.sasol.com | ; Hendrik Kamsteeg; Michaela; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Roshanlal | ; hendrik.kamsteeg@de.sasol.com; michaela.schulz@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rohemwani@deloitte.com | R2D | 20147 |  |  | * | NA | 2025-09-21 00:25 | 2025-09-21 01:25
20149 | STRIVE.R2.MC1.2384.1277.1.653.67.5 | N | N | N | Planned |  | Historical P&L Load into S/4 and share Post-Load | 2 hrs | 2025-09-21 01:25 | 2025-09-21 03:25 | Moonalisa | mooghosh@deloitte.com | Alex Miles; Satyajit; Roman Mäkilä; Hendrik Kamsteeg; Oluf baren; Daniel Lohmann; Tatiana; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Roshanlal | almiles@deloitte.de; sapatnaik@deloitte.com; roman.makila@deloitte.fi; hendrik.kamsteeg@de.sasol.com; oluf.braren@de.sasol.com; dlohmann@deloitte.de; tvinogradova@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rohemwani@deloitte.com | R2D | 20148 |  |  | * | NA | 2025-09-21 01:25 | 2025-09-21 03:25
20150 | STRIVE.R2.MC1.2384.1277.1.653.67.6 | N | N | N | Planned |  | Historical P&L Post-Load Validation and Sign-off | 2 hrs | 2025-09-21 03:25 | 2025-09-21 05:25 | Hendrik Kamsteeg | hendrik.kamsteeg@de.sasol.com | Michaela; Oluf baren; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tatiana; Satyajit; Alex Miles; Roshanlal | michaela.schulz@de.sasol.com; oluf.braren@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de; sapatnaik@deloitte.com; almiles@deloitte.de; rohemwani@deloitte.com | R2D | 20149 |  |  | * | NA | 2025-09-21 03:25 | 2025-09-21 05:25
20151 | STRIVE.R2.MC1.2384.1277.1.653.67.7 | N | N | N | Planned |  | Historical P&L Conduct Settlement from WBS to AuC as per 30.06.2024 | 2 hrs | 2025-09-21 05:25 | 2025-09-21 07:25 | Clara Mori | clara.mori@it.sasol.com | Roshanlal; Tatiana; Daniel Lohmann; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | rohemwani@deloitte.com; tvinogradova@deloitte.de; dlohmann@deloitte.de; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | R2D | 20150 |  |  | * | NA | 2025-09-21 05:25 | 2025-09-21 07:25
20152 | STRIVE.R2.MC1.2384.1277.1.653.67.8 | N | N | N | Planned |  | Historical P&L Close Period 12/2024 (OB52) and Close FY 2024 in AA (OAAQ) | 2 hrs | 2025-09-21 07:25 | 2025-09-21 09:26 | Alexandra Ruff | aruff@deloitte.de | Mohamed Ibrahim; Roshanlal; Daniel Lohmann; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | mibrahimjs@deloitte.com; rohemwani@deloitte.com; dlohmann@deloitte.de; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | R2D | 20151 |  |  | * | NA | 2025-09-21 07:25 | 2025-09-21 09:26
20153 | STRIVE.R2.MC1.2384.1277.1.729 | [5 empty] | S2P | 582.11 hrs | 2025-07-14 08:00 | 2025-08-07 15:44 | [8 empty] | * | NA | 2025-07-14 08:00 | 2025-08-07 15:44
20154 | STRIVE.R2.MC1.2384.1277.1.729.1 | N | N | N | Ready |  | Enables users in Coupa | 4 hrs | 2025-09-10 08:00 | 2025-09-10 12:00 | Rahul Sengupta | rahusengupta@deloitte.com | Pournami Nair; Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  |  |  |  | 2025-09-10 08:00 | 2025-09-10 08:00 | 2025-09-10 12:00
20155 | STRIVE.R2.MC1.2384.1277.1.729.2 | N | N | N | Planned |  | Assign Users to Approval Group | 4 hrs | 2025-09-10 12:01 | 2025-09-10 16:01 | Rahul Sengupta | rahusengupta@deloitte.com | Pournami Nair; Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 20154 |  |  | * | NA | 2025-09-10 12:01 | 2025-09-10 16:01
20156 | STRIVE.R2.MC1.2384.1277.1.729.3 | N | N | N | Planned |  | Enable Email Notifications | 4 hrs | 2025-09-10 16:01 | 2025-09-10 20:01 | Rahul Sengupta | rahusengupta@deloitte.com | Pournami Nair; Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pounair@deloitte.com; kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 20155 |  |  | * | NA | 2025-09-10 16:01 | 2025-09-10 20:01
20157 | STRIVE.R2.MC1.2384.1277.1.729.4 | N | N | N | Planned |  | Configure Punchouts in Coupa | 4 hrs | 2025-09-10 12:01 | 2025-09-10 16:01 | Supriya | supriychakraborty@deloitte.com | Adelin Apotsu; Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | aapostu@deloittece.com; apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 20154,19729 |  |  |  | 2025-08-28 08:00 | 2025-09-10 12:01 | 2025-09-10 16:01
20158 | STRIVE.R2.MC1.2384.1277.1.729.5 | N | N | N | Planned |  | Update Company Code Information | 4 hrs | 2025-09-10 16:01 | 2025-09-10 20:01 | Pournami Nair | pounair@deloitte.com | Prasanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rahul Sengupta; S2P Team | kalprasanth@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rahusengupta@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa | 20157 |  |  |  | 2025-08-28 08:00 | 2025-09-10 16:01 | 2025-09-10 20:01
20159 | STRIVE.R2.MC1.2384.1277.1.729.6 | N | N | N | Ready |  | Security roles mapped data to be validated | 4 hrs | 2025-09-10 16:01 | 2025-09-10 20:01 | Prasanth | kalprasanth@deloitte.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  |  | 2025-09-10 16:01 | 2025-09-10 16:01 | 2025-09-10 20:01
20160 | STRIVE.R2.MC1.2384.1277.1.729.7 | N | N | N | Ready |  | Validate Transported Variants for Batch Jobs | 4 hrs | 2025-09-10 16:01 | 2025-09-10 20:01 | Prasanth | kalprasanth@deloitte.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  |  | 2025-09-10 16:01 | 2025-09-10 16:01 | 2025-09-10 20:01
20161 | STRIVE.R2.MC1.2384.1277.1.729.8 | N | N | N | Ready |  | Maintain Non-Transportable Variants for Batch Jobs | 4 hrs | 2025-09-10 16:01 | 2025-09-10 20:01 | Prasanth | kalprasanth@deloitte.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  |  | 2025-09-10 16:01 | 2025-09-10 16:01 | 2025-09-10 20:01
20162 | STRIVE.R2.MC1.2384.1277.1.738 | [5 empty] | R2P | 2540.08 hrs | 2025-07-14 08:00 | 2025-10-28 11:09 | [6 empty] | 2025-08-20 14:41 |  | * | NA | 2025-07-14 08:00 | 2025-10-28 11:09
20163 | STRIVE.R2.MC1.2384.1277.1.738.1 | Y | Y | Y | Complete |  | Assign RFC Destinations to Various Application Cases | 0.02 hrs | 2025-08-28 16:04 | 2025-08-28 16:05 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 18183,20166 | 2025-08-28 16:04 | 2025-08-28 16:05 |  | 2025-08-20 09:41 | 2025-08-28 16:04 | 2025-08-28 16:05
20164 | STRIVE.R2.MC1.2384.1277.1.738.2 | Y | N | N | Sent |  | Maintain Business System Group | 2 hrs | 2025-09-05 10:00 | 2025-09-05 12:00 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20163,18183 |  |  |  | 2025-09-05 10:00 | 2025-09-05 10:00 | 2025-09-05 12:00
20165 | STRIVE.R2.MC1.2384.1277.1.738.3 | N | N | N | Planned |  | Assign Logical System and Queue Type | 2 hrs | 2025-09-05 12:01 | 2025-09-05 14:01 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20164 |  |  | * | NA | 2025-09-05 12:01 | 2025-09-05 14:01
20166 | STRIVE.R2.MC1.2384.1277.1.738.4 | Y | Y | Y | Complete |  | Ensure Specify APO release is configured for the client | 0.03 hrs | 2025-08-22 12:11 | 2025-08-22 12:13 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 18184 | 2025-08-22 12:11 | 2025-08-22 12:13 |  | 2025-08-20 14:41 | 2025-08-22 12:11 | 2025-08-22 12:13
20167 | STRIVE.R2.MC1.2384.1277.1.738.5 | Y | Y | Y | Complete |  | Set Target System and Queue Type | 0 hrs | 2025-08-28 16:06 | 2025-08-28 16:06 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20166 | 2025-08-28 16:06 | 2025-08-28 16:06 |  | 2025-08-20 14:41 | 2025-08-28 16:06 | 2025-08-28 16:06
20168 | STRIVE.R2.MC1.2384.1277.1.738.6 | Y | Y | Y | Complete |  | Verify if BF11 setting imported | 0.07 hrs | 2025-08-22 12:16 | 2025-08-22 12:20 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 18184 | 2025-08-22 12:16 | 2025-08-22 12:20 |  | 2025-08-20 14:41 | 2025-08-22 12:16 | 2025-08-22 12:20
20169 | STRIVE.R2.MC1.2384.1277.1.738.7 | Y | Y | Y | Complete |  | Activate CIF Queues | 0.02 hrs | 2025-08-22 12:20 | 2025-08-22 12:21 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 18184 | 2025-08-22 12:20 | 2025-08-22 12:21 |  | 2025-08-20 14:41 | 2025-08-22 12:20 | 2025-08-22 12:21
20170 | STRIVE.R2.MC1.2384.1277.1.738.8 | Y | Y | Y | Complete |  | Ensure CIF Parameters are maintained in CFC2 | 0.02 hrs | 2025-08-28 16:07 | 2025-08-28 16:08 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20169,18184 | 2025-08-28 16:07 | 2025-08-28 16:08 |  | 2025-08-20 14:41 | 2025-08-28 16:07 | 2025-08-28 16:08
20171 | STRIVE.R2.MC1.2384.1277.1.738.9 | N | N | N | Ready |  | Ensure Settings for the Transfer of Resources to SAP APO aresetup in CFC9 | 2 hrs | 2025-09-10 10:00 | 2025-09-10 12:00 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20170 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 12:00
20172 | STRIVE.R2.MC1.2384.1277.1.738.10 | N | N | N | Planned |  | Create Model and Version PP/DS | 2 hrs | 2025-09-10 12:01 | 2025-09-10 14:01 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20171 |  |  |  | 2025-09-10 10:00 | 2025-09-10 12:01 | 2025-09-10 14:01
20173 | STRIVE.R2.MC1.2384.1277.1.738.11 | N | N | N | Planned |  | Create SCM location | 2 hrs | 2025-09-10 14:01 | 2025-09-10 16:01 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20172 |  |  |  | 2025-09-10 10:00 | 2025-09-10 14:01 | 2025-09-10 16:01
20174 | STRIVE.R2.MC1.2384.1277.1.738.12 | N | N | N | Planned |  | Assign MRP to SCM location | 2 hrs | 2025-09-10 16:01 | 2025-09-10 18:01 | Shivani Kulkarni | shivankulkarni@deloitte.com | Amit das; Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande; Mousikta chanda; Shreyas Singh Kunwar | amitdas3@deloitte.com; cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com; mouchanda@deloitte.com; shkunwar@deloitte.com | R2P | 20173 |  |  |  | 2025-08-20 14:41 | 2025-09-10 16:01 | 2025-09-10 18:01
20175 | STRIVE.R2.MC1.2384.1277.1.738.13 | Y | Y | Y | Complete |  | R2P-QM -Load Code Group | 0 hrs | 2025-08-29 18:39 | 2025-08-29 18:40 | Pamela Mihali | pamihali@deloitte.de | Abhishek Parab; Dhruv Kansal; USI STRIVE CUTOVER; Amit das; Mousikta chanda; Nilesh Deshpande | abhparab@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; amitdas3@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P |  | 2025-08-29 18:39 | 2025-08-29 18:40 |  | 2025-08-20 14:41 | 2025-08-29 18:39 | 2025-08-29 18:40
20176 | STRIVE.R2.MC1.2384.1277.1.738.14 | Y | Y | I | Issue |  | R2P-QM- Load Selected Sets | 2 hrs | 2025-08-20 14:41 | 2025-08-20 16:41 | Pamela Mihali | pamihali@deloitte.de | Abhishek Parab; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | abhparab@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  |  | 2025-08-20 14:41 | 2025-08-20 14:41 | 2025-08-20 16:41
20177 | STRIVE.R2.MC1.2384.1277.1.738.15 | Y | N | N | Sent |  | R2P-QM- Verify Migration of QM TR | 2 hrs | 2025-08-20 14:41 | 2025-08-20 16:41 | Pamela Mihali | pamihali@deloitte.de | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande; Abhishek Parab | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com; abhparab@deloitte.com | R2P |  |  |  |  | 2025-08-20 14:41 | 2025-08-20 14:41 | 2025-08-20 16:41
40156 | STRIVE.R2.MC1.2384.1277.1.738.241 | Y | Y | Y | Complete |  | Create Standard Text for the Quality Certificate | 24.63 hrs | 2025-08-21 11:30 | 2025-08-22 12:13 | Suruthi | ssubramaniamgovin@deloitte.com | Abhishek Parab; Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | abhparab@deloitte.com; pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  | 2025-08-21 11:30 | 2025-08-22 12:13 |  | 2025-08-20 14:41 | 2025-08-21 11:30 | 2025-08-22 12:13
20974 | STRIVE.R2.MC1.2384.1277.1.1232 | [5 empty] | R2P - EHS | 1404.13 hrs | 2025-07-14 08:00 | 2025-09-11 00:03 | [6 empty] | 2025-07-14 08:00 |  | * | NA | 2025-07-14 08:00 | 2025-09-11 00:03
20975 | STRIVE.R2.MC1.2384.1277.1.1232.195 | Y | Y | Y | Complete |  | R2P- EHS - Provide list of external transport import to basis for the import | 2 hrs | 2025-07-29 11:10 | 2025-08-11 08:31 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-07-29 11:10 |  | * | NA | 2025-07-29 11:10 | 2025-08-11 08:31
20976 | STRIVE.R2.MC1.2384.1277.1.1232.196 | Y | Y | Y | Complete |  | R2P-EHS- Create EHS TCP IP connections | 4 hrs | 2025-07-14 08:00 | 2025-07-14 12:00 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-07-14 08:00 | 2025-07-14 12:00 | * | NA | 2025-07-14 08:00 | 2025-07-14 12:00
20977 | STRIVE.R2.MC1.2384.1277.1.1232.197 | Y | Y | Y | Complete |  | R2P-EHS- Provide CL01, CL02, CT04, CGB7 access in MDG and S/4 system to user assigned to shgour@deloitte.com | 434.99 hrs | 2025-08-11 08:00 | 2025-08-29 12:13 | GRC | dttsasolsecuritygrcteam@deloitte.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-08-11 08:00 | 2025-08-29 12:13 | * | NA | 2025-08-11 08:00 | 2025-08-29 12:13
20978 | STRIVE.R2.MC1.2384.1277.1.1232.198 | Y | Y | Y | Complete |  | R2P-EHS- Perform CGB7& Create SVT Class-001 (Z_SAP_EHS_SVT) and Characteristic in MDG system | 0 hrs | 2025-08-05 22:11 | 2025-08-05 22:11 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20977 | 2025-08-05 22:11 | 2025-08-05 22:11 | * | NA | 2025-08-05 22:11 | 2025-08-05 22:11
20979 | STRIVE.R2.MC1.2384.1277.1.1232.199 | Y | Y | Y | Complete |  | R2P-EHS- Create SVT (Z_SAP_EHS_SVT), Polymer (Z_SAP_POLYMER) Class and Characteristic in S/4 system | 0 hrs | 2025-08-05 22:11 | 2025-08-05 22:11 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20978 | 2025-08-05 22:11 | 2025-08-05 22:11 | * | NA | 2025-08-05 22:11 | 2025-08-05 22:11
20980 | STRIVE.R2.MC1.2384.1277.1.1232.200 | Y | Y | Y | Complete |  | R2P-EHS- Verify EHS TCP IP connections | 4 hrs | 2025-08-05 13:05 | 2025-08-06 08:05 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20976 | 2025-08-05 13:05 | 2025-08-06 08:05 | * | NA | 2025-08-05 13:05 | 2025-08-06 08:05
20981 | STRIVE.R2.MC1.2384.1277.1.1232.201 | Y | Y | Y | Complete |  | R2P- EHS- Verify migration of Property Tree TR | 11.92 hrs | 2025-08-05 13:05 | 2025-08-06 17:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20975 | 2025-08-05 13:05 | 2025-08-06 17:00 | * | NA | 2025-08-05 13:05 | 2025-08-06 17:00
20982 | STRIVE.R2.MC1.2384.1277.1.1232.202 | Y | Y | Y | Complete |  | R2P- EHS- Verify migration of EHS configuration TR | 11.92 hrs | 2025-08-05 13:05 | 2025-08-06 17:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-08-05 13:05 | 2025-08-06 17:00 | * | NA | 2025-08-05 13:05 | 2025-08-06 17:00
20983 | STRIVE.R2.MC1.2384.1277.1.1232.203 | Y | Y | Y | Complete |  | R2P- EHS- Generate Standard Phrase Sets | 2.68 hrs | 2025-08-07 14:19 | 2025-08-07 17:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20981 | 2025-08-07 14:19 | 2025-08-07 17:00 | * | NA | 2025-08-07 14:19 | 2025-08-07 17:00
20984 | STRIVE.R2.MC1.2384.1277.1.1232.204 | Y | Y | Y | Complete |  | R2P- EHS- Match Up Master Data- flag"Match up ValAss type and char."only | 2.68 hrs | 2025-08-07 14:19 | 2025-08-07 17:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20983 | 2025-08-07 14:19 | 2025-08-07 17:00 | * | NA | 2025-08-07 14:19 | 2025-08-07 17:00
20985 | STRIVE.R2.MC1.2384.1277.1.1232.205 | Y | Y | Y | Complete |  | R2P- EHS- Match Up Master Data- flag"Activate Phrasing of Characteristics" | 2.68 hrs | 2025-08-07 14:19 | 2025-08-07 17:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20984 | 2025-08-07 14:19 | 2025-08-07 17:00 | * | NA | 2025-08-07 14:19 | 2025-08-07 17:00
20986 | STRIVE.R2.MC1.2384.1277.1.1232.206 | Y | Y | Y | Complete |  | R2P- EHS- Set up number range for Phrases | 0 hrs | 2025-08-06 20:51 | 2025-08-06 20:51 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20985 | 2025-08-06 20:51 | 2025-08-06 20:51 | * | NA | 2025-08-06 20:51 | 2025-08-06 20:51
20987 | STRIVE.R2.MC1.2384.1277.1.1232.207 | Y | Y | Y | Complete |  | R2P- EHS- Create Variant for Phrase Import Program | 0 hrs | 2025-08-06 19:58 | 2025-08-06 19:58 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20985 | 2025-08-06 19:58 | 2025-08-06 19:58 | * | NA | 2025-08-06 19:58 | 2025-08-06 19:58
20988 | STRIVE.R2.MC1.2384.1277.1.1232.208 | Y | Y | Y | Complete |  | R2P- EHS- Upload files in AL11 for 2504 Standard phrase and phrase set including corrections | 10.5 hrs | 2025-08-07 14:18 | 2025-08-08 16:48 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20987 | 2025-08-07 14:18 | 2025-08-08 16:48 | * | NA | 2025-08-07 14:18 | 2025-08-08 16:48
20989 | STRIVE.R2.MC1.2384.1277.1.1232.209 | Y | Y | Y | Complete |  | R2P- EHS- Merge 2504 standard phrase to CUST library | 10.5 hrs | 2025-08-07 14:18 | 2025-08-08 16:48 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20988 | 2025-08-07 14:18 | 2025-08-08 16:48 | * | NA | 2025-08-07 14:18 | 2025-08-08 16:48
20990 | STRIVE.R2.MC1.2384.1277.1.1232.210 | Y | Y | Y | Complete |  | R2P- EHS- Import 2504 Phrase Set Assignment | 10.49 hrs | 2025-08-07 14:19 | 2025-08-08 16:48 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20989 | 2025-08-07 14:19 | 2025-08-08 16:48 | * | NA | 2025-08-07 14:19 | 2025-08-08 16:48
20991 | STRIVE.R2.MC1.2384.1277.1.1232.211 | N | N | N | Ready |  | R2P-EHS- Create CVD2 address number for legal entities- Opesus | 1 hrs | 2025-08-20 08:00 | 2025-08-20 09:00 | Claudia | claudia.valdes@opesus.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20990 |  |  |  | 2025-08-20 08:00 | 2025-08-20 08:00 | 2025-08-20 09:00
20992 | STRIVE.R2.MC1.2384.1277.1.1232.212 | Y | Y | Y | Complete |  | R2P- EHS- Verify migration of Regulatory Content TR | 10.5 hrs | 2025-08-20 08:00 | 2025-08-21 10:30 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-08-20 08:00 | 2025-08-21 10:30 | * | NA | 2025-08-20 08:00 | 2025-08-21 10:30
20993 | STRIVE.R2.MC1.2384.1277.1.1232.213 | Y | Y | Y | Complete |  | R2P- EHS- Upload files in AL11 for 2504 PS and DG phrase and phrase set. | 3.01 hrs | 2025-08-20 08:00 | 2025-08-23 01:17 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20992 | 2025-08-20 08:00 | 2025-08-23 01:17 | * | NA | 2025-08-20 08:00 | 2025-08-23 01:17
20994 | STRIVE.R2.MC1.2384.1277.1.1232.214 | Y | Y | Y | Complete |  | R2P- EHS- Merge 2504 PS and DG phrase to Cust library | 3.01 hrs | 2025-08-20 08:00 | 2025-08-23 01:17 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20993 | 2025-08-20 08:00 | 2025-08-23 01:17 | * | NA | 2025-08-20 08:00 | 2025-08-23 01:17
20995 | STRIVE.R2.MC1.2384.1277.1.1232.215 | Y | Y | Y | Complete |  | R2P- EHS- Import 2504 PS and DG Phrase Set Assignment | 3.02 hrs | 2025-08-20 08:00 | 2025-08-23 01:17 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20994 | 2025-08-20 08:00 | 2025-08-23 01:17 | * | NA | 2025-08-20 08:00 | 2025-08-23 01:17
20996 | STRIVE.R2.MC1.2384.1277.1.1232.216 | Y | Y | Y | Complete |  | R2P- EHS- Provide upload files for Custom Phrase | 217.26 hrs | 2025-08-19 15:39 | 2025-08-28 17:30 | Hans Jorg | hansjorg.becker@de.sasol.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati; Torsten Freydt | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P |  | 2025-08-19 15:39 | 2025-08-28 17:30 |  | 2025-08-20 08:00 | 2025-08-19 15:39 | 2025-08-28 17:30
20997 | STRIVE.R2.MC1.2384.1277.1.1232.217 | Y | Y | Y | Complete |  | R2P- EHS- Upload files on AL11 for Custom Phrase Import | 28.03 hrs | 2025-08-28 14:13 | 2025-08-29 21:36 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20996 | 2025-08-28 14:13 | 2025-08-29 21:36 |  | 2025-08-20 08:00 | 2025-08-28 14:13 | 2025-08-29 21:36
20998 | STRIVE.R2.MC1.2384.1277.1.1232.218 | Y | Y | Y | Complete |  | R2P-EHS- Import Custom Phrases based on Phrases shared by Sasol | 65.74 hrs | 2025-08-28 14:12 | 2025-09-01 15:32 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20997 | 2025-08-28 14:12 | 2025-09-01 15:32 |  | 2025-08-25 10:00 | 2025-08-28 14:12 | 2025-09-01 15:32
20999 | STRIVE.R2.MC1.2384.1277.1.1232.219 | Y | Y | Y | Complete |  | R2P-EHS- Merge Custom Phrases to CUST library | 0 hrs | 2025-08-28 14:12 | 2025-09-01 15:33 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20998 | 2025-08-28 14:12 | 2025-09-01 15:33 |  | 2025-08-20 08:00 | 2025-08-28 14:12 | 2025-09-01 15:33
21000 | STRIVE.R2.MC1.2384.1277.1.1232.220 | Y | Y | Y | Complete |  | R2P-EHS- Manually Create custom Class | 97.92 hrs | 2025-08-28 14:11 | 2025-09-01 19:42 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20996 | 2025-08-28 14:11 | 2025-09-01 19:42 |  | 2025-08-25 11:00 | 2025-08-28 14:11 | 2025-09-01 19:42
21001 | STRIVE.R2.MC1.2384.1277.1.1232.221 | Y | Y | Y | Complete |  | R2P- EHS- Manually Create Custom Characteristic | 27.05 hrs | 2025-08-28 14:11 | 2025-08-29 21:37 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21000 | 2025-08-28 14:11 | 2025-08-29 21:37 |  | 2025-08-25 11:00 | 2025-08-28 14:11 | 2025-08-29 21:37
21002 | STRIVE.R2.MC1.2384.1277.1.1232.222 | Y | Y | Y | Complete |  | R2P-EHS- Manually Create Custom Phrase sets | 0 hrs | 2025-08-28 14:11 | 2025-08-29 21:37 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21001 | 2025-08-28 14:11 | 2025-08-29 21:37 |  | 2025-08-25 11:00 | 2025-08-28 14:11 | 2025-08-29 21:37
21003 | STRIVE.R2.MC1.2384.1277.1.1232.223 | Y | N | N | Sent |  | R2P-EHS- Validate Class and Characteristic | 1 hrs | 2025-09-05 14:01 | 2025-09-05 15:01 | Klaus | klaus.heitkamp@de.sasol.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21002 |  |  |  | 2025-09-05 14:01 | 2025-09-05 14:01 | 2025-09-05 15:01
21004 | STRIVE.R2.MC1.2384.1277.1.1232.224 | Y | Y | Y | Complete |  | R2P-EHS- Assign Phrases to custom phrase sets | 0 hrs | 2025-09-01 16:37 | 2025-09-01 19:55 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21003 | 2025-09-01 16:37 | 2025-09-01 19:55 |  | 2025-09-05 14:01 | 2025-09-01 16:37 | 2025-09-01 19:55
21005 | STRIVE.R2.MC1.2384.1277.1.1232.225 | Y | Y | Y | Complete |  | R2P-EHS- Perform Import of Custom Phrase Sets | 0 hrs | 2025-09-01 16:37 | 2025-09-01 19:46 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21004 | 2025-09-01 16:37 | 2025-09-01 19:46 |  | 2025-09-05 14:01 | 2025-09-01 16:37 | 2025-09-01 19:46
21006 | STRIVE.R2.MC1.2384.1277.1.1232.226 | Y | Y | Y | Complete |  | R2P- EHS- Setup Phrases Number Range in S4 to Internal | 0 hrs | 2025-09-01 16:37 | 2025-09-01 19:46 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21005 | 2025-09-01 16:37 | 2025-09-01 19:46 |  | 2025-09-05 14:01 | 2025-09-01 16:37 | 2025-09-01 19:46
21007 | STRIVE.R2.MC1.2384.1277.1.1232.227 | N | N | N | Ready |  | R2P-EHS- Upload Label, TDS, eSDS template in AL11 | 1 hrs | 2025-09-05 14:01 | 2025-09-05 15:01 | Harish Kristapati | hkristapati@deloitte.com | Priyanka Singhal; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov | priyasinghal@deloitte.com; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de | R2P |  |  |  |  | 2025-09-05 14:01 | 2025-09-05 14:01 | 2025-09-05 15:01
21008 | STRIVE.R2.MC1.2384.1277.1.1232.228 | N | N | N | Planned |  | R2P-EHS- Import Label, TDS, eSDS template | 1 hrs | 2025-09-10 10:00 | 2025-09-10 11:00 | Harish Kristapati | hkristapati@deloitte.com | Priyanka Singhal; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov | priyasinghal@deloitte.com; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de | R2P | 21007 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 11:00
21009 | STRIVE.R2.MC1.2384.1277.1.1232.229 | N | N | N | Planned |  | R2P-EHS- Validate and Release the template | 1 hrs | 2025-09-10 11:00 | 2025-09-10 12:00 | Harish Kristapati | hkristapati@deloitte.com | Priyanka Singhal; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov | priyasinghal@deloitte.com; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de | R2P | 21008 |  |  |  | 2025-09-05 14:01 | 2025-09-10 11:00 | 2025-09-10 12:00
21010 | STRIVE.R2.MC1.2384.1277.1.1232.230 | N | N | N | Planned |  | R2P-EHS- Create Generation variants for Labels, TDS, eSDS | 1 hrs | 2025-09-10 12:01 | 2025-09-10 13:01 | Harish Kristapati | hkristapati@deloitte.com | Priyanka Singhal; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov | priyasinghal@deloitte.com; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de | R2P | 21009 |  |  |  | 2025-09-05 14:01 | 2025-09-10 12:01 | 2025-09-10 13:01
21011 | STRIVE.R2.MC1.2384.1277.1.1232.231 | N | N | N | Planned |  | R2P-EHS- Create Label Stocks | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Harish Kristapati | hkristapati@deloitte.com | Priyanka Singhal; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov | priyasinghal@deloitte.com; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de | R2P | 21010 |  |  |  | 2025-09-05 14:01 | 2025-09-10 13:01 | 2025-09-10 14:01
21012 | STRIVE.R2.MC1.2384.1277.1.1232.232 | N | N | N | Ready |  | R2P-EHS- Define Inheritance Templates | 1 hrs | 2025-09-10 10:00 | 2025-09-10 11:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21006 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 11:00
21013 | STRIVE.R2.MC1.2384.1277.1.1232.233 | Y | N | N | Sent |  | R2P- EHS- Provide Upload files for all Spec Types | 1 hrs | 2025-09-10 10:00 | 2025-09-10 11:00 | Hans Jorg | hansjorg.becker@de.sasol.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati; Torsten Freydt | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com; Torsten.Freydt-Olek@de.sasol.com | R2P | 21006 |  |  |  | 2025-09-10 10:00 | 2025-09-10 10:00 | 2025-09-10 11:00
21014 | STRIVE.R2.MC1.2384.1277.1.1232.234 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-LIST_SUB | 1 hrs | 2025-09-10 11:00 | 2025-09-10 12:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21013 |  |  |  | 2025-09-10 10:00 | 2025-09-10 11:00 | 2025-09-10 12:00
21015 | STRIVE.R2.MC1.2384.1277.1.1232.235 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-LS_UN_SUB | 1 hrs | 2025-09-10 11:00 | 2025-09-10 12:00 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21013 |  |  |  | 2025-09-10 10:00 | 2025-09-10 11:00 | 2025-09-10 12:00
21016 | STRIVE.R2.MC1.2384.1277.1.1232.236 | N | N | N | Planned |  | R2P- EHS- LIST_SUB&LS_UN_SUB update via 3E content update | 1 hrs | 2025-09-10 12:01 | 2025-09-10 13:01 | Klaus | klaus.heitkamp@de.sasol.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21014,21015 |  |  |  | 2025-09-10 10:00 | 2025-09-10 12:01 | 2025-09-10 13:01
21017 | STRIVE.R2.MC1.2384.1277.1.1232.237 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-DG_CL_SUB | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21016 |  |  |  | 2025-09-10 10:00 | 2025-09-10 13:01 | 2025-09-10 14:01
21018 | STRIVE.R2.MC1.2384.1277.1.1232.238 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-Z_COMPANY | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21016 |  |  |  | 2025-09-10 10:00 | 2025-09-10 13:01 | 2025-09-10 14:01
21019 | STRIVE.R2.MC1.2384.1277.1.1232.239 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-Z_ER_INFO | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21016 |  |  |  | 2025-09-10 10:00 | 2025-09-10 13:01 | 2025-09-10 14:01
21020 | STRIVE.R2.MC1.2384.1277.1.1232.240 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-ZEXPORT | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21016 |  |  |  | 2025-09-10 10:00 | 2025-09-10 13:01 | 2025-09-10 14:01
20950 | STRIVE.R2.MC1.2384.1277.1.1232.170 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-ZHAND | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21016 |  |  |  | 2025-09-10 10:00 | 2025-09-10 13:01 | 2025-09-10 14:01
20951 | STRIVE.R2.MC1.2384.1277.1.1232.171 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-ZHAZ_IND | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21016 |  |  |  | 2025-09-10 10:00 | 2025-09-10 13:01 | 2025-09-10 14:01
20952 | STRIVE.R2.MC1.2384.1277.1.1232.172 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-ZKAPALLG-->ZGENERIC | 1 hrs | 2025-09-10 13:01 | 2025-09-10 14:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21016 |  |  |  | 2025-09-10 10:00 | 2025-09-10 13:01 | 2025-09-10 14:01
20953 | STRIVE.R2.MC1.2384.1277.1.1232.173 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-PURE_SUB | 1 hrs | 2025-09-10 14:01 | 2025-09-10 15:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 21017 |  |  |  | 2025-09-10 10:00 | 2025-09-10 14:01 | 2025-09-10 15:01
20954 | STRIVE.R2.MC1.2384.1277.1.1232.174 | N | N | N | Planned |  | R2P- EHS- Create Inheritance templates for PURE_SUB | 1 hrs | 2025-09-10 15:01 | 2025-09-10 16:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20953 |  |  |  | 2025-09-10 10:00 | 2025-09-10 15:01 | 2025-09-10 16:01
20955 | STRIVE.R2.MC1.2384.1277.1.1232.175 | N | N | N | Planned |  | R2P- EHS- Perform Inheritance Load for PURE_SUB | 1 hrs | 2025-09-10 16:01 | 2025-09-10 17:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20954 |  |  |  | 2025-08-25 11:00 | 2025-09-10 16:01 | 2025-09-10 17:01
20956 | STRIVE.R2.MC1.2384.1277.1.1232.176 | N | N | N | Planned |  | R2P- EHS- Execute Rule for PURE_SUB | 1 hrs | 2025-09-10 17:01 | 2025-09-10 18:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20955 |  |  |  | 2025-08-25 11:00 | 2025-09-10 17:01 | 2025-09-10 18:01
20957 | STRIVE.R2.MC1.2384.1277.1.1232.177 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-REAL_SUB | 1 hrs | 2025-09-10 18:01 | 2025-09-10 19:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20956 |  |  |  | 2025-08-25 11:00 | 2025-09-10 18:01 | 2025-09-10 19:01
20958 | STRIVE.R2.MC1.2384.1277.1.1232.178 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-REAL_SUB_E | 1 hrs | 2025-09-10 19:01 | 2025-09-10 20:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20957 |  |  |  | 2025-08-25 11:00 | 2025-09-10 19:01 | 2025-09-10 20:01
20959 | STRIVE.R2.MC1.2384.1277.1.1232.179 | N | N | N | Planned |  | R2P- EHS- Import Substance Specification-REAL_GRP | 1 hrs | 2025-09-10 19:01 | 2025-09-10 20:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20957 |  |  |  | 2025-08-25 11:00 | 2025-09-10 19:01 | 2025-09-10 20:01
20960 | STRIVE.R2.MC1.2384.1277.1.1232.180 | N | N | N | Planned |  | R2P- EHS- Create Inheritance templates for REAL_SUB | 1 hrs | 2025-09-10 20:01 | 2025-09-10 21:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20959 |  |  |  | 2025-08-25 11:00 | 2025-09-10 20:01 | 2025-09-10 21:01
20961 | STRIVE.R2.MC1.2384.1277.1.1232.181 | N | N | N | Planned |  | R2P- EHS- Inheritance Load for REAL_SUB | 1 hrs | 2025-09-10 21:01 | 2025-09-10 22:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20960 |  |  |  | 2025-08-25 11:00 | 2025-09-10 21:01 | 2025-09-10 22:01
20962 | STRIVE.R2.MC1.2384.1277.1.1232.182 | N | N | N | Planned |  | R2P- EHS- Execute Rule for REAL_SUB | 1 hrs | 2025-09-10 22:01 | 2025-09-10 23:01 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20961 |  |  |  | 2025-08-25 11:00 | 2025-09-10 22:01 | 2025-09-10 23:01
20963 | STRIVE.R2.MC1.2384.1277.1.1232.183 | N | N | N | Planned |  | R2P- EHS- Perform ZSS mapping for all Spec Types | 1 hrs | 2025-09-10 23:01 | 2025-09-11 00:03 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20962 |  |  |  | 2025-09-06 06:03 | 2025-09-10 23:01 | 2025-09-11 00:03
20964 | STRIVE.R2.MC1.2384.1277.1.1232.184 | N | N | N | Ready |  | R2P - EHS- Maintain S2S Setup- Opesus | 1 hrs | 2025-09-06 06:03 | 2025-09-06 07:03 | Claudia | claudia.valdes@opesus.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  |  |  |  | 2025-09-06 06:03 | 2025-09-06 06:03 | 2025-09-06 07:03
20965 | STRIVE.R2.MC1.2384.1277.1.1232.185 | N | N | N | Planned |  | R2P - EHS- Provide authorizations for OA2C Configurations- Opesus | 1 hrs | 2025-09-06 07:03 | 2025-09-06 08:04 | GRC | dttsasolsecuritygrcteam@deloitte.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20964 |  |  |  | 2025-09-06 06:03 | 2025-09-06 07:03 | 2025-09-06 08:04
20966 | STRIVE.R2.MC1.2384.1277.1.1232.186 | N | N | N | Planned |  | R2P - EHS- Maintain OA2C Configurations- Opesus | 1 hrs | 2025-09-06 08:04 | 2025-09-06 09:04 | Claudia | claudia.valdes@opesus.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20965 |  |  |  | 2025-09-06 06:03 | 2025-09-06 08:04 | 2025-09-06 09:04
20967 | STRIVE.R2.MC1.2384.1277.1.1232.187 | N | N | N | Planned |  | R2P - EHS- Grant OA2C Token to Users- Opesus | 1 hrs | 2025-09-06 09:04 | 2025-09-06 10:04 | Claudia | claudia.valdes@opesus.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20966 |  |  |  | 2025-09-06 06:03 | 2025-09-06 09:04 | 2025-09-06 10:04
20968 | STRIVE.R2.MC1.2384.1277.1.1232.188 | N | N | N | Planned |  | R2P - EHS- Check S2S Connection- Opesus | 1 hrs | 2025-09-06 10:04 | 2025-09-06 11:04 | Claudia | claudia.valdes@opesus.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20967 |  |  |  | 2025-09-06 06:03 | 2025-09-06 10:04 | 2025-09-06 11:04
20969 | STRIVE.R2.MC1.2384.1277.1.1232.189 | N | N | N | Planned |  | R2P - EHS- Define AL11 file path for Italian Portal,PDB | 1 hrs | 2025-09-06 11:04 | 2025-09-06 12:05 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Singhal; Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20968 |  |  |  | 2025-09-06 06:03 | 2025-09-06 11:04 | 2025-09-06 12:05
20970 | STRIVE.R2.MC1.2384.1277.1.1232.190 | N | N | N | Planned |  | R2P - EHS- Vendor SDS files upload in AL11 | 1 hrs | 2025-09-06 12:05 | 2025-09-06 13:05 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Shahid Sheikh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; smohdshahid@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 20969 |  |  |  | 2025-09-06 06:03 | 2025-09-06 12:05 | 2025-09-06 13:05
94450 | STRIVE.R2.MC1.2384.1277.1.1232.246 | Y | Y | Y | Complete |  | R2P- EHS - Provide list of external transport import to basis for the import | 0.07 hrs | 2025-09-02 12:29 | 2025-09-02 12:33 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-09-02 12:29 | 2025-09-02 12:33 |  | 2025-09-06 12:05 | 2025-09-02 12:29 | 2025-09-02 12:33
94451 | STRIVE.R2.MC1.2384.1277.1.1232.247 | Y | Y | Y | Complete |  | R2P -EHS- Basis Team to Import 2507 3E External Transports | 0 hrs | 2025-09-02 15:04 | 2025-09-02 15:04 | Basis | DeloitteSASOLBasisTeam@deloitte.com | Priyanka Singhal; Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | priyasinghal@deloitte.com; shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | Basis | 94450 | 2025-09-02 15:04 | 2025-09-02 15:04 |  | 2025-09-06 12:05 | 2025-09-02 15:04 | 2025-09-02 15:04
94452 | STRIVE.R2.MC1.2384.1277.1.1232.248 | Y | Y | Y | Complete |  | R2P- EHS- Verify migration of Regulatory Content TR | 0.38 hrs | 2025-09-02 15:19 | 2025-09-02 15:42 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P | 94451 | 2025-09-02 15:19 | 2025-09-02 15:42 |  | 2025-09-06 12:05 | 2025-09-02 15:19 | 2025-09-02 15:42
94447 | STRIVE.R2.MC1.2384.1277.1.1232.243 | Y | Y | Y | Complete |  | R2P- EHS- Upload files in AL11 for 2507 PS and DG phrase and phrase set including corrections | 3.17 hrs | 2025-09-02 12:46 | 2025-09-02 15:56 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-09-02 12:46 | 2025-09-02 15:56 |  | 2025-09-06 12:05 | 2025-09-02 12:46 | 2025-09-02 15:56
94448 | STRIVE.R2.MC1.2384.1277.1.1232.244 | Y | Y | Y | Complete |  | R2P- EHS- Merge 2507 PS and DG phrase to Cust library | 3.18 hrs | 2025-09-02 12:46 | 2025-09-02 15:56 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-09-02 12:46 | 2025-09-02 15:56 |  | 2025-09-06 12:05 | 2025-09-02 12:46 | 2025-09-02 15:56
94449 | STRIVE.R2.MC1.2384.1277.1.1232.245 | Y | Y | Y | Complete |  | R2P- EHS- Import 2507 PS and DG Phrase Set Assignment | 3.19 hrs | 2025-09-02 12:46 | 2025-09-02 15:57 | Priyanka Singhal | priyasinghal@deloitte.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  | 2025-09-02 12:46 | 2025-09-02 15:57 |  | 2025-09-06 12:05 | 2025-09-02 12:46 | 2025-09-02 15:57
94446 | STRIVE.R2.MC1.2384.1277.1.1232.242 | N | N | N | Ready |  | R2P-EHS- EPN 5.3 - External Transport Import - Opesus | 1 hrs | 2025-09-06 12:05 | 2025-09-06 13:05 | Claudia | claudia.valdes@opesus.com | Sheena Gour; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Alex Larionov; Harish Kristapati | shgour@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; allarionov@deloitte.de; hkristapati@deloitte.com | R2P |  |  |  |  | 2025-09-06 12:05 | 2025-09-06 12:05 | 2025-09-06 13:05
20265 | STRIVE.R2.MC1.2384.1277.1.1232.103 | Y | Y | Y | Complete |  | R2P-PP-Validate&Confirm R2P Team System Access | 9.5 hrs | 2025-08-25 11:00 | 2025-08-26 12:31 | Varsha Gupta | varshagupta7@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  | 2025-08-25 11:00 | 2025-08-26 12:31 | * | NA | 2025-08-25 11:00 | 2025-08-26 12:31
20266 | STRIVE.R2.MC1.2384.1277.1.1232.104 | Y | Y | Y | Complete |  | R2P-PP-Process Order Type Number Range | 0.15 hrs | 2025-08-20 08:00 | 2025-08-20 08:09 | Varsha Gupta | varshagupta7@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  | 2025-08-20 08:00 | 2025-08-20 08:09 | * | NA | 2025-08-20 08:00 | 2025-08-20 08:09
20267 | STRIVE.R2.MC1.2384.1277.1.1232.105 | Y | Y | Y | Complete |  | R2P-PP-Planned Order Number Range | 0.16 hrs | 2025-08-20 08:00 | 2025-08-20 08:09 | Varsha Gupta | varshagupta7@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  | 2025-08-20 08:00 | 2025-08-20 08:09 | * | NA | 2025-08-20 08:00 | 2025-08-20 08:09
20269 | STRIVE.R2.MC1.2384.1277.1.1232.107 | Y | Y | Y | Complete |  | R2P-PP-Validate MRP Schedule | 0 hrs | 2025-08-20 09:00 | 2025-08-20 09:00 | Varsha Gupta | varshagupta7@deloitte.com | Amit das; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amitdas3@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  | 2025-08-20 09:00 | 2025-08-20 09:00 | * | NA | 2025-08-20 09:00 | 2025-08-20 09:00
20270 | STRIVE.R2.MC1.2384.1277.1.1232.108 | Y | Y | Y | Complete |  | R2P-IM-TR configuration validation - Precutover | 0 hrs | 2025-08-19 13:03 | 2025-08-19 13:03 | Aniket Kulkarni | anikulkarni@deloitte.com | Masood Mohd Abdul; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mohmasood@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  | 2025-08-19 13:03 | 2025-08-19 13:03 |  | 2025-08-20 10:00 | 2025-08-19 13:03 | 2025-08-19 13:03
20271 | STRIVE.R2.MC1.2384.1277.1.1232.109 | Y | Y | Y | Complete |  | R2P-IM- Smoke Testing for IM Fiori Apps and T Codes | 0 hrs | 2025-08-28 16:19 | 2025-08-28 16:19 | Aniket Kulkarni | anikulkarni@deloitte.com | Masood Mohd Abdul; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mohmasood@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  | 2025-08-28 16:19 | 2025-08-28 16:19 |  | 2025-08-20 11:00 | 2025-08-28 16:19 | 2025-08-28 16:19
20308 | STRIVE.R2.MC1.2384.1277.1.884 | [5 empty] | MC1 Transport Import and Validation | 99.68 hrs | 2025-08-30 08:00 | 2025-09-03 11:57 | [8 empty] | * | NA | 2025-08-30 08:00 | 2025-09-03 11:57
20309 | STRIVE.R2.MC1.2384.1277.1.884.1 | N | N | N | Planned |  | MC 1 Transport Import and Validation - R2D | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Roshanlal | rohemwani@deloitte.com | Alexandra Ruff; ; Mousikta chanda; Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER | aruff@deloitte.de; ; mouchanda@deloitte.com; dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com | R2D |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20310 | STRIVE.R2.MC1.2384.1277.1.884.2 | N | N | N | Planned |  | MC 1 Transport Import and Validation - R2P | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Amit das | amitdas3@deloitte.com | Claudiu; Nilesh Deshpande; Mousikta chanda; Pamela Mihali; Abhishek Parab; Sheena Gour; Deepika Agarwal; Shivani Kulkarni; Aniket Kulkarni; Dhruv Kansal; USI STRIVE CUTOVER; Jay Saini | cljipa@deloitte.de; nideshpande@deloitte.com; mouchanda@deloitte.com; pamihali@deloitte.de; abhparab@deloitte.com; shgour@deloitte.com; deepikaagarwal@deloitte.de; shivankulkarni@deloitte.com; anikulkarni@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaysaini4@deloitte.com | R2P |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20311 | STRIVE.R2.MC1.2384.1277.1.884.3 | N | N | N | Planned |  | MC 1 Transport Import and Validation - S2P | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Prasanth | kalprasanth@deloitte.com | Aparajita Mukherjee; Mousikta chanda; Milton; Sandeep Galhotra; Dhruv Kansal; USI STRIVE CUTOVER; S2P Team | apamukherjee@deloitte.com; mouchanda@deloitte.com; miltjones@deloitte.com; sagalhotra@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20312 | STRIVE.R2.MC1.2384.1277.1.884.4 | N | N | N | Planned |  | MC 1 Transport Import and Validation - P2C | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Shubham Mishra | spratapmishra@deloitte.com | Malta; Diego Zarate; Valentijn; Ramesh SathishKumar; Tripti mehta; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | mawilhelm@deloitte.de; dzarate@deloitte.com; vvandriessen@deloitte.com; satramesh@deloitte.com; trimehta@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20313 | STRIVE.R2.MC1.2384.1277.1.884.5 | N | N | N | Planned |  | MC 1 Transport Import and Validation - MOR PS | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Mythili | myboyapati@deloitte.com | Jay Patel; Nikhil Gupta; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Amit Jha; Vinod; Krishna Teja | jaypatel6@deloitte.com; mrgupta3@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ajha2@deloitte.no; vinodkumar692@deloitte.com; krishn@deloitte.com | MOR |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20314 | STRIVE.R2.MC1.2384.1277.1.884.6 | N | N | N | Planned |  | MC 1 Transport Import and Validation - MDG | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tushar; Amol Paswan; Tulika Pal; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | tamrutkar@deloitte.de; ampaswan@deloitte.com; tupal@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | MDG |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20315 | STRIVE.R2.MC1.2384.1277.1.884.7 | N | N | N | Planned |  | MC 1 Transport Import and Validation - ABAP | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Gurmandeep Singh | gurmandsingh@deloitte.com | Shivraj; Ashish patil; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Satish rahangadale | shivrsinha@deloitte.com; ashishspatil@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20316 | STRIVE.R2.MC1.2384.1277.1.884.8 | N | N | N | Planned |  | Update Email Template for Flexible workflows | 4 hrs | 2025-09-20 12:01 | 2025-09-20 16:01 | Ashish patil | ashishspatil@deloitte.com | Gurmandeep Singh; Shivraj; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Satish rahangadale | gurmandsingh@deloitte.com; shivrsinha@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; srahangdale@deloitte.com | ABAP | 20315 |  |  |  | 2025-09-20 08:00 | 2025-09-20 12:01 | 2025-09-20 16:01
20317 | STRIVE.R2.MC1.2384.1277.1.884.9 | N | N | N | Planned |  | MC 1 Transport Import and Validation - GRC/Security | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Somitra | sothapa@deloitte.com | Quinten Broeckx ; Naman; Mousikta chanda; Jayasurya; Ankush; Dhruv Kansal; USI STRIVE CUTOVER | qbroeckx@deloitte.be; njaswani@deloitte.com; mouchanda@deloitte.com; jayasur@deloitte.com; amisri@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | GRC |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20318 | STRIVE.R2.MC1.2384.1277.1.884.10 | N | N | N | Planned |  | MC 1 Transport Import and Validation - DM | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Alex Miles | almiles@deloitte.de | Satyajit Patnaik; Savri Sumeet Jagatap; Roman Mäkilä; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Rushikesh Mahendrakar | sapatnaik@deloitte.com; ssumeetjagatap@deloitte.com; roman.makila@deloitte.fi; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rumahendrakar@deloitte.com | DM |  |  |  |  | 2025-09-20 08:00 | 2025-09-20 08:00 | 2025-09-20 12:00
20319 | STRIVE.R2.MC1.2384.1277.1.884.11 | N | N | N | Planned |  | Variant creation for VAT register report | 4 hrs | 2025-09-20 12:01 | 2025-09-20 16:01 | Aquib Iqbal | aquiqbal@deloitte.com | Roshanlal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Tatiana | rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de | R2D | 20309 |  |  |  | 2025-09-20 08:00 | 2025-09-20 12:01 | 2025-09-20 16:01
20320 | STRIVE.R2.MC1.2384.1277.1.896 | [5 empty] | Integration | 3832.63 hrs | 2025-09-05 08:00 | 2026-02-12 11:18 | [8 empty] | * | NA | 2025-09-05 08:00 | 2026-02-12 11:18
20321 | STRIVE.R2.MC1.2384.1277.1.896.1 | [5 empty] | Interface Activation | 3644.06 hrs | 2025-09-05 08:00 | 2026-02-04 14:13 | [8 empty] | * | NA | 2025-09-05 08:00 | 2026-02-04 14:13
20322 | STRIVE.R2.MC1.2384.1277.1.896.1.1 | [5 empty] | S/4HANA-COUPA (Placeholder for Wave 1 Interfaces) | 2349.32 hrs | 2025-09-05 08:00 | 2025-12-12 11:51 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-12-12 11:51
20325 | STRIVE.R2.MC1.2384.1277.1.896.1.1.3 | [5 empty] | S2P_I_045-Integration of PIR from Coupa to S4 | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20326 | STRIVE.R2.MC1.2384.1277.1.896.1.1.3.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation -S2P_I_045 to activate | 1 hrs | 2025-09-15 13:01 | 2025-09-15 14:01 | Pournami Nair | pounair@deloitte.com | Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19017 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
20327 | STRIVE.R2.MC1.2384.1277.1.896.1.1.3.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_045 | 1 hrs | 2025-09-15 14:01 | 2025-09-15 15:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20326 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
20328 | STRIVE.R2.MC1.2384.1277.1.896.1.1.3.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_045 | 1 hrs | 2025-09-15 15:01 | 2025-09-15 16:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20327 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
20329 | STRIVE.R2.MC1.2384.1277.1.896.1.1.7 | [5 empty] | S2P_I_046_Integration of Invoices from S4 to Coupa (ERS Invoice) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20330 | STRIVE.R2.MC1.2384.1277.1.896.1.1.7.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_046 | 1 hrs | 2025-09-15 13:01 | 2025-09-15 14:01 | Pournami Nair | pounair@deloitte.com | Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19023 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
20331 | STRIVE.R2.MC1.2384.1277.1.896.1.1.7.2 | N | N | N | Planned |  | Deploy the Iflow in CPI (Schedule the interface to run daily at 12PM) - S2P_I_046 | 1 hrs | 2025-09-15 14:01 | 2025-09-15 15:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20330 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
20332 | STRIVE.R2.MC1.2384.1277.1.896.1.1.7.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_046 | 1 hrs | 2025-09-15 15:01 | 2025-09-15 16:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20331 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
20333 | STRIVE.R2.MC1.2384.1277.1.896.1.1.11 | [5 empty] | S2P_I_047_Quantity Contract Interface for PR | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | [5 empty] | 20341 |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20334 | STRIVE.R2.MC1.2384.1277.1.896.1.1.11.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_047 | 1 hrs | 2025-09-15 13:01 | 2025-09-15 14:01 | Pournami Nair | pounair@deloitte.com | Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19029 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
20335 | STRIVE.R2.MC1.2384.1277.1.896.1.1.11.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_047 | 1 hrs | 2025-09-15 14:01 | 2025-09-15 15:01 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20334 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
20336 | STRIVE.R2.MC1.2384.1277.1.896.1.1.11.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_047 | 1 hrs | 2025-09-15 15:01 | 2025-09-15 16:01 | Naga reddy | nnagasubbareddy@deloitte.com | ; Yashwanth; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; myakumar@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20335 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
20337 | STRIVE.R2.MC1.2384.1277.1.896.1.1.15 | [5 empty] | S2P_I_048_Quantity Contract Interface for PO | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | [5 empty] | 20341 |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20338 | STRIVE.R2.MC1.2384.1277.1.896.1.1.15.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_048 | 1 hrs | 2025-09-15 13:01 | 2025-09-15 14:01 | Pournami Nair | pounair@deloitte.com | Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19035 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
20339 | STRIVE.R2.MC1.2384.1277.1.896.1.1.15.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_048 | 1 hrs | 2025-09-15 14:01 | 2025-09-15 15:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; ; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; ; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20338 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
20340 | STRIVE.R2.MC1.2384.1277.1.896.1.1.15.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_048 | 1 hrs | 2025-09-15 15:01 | 2025-09-15 16:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Naga reddy; ; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; ; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20339 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
20341 | STRIVE.R2.MC1.2384.1277.1.896.1.1.19 | [5 empty] | S2P_I_049-PO Closure automation | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20342 | STRIVE.R2.MC1.2384.1277.1.896.1.1.19.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_049 | 1 hrs | 2025-09-15 13:01 | 2025-09-15 14:01 | Pournami Nair | pounair@deloitte.com | Aparajita Mukherjee; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | apamukherjee@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19041 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
20343 | STRIVE.R2.MC1.2384.1277.1.896.1.1.19.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_049 | 1 hrs | 2025-09-15 14:01 | 2025-09-15 15:01 | Naga reddy | nnagasubbareddy@deloitte.com | ; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20342 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
20344 | STRIVE.R2.MC1.2384.1277.1.896.1.1.19.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_049 | 1 hrs | 2025-09-15 15:01 | 2025-09-15 16:01 | Naga reddy | nnagasubbareddy@deloitte.com | ; Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20343 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
20345 | STRIVE.R2.MC1.2384.1277.1.896.1.1.23 | [5 empty] | S2P_I_050-Supplier Interface Coupa to MDG redesign (Part of CR059) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20346 | STRIVE.R2.MC1.2384.1277.1.896.1.1.23.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_050 | 1 hrs | 2025-09-15 13:01 | 2025-09-15 14:01 | Pournami | pounair@deloitte.com | Pournami Nair; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rabbani; S2P Team | pounair@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; skhadarmohammadra@deloitte.com; usisasols2p@deloitte.com | S2P | 19047 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
20347 | STRIVE.R2.MC1.2384.1277.1.896.1.1.23.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_050 | 1 hrs | 2025-09-15 14:01 | 2025-09-15 15:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20346 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
20348 | STRIVE.R2.MC1.2384.1277.1.896.1.1.23.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_050 | 1 hrs | 2025-09-15 15:01 | 2025-09-15 16:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20347 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
20349 | STRIVE.R2.MC1.2384.1277.1.896.1.1.27 | [5 empty] | S2P_I_057-Integrate Ok2Pay file from Coupa to S4 (Non PO Invoice, PO Invoice, Credit Memos) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20350 | STRIVE.R2.MC1.2384.1277.1.896.1.1.27.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_057 | 1 hrs | 2025-09-15 13:01 | 2025-09-15 14:01 | Rabbani | skhadarmohammadra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pournami; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com | S2P | 19053 |  |  | * | NA | 2025-09-15 13:01 | 2025-09-15 14:01
20351 | STRIVE.R2.MC1.2384.1277.1.896.1.1.27.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_057 | 1 hrs | 2025-09-15 14:01 | 2025-09-15 15:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20350 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 15:01
20352 | STRIVE.R2.MC1.2384.1277.1.896.1.1.27.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_057 | 1 hrs | 2025-09-15 15:01 | 2025-09-15 16:01 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20351 |  |  | * | NA | 2025-09-15 15:01 | 2025-09-15 16:01
20353 | STRIVE.R2.MC1.2384.1277.1.896.1.1.31 | [5 empty] | S2P_I_022-Work Orders Created in S4 to Coupa | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20354 | STRIVE.R2.MC1.2384.1277.1.896.1.1.31.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_022 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pournami; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20355 | STRIVE.R2.MC1.2384.1277.1.896.1.1.31.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_022 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Vara Sai Prasad Pullabhotla | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; vpullabhotla@deloitte.com | Integration | 20354 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20356 | STRIVE.R2.MC1.2384.1277.1.896.1.1.31.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_022 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Vara Sai Prasad Pullabhotla | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; vpullabhotla@deloitte.com | Integration | 20355 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20357 | STRIVE.R2.MC1.2384.1277.1.896.1.1.35 | [5 empty] | S2P_I_023-Integrate Payment status from S/4 to Coupa in case of Payment processed successfully and payment reversals scenarios | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20358 | STRIVE.R2.MC1.2384.1277.1.896.1.1.35.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_023 to activate on 1st April 9:15 AM CET | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pournami; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20359 | STRIVE.R2.MC1.2384.1277.1.896.1.1.35.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_023 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Pragyesh Kumar | pkumargoyal@deloitte.com | Saurabh Kumar; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | saurabhkumar397@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20358 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20360 | STRIVE.R2.MC1.2384.1277.1.896.1.1.35.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_023 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Pragyesh Kumar | pkumargoyal@deloitte.com | Saurabh Kumar; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | saurabhkumar397@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20359 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20361 | STRIVE.R2.MC1.2384.1277.1.896.1.1.39 | [5 empty] | S2P_I_024 - Integration of Receipt from SAP S4 HANA to Coupa | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20362 | STRIVE.R2.MC1.2384.1277.1.896.1.1.39.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_024 to activate on 1st April 8:30 AM CET | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pournami; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20363 | STRIVE.R2.MC1.2384.1277.1.896.1.1.39.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_024 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 20362 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20364 | STRIVE.R2.MC1.2384.1277.1.896.1.1.39.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_024 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Saurabh Kumar; Naga; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | saurabhkumar397@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Integration | 20363 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20365 | STRIVE.R2.MC1.2384.1277.1.896.1.1.43 | [5 empty] | S2P_I_025 - Integration of Receipt from Coupa to S4 | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20366 | STRIVE.R2.MC1.2384.1277.1.896.1.1.43.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_025 to activate on 1st April 8:30 AM CET | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pournami; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20367 | STRIVE.R2.MC1.2384.1277.1.896.1.1.43.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_025 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Naga | saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nnagasubbareddy@deloitte.com | Integration | 20366 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20368 | STRIVE.R2.MC1.2384.1277.1.896.1.1.43.3 | N | N | N | Planned |  | Validate, if interface is activated - S2P_I_025 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Aman Anand | amananand2@deloitte.com | Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Naga | saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; nnagasubbareddy@deloitte.com | Integration | 20367 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20369 | STRIVE.R2.MC1.2384.1277.1.896.1.1.47 |  |  |  |  | Delete | S2P_I_035-Integration of Exchange Rates from S4 to Coupa | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20370 | STRIVE.R2.MC1.2384.1277.1.896.1.1.47.1 | N | N | N | Planned | Delete | Provide confirmation to the integration team for interface activation - S2P_I_035 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pournami; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20371 | STRIVE.R2.MC1.2384.1277.1.896.1.1.47.2 | N | N | N | Planned | Delete | Deploy the Iflow in CPI - S2P_I_035 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 20370 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20372 | STRIVE.R2.MC1.2384.1277.1.896.1.1.47.3 | N | N | N | Planned | Delete | Validate, if interface is activated - S2P_I_035 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | Integration | 20371 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20373 | STRIVE.R2.MC1.2384.1277.1.896.1.1.51 | [5 empty] | S2P_I_043_Integration of POs from S4 to Coupa | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20374 | STRIVE.R2.MC1.2384.1277.1.896.1.1.51.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - S2P_I_043 to activate on 1st April 10:00 AM CET | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Pournami; S2P Team | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; pounair@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20375 | STRIVE.R2.MC1.2384.1277.1.896.1.1.51.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - S2P_I_043 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Saurabh Kumar; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; saurabhkumar397@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20374 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20376 | STRIVE.R2.MC1.2384.1277.1.896.1.1.51.3 | N | N | N | Planned |  | Validate, if interface is activated -S2P_I_043 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Pragyesh | pkumargoyal@deloitte.com | Naga reddy; Yashwanth; Saurabh Kumar; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; myakumar@deloitte.com; saurabhkumar397@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20375 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20402 | STRIVE.R2.MC1.2384.1277.1.896.1.81 | [5 empty] | R2P Interfaces Wave 1 | 244.8 hrs | 2025-09-15 08:00 | 2025-09-25 13:29 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-25 13:29
94912 | STRIVE.R2.MC1.2384.1277.1.896.1.81.37 | [5 empty] | R2P_I_050-EHS:Transit Interface (MARL)- Includes Dangerous Goods | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94913 | STRIVE.R2.MC1.2384.1277.1.896.1.81.37.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_050 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94911 | STRIVE.R2.MC1.2384.1277.1.896.1.81.37.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_050 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94913 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94910 | STRIVE.R2.MC1.2384.1277.1.896.1.81.37.3 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_050 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94911 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21062 | STRIVE.R2.MC1.2384.1277.1.896.1.81.17 | [5 empty] | R2P_I_071 - EHS - TDS Interface to ProductDatabase | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21063 | STRIVE.R2.MC1.2384.1277.1.896.1.81.17.37 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_071 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21094 | STRIVE.R2.MC1.2384.1277.1.896.1.81.17.68 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_071 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21063 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21095 | STRIVE.R2.MC1.2384.1277.1.896.1.81.17.69 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_071 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21094 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21096 | STRIVE.R2.MC1.2384.1277.1.896.1.81.18 | [5 empty] | R2P_I_060 -EHS- Opesus (PCN) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21097 | STRIVE.R2.MC1.2384.1277.1.896.1.81.18.71 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_060 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21098 | STRIVE.R2.MC1.2384.1277.1.896.1.81.18.72 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_060 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21097 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21099 | STRIVE.R2.MC1.2384.1277.1.896.1.81.18.73 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_060 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21098 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94922 | STRIVE.R2.MC1.2384.1277.1.896.1.81.39 | [5 empty] | R2P_I_062-LIMS 1 : Samplemanager (Brunsbüttel) - Outbound inventory update | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94923 | STRIVE.R2.MC1.2384.1277.1.896.1.81.39.82 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_062 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94924 | STRIVE.R2.MC1.2384.1277.1.896.1.81.39.83 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_062 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94923 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94925 | STRIVE.R2.MC1.2384.1277.1.896.1.81.39.84 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_062 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94924 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94926 | STRIVE.R2.MC1.2384.1277.1.896.1.81.40 | [5 empty] | R2P_I_063-LIMS 1 : Samplemanager (Brunsbüttel) - Inbound process order details | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94927 | STRIVE.R2.MC1.2384.1277.1.896.1.81.40.86 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_063 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94928 | STRIVE.R2.MC1.2384.1277.1.896.1.81.40.87 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_063 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94927 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94929 | STRIVE.R2.MC1.2384.1277.1.896.1.81.40.88 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_063 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94928 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94918 | STRIVE.R2.MC1.2384.1277.1.896.1.81.41 | [5 empty] | R2P_I_071-SAP EHS- TDS Interface to ProductDatabse -Digital | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94919 | STRIVE.R2.MC1.2384.1277.1.896.1.81.41.78 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_071 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94920 | STRIVE.R2.MC1.2384.1277.1.896.1.81.41.79 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_071 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94919 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94921 | STRIVE.R2.MC1.2384.1277.1.896.1.81.41.80 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_071 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94920 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21100 | STRIVE.R2.MC1.2384.1277.1.896.1.81.19 | [5 empty] | R2P_I_072 -EHS - Interface to EasyTra | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21101 | STRIVE.R2.MC1.2384.1277.1.896.1.81.19.75 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_072 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21102 | STRIVE.R2.MC1.2384.1277.1.896.1.81.19.76 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_072 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21101 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21103 | STRIVE.R2.MC1.2384.1277.1.896.1.81.19.77 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_072 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21102 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21104 | STRIVE.R2.MC1.2384.1277.1.896.1.81.20 | [5 empty] | R2P_I_052 -EHS- Transfer of Phrases to Evonik | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21105 | STRIVE.R2.MC1.2384.1277.1.896.1.81.20.79 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_052 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21106 | STRIVE.R2.MC1.2384.1277.1.896.1.81.20.80 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_052 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21105 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21107 | STRIVE.R2.MC1.2384.1277.1.896.1.81.20.81 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_052 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21106 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21108 | STRIVE.R2.MC1.2384.1277.1.896.1.81.21 | [5 empty] | R2P_I_051 -EHS- EH&S data to Ebsoft at Evonik | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21109 | STRIVE.R2.MC1.2384.1277.1.896.1.81.21.83 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_051 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Sheena Gour | shgour@deloitte.com | Priyanka Singhal; Nilesh Deshpande; Jay Saini; Deepika Agarwal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | priyasinghal@deloitte.com; nideshpande@deloitte.com; jaysaini4@deloitte.com; deepikaagarwal@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21110 | STRIVE.R2.MC1.2384.1277.1.896.1.81.21.84 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_051 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21109 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21111 | STRIVE.R2.MC1.2384.1277.1.896.1.81.21.85 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_051 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21110 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21112 | STRIVE.R2.MC1.2384.1277.1.896.1.81.22 | [5 empty] | R2P_I_056 -IM_KRUSE high storage warehouse - Inbound - STOs | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21113 | STRIVE.R2.MC1.2384.1277.1.896.1.81.22.87 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_056 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aniket Kulkarni | anikulkarni@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21114 | STRIVE.R2.MC1.2384.1277.1.896.1.81.22.88 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_056 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21113 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21115 | STRIVE.R2.MC1.2384.1277.1.896.1.81.22.89 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_056 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21114 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21116 | STRIVE.R2.MC1.2384.1277.1.896.1.81.23 | [5 empty] | R2P_I_057 -IM_KRUSE high storage warehouse - Inbound - Deliveries | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21117 | STRIVE.R2.MC1.2384.1277.1.896.1.81.23.91 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_057 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aniket Kulkarni | anikulkarni@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21118 | STRIVE.R2.MC1.2384.1277.1.896.1.81.23.92 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_057 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21117 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21119 | STRIVE.R2.MC1.2384.1277.1.896.1.81.23.93 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_057 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21118 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21120 | STRIVE.R2.MC1.2384.1277.1.896.1.81.24 | [5 empty] | R2P_I_059 -IM_KRUSE high storage warehouse - Inbound - Repack | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21121 | STRIVE.R2.MC1.2384.1277.1.896.1.81.24.95 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_059 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aniket Kulkarni | anikulkarni@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21122 | STRIVE.R2.MC1.2384.1277.1.896.1.81.24.96 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_059 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21121 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21123 | STRIVE.R2.MC1.2384.1277.1.896.1.81.24.97 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_059 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21122 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21128 | STRIVE.R2.MC1.2384.1277.1.896.1.81.26 | [5 empty] | R2P_I_061 - QM Analytical equipment (Gas Chromatographe) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21129 | STRIVE.R2.MC1.2384.1277.1.896.1.81.26.103 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_061 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal; Aniket Kulkarni | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de; anikulkarni@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21130 | STRIVE.R2.MC1.2384.1277.1.896.1.81.26.104 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_061 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21129 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21131 | STRIVE.R2.MC1.2384.1277.1.896.1.81.26.105 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_061 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21130 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21132 | STRIVE.R2.MC1.2384.1277.1.896.1.81.27 | [5 empty] | R2P_I_064 -DIGITAL: OMA (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21133 | STRIVE.R2.MC1.2384.1277.1.896.1.81.27.107 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_064 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21134 | STRIVE.R2.MC1.2384.1277.1.896.1.81.27.108 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_064 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21133 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21135 | STRIVE.R2.MC1.2384.1277.1.896.1.81.27.109 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_064 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21134 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21136 | STRIVE.R2.MC1.2384.1277.1.896.1.81.28 | [5 empty] | R2P_I_073 -DIGITAL: OMA (Intbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21137 | STRIVE.R2.MC1.2384.1277.1.896.1.81.28.111 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_073 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21138 | STRIVE.R2.MC1.2384.1277.1.896.1.81.28.112 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_073 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21137 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21139 | STRIVE.R2.MC1.2384.1277.1.896.1.81.28.113 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_073 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21138 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21140 | STRIVE.R2.MC1.2384.1277.1.896.1.81.29 | [5 empty] | R2P_I_066 - S/4 HANA to LISA outbound interface | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21141 | STRIVE.R2.MC1.2384.1277.1.896.1.81.29.115 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_066 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21142 | STRIVE.R2.MC1.2384.1277.1.896.1.81.29.116 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_066 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21141 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21143 | STRIVE.R2.MC1.2384.1277.1.896.1.81.29.117 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_066 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21142 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21144 | STRIVE.R2.MC1.2384.1277.1.896.1.81.30 | [5 empty] | R2P_I_067 - S/4 HANA to LISA Inbound GI interface | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21145 | STRIVE.R2.MC1.2384.1277.1.896.1.81.30.119 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_067 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21146 | STRIVE.R2.MC1.2384.1277.1.896.1.81.30.120 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_067 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21145 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21147 | STRIVE.R2.MC1.2384.1277.1.896.1.81.30.121 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_067 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21146 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21148 | STRIVE.R2.MC1.2384.1277.1.896.1.81.31 | [5 empty] | R2P_I_068 - S/4 HANA to LISA Inbound GR interface | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21149 | STRIVE.R2.MC1.2384.1277.1.896.1.81.31.123 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_068 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21150 | STRIVE.R2.MC1.2384.1277.1.896.1.81.31.124 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_068 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21149 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21151 | STRIVE.R2.MC1.2384.1277.1.896.1.81.31.125 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_068 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21150 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21152 | STRIVE.R2.MC1.2384.1277.1.896.1.81.32 | [5 empty] | R2P_I_069 - IP21 Tank level interface | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21153 | STRIVE.R2.MC1.2384.1277.1.896.1.81.32.127 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_069 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aniket Kulkarni | anikulkarni@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21154 | STRIVE.R2.MC1.2384.1277.1.896.1.81.32.128 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_069 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21153 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21155 | STRIVE.R2.MC1.2384.1277.1.896.1.81.32.129 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_069 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21154 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21064 | STRIVE.R2.MC1.2384.1277.1.896.1.81.33 | [5 empty] | R2P_I_070 - SAAB Tank level interface | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21065 | STRIVE.R2.MC1.2384.1277.1.896.1.81.33.39 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_070 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Aniket Kulkarni | anikulkarni@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21066 | STRIVE.R2.MC1.2384.1277.1.896.1.81.33.40 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_070 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21065 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21067 | STRIVE.R2.MC1.2384.1277.1.896.1.81.33.41 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_070 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21066 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
21068 | STRIVE.R2.MC1.2384.1277.1.896.1.81.34 | [5 empty] | R2P_I_074 - LISA(MES) Material Master outbound Interface | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
21069 | STRIVE.R2.MC1.2384.1277.1.896.1.81.34.43 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_074 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
21070 | STRIVE.R2.MC1.2384.1277.1.896.1.81.34.44 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_074 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21069 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
21071 | STRIVE.R2.MC1.2384.1277.1.896.1.81.34.45 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_074 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 21070 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94939 | STRIVE.R2.MC1.2384.1277.1.896.1.81.42 | [5 empty] | R2P_I_076-Kruse Material Master data interface from S4 to KRUSE | 42 hrs | 2025-09-15 08:00 | 2025-09-17 02:07 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 02:07
94940 | STRIVE.R2.MC1.2384.1277.1.896.1.81.42.55 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_076 | 14 hrs | 2025-09-15 08:00 | 2025-09-15 22:01 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94941 | STRIVE.R2.MC1.2384.1277.1.896.1.81.42.56 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_076 | 14 hrs | 2025-09-15 22:01 | 2025-09-16 12:05 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94940 |  |  | * | NA | 2025-09-15 22:01 | 2025-09-16 12:05
94942 | STRIVE.R2.MC1.2384.1277.1.896.1.81.42.57 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_076 | 14 hrs | 2025-09-16 12:05 | 2025-09-17 02:07 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94941 |  |  | * | NA | 2025-09-16 12:05 | 2025-09-17 02:07
94943 | STRIVE.R2.MC1.2384.1277.1.896.1.81.43 | [5 empty] | R2P_I_077-Relabeling, Repackaging, Refilling Outbound Process Order Interface from S4 to Kruse | 42 hrs | 2025-09-15 08:00 | 2025-09-17 02:07 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 02:07
94944 | STRIVE.R2.MC1.2384.1277.1.896.1.81.43.59 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_077 | 14 hrs | 2025-09-15 08:00 | 2025-09-15 22:01 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94945 | STRIVE.R2.MC1.2384.1277.1.896.1.81.43.60 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_077 | 14 hrs | 2025-09-15 22:01 | 2025-09-16 12:05 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94944 |  |  | * | NA | 2025-09-15 22:01 | 2025-09-16 12:05
94934 | STRIVE.R2.MC1.2384.1277.1.896.1.81.43.49 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_077 | 14 hrs | 2025-09-16 12:05 | 2025-09-17 02:07 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94945 |  |  | * | NA | 2025-09-16 12:05 | 2025-09-17 02:07
94935 | STRIVE.R2.MC1.2384.1277.1.896.1.81.44 | [5 empty] | R2P_I_078-GR, GI, Confirm Process Order Inbound Interface from Kruse | 42 hrs | 2025-09-15 08:00 | 2025-09-17 02:07 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 02:07
94936 | STRIVE.R2.MC1.2384.1277.1.896.1.81.44.51 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_078 | 14 hrs | 2025-09-15 08:00 | 2025-09-15 22:01 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94937 | STRIVE.R2.MC1.2384.1277.1.896.1.81.44.52 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_078 | 14 hrs | 2025-09-15 22:01 | 2025-09-16 12:05 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94936 |  |  | * | NA | 2025-09-15 22:01 | 2025-09-16 12:05
94932 | STRIVE.R2.MC1.2384.1277.1.896.1.81.44.47 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_078 | 14 hrs | 2025-09-16 12:05 | 2025-09-17 02:07 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94937 |  |  | * | NA | 2025-09-16 12:05 | 2025-09-17 02:07
94933 | STRIVE.R2.MC1.2384.1277.1.896.1.81.45 | [5 empty] | R2P_I_XXX-Kruse Spares handling in BBT warehouse through HU's | 42 hrs | 2025-09-15 08:00 | 2025-09-17 02:07 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-17 02:07
94931 | STRIVE.R2.MC1.2384.1277.1.896.1.81.45.46 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2P_I_XXX | 14 hrs | 2025-09-15 08:00 | 2025-09-15 22:01 | Jay Saini | jaysaini4@deloitte.com | Nilesh Deshpande; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deepika Agarwal | nideshpande@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; deepikaagarwal@deloitte.de | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 22:01
94947 | STRIVE.R2.MC1.2384.1277.1.896.1.81.45.62 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2P_I_XXX | 14 hrs | 2025-09-15 22:01 | 2025-09-16 12:05 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94931 |  |  | * | NA | 2025-09-15 22:01 | 2025-09-16 12:05
94946 | STRIVE.R2.MC1.2384.1277.1.896.1.81.45.61 | N | N | N | Planned |  | Validate, if interface is activated - R2P_I_XXX | 14 hrs | 2025-09-16 12:05 | 2025-09-17 02:07 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yaswanth; Naga; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94947 |  |  | * | NA | 2025-09-16 12:05 | 2025-09-17 02:07
20419 | STRIVE.R2.MC1.2384.1277.1.896.1.98 | [5 empty] | S/4HANA-Shift Connector (Placeholder for Wave 1 Interfaces) | 1152.23 hrs | 2025-09-15 08:00 | 2025-11-02 11:26 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-11-02 11:26
20420 | STRIVE.R2.MC1.2384.1277.1.896.1.98.1 | [5 empty] | MOR_I_013-Shift-connector Equipment (outbound) | 456.17 hrs | 2025-09-15 08:00 | 2025-10-04 09:26 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-04 09:26
20421 | STRIVE.R2.MC1.2384.1277.1.896.1.98.1.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - Shift Connector - MOR_I_013 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Dhruv Kansal | jaypatel6@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20422 | STRIVE.R2.MC1.2384.1277.1.896.1.98.1.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - Shift Connector - MOR_I_013 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20421 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20423 | STRIVE.R2.MC1.2384.1277.1.896.1.98.1.3 | N | N | N | Planned |  | Validate, if interface is activated - Shift Connector - MOR_I_013 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20422 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20424 | STRIVE.R2.MC1.2384.1277.1.896.1.98.5 | [5 empty] | MOR_I_014-Shift-connector Functional location (outbound) | 1152.23 hrs | 2025-09-15 08:00 | 2025-11-02 11:26 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-11-02 11:26
20425 | STRIVE.R2.MC1.2384.1277.1.896.1.98.5.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - MOR_I_014 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Dhruv Kansal | jaypatel6@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20426 | STRIVE.R2.MC1.2384.1277.1.896.1.98.5.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - MOR_I_014 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20425 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20427 | STRIVE.R2.MC1.2384.1277.1.896.1.98.5.3 | N | N | N | Planned |  | Validate, if interface is activated - MOR_I_014 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20426 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94964 | STRIVE.R2.MC1.2384.1277.1.896.1.98.9 | [5 empty] | MOR_I_016-Shift-connector notifications create/update (outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94965 | STRIVE.R2.MC1.2384.1277.1.896.1.98.9.21 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - Shift Connector - MOR_I_016 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Dhruv Kansal | jaypatel6@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94966 | STRIVE.R2.MC1.2384.1277.1.896.1.98.9.22 | N | N | N | Planned |  | Deploy the Iflow in CPI - Shift Connector - MOR_I_016 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94965 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94967 | STRIVE.R2.MC1.2384.1277.1.896.1.98.9.23 | N | N | N | Planned |  | Validate, if interface is activated - Shift Connector - MOR_I_016 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94966 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94968 | STRIVE.R2.MC1.2384.1277.1.896.1.98.10 | [5 empty] | MOR_I_015-Shift-connector notifications update (inbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94969 | STRIVE.R2.MC1.2384.1277.1.896.1.98.10.25 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - MOR_I_015 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Dhruv Kansal | jaypatel6@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94970 | STRIVE.R2.MC1.2384.1277.1.896.1.98.10.26 | N | N | N | Planned |  | Deploy the Iflow in CPI - MOR_I_015 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94969 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94971 | STRIVE.R2.MC1.2384.1277.1.896.1.98.10.27 | N | N | N | Planned |  | Validate, if interface is activated - MOR_I_015 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94970 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94972 | STRIVE.R2.MC1.2384.1277.1.896.1.98.11 | [5 empty] | MOR_I_017-COMOS interface - 1 | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94973 | STRIVE.R2.MC1.2384.1277.1.896.1.98.11.29 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - Shift Connector - MOR_I_017 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Dhruv Kansal | jaypatel6@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94980 | STRIVE.R2.MC1.2384.1277.1.896.1.98.11.36 | N | N | N | Planned |  | Deploy the Iflow in CPI - Shift Connector - MOR_I_017 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94973 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94981 | STRIVE.R2.MC1.2384.1277.1.896.1.98.11.37 | N | N | N | Planned |  | Validate, if interface is activated - Shift Connector - MOR_I_017 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94980 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94982 | STRIVE.R2.MC1.2384.1277.1.896.1.98.12 | [5 empty] | MOR_I_018-COMOS interface - 2 | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94983 | STRIVE.R2.MC1.2384.1277.1.896.1.98.12.39 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - MOR_I_018 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Vinod Kumar | vinodkumar692@deloitte.com | Jay Patel; USI STRIVE CUTOVER; suyash Chhawala; Mousikta chanda; Dhruv Kansal | jaypatel6@deloitte.com; usistrivecutover@deloitte.com; schhawala@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94984 | STRIVE.R2.MC1.2384.1277.1.896.1.98.12.40 | N | N | N | Planned |  | Deploy the Iflow in CPI - MOR_I_018 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94983 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94985 | STRIVE.R2.MC1.2384.1277.1.896.1.98.12.41 | N | N | N | Planned |  | Validate, if interface is activated - MOR_I_018 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94984 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94986 | STRIVE.R2.MC1.2384.1277.1.896.1.98.13 | [5 empty] | R2D_I_019-FS Interface for reporting to tax authorities (i.e. ELSTER) - sales and purchase tax | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94987 | STRIVE.R2.MC1.2384.1277.1.896.1.98.13.43 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2D_I_019 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Roshan | rohemwani@deloitte.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Tatiana | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; tvinogradova@deloitte.de | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94988 | STRIVE.R2.MC1.2384.1277.1.896.1.98.13.44 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2D_I_019 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94987 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94989 | STRIVE.R2.MC1.2384.1277.1.896.1.98.13.45 | N | N | N | Planned |  | Validate, if interface is activated - R2D_I_019 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94988 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95035 | STRIVE.R2.MC1.2384.1277.1.896.1.98.14 | [5 empty] | P2C_I_400- TM: Evonik interface (Inbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95036 | STRIVE.R2.MC1.2384.1277.1.896.1.98.14.91 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_400 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95037 | STRIVE.R2.MC1.2384.1277.1.896.1.98.14.92 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_400 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95036 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95038 | STRIVE.R2.MC1.2384.1277.1.896.1.98.14.93 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_400 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95037 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95039 | STRIVE.R2.MC1.2384.1277.1.896.1.98.15 |  |  |  |  | Update | P2C_I_401-TM: Evonik Interface (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95040 | STRIVE.R2.MC1.2384.1277.1.896.1.98.15.95 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_401 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95041 | STRIVE.R2.MC1.2384.1277.1.896.1.98.15.96 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_401 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95040 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95042 | STRIVE.R2.MC1.2384.1277.1.896.1.98.15.97 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_401 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95041 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95043 | STRIVE.R2.MC1.2384.1277.1.896.1.98.16 |  |  |  |  | Update | P2C_I_415-TM: UKL Rail Interface (Inbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95044 | STRIVE.R2.MC1.2384.1277.1.896.1.98.16.99 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_415 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95045 | STRIVE.R2.MC1.2384.1277.1.896.1.98.16.100 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_415 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95044 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95046 | STRIVE.R2.MC1.2384.1277.1.896.1.98.16.101 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_415 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95045 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95047 | STRIVE.R2.MC1.2384.1277.1.896.1.98.17 | [5 empty] | P2C_I_416-TM: UKL Rail Interface (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95048 | STRIVE.R2.MC1.2384.1277.1.896.1.98.17.103 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_416 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95049 | STRIVE.R2.MC1.2384.1277.1.896.1.98.17.104 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_416 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95048 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95050 | STRIVE.R2.MC1.2384.1277.1.896.1.98.17.105 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_416 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95049 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95051 | STRIVE.R2.MC1.2384.1277.1.896.1.98.18 | [5 empty] | P2C_I_405-TM: Yard Management at Brunsbüttel (Inbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95052 | STRIVE.R2.MC1.2384.1277.1.896.1.98.18.107 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_405 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95053 | STRIVE.R2.MC1.2384.1277.1.896.1.98.18.108 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_405 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95052 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95054 | STRIVE.R2.MC1.2384.1277.1.896.1.98.18.109 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_405 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95053 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95055 | STRIVE.R2.MC1.2384.1277.1.896.1.98.19 | [5 empty] | P2C_I_406- TM: Yard Management at Brunsbüttel (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95056 | STRIVE.R2.MC1.2384.1277.1.896.1.98.19.111 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_406 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95057 | STRIVE.R2.MC1.2384.1277.1.896.1.98.19.112 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_406 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95056 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95058 | STRIVE.R2.MC1.2384.1277.1.896.1.98.19.113 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_406 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95057 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95059 | STRIVE.R2.MC1.2384.1277.1.896.1.98.20 | [5 empty] | P2C_I_200-SD: Brenntag-Sales order interface - inbound​ | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95060 | STRIVE.R2.MC1.2384.1277.1.896.1.98.20.115 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_200 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Ilja | iholub@deloitte.it | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95061 | STRIVE.R2.MC1.2384.1277.1.896.1.98.20.116 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_200 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95060 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95062 | STRIVE.R2.MC1.2384.1277.1.896.1.98.20.117 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_200 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95061 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95063 | STRIVE.R2.MC1.2384.1277.1.896.1.98.21 | [5 empty] | P2C_I_201-Tungsten interface - Invoicing for Germany | 1 hrs | 2025-09-05 08:00 | 2025-09-05 09:00 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-09-05 09:00
95064 | STRIVE.R2.MC1.2384.1277.1.896.1.98.21.119 | N | N | N | Ready |  | Provide confirmation to the integration team for interface activation - P2C_I_201 | 1 hrs | 2025-09-05 08:00 | 2025-09-05 09:00 | Rajeev Mishra | rajeemishra@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 09:00
95065 | STRIVE.R2.MC1.2384.1277.1.896.1.98.21.120 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_201 | 1 hrs | 2025-09-05 09:00 | 2025-09-05 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95064 |  |  | * | NA | 2025-09-05 09:00 | 2025-09-05 10:00
95066 | STRIVE.R2.MC1.2384.1277.1.896.1.98.21.121 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_201 | 1 hrs | 2025-09-05 10:00 | 2025-09-05 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95065 |  |  | * | NA | 2025-09-05 10:00 | 2025-09-05 11:00
95067 | STRIVE.R2.MC1.2384.1277.1.896.1.98.22 | [5 empty] | P2C_I_204: Pricing Hub (Digital Tool) - Inbound to SAP (CPI) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95068 | STRIVE.R2.MC1.2384.1277.1.896.1.98.22.123 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_204 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajeev Mishra | rajeemishra@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95069 | STRIVE.R2.MC1.2384.1277.1.896.1.98.22.124 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_204 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95068 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95070 | STRIVE.R2.MC1.2384.1277.1.896.1.98.22.125 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_204 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95069 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95071 | STRIVE.R2.MC1.2384.1277.1.896.1.98.23 | [5 empty] | P2C_I_300-KRUSE high storage warehouse - Outbound - Deliveries | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95072 | STRIVE.R2.MC1.2384.1277.1.896.1.98.23.127 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_300 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95073 | STRIVE.R2.MC1.2384.1277.1.896.1.98.23.128 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_300 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95072 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95074 | STRIVE.R2.MC1.2384.1277.1.896.1.98.23.129 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_300 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95073 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
94990 | STRIVE.R2.MC1.2384.1277.1.896.1.98.24 | [5 empty] | P2C_I_301-KRUSE high storage warehouse - Outbound - STOs | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
94991 | STRIVE.R2.MC1.2384.1277.1.896.1.98.24.47 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_301 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95002 | STRIVE.R2.MC1.2384.1277.1.896.1.98.24.1 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_301 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94991 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95003 | STRIVE.R2.MC1.2384.1277.1.896.1.98.24.58 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_301 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95002 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95004 | STRIVE.R2.MC1.2384.1277.1.896.1.98.25 | [5 empty] | P2C_I_419-TM: Dock Appt Scheduling Updates | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95005 | STRIVE.R2.MC1.2384.1277.1.896.1.98.25.60 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_419 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95006 | STRIVE.R2.MC1.2384.1277.1.896.1.98.25.61 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_419 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95005 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95007 | STRIVE.R2.MC1.2384.1277.1.896.1.98.25.62 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_419 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95006 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95008 | STRIVE.R2.MC1.2384.1277.1.896.1.98.26 | [5 empty] | P2C_I_422-TM: Ext. Storage : ALBLAS (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95009 | STRIVE.R2.MC1.2384.1277.1.896.1.98.26.64 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_422 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95010 | STRIVE.R2.MC1.2384.1277.1.896.1.98.26.65 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_422 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95009 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95011 | STRIVE.R2.MC1.2384.1277.1.896.1.98.26.66 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_422 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95010 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95012 | STRIVE.R2.MC1.2384.1277.1.896.1.98.27 | [5 empty] | P2C_I_423-TM: Ext. Storage : VOPAK (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95013 | STRIVE.R2.MC1.2384.1277.1.896.1.98.27.68 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_423 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95014 | STRIVE.R2.MC1.2384.1277.1.896.1.98.27.69 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_423 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95013 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95015 | STRIVE.R2.MC1.2384.1277.1.896.1.98.27.70 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_423 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95014 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95016 | STRIVE.R2.MC1.2384.1277.1.896.1.98.28 | [5 empty] | P2C_I_424-TM: Ext. Storage : PALOG (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95017 | STRIVE.R2.MC1.2384.1277.1.896.1.98.28.72 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_424 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95018 | STRIVE.R2.MC1.2384.1277.1.896.1.98.28.73 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_424 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95017 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95019 | STRIVE.R2.MC1.2384.1277.1.896.1.98.28.74 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_424 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95018 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95020 | STRIVE.R2.MC1.2384.1277.1.896.1.98.29 | [5 empty] | P2C_I_425-TM: Ext. Storage : TANQUID (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95021 | STRIVE.R2.MC1.2384.1277.1.896.1.98.29.76 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_425 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95022 | STRIVE.R2.MC1.2384.1277.1.896.1.98.29.77 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_425 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95021 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95023 | STRIVE.R2.MC1.2384.1277.1.896.1.98.29.78 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_425 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95022 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95024 | STRIVE.R2.MC1.2384.1277.1.896.1.98.30 | [5 empty] | P2C_I_426-FICO - TM: Ext. Storage : DP WORLD (Outbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95025 | STRIVE.R2.MC1.2384.1277.1.896.1.98.30.80 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_426 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95026 | STRIVE.R2.MC1.2384.1277.1.896.1.98.30.81 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_426 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95025 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95027 | STRIVE.R2.MC1.2384.1277.1.896.1.98.30.82 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_426 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95026 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95028 | STRIVE.R2.MC1.2384.1277.1.896.1.98.31 | [5 empty] | P2C_I_427-TM: Ext. Storage : VOPAK (Inbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95029 | STRIVE.R2.MC1.2384.1277.1.896.1.98.31.84 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_427 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
95030 | STRIVE.R2.MC1.2384.1277.1.896.1.98.31.85 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_427 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95029 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
95031 | STRIVE.R2.MC1.2384.1277.1.896.1.98.31.86 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_427 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95030 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
95032 | STRIVE.R2.MC1.2384.1277.1.896.1.98.32 | [5 empty] | P2C_I_428-TM: Ext. Storage : PALOG (Inbound) | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
95033 | STRIVE.R2.MC1.2384.1277.1.896.1.98.32.88 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - P2C_I_428 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
94992 | STRIVE.R2.MC1.2384.1277.1.896.1.98.32.48 | N | N | N | Planned |  | Deploy the Iflow in CPI - P2C_I_428 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 95033 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
94993 | STRIVE.R2.MC1.2384.1277.1.896.1.98.32.49 | N | N | N | Planned |  | Validate, if interface is activated - P2C_I_428 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Saurabh Kumar | saurabhkumar397@deloitte.com | Yashwanth; Naga reddy; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 94992 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20453 | STRIVE.R2.MC1.2384.1277.1.896.133 | [5 empty] | S/4HANA-SAP PF1 (Placeholder for Wave 1 Interfaces) | 96.71 hrs | 2025-09-15 08:00 | 2025-09-19 08:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-19 08:59
20454 | STRIVE.R2.MC1.2384.1277.1.896.133.1 | [5 empty] | R2D_I_001_Exchange rates fetch for daily conversions | 96.71 hrs | 2025-09-15 08:00 | 2025-09-19 08:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-19 08:59
20455 | STRIVE.R2.MC1.2384.1277.1.896.133.1.1 | N | N | N | Planned |  | Check the configuration in S4 - R2D_I_001 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Gurmandeep Singh | gurmandsingh@deloitte.com | Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20483 | STRIVE.R2.MC1.2384.1277.1.896.205 | [5 empty] | OneStream (Placeholder for Wave 1 Interfaces) | 144.57 hrs | 2025-09-15 08:00 | 2025-09-21 08:58 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-21 08:58
20484 | STRIVE.R2.MC1.2384.1277.1.896.205.4 | [5 empty] | R2D_I_014_One stream connection with S4 | 144.57 hrs | 2025-09-15 08:00 | 2025-09-21 08:58 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-21 08:58
20485 | STRIVE.R2.MC1.2384.1277.1.896.205.4.3 | N | N | N | Planned |  | Validate, the configuration/connection - R2D_I_014 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Yashaswi Rahut | yarahut@deloitte.com | Gurmandeep Singh; Naga; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal | gurmandsingh@deloitte.com; nnagasubbareddy@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com | Integration |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20486 | STRIVE.R2.MC1.2384.1277.1.896.205.4.4 | N | N | N | Planned |  | Maintain table “ZBW_MSK_RULES” | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Michaela | michaela.schulz@de.sasol.com | Yashaswi; Roshanlal Hemwani; Tatiana; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | yarahut@deloitte.com; rohemwani@deloitte.com; tvinogradova@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20487 | STRIVE.R2.MC1.2384.1277.1.896.205.25 | [5 empty] | S4HANA - EinvoiceSDI (Placeholder for Wave 1 Interfaces) | 1774.42 hrs | 2025-09-15 08:00 | 2025-11-28 11:21 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-11-28 11:21
20488 | STRIVE.R2.MC1.2384.1277.1.896.205.25.1 | [5 empty] | R2D_I_015_Send accounting data to SDI (e-Invoicing Italy) | 484.48 hrs | 2025-09-15 08:00 | 2025-10-05 13:50 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-05 13:50
20489 | STRIVE.R2.MC1.2384.1277.1.896.205.25.1.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - R2D_I_015 to activate on 28th March, 9:00 PM CET | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Siddhesh | sibaraskar@deloitte.com | Tripti mehta; Ramesh SathishKumar; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | trimehta@deloitte.com; satramesh@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20490 | STRIVE.R2.MC1.2384.1277.1.896.205.25.1.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - R2D_I_015 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 20489 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20491 | STRIVE.R2.MC1.2384.1277.1.896.205.25.1.3 | N | N | N | Planned |  | Validate, if interface is activated - R2D_I_015 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com | Integration | 20490 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20492 | STRIVE.R2.MC1.2384.1277.1.896.205.25.1.4 | N | N | N | Planned |  | CNAME Configuration at Network Domain Level | 1 hrs | 2025-09-15 11:00 | 2025-09-15 12:00 | Bernd Gawehn | Bernd.Gawehn@consultary.de | Christian Witt; Yashwanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | christian.witt@de.sasol.com; myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure | 20491 |  |  | * | NA | 2025-09-15 11:00 | 2025-09-15 12:00
20497 | STRIVE.R2.MC1.2384.1277.1.896.205.35 | [5 empty] | IBP (Placeholder for Wave 1 Interfaces) | 173.45 hrs | 2025-09-15 08:00 | 2025-09-22 13:56 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-22 13:56
20498 | STRIVE.R2.MC1.2384.1277.1.896.205.35.1 | [5 empty] | IBP_I_001 - BW to OMP : Customer Extract | 173.45 hrs | 2025-09-15 08:00 | 2025-09-22 13:56 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-22 13:56
20499 | STRIVE.R2.MC1.2384.1277.1.896.205.35.1.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - IBP_I_001 to activate on Date TBD | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Edurado; David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | eduardo.gouveia@us.sasol.com; david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20500 | STRIVE.R2.MC1.2384.1277.1.896.205.35.1.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - IBP_I_001 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20499 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20501 | STRIVE.R2.MC1.2384.1277.1.896.205.35.1.3 | N | N | N | Planned |  | Validate, if interface is activated - IBP_I_001 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20500 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20502 | STRIVE.R2.MC1.2384.1277.1.896.205.35.5 | [5 empty] | IBP_I_005 - BW to OMP : Sales Forecast Extract | 173.45 hrs | 2025-09-15 08:00 | 2025-09-22 13:56 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-22 13:56
20503 | STRIVE.R2.MC1.2384.1277.1.896.205.35.5.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - IBP_I_005 to activate on Date TBD | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Edurado; David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | eduardo.gouveia@us.sasol.com; david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20504 | STRIVE.R2.MC1.2384.1277.1.896.205.35.5.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - IBP_I_005 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20503 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20505 | STRIVE.R2.MC1.2384.1277.1.896.205.35.5.3 | N | N | N | Planned |  | Validate, if interface is activated - IBP_I_005 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20504 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20506 | STRIVE.R2.MC1.2384.1277.1.896.205.35.9 | [5 empty] | IBP_I_010 - BW to OMP : Product Extract | 173.45 hrs | 2025-09-15 08:00 | 2025-09-22 13:56 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-22 13:56
20507 | STRIVE.R2.MC1.2384.1277.1.896.205.35.9.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - IBP_I_010 to activate on Date TBD | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Edurado; David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | eduardo.gouveia@us.sasol.com; david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20508 | STRIVE.R2.MC1.2384.1277.1.896.205.35.9.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - IBP_I_010 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20507 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20509 | STRIVE.R2.MC1.2384.1277.1.896.205.35.9.3 | N | N | N | Planned |  | Validate, if interface is activated - IBP_I_010 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20508 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20510 | STRIVE.R2.MC1.2384.1277.1.896.205.35.13 | [5 empty] | IBP_I_011 - BW to OMP : Forecast Item Extract | 173.45 hrs | 2025-09-15 08:00 | 2025-09-22 13:56 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-22 13:56
20511 | STRIVE.R2.MC1.2384.1277.1.896.205.35.13.1 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - IBP_I_011 to activate on Date TBD | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Edurado; David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | eduardo.gouveia@us.sasol.com; david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20512 | STRIVE.R2.MC1.2384.1277.1.896.205.35.13.2 | N | N | N | Planned |  | Deploy the Iflow in CPI - IBP_I_011 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20511 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20513 | STRIVE.R2.MC1.2384.1277.1.896.205.35.13.3 | N | N | N | Planned |  | Validate, if interface is activated - IBP_I_011 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20512 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
40078 | STRIVE.R2.MC1.2384.1277.1.896.205.35.28 | [5 empty] | IBP_I_006 | 3 hrs | 2025-09-15 08:00 | 2025-09-15 11:00 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-15 11:00
40079 | STRIVE.R2.MC1.2384.1277.1.896.205.35.28.4 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation - IBP_I_006 to activate on Date TBD | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sahgal | rasahgal@deloitte.com | Edurado; David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | eduardo.gouveia@us.sasol.com; david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
40077 | STRIVE.R2.MC1.2384.1277.1.896.205.35.28.5 | N | N | N | Planned |  | Deploy the Iflow in CPI - IBP_I_006 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 40079 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
40076 | STRIVE.R2.MC1.2384.1277.1.896.205.35.28.6 | N | N | N | Planned |  | Validate, if interface is activated - IBP_I_006 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 40077 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20519 | STRIVE.R2.MC1.2384.1277.1.896.205.35.22 | [5 empty] | Tungsten (Placeholder for Wave 1 Interfaces) | 437.16 hrs | 2025-09-15 08:00 | 2025-10-03 14:23 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-03 14:23
20520 | STRIVE.R2.MC1.2384.1277.1.896.205.35.22.1 | [5 empty] | P2C_I_006 | 437.16 hrs | 2025-09-15 08:00 | 2025-10-03 14:23 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-10-03 14:23
20521 | STRIVE.R2.MC1.2384.1277.1.896.205.35.22.1.1 | N | N | N | Planned |  | Raise Ticket in Tungsten Portal to setup the CPI Public Key | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Manuel | Manuel.Roellinghoff@de.sasol.com | Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20522 | STRIVE.R2.MC1.2384.1277.1.896.205.35.22.1.2 | N | N | N | Planned |  | Provide confirmation to the integration team for interface activation-P2C_I_006 to activate on 28th March 9:00 PM CET | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Siddhesh | sibaraskar@deloitte.com | Yashwanth; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20523 | STRIVE.R2.MC1.2384.1277.1.896.205.35.22.1.3 | N | N | N | Planned |  | Deploy the Iflow in CPI-P2C_I_006 | 1 hrs | 2025-09-15 09:00 | 2025-09-15 10:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20522 |  |  | * | NA | 2025-09-15 09:00 | 2025-09-15 10:00
20524 | STRIVE.R2.MC1.2384.1277.1.896.205.35.22.1.4 | N | N | N | Planned |  | Validate, if interface is activated-P2C_I_006 | 1 hrs | 2025-09-15 10:00 | 2025-09-15 11:00 | Yashwanth | myakumar@deloitte.com | Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Integration | 20523 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 11:00
20525 | STRIVE.R2.MC1.2384.1277.1.1101 | [5 empty] | Printer setup | 73.78 hrs | 2025-09-15 08:00 | 2025-09-18 09:59 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-18 09:59
20526 | STRIVE.R2.MC1.2384.1277.1.1101.1 | N | N | N | Planned |  | Complete SPAD information for printer setup - R2P | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Dr.Jürgen Heinrichs | Juergen.Heinrichs@de.sasol.com | Claudiu; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | cljipa@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20527 | STRIVE.R2.MC1.2384.1277.1.1101.2 | N | N | N | Planned |  | Complete SPAD information for printer setup - P2C | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Rob Hall | rob.hall@sasol.com | Diego Zarate; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dzarate@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20528 | STRIVE.R2.MC1.2384.1277.1.1101.3 | N | N | N | Planned |  | Complete SPAD information for printer setup - S2P | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Evan Rademeyer | evan.rademeyer@us.sasol.com | Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20529 | STRIVE.R2.MC1.2384.1277.1.1101.4 | N | N | N | Planned |  | Complete SPAD information forprinter setup - MOR | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Elisa Latona | elisa.latona@it.sasol.com | Amit Jha; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ajha2@deloitte.no; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20530 | STRIVE.R2.MC1.2384.1277.1.1101.5 | N | N | N | Planned |  | Complete SPAD information for printer setup - R2D | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Francois Conradie | francois.conradie@de.sasol.com | Alexandra Ruff; Dhruv Kansal; USI STRIVE CUTOVER; Roshanlal; Mousikta chanda; Tatiana | aruff@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rohemwani@deloitte.com; mouchanda@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20531 | STRIVE.R2.MC1.2384.1277.1.1101.6 | N | N | N | Planned |  | Complete SPAD information for printer setup - IBP | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | David Conradie | david.conradie1@sasol.com | Rajat Sahgal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rasahgal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20532 | STRIVE.R2.MC1.2384.1277.1.1108 | [5 empty] | Batch Job setup in PROD System and update the tracker | 73.78 hrs | 2025-09-05 08:00 | 2025-09-08 09:59 | [6 empty] | 2025-08-28 16:54 |  | * | NA | 2025-09-05 08:00 | 2025-09-08 09:59
20533 | STRIVE.R2.MC1.2384.1277.1.1108.1 | Y | Y | Y | Complete |  | Define Batch Job in PROD System and update the tracker - R2P | 71.87 hrs | 2025-08-29 19:34 | 2025-09-01 19:38 | Amit das | amitdas3@deloitte.com | Claudiu; Jay Saini; Mousikta chanda; Pamela Mihali; Abhishek Parab; Sheena Gour; Deepika Agarwal; Shivani Kulkarni; Aniket Kulkarni; Dhruv Kansal; USI STRIVE CUTOVER; Nilesh Deshpande | cljipa@deloitte.de; jaysaini4@deloitte.com; mouchanda@deloitte.com; pamihali@deloitte.de; abhparab@deloitte.com; shgour@deloitte.com; deepikaagarwal@deloitte.de; shivankulkarni@deloitte.com; anikulkarni@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; nideshpande@deloitte.com | R2P |  | 2025-08-29 19:34 | 2025-09-01 19:38 | * | NA | 2025-08-29 19:34 | 2025-09-01 19:38
20534 | STRIVE.R2.MC1.2384.1277.1.1108.2 | Y | N | N | Sent |  | Define Batch Job in PROD System and update the tracker - S2P | 2 hrs | 2025-09-05 08:00 | 2025-09-05 10:00 | Prasanth | kalprasanth@deloitte.com | Aparajita Mukherjee; Mousikta chanda; Milton; Dhruv Kansal; USI STRIVE CUTOVER; S2P Team | apamukherjee@deloitte.com; mouchanda@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 10:00
20535 | STRIVE.R2.MC1.2384.1277.1.1108.3 | Y | N | N | Sent |  | Define Batch Job in PROD System and update the tracker - P2C | 2 hrs | 2025-09-05 08:00 | 2025-09-05 10:00 | Shubham Mishra | spratapmishra@deloitte.com | Malta; Diego Zarate; Valentijn; Ramesh SathishKumar; Tripti mehta; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | mawilhelm@deloitte.de; dzarate@deloitte.com; vvandriessen@deloitte.com; satramesh@deloitte.com; trimehta@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 10:00
20536 | STRIVE.R2.MC1.2384.1277.1.1108.4 | Y | Y | Y | Complete |  | Define Batch Job in PROD System and update the tracker - R2D | 189.08 hrs | 2025-08-28 16:54 | 2025-09-05 14:31 | Roshanlal | rohemwani@deloitte.com | Alexandra Ruff; ; Mousikta chanda; Daniel Lohmann; Dhruv Kansal; USI STRIVE CUTOVER | aruff@deloitte.de; ; mouchanda@deloitte.com; dlohmann@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com | R2D |  | 2025-08-28 16:54 | 2025-09-05 14:31 | * | NA | 2025-08-28 16:54 | 2025-09-05 14:31
20537 | STRIVE.R2.MC1.2384.1277.1.1108.5 | Y | Y | Y | Complete |  | Define Batch Job in PROD System and update the tracker - MOR | 164.84 hrs | 2025-08-28 17:08 | 2025-09-04 14:27 | Mythili | myboyapati@deloitte.com | Krishna Teja; Vinod; Jay Patel; Nikhil Gupta; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Amit Jha | krishn@deloitte.com; vinodkumar692@deloitte.com; jaypatel6@deloitte.com; mrgupta3@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; ajha2@deloitte.no | MOR |  | 2025-08-28 17:08 | 2025-09-04 14:27 | * | NA | 2025-08-28 17:08 | 2025-09-04 14:27
20538 | STRIVE.R2.MC1.2384.1277.1.1108.6 | Y | Y | Y | Complete |  | Define Batch Job in PROD System and update the tracker - MDG | 0 hrs | 2025-09-04 19:40 | 2025-09-04 19:40 | Amol Paswan | ampaswan@deloitte.com | Tulika Pal; ; Tushar; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | tupal@deloitte.com; ; tamrutkar@deloitte.de; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | MDG |  | 2025-09-04 19:40 | 2025-09-04 19:40 | * | NA | 2025-09-04 19:40 | 2025-09-04 19:40
20539 | STRIVE.R2.MC1.2384.1277.1.1108.7 | Y | N | N | Sent |  | Define Batch Job in PROD System and update the tracker - ABAP | 2 hrs | 2025-09-05 08:00 | 2025-09-05 10:00 | Gurmandeep Singh | gurmandsingh@deloitte.com | Shivraj; Ashish patil; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Satish rahangadale | shivrsinha@deloitte.com; ashishspatil@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; srahangdale@deloitte.com | ABAP |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 10:00
20540 | STRIVE.R2.MC1.2384.1277.1.1108.8 | Y | N | N | Sent |  | Define Batch Job in PROD System and update the tracker - GRC/Security | 2 hrs | 2025-09-05 08:00 | 2025-09-05 10:00 | Somitra | sothapa@deloitte.com | Quinten Broeckx ; Naman; Mousikta chanda; Jayasurya; Ankush; Dhruv Kansal; USI STRIVE CUTOVER | qbroeckx@deloitte.be; njaswani@deloitte.com; mouchanda@deloitte.com; jayasur@deloitte.com; amisri@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | Security |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 10:00
20541 | STRIVE.R2.MC1.2384.1277.1.1108.9 | N | N | N | Ready |  | Schedule Batch Job | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Jens Nissen | Jens.Nissen@de.sasol.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20542 | STRIVE.R2.MC1.2384.1277.1.1118 | [5 empty] | DMS Archiving | 123.62 hrs | 2025-09-15 08:00 | 2025-09-20 11:57 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-20 11:57
20543 | STRIVE.R2.MC1.2384.1277.1.1118.1 | N | N | N | Planned |  | Setup archiving repository based on the provided information in the tracker | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Rico van den Berg; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Deloitte BASIS | rico.vandenberg@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; DeloitteSASOLBasisTeam@deloitte.com | Sasol Infrastructure |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20544 | STRIVE.R2.MC1.2384.1277.1.1120 | [5 empty] | Microsoft Form | 2639.42 hrs | 2025-09-15 08:00 | 2026-01-03 14:46 | [8 empty] | * | NA | 2025-09-15 08:00 | 2026-01-03 14:46
20545 | STRIVE.R2.MC1.2384.1277.1.1120.1 | N | N | N | Planned |  | System Access for Microsoft Form | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Ankush; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amisri@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20546 | STRIVE.R2.MC1.2384.1277.1.1120.2 | N | N | N | Planned |  | System User creation for Microsoft Form | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Shubham Thakur | Shubhathakur@deloitte.com | Ankush; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amisri@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC | 20545 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 12:00
20547 | STRIVE.R2.MC1.2384.1277.1.1120.3 | N | N | N | Planned |  | System User Creation for Email server destination for Microsoft Form | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Shubham Thakur | Shubhathakur@deloitte.com | Ankush; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amisri@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | GRC |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20548 | STRIVE.R2.MC1.2384.1277.1.1120.4 | N | N | N | Planned |  | Adding Destination in SAP Build for Microsoft Form | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Joseph Barber | joseph.barber@us.sasol.com | Nikhil Gupta; Amit Jha; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mrgupta3@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20549 | STRIVE.R2.MC1.2384.1277.1.1120.5 | N | N | N | Planned |  | Action Project Creation for Microsoft Form | 2 hrs | 2025-09-15 10:00 | 2025-09-15 12:00 | Joseph Barber | joseph.barber@us.sasol.com | Nikhil Gupta; Amit Jha; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mrgupta3@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 20548 |  |  | * | NA | 2025-09-15 10:00 | 2025-09-15 12:00
20550 | STRIVE.R2.MC1.2384.1277.1.1120.6 | N | N | N | Planned |  | Import Form from Dev/QA system for Microsoft Form | 2 hrs | 2025-09-15 12:01 | 2025-09-15 14:01 | Joseph Barber | joseph.barber@us.sasol.com | Nikhil Gupta; Amit Jha; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mrgupta3@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 20549 |  |  | * | NA | 2025-09-15 12:01 | 2025-09-15 14:01
20551 | STRIVE.R2.MC1.2384.1277.1.1120.7 | N | N | N | Planned |  | Export Microsoft Form in Production | 2 hrs | 2025-09-15 14:01 | 2025-09-15 16:01 | Joseph Barber | joseph.barber@us.sasol.com | Nikhil Gupta; Amit Jha; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | mrgupta3@deloitte.com; ajha2@deloitte.no; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 20550 |  |  | * | NA | 2025-09-15 14:01 | 2025-09-15 16:01
20553 | STRIVE.R2.MC1.2384.1277.1.1129 | [5 empty] | One Source | 1345.65 hrs | 2025-09-15 08:00 | 2025-11-10 13:24 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-11-10 13:24
20554 | STRIVE.R2.MC1.2384.1277.1.1129.1 | N | N | N | Planned |  | User access for one source IDT log / role mapping | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Naman | njaswani@deloitte.com | Ankush; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amisri@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Security |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20555 | STRIVE.R2.MC1.2384.1277.1.1129.2 | N | N | N | Planned |  | Obejct Validation before fuctional import | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Shailesh Khobargade | skhobragade@deloitte.com | Pragyesh Kumar; Mousikta chanda | pkumargoyal@deloitte.com; mouchanda@deloitte.com | Onesource |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20556 | STRIVE.R2.MC1.2384.1277.1.1129.3 | N | N | N | Planned |  | Validate Tax TRs | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Aquib Iqbal | aquiqbal@deloitte.com | Roshanlal; Dhruv Kansal; USI STRIVE CUTOVER; Tatiana; Mousikta chanda | rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tvinogradova@deloitte.de; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20557 | STRIVE.R2.MC1.2384.1277.1.1129.4 | N | N | N | Planned |  | Tax rate maintenance | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Aquib Iqbal | aquiqbal@deloitte.com | Roshanlal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20558 | STRIVE.R2.MC1.2384.1277.1.1129.5 | N | N | N | Planned |  | Run program RV80HGEN in SE38 to activate formulas | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Aquib Iqbal | aquiqbal@deloitte.com | Roshanlal; Dhruv Kansal; USI STRIVE CUTOVER; Tatiana; Mousikta chanda | rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tvinogradova@deloitte.de; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20559 | STRIVE.R2.MC1.2384.1277.1.1129.6 | N | N | N | Planned |  | Remove % from Onesource conditions types in transaction FV12 | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Aquib Iqbal | aquiqbal@deloitte.com | Roshanlal; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | rohemwani@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2D |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20560 | STRIVE.R2.MC1.2384.1277.1.1129.7 | N | N | N | Planned |  | Creation of ZITD Condition Records - VK11 - make sure to maintain for all combinations of customer and material | 2 hrs | 2025-09-15 08:00 | 2025-09-15 10:00 | Mousikta chanda | mouchanda@deloitte.com |  |  | P2C | 19607,19541 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 10:00
20561 | STRIVE.R2.MC1.2384.1277.1.1137 | [5 empty] | Smoke Test | 315.01 hrs | 2025-09-15 08:00 | 2025-09-28 11:53 | [8 empty] | * | NA | 2025-09-15 08:00 | 2025-09-28 11:53
20562 | STRIVE.R2.MC1.2384.1277.1.1137.1 | N | N | N | Planned |  | Perform smoke test-MDG_I_020 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amol; Tushar | tupal@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ampaswan@deloitte.com; tamrutkar@deloitte.de | MDG | 19633 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20563 | STRIVE.R2.MC1.2384.1277.1.1137.2 | N | N | N | Planned |  | Perform smoke test-MDG_I_040 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amol; Tushar | tupal@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ampaswan@deloitte.com; tamrutkar@deloitte.de | MDG | 19551 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20564 | STRIVE.R2.MC1.2384.1277.1.1137.3 | N | N | N | Planned |  | Perform smoke test - MDG_I_200 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amol; Tushar | tupal@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ampaswan@deloitte.com; tamrutkar@deloitte.de | MDG | 19433 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20565 | STRIVE.R2.MC1.2384.1277.1.1137.4 | N | N | N | Planned |  | Perform smoke test - MDG_I_210 | 1 hrs | 2025-09-15 08:00 | 2025-09-15 09:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amol; Tushar | tupal@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ampaswan@deloitte.com; tamrutkar@deloitte.de | S2P | 19433 |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 09:00
20569 | STRIVE.R2.MC1.2384.1277.1.1145 | [5 empty] | Ramp Down | 2012.58 hrs | 2025-09-05 08:00 | 2025-11-28 10:11 | [6 empty] | 2025-09-05 08:00 |  | * | NA | 2025-09-05 08:00 | 2025-11-28 10:11
20570 | STRIVE.R2.MC1.2384.1277.1.1145.1 |  |  |  | Complete |  | P2C (Relevant for Production Cutover) | 822.72 hrs | 2025-09-15 08:00 | 2025-10-19 17:00 | [6 empty] | 2025-09-10 16:45 |  | * | NA | 2025-09-15 08:00 | 2025-10-19 17:00
20571 | STRIVE.R2.MC1.2384.1277.1.1145.1.1 | Y | Y | Y | Complete |  | Standard preorder for Jan 26& Feb 26 from Sasol Germany and Slovakia to be sent out as usual | 0 hrs | 2025-09-10 16:45 | 2025-09-10 16:45 | Hans Ringst | hans.ringst@de.sasol.com | Maria Teresa Denti; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | mariateresa.denti@it.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C |  | 2025-09-10 16:45 | 2025-09-10 16:45 | * | NA | 2025-09-10 16:45 | 2025-09-10 16:45
20572 | STRIVE.R2.MC1.2384.1277.1.1145.1.2 | Y | Y | Y | Complete |  | Customer awareness notifcation of Sasol Germany and Slovakia Go-Live | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Ben Jones | ben.jones@de.sasol.com | Hans Ringst; Rob Hall; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | hans.ringst@de.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20573 | STRIVE.R2.MC1.2384.1277.1.1145.1.3 | Y | Y | Y | Complete |  | Notification of Go-Live date, Black-out& preorder before Go-Live | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Ben Jones | ben.jones@de.sasol.com | Hans Ringst; Rob Hall; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | hans.ringst@de.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20574 | STRIVE.R2.MC1.2384.1277.1.1145.1.4 | Y | Y | Y | Complete |  | Update of business continuity plans for customer fulfilment& logistics | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Patrizia | patrizia.vergani@it.sasol.com | Rob Hall; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | rob.hall@sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20575 | STRIVE.R2.MC1.2384.1277.1.1145.1.5 | Y | Y | Y | Complete |  | Finalize last ship dates in the old system | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Rob Hall; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | rob.hall@sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20576 | STRIVE.R2.MC1.2384.1277.1.1145.1.6 | Y | Y | Y | Complete |  | finalize last order date in the old system | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Rob Hall; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | rob.hall@sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20577 | STRIVE.R2.MC1.2384.1277.1.1145.1.7 | Y | Y | Y | Complete |  | Stop Creation of Master Data (Customer/Hierarchy/Pricing/Output) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Antonio Sciullodi | antonio.sciullodi@de.sasol.com | Jessica Goffi; Rob Hall; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | Jessica.Goffi@it.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20578 | STRIVE.R2.MC1.2384.1277.1.1145.1.8 | Y | Y | Y | Complete |  | Stop any batch jobs running for Delivery or Invoice creation | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20579 | STRIVE.R2.MC1.2384.1277.1.1145.1.9 | Y | Y | Y | Complete |  | Close open sales orders in legacy system | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Rob Hall; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER | rob.hall@sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20580 | STRIVE.R2.MC1.2384.1277.1.1145.1.10 | Y | Y | Y | Complete |  | Publish to internal teams, Sales Milestones and plans for Prod cutover : Communicate and align with Warehouse on cutoff dates for Sales Orders, instructions on Shipment holds, return holds, cancellations of unshipped orders (will be re-created in new syst | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria Teresa Denti; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | mariateresa.denti@it.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20581 | STRIVE.R2.MC1.2384.1277.1.1145.1.11 | Y | Y | Y | Complete |  | Returns Cutoff : Last day to process Returns and Credit Memos | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria Teresa Denti; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | mariateresa.denti@it.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20582 | STRIVE.R2.MC1.2384.1277.1.1145.1.12 | Y | Y | Y | Complete |  | Run freight settlement procedures / Finalise invoices with carriers | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20583 | STRIVE.R2.MC1.2384.1277.1.1145.1.13 | Y | Y | Y | Complete |  | Final date for goods issues& goods receipts | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20584 | STRIVE.R2.MC1.2384.1277.1.1145.1.14 | Y | Y | Y | Complete |  | Finalize SD Billing Cutoff Date (outbound invoices) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Rob Hall | rob.hall@sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20585 | STRIVE.R2.MC1.2384.1277.1.1145.1.15 | Y | Y | Y | Complete |  | Identify data to use in Smoke Test (material, customer, plant) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Rob Hall | rob.hall@sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20586 | STRIVE.R2.MC1.2384.1277.1.1145.1.16 | Y | Y | Y | Complete |  | Change dates to post go-live for any customer orders that do not ship (verify with customer) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria Teresa Denti; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | mariateresa.denti@it.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20587 | STRIVE.R2.MC1.2384.1277.1.1145.1.17 | Y | Y | Y | Complete |  | Establish cutoff time for Customer Pick up | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria Teresa Denti; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER; Dhruv Kansal | mariateresa.denti@it.sasol.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20588 | STRIVE.R2.MC1.2384.1277.1.1145.1.18 | Y | Y | Y | Complete |  | Backup procedures are available for ship dates during BLACKOUT of 1.5 working days. For a longer BLACKOUT period, alternative procedures would have to be developed impacting loading, sales, operations, compliance (tax, customs etc.) and safety | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20589 | STRIVE.R2.MC1.2384.1277.1.1145.1.19 | Y | Y | Y | Complete |  | Extract Master list of orders / deliveries from ECC A01 into Excel / .pdf format (+ pre prepare documents on legacy system for use in blackout) | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20590 | STRIVE.R2.MC1.2384.1277.1.1145.1.20 | Y | Y | Y | Complete |  | Disconnect AP1/AX4 interface from AP1 based on instruction from Joern Ladehoff | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20591 | STRIVE.R2.MC1.2384.1277.1.1145.1.21 | Y | Y | Y | Complete |  | Send transportation order confirmation to carriers by email | 4 hrs | 2025-09-15 08:00 | 2025-09-15 12:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-15 08:00 | 2025-09-15 12:00
20592 | STRIVE.R2.MC1.2384.1277.1.1145.23 |  |  |  | Complete |  | R2D (Not relevant for MC1) | 1940.65 hrs | 2025-09-05 08:00 | 2025-11-25 10:03 | [8 empty] | * | NA | 2025-09-05 08:00 | 2025-11-25 10:03
20593 | STRIVE.R2.MC1.2384.1277.1.1145.23.1 | Y | Y | Y | Complete |  | Last day to enter Accounts Recievables invoices (manual only) (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20594 | STRIVE.R2.MC1.2384.1277.1.1145.23.2 | Y | Y | Y | Complete |  | Payroll payment - expense posting file (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Alessandra Dallavalle | alessandra.dallavalle@it.sasol.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20595 | STRIVE.R2.MC1.2384.1277.1.1145.23.3 | Y | Y | Y | Complete |  | A/P Invoices posted (cut off decided by AP) (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20596 | STRIVE.R2.MC1.2384.1277.1.1145.23.4 | Y | Y | Y | Complete |  | Last vendor payment processed (from bank statement) (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Vergani Patrizia | patrizia.vergani@it.sasol.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20597 | STRIVE.R2.MC1.2384.1277.1.1145.23.5 | Y | Y | Y | Complete |  | Check: All e-invoicing A/P invoices processed. (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20598 | STRIVE.R2.MC1.2384.1277.1.1145.23.6 | Y | Y | Y | Complete |  | Set up detailed period control in Legacy environment (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Donida Pierangela | piera.donida@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20599 | STRIVE.R2.MC1.2384.1277.1.1145.23.7 | Y | Y | Y | Complete |  | Block account postings: Accounts Payable via Period Control (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20600 | STRIVE.R2.MC1.2384.1277.1.1145.23.8 | Y | Y | Y | Complete |  | Postings& Check: All A/R Invoices (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20601 | STRIVE.R2.MC1.2384.1277.1.1145.23.9 | Y | Y | Y | Complete |  | Check: Delivery/ Invoices matched (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20602 | STRIVE.R2.MC1.2384.1277.1.1145.23.10 | Y | Y | Y | Complete |  | Check: All e-invoicing A/R processed. (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20603 | STRIVE.R2.MC1.2384.1277.1.1145.23.11 | Y | Y | Y | Complete |  | Intercompany matching (recon.) (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20604 | STRIVE.R2.MC1.2384.1277.1.1145.23.12 | Y | Y | Y | Complete |  | Early billing of pipeline transfers / accruals (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20605 | STRIVE.R2.MC1.2384.1277.1.1145.23.13 | Y | Y | Y | Complete |  | Processing/Upload of Bank Statements as of 31.Mar.2025 (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Patrizia | patrizia.vergani@it.sasol.com | USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20606 | STRIVE.R2.MC1.2384.1277.1.1145.23.14 | Y | Y | Y | Complete |  | Extraction of open AP& AR items (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20607 | STRIVE.R2.MC1.2384.1277.1.1145.23.15 | Y | Y | Y | Complete |  | Block account postings: Accounts Receivables (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Mousikta chanda; Dhruv Kansal; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; dhkansal@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20608 | STRIVE.R2.MC1.2384.1277.1.1145.23.16 | Y | Y | Y | Complete |  | Check:All postings (material movements) to Process orders complete. (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20609 | STRIVE.R2.MC1.2384.1277.1.1145.23.17 | Y | Y | Y | Complete |  | Check:All postings (material movements) to Plant Maintenance orders complete. (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Dhruv Kansal | dhkansal@deloitte.com | USI STRIVE CUTOVER; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | usistrivecutover@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20610 | STRIVE.R2.MC1.2384.1277.1.1145.23.18 | Y | Y | Y | Complete |  | Check:All postings (material movements) to Projects/WBS (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20611 | STRIVE.R2.MC1.2384.1277.1.1145.23.19 | Y | Y | Y | Complete |  | Check:All Misc.material movements complete. (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20612 | STRIVE.R2.MC1.2384.1277.1.1145.23.20 | Y | Y | Y | Complete |  | Block account postings: Material Movements (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20613 | STRIVE.R2.MC1.2384.1277.1.1145.23.21 | Y | Y | Y | Complete |  | Block account postings: General Ledger (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | USI STRIVE CUTOVER | usistrivecutover@deloitte.com | Dhruv Kansal; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | dhkansal@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20614 | STRIVE.R2.MC1.2384.1277.1.1145.23.22 | Y | Y | Y | Complete |  | Perform inventory closing in legacy (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20615 | STRIVE.R2.MC1.2384.1277.1.1145.23.23 | Y | Y | Y | Complete |  | Extraction of inventory values at GL account level as per 28.02.2025 (Not relevant for MC1) | 4 hrs | 2025-09-05 08:00 | 2025-09-05 12:00 | Oluf baren | oluf.braren@de.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-05 08:00 | 2025-09-05 12:00
20616 | STRIVE.R2.MC1.2384.1277.1.1145.47 | [5 empty] | MOR | 648.97 hrs | 2025-09-20 08:00 | 2025-10-17 10:46 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-17 10:46
20617 | STRIVE.R2.MC1.2384.1277.1.1145.47.1 | N | N | N | Planned |  | Do a physical inventory count for spare parts | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | ; Matteo Bartesaghi; Aureliano Muccio; Sven Gelking; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Elisa Latona; Sergio; Joseph Barber | ; Matteo.Bartesaghi@it.sasol.com; Aureliano.Muccio@it.sasol.com; sven.gelking@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20618 | STRIVE.R2.MC1.2384.1277.1.1145.47.2 | N | N | N | Planned |  | Post the physical inventory count in ECC | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | ; Matteo Bartesaghi; Aureliano Muccio; Sven Gelking; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sergio; Elisa Latona; Joseph Barber | ; Matteo.Bartesaghi@it.sasol.com; Aureliano.Muccio@it.sasol.com; sven.gelking@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20619 | STRIVE.R2.MC1.2384.1277.1.1145.47.3 | N | N | N | Planned |  | Creation of new equipment in the system ECC | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Massimo vinci; Aureliano Muccio; Dhruv Kansal; Sven Gelking; Mousikta chanda; USI STRIVE CUTOVER; Elisa Latona; Sergio; Joseph Barber | massimo.vinci@it.sasol.com; Aureliano.Muccio@it.sasol.com; dhkansal@deloitte.com; sven.gelking@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20620 | STRIVE.R2.MC1.2384.1277.1.1145.47.4 | Y | Y | Y | Complete |  | Close as much as possible open work order in the legacy system (Not relevant for MC1) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Adelfo Roccaforte | Adelfo.Roccaforte@it.sasol.com | Matteo Bartesaghi; Luca Capurro; Dhruv Kansal; Sven Gelking; Mousikta chanda; USI STRIVE CUTOVER; Sergio; Elisa Latona; Joseph Barber | Matteo.Bartesaghi@it.sasol.com; luca.capurro@it.sasol.com; dhkansal@deloitte.com; sven.gelking@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20621 | STRIVE.R2.MC1.2384.1277.1.1145.47.5 | N | N | N | Planned |  | Create Excel sheet for manually capturing maintenance notifications during blackout | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Elisa Latona | elisa.latona@it.sasol.com | Joseph Barber; Sergio; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | joseph.barber@us.sasol.com; sergio.guzzo@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20622 | STRIVE.R2.MC1.2384.1277.1.1145.47.6 | N | N | N | Planned |  | Communicate procedure of capturing maintenance notifications manually in excel to units | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Elisa Latona | elisa.latona@it.sasol.com | Francesco Geradi; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | francesco.geradi@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20623 | STRIVE.R2.MC1.2384.1277.1.1145.47.7 | N | N | N | Planned |  | Train users how to use excel sheets for manually capturing maintenance notifications | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Elisa Latona | elisa.latona@it.sasol.com | Francesco Geradi; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | francesco.geradi@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20624 | STRIVE.R2.MC1.2384.1277.1.1145.47.8 | N | N | N | Planned |  | Share storage location of Excel Sheet for manually capturing maintenance notifications with users | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Elisa Latona | elisa.latona@it.sasol.com | Francesco Geradi; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | francesco.geradi@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20625 | STRIVE.R2.MC1.2384.1277.1.1145.47.9 | N | N | N | Planned |  | Limit goods movements for spare parts (ERSA materials) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | ; Matteo Bartesaghi; Elisa Latona; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Luca Capurro; Sven Gelking; Sergio; Joseph Barber | ; Matteo.Bartesaghi@it.sasol.com; elisa.latona@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; luca.capurro@it.sasol.com; sven.gelking@de.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20626 | STRIVE.R2.MC1.2384.1277.1.1145.47.10 | N | N | N | Planned |  | Limit creation of New Notifications in the existing system for P4 and stop creation for P8 | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Guglielmo Arrabito; Antonio Tulumello; Mauro Congiu; Dhruv Kansal; Sven Gelking; Mousikta chanda; USI STRIVE CUTOVER; Elisa Latona; Sergio; Joseph Barber | Guglielmo.Arrabito@it.sasol.com; Antonio.Tulumello@it.sasol.com; Mauro.Congiu@it.sasol.com; dhkansal@deloitte.com; sven.gelking@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
95087 | STRIVE.R2.MC1.2384.1277.1.1145.47.11 | N | N | N | Planned |  | Maintain Authorization for Bucket and Item | 5 hrs | 2025-09-20 08:00 | 2025-09-20 13:01 | Elisa Latona | elisa.latona@it.sasol.com | Mythili; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Brink du Preez; Thomas Eifert; Robert Nock; Stefan Liechart | myboyapati@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; brink.dupreez@de.sasol.com; thomas.eifert@de.sasol.com; robert.nock@de.sasol.com; stefan.leichert@de.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 13:01
20627 | STRIVE.R2.MC1.2384.1277.1.1145.58 | [5 empty] | IBP | 1415.43 hrs | 2025-09-20 08:00 | 2025-11-18 11:22 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-11-18 11:22
20628 | STRIVE.R2.MC1.2384.1277.1.1145.58.1 | N | N | N | Planned |  | Support pre-orders and/or prebuild (and/or prioritize material) - earlier orders will show up in order book and planned/scheduled accordingly. Early vessel arrivals will be planned/scheduled based on newest arrival date provided. Part of normal planning/s | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Marcello Trapani | marcello.trapani@it.sasol.com | Vito Piscopiello; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Rajat Sahgal | vito.piscopiello@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; rasahgal@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20629 | STRIVE.R2.MC1.2384.1277.1.1145.58.2 | N | N | N | Planned |  | freeze production plan (communicate to plants) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Marcello Trapani | marcello.trapani@it.sasol.com | Vito Piscopiello; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Rajat Sahgal | vito.piscopiello@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; rasahgal@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20630 | STRIVE.R2.MC1.2384.1277.1.1145.58.3 | N | N | N | Planned |  | Setup profiles, pyramids. Update manual upload files with new S/4 numbers and load into OMP PROD. DP. | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Elisa Sasco | elisa.sasco@it.sasol.com | Chantelle Crause; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | chantelle.crause@sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20631 | STRIVE.R2.MC1.2384.1277.1.1145.58.4 | N | N | N | Planned |  | Inter site movements - plan receipts and sends to occur before or after black-out (try and prevent sending/receiving to other sites over the black-out weekend) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Marcello Trapani | marcello.trapani@it.sasol.com | Vito Piscopiello; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Rajat Sahgal | vito.piscopiello@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; rasahgal@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20632 | STRIVE.R2.MC1.2384.1277.1.1145.58.5 | N | N | N | Planned |  | Run all connectors and interfaces to sync data in all systems. Update interfaces with new mappings where needed. | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Edurado | eduardo.gouveia@us.sasol.com | USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Rajat Sahgal | usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; rasahgal@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20633 | STRIVE.R2.MC1.2384.1277.1.1145.58.6 | N | N | N | Planned |  | Setup profiles, pyramids, and update manual material numbers in the continuous production framework. Update manual upload files with new S/4 numbers and load into OMP PROD. SP. | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Marcello Trapani | marcello.trapani@it.sasol.com | Sandrilka; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sandrika.chetty@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20634 | STRIVE.R2.MC1.2384.1277.1.1145.65 | [5 empty] | R2P | 798.78 hrs | 2025-09-20 08:00 | 2025-10-23 17:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-23 17:00
20635 | STRIVE.R2.MC1.2384.1277.1.1145.65.1 | N | N | N | Planned |  | Identify open documents which can be closed before blackout | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Jorg | hansjorg.becker@de.sasol.com | Claudiu; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Dr.Jürgen Heinrichs; Torsten Freydt; Jay Saini | cljipa@deloitte.de; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; Juergen.Heinrichs@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; jaysaini4@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20636 | STRIVE.R2.MC1.2384.1277.1.1145.65.2 | N | N | N | Planned |  | Open and planned Sales orders (for the blackout time) from Customer Fulfiment and P&O in Excel (Terranova - extract from EASCON) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Rob Hall; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dr.Jürgen Heinrichs | rob.hall@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Juergen.Heinrichs@de.sasol.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20637 | STRIVE.R2.MC1.2384.1277.1.1145.65.3 | N | N | N | Planned |  | Align delievery dates of raw materials including all documents | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Vito Piscopiello | vito.piscopiello@it.sasol.com | Marino Deceglia; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Dr.Jürgen Heinrichs | marino.deceglia@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; Juergen.Heinrichs@de.sasol.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20638 | STRIVE.R2.MC1.2384.1277.1.1145.65.4 | N | N | N | Planned |  | Provide shipping documents (from suppliers, for customers) in advance | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Marino Deceglia | marino.deceglia@it.sasol.com | Michele Imbriani; Dr.Jürgen Heinrichs; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; Juergen.Heinrichs@de.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20639 | STRIVE.R2.MC1.2384.1277.1.1145.65.5 | N | N | N | Planned |  | Download and save as PDF all relevant SDS for sending to customer in alignment with Production plan | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Klaus | klaus.heitkamp@de.sasol.com | Dhruv Kansal; Dr.Jürgen Heinrichs; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; Juergen.Heinrichs@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20640 | STRIVE.R2.MC1.2384.1277.1.1145.65.6 | N | N | N | Planned |  | Print out of DG labels in alignment with production plan | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Giuseppe Blundo | giuseppe.blundo@it.sasol.com | Massimo Polledri; Dhruv Kansal; USI STRIVE CUTOVER; Dr.Jürgen Heinrichs | massimo.polledri@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; Juergen.Heinrichs@de.sasol.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20641 | STRIVE.R2.MC1.2384.1277.1.1145.65.7 | N | N | N | Planned |  | Mapping of existing stock levels to the new organisational structure (new storage locations will be added) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Jorg | hansjorg.becker@de.sasol.com | Francesco Geradi; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Dr.Jürgen Heinrichs; Torsten Freydt; Jay Saini | francesco.geradi@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; Juergen.Heinrichs@de.sasol.com; Torsten.Freydt-Olek@de.sasol.com; jaysaini4@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20642 | STRIVE.R2.MC1.2384.1277.1.1145.73 | [5 empty] | S2P | 798.78 hrs | 2025-09-20 08:00 | 2025-10-23 17:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-23 17:00
20643 | STRIVE.R2.MC1.2384.1277.1.1145.73.1 | N | N | N | Planned |  | Contracts / Outline Agreements Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20644 | STRIVE.R2.MC1.2384.1277.1.1145.73.2 | N | N | N | Planned |  | Purchase Info Records Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20645 | STRIVE.R2.MC1.2384.1277.1.1145.73.3 | N | N | N | Planned |  | Purchase Requisitions Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20646 | STRIVE.R2.MC1.2384.1277.1.1145.73.4 | N | N | N | Planned |  | Purchase Orders / Scheduling Agreements / Subcontracting Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20647 | STRIVE.R2.MC1.2384.1277.1.1145.73.5 | N | N | N | Planned |  | Goods Receipts (process invoice) Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20648 | STRIVE.R2.MC1.2384.1277.1.1145.73.6 | N | N | N | Planned |  | Service Entries (process invoice) Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20649 | STRIVE.R2.MC1.2384.1277.1.1145.73.7 | N | N | N | Planned |  | Unaccepted Service Entries Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20650 | STRIVE.R2.MC1.2384.1277.1.1145.73.8 | N | N | N | Planned |  | Suppliers/Vendors Data Validation/Data Cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20651 | STRIVE.R2.MC1.2384.1277.1.1145.73.9 | N | N | N | Planned |  | Service Masters data validation/data cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20652 | STRIVE.R2.MC1.2384.1277.1.1145.73.10 | N | N | N | Planned |  | Material Masters Data Validation/Data cleansing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20653 | STRIVE.R2.MC1.2384.1277.1.1145.73.11 | N | N | N | Planned |  | Supplier Enablement: Business to begin the process of extracting contracts from legacy ECC and storing in central location for Coupa upload | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20654 | STRIVE.R2.MC1.2384.1277.1.1145.73.12 | N | N | N | Planned |  | Continuity Plan Sign Off | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20655 | STRIVE.R2.MC1.2384.1277.1.1145.73.13 | N | N | N | Planned |  | Create Hold Register(s) for Business to populate during Black-Out | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Evan Rademeyer | evan.rademeyer@us.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20656 | STRIVE.R2.MC1.2384.2510 | [5 empty] | Blackout | 96.68 hrs | 2025-09-20 08:00 | 2025-09-24 08:57 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-24 08:57
20657 | STRIVE.R2.MC1.2384.2510.1 | [5 empty] | MOR | 798.78 hrs | 2025-09-20 08:00 | 2025-10-23 17:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-23 17:00
20658 | STRIVE.R2.MC1.2384.2510.1.1 | N | N | N | Planned |  | Manage notification creation in excel | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Guglielmo Arrabito; Antonio Tulumello; Mauro Congiu; Dhruv Kansal; Sven Gelking; Mousikta chanda; USI STRIVE CUTOVER; Sergio; Elisa Latona; Joseph Barber | Guglielmo.Arrabito@it.sasol.com; Antonio.Tulumello@it.sasol.com; Mauro.Congiu@it.sasol.com; dhkansal@deloitte.com; sven.gelking@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20659 | STRIVE.R2.MC1.2384.2510.3 |  |  |  | Complete |  | P2C (Required for Production Cutover) | 798.78 hrs | 2025-09-20 08:00 | 2025-10-23 17:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-23 17:00
20660 | STRIVE.R2.MC1.2384.2510.3.1 | Y | Y | Y | Complete |  | Update of black out progress for customer fulfilment& logistics | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Rob Hall; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | rob.hall@sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20661 | STRIVE.R2.MC1.2384.2510.3.2 | Y | Y | Y | Complete |  | Manual sales ordercreation, product confirmation | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria teresa; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | mariateresa.denti@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20662 | STRIVE.R2.MC1.2384.2510.3.3 | Y | Y | Y | Complete |  | Manual order collection during blackout | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria teresa; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | mariateresa.denti@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20663 | STRIVE.R2.MC1.2384.2510.3.4 | Y | Y | Y | Complete |  | Daily product availability fo sale provided by Inventory Manangement | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Michele Imbriani; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20664 | STRIVE.R2.MC1.2384.2510.3.5 | Y | Y | Y | Complete |  | Manually validate prices | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria teresa; Dhruv Kansal; Rob Hall; Mousikta chanda; USI STRIVE CUTOVER | mariateresa.denti@it.sasol.com; dhkansal@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20665 | STRIVE.R2.MC1.2384.2510.9 |  |  |  | Complete |  | R2D (Not relevant for MC1) | 798.78 hrs | 2025-09-20 08:00 | 2025-10-23 17:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-23 17:00
20666 | STRIVE.R2.MC1.2384.2510.9.1 | Y | Y | Y | Complete |  | Management incoming invoices during blackout period (set up of mailbox, entry channels) for incomning invoices during blackout) (Not relevant for MC1) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Dhruv Kansal | dhkansal@deloitte.com | Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20667 | STRIVE.R2.MC1.2384.2510.9.2 | Y | Y | Y | Complete |  | Release new standard cost estimates with validity 01.04.2025 (Not relevant for MC1) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20668 | STRIVE.R2.MC1.2384.2510.9.3 | Y | Y | Y | Complete |  | Check: Load inventory to the target (only quantity, without value) with posting date 01.03.2025 is complete (Not relevant for MC1) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Mousikta chanda; Dhruv Kansal; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20669 | STRIVE.R2.MC1.2384.2510.13 | [5 empty] | R2P | 2282.5 hrs | 2025-09-20 08:00 | 2025-12-24 16:51 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-12-24 16:51
20670 | STRIVE.R2.MC1.2384.2510.13.1 | N | N | N | Planned |  | Communicate to units: Maintenance Notification: Limitation to a minimum | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Guglielmo Arrabito | Guglielmo.Arrabito@it.sasol.com | Antonio Tulumello; Dhruv Kansal; Dr.Jürgen Heinrichs; Mousikta chanda; USI STRIVE CUTOVER | Antonio.Tulumello@it.sasol.com; dhkansal@deloitte.com; Juergen.Heinrichs@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20671 | STRIVE.R2.MC1.2384.2510.13.2 | N | N | N | Planned |  | Reconciliation of consumptions of rawmaterial and production volumes out of MES after 00:00 h on 01.03.2025 to enable month closing | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Guglielmo Arrabito | Guglielmo.Arrabito@it.sasol.com | Antonio Tulumello; Dhruv Kansal; Dr.Jürgen Heinrichs; Mousikta chanda; USI STRIVE CUTOVER | Antonio.Tulumello@it.sasol.com; dhkansal@deloitte.com; Juergen.Heinrichs@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20672 | STRIVE.R2.MC1.2384.2510.16 | [5 empty] | S2P | 408.35 hrs | 2025-09-20 08:00 | 2025-10-07 09:29 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 09:29
20673 | STRIVE.R2.MC1.2384.2510.16.1 | N | N | N | Planned |  | Hold Register - New / Change Purchase Requisitions / Purchase Order's | 3.02 hrs | 2025-09-20 08:00 | 2025-09-20 11:01 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:01
20674 | STRIVE.R2.MC1.2384.2510.16.2 | N | N | N | Planned |  | Hold Register - New / Change Supplier Master Data | 3.03 hrs | 2025-09-20 08:00 | 2025-09-20 11:02 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:02
20675 | STRIVE.R2.MC1.2384.2510.16.3 | N | N | N | Planned |  | Hold Register - New / Change Material and Service Master | 3.03 hrs | 2025-09-20 08:00 | 2025-09-20 11:02 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:02
20676 | STRIVE.R2.MC1.2384.2510.16.4 | N | N | N | Planned |  | Hold Register - New / Change Contracts | 3.03 hrs | 2025-09-20 08:00 | 2025-09-20 11:02 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:02
20677 | STRIVE.R2.MC1.2384.2510.16.5 | N | N | N | Planned |  | Hold Register - New Sourcing Events | 3.03 hrs | 2025-09-20 08:00 | 2025-09-20 11:02 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:02
20678 | STRIVE.R2.MC1.2384.2510.16.6 | N | N | N | Planned |  | Hold Register - New Unaccepted Service Entry | 3.03 hrs | 2025-09-20 08:00 | 2025-09-20 11:02 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:02
20679 | STRIVE.R2.MC1.2384.2510.16.7 | N | N | N | Planned |  | Final Goods Receipts/Issues | 3 hrs | 2025-09-20 08:00 | 2025-09-20 11:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:00
20680 | STRIVE.R2.MC1.2384.2510.24 | [5 empty] | SDI | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20681 | STRIVE.R2.MC1.2384.2510.24.1 | N | N | N | Planned |  | Swap of the Target URLs in SDI Portal | 2.5 hrs | 2025-09-20 08:00 | 2025-09-20 10:30 | Chiara Cameroni | chiara.cameroni@it.sasol.com | Yaswanth Kumar; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol Infrastructure |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:30
20682 | STRIVE.R2.MC1.2384.2536 | [5 empty] | Post-Cutover | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20683 | STRIVE.R2.MC1.2384.2536.1 | [5 empty] | Smoke Test | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20684 | STRIVE.R2.MC1.2384.2536.1.1 | [5 empty] | Integration | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20685 | STRIVE.R2.MC1.2384.2536.1.1.1 | [5 empty] | MDG | 72.78 hrs | 2025-09-20 08:00 | 2025-09-23 08:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 08:59
20686 | STRIVE.R2.MC1.2384.2536.1.1.1.1 | N | N | N | Planned |  | Perform smoke test-MDG_I_180 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Tulika Pal | tupal@deloitte.com | Rajat Sharma; ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | rajatsharma67@deloitte.com; ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19155 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20687 | STRIVE.R2.MC1.2384.2536.1.1.1.2 | N | N | N | Planned |  | Perform smoke test-MDG_I_170 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Tulika Pal | tupal@deloitte.com | Biney; Pragyesh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | bkaur@deloitte.de; pkumargoyal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 19146 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20688 | STRIVE.R2.MC1.2384.2536.1.1.1.3 | N | N | N | Planned |  | Perform smoke test-MDG_I_210 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Rajat Sharma | rajatsharma67@deloitte.com | Tulika Pal; ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | tupal@deloitte.com; ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MDG |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20689 | STRIVE.R2.MC1.2384.2536.1.1.5 | [5 empty] | S/4HANA-COUPA (Placeholder for Wave 1 Interfaces) | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20690 | STRIVE.R2.MC1.2384.2536.1.1.5.1 | N | N | N | Planned |  | Upload approval chains in prod | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Rahul Sengupta | rahusengupta@deloitte.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20691 | STRIVE.R2.MC1.2384.2536.1.1.5.2 | [5 empty] | S2P_I_009-Integration of PR created from Maintenance Order from SAP to Coupa_v.01 | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20692 | STRIVE.R2.MC1.2384.2536.1.1.5.2.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_009 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami Nair | pounair@deloitte.com | Yaswanth; Naga reddy; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20328 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20693 | STRIVE.R2.MC1.2384.2536.1.1.5.4 | [5 empty] | S2P_I_010_Integrate MRP Purchase Requisitions created in S4 to Coupa | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20694 | STRIVE.R2.MC1.2384.2536.1.1.5.4.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_010 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami Nair | pounair@deloitte.com | Yaswanth; Naga reddy; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20332 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20695 | STRIVE.R2.MC1.2384.2536.1.1.5.6 | [5 empty] | S2P_I_016_Purchase Order changes done in Coupa to S/4 HANA | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20696 | STRIVE.R2.MC1.2384.2536.1.1.5.6.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_016 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami Nair | pounair@deloitte.com | Yaswanth; Naga reddy; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20336 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20697 | STRIVE.R2.MC1.2384.2536.1.1.5.8 | [5 empty] | S2P_I_017_Purchase Order Cancelled in Coupa to S/4 | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20698 | STRIVE.R2.MC1.2384.2536.1.1.5.8.1 | N | N | N | Planned |  | Perform smoke test-S2P_I_017 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami Nair | pounair@deloitte.com | Yaswanth; Naga reddy; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20340 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20699 | STRIVE.R2.MC1.2384.2536.1.1.5.10 | [5 empty] | S2P_I_018-PO created in Coupa to S/4 HANA | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20700 | STRIVE.R2.MC1.2384.2536.1.1.5.10.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_018 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami Nair | pounair@deloitte.com | Yaswanth; Naga reddy; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20344 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20701 | STRIVE.R2.MC1.2384.2536.1.1.5.12 | [5 empty] | S2P_I_019-Integrate Ok2Pay file from Coupa to S4 (Non PO Invoice, PO Invoice, Credit Memos) | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20702 | STRIVE.R2.MC1.2384.2536.1.1.5.12.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_019 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Akshat Pradeep | akspradeep@deloitte.com | Yaswanth; Naga reddy; Saurabh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; saurabhkumar397@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20348 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20703 | STRIVE.R2.MC1.2384.2536.1.1.5.14 | [5 empty] | S2P_I_020-WBS Elements Created in S4 to Coupa | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20704 | STRIVE.R2.MC1.2384.2536.1.1.5.14.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_020 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Yaswanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com; usisasols2p@deloitte.com | S2P | 20352 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20705 | STRIVE.R2.MC1.2384.2536.1.1.5.16 | [5 empty] | S2P_I_022-Work Orders Created in S4 to Coupa | 48.87 hrs | 2025-09-20 08:00 | 2025-09-22 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:00
20706 | STRIVE.R2.MC1.2384.2536.1.1.5.16.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_022 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Rabbani | skhadarmohammadra@deloitte.com | Yaswanth; Naga reddy; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Saurabh Kumar; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; saurabhkumar397@deloitte.com; usisasols2p@deloitte.com | S2P | 20356 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20707 | STRIVE.R2.MC1.2384.2536.1.1.5.18 | [5 empty] | S2P_I_023-Integrate Payment status from S/4 to Coupa in case of Payment processed successfully and payment reversals scenarios | 49.85 hrs | 2025-09-20 08:00 | 2025-09-22 09:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:59
20708 | STRIVE.R2.MC1.2384.2536.1.1.5.18.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_023 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami | pounair@deloitte.com | Yaswanth; Naga reddy; Pragyesh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; pkumargoyal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20360 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20709 | STRIVE.R2.MC1.2384.2536.1.1.5.20 | [5 empty] | S2P_I_024 - Integration of Receipt from SAP S4 HANA to Coupa | 72.78 hrs | 2025-09-20 08:00 | 2025-09-23 08:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 08:59
20710 | STRIVE.R2.MC1.2384.2536.1.1.5.20.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_024 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami | pounair@deloitte.com | Yaswanth; Naga reddy; Riya; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; riychoudhary@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20364 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20711 | STRIVE.R2.MC1.2384.2536.1.1.5.22 | [5 empty] | S2P_I_025 - Integration of Receipt from Coupa to S4 | 72.78 hrs | 2025-09-20 08:00 | 2025-09-23 08:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 08:59
20712 | STRIVE.R2.MC1.2384.2536.1.1.5.22.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_025 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami | pounair@deloitte.com | Yaswanth; Naga reddy; ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | myakumar@deloitte.com; nnagasubbareddy@deloitte.com; ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20368 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20713 | STRIVE.R2.MC1.2384.2536.1.1.5.24 | [5 empty] | S2P_I_035-Integration of Exchange Rates from S4 to Coupa | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20714 | STRIVE.R2.MC1.2384.2536.1.1.5.24.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_035 | 0.05 hrs | 2025-09-20 08:00 | 2025-09-20 08:03 | Pournami | pounair@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20372 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:03
20715 | STRIVE.R2.MC1.2384.2536.1.1.5.26 | [5 empty] | S2P_I_043_Integration of POs from S4 to Coupa | 49.85 hrs | 2025-09-20 08:00 | 2025-09-22 09:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:59
20716 | STRIVE.R2.MC1.2384.2536.1.1.5.26.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_043 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami | pounair@deloitte.com | Pragyesh; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | pkumargoyal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P | 20376 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20717 | STRIVE.R2.MC1.2384.2536.1.1.5.28 | [5 empty] | S2P_I_026 Vendor Invoices | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20718 | STRIVE.R2.MC1.2384.2536.1.1.5.28.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_026 | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Adelin Apotsu | aapostu@deloittece.com | Aparajita Mukherjee; Milton; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; ; S2P Team | apamukherjee@deloitte.com; miltjones@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ; usisasols2p@deloitte.com | S2P_Coupa |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20719 | STRIVE.R2.MC1.2384.2536.1.1.5.30 | [5 empty] | S2P_I_036 Budget Check | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20720 | STRIVE.R2.MC1.2384.2536.1.1.5.30.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_036 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pournami | pounair@deloitte.com | Pragyesh Kumar; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | pkumargoyal@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | S2P_Coupa |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20721 | STRIVE.R2.MC1.2384.2536.1.1.37 | [5 empty] | S/4HANA-OilRight (Placeholder for Wave 1 Interfaces) | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20722 | STRIVE.R2.MC1.2384.2536.1.1.37.1 | [5 empty] | R2P_I_010-Inbound_GoodsReceipts_OilRights to S4 | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20723 | STRIVE.R2.MC1.2384.2536.1.1.37.1.1 | N | N | N | Planned |  | Perform smoke test - R2P_I_010 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Claudiu | cljipa@deloitte.de | Sonali Prakash; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | soprakash@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20724 | STRIVE.R2.MC1.2384.2536.1.1.37.3 | [5 empty] | R2P_I_011-STRIVE_R2P_BulkMaterials_to_OilRight | 72.78 hrs | 2025-09-20 08:00 | 2025-09-23 08:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 08:59
20725 | STRIVE.R2.MC1.2384.2536.1.1.37.3.1 | N | N | N | Planned |  | Perform smoke test - R2P_I_011 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Claudiu | cljipa@deloitte.de | Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20726 | STRIVE.R2.MC1.2384.2536.1.1.37.5 | [5 empty] | R2P_I_013-STRIVE_R2P_Deliveries_to_OILRightt | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20727 | STRIVE.R2.MC1.2384.2536.1.1.37.5.1 | N | N | N | Planned |  | Perform smoke test - R2P_I_013 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Claudiu | cljipa@deloitte.de | Aman Anand; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | amananand2@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20728 | STRIVE.R2.MC1.2384.2536.1.1.44 | [5 empty] | S/4HANA-Safework (Placeholder for Wave 1 Interfaces) | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20729 | STRIVE.R2.MC1.2384.2536.1.1.44.1 | [5 empty] | MOR_I_011-Inbound Interface from Safe Work to update work order and operation details in SAP | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20730 | STRIVE.R2.MC1.2384.2536.1.1.44.1.1 | N | N | N | Planned |  | Perform smoke test - MOR_I_011 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Jay Patel | jaypatel6@deloitte.com | ; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | ; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | MOR | 20423 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20731 | STRIVE.R2.MC1.2384.2536.1.1.44.3 | [5 empty] | MOR_I_012-Outbound Interface from SAP to Safe Work to send work order and notification details | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20732 | STRIVE.R2.MC1.2384.2536.1.1.44.3.1 | N | N | N | Planned |  | Perform smoke test - MOR_I_012 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Jay Patel | jaypatel6@deloitte.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Aman Anand | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amananand2@deloitte.com | MOR | 20427 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20733 | STRIVE.R2.MC1.2384.2536.1.1.49 | [5 empty] | S/4HANA-ETRM (Placeholder for Wave 1 Interfaces) | 267.27 hrs | 2025-09-20 08:00 | 2025-10-01 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-01 12:00
20736 | STRIVE.R2.MC1.2384.2536.1.1.49.3 | [5 empty] | S2P_I_041_Integration of POs from ETRM to S4 Hana | 267.27 hrs | 2025-09-20 08:00 | 2025-10-01 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-01 12:00
20737 | STRIVE.R2.MC1.2384.2536.1.1.49.3.1 | N | N | N | Planned |  | Perform smoke test - S2P_I_041 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Siddhesh | sibaraskar@deloitte.com | Sonali Prakash; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; S2P Team | soprakash@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; usisasols2p@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20743 | STRIVE.R2.MC1.2384.2536.1.1.59 | [5 empty] | S/4HANA-SAP PF1 (Placeholder for Wave 1 Interfaces) | 49.85 hrs | 2025-09-20 08:00 | 2025-09-22 09:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:59
20744 | STRIVE.R2.MC1.2384.2536.1.1.59.1 | [5 empty] | R2D_I_001_Exchangerates fetch for daily conversions | 49.85 hrs | 2025-09-20 08:00 | 2025-09-22 09:59 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-22 09:59
20745 | STRIVE.R2.MC1.2384.2536.1.1.59.1.1 | N | N | N | Planned |  | Trigger exchange rates from RSA system | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Roshanlal | rohemwani@deloitte.com | Gurmandeep Singh; Dhruv Kansal; USI STRIVE CUTOVER; Tatiana; Mousikta chanda | gurmandsingh@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; tvinogradova@deloitte.de; mouchanda@deloitte.com | R2D | 20455 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20751 | STRIVE.R2.MC1.2384.2536.1.1.87 | [5 empty] | C4C-PDB (Placeholder for Wave 1 Interfaces) | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20752 | STRIVE.R2.MC1.2384.2536.1.1.87.3 | [5 empty] | P2C_I_027-C4C to PDB Integration via APIM | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20753 | STRIVE.R2.MC1.2384.2536.1.1.87.3.2 | N | N | N | Planned |  | Perform smoke test - P2C_I_027 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pooja navelkar | pooja.navelkar@us.sasol.com | Omkar Ranade; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | omkar.ranade@us.sasol.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | C4C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20759 | STRIVE.R2.MC1.2384.2536.1.1.75 | [5 empty] | IBP (Placeholder for Wave 1 Interfaces) | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20760 | STRIVE.R2.MC1.2384.2536.1.1.75.1 | [5 empty] | Scheduler | 458.12 hrs | 2025-09-20 08:00 | 2025-10-09 11:23 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-09 11:23
20761 | STRIVE.R2.MC1.2384.2536.1.1.75.1.1 | N | N | N | Planned |  | Setup Scheduler and Deploy iflow for IBP Interfaces IBP_I_001, 005, 010, 011 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Yashwanth | myakumar@deloitte.com | ; Naga; Aman Anand; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | ; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20762 | STRIVE.R2.MC1.2384.2536.1.1.75.1.2 | N | N | N | Planned |  | Validate Scheduler and Deployment for IBP Interfaces IBP_I_001, 005, 010, 011 | 1 hrs | 2025-09-20 09:00 | 2025-09-20 10:00 | Yashwanth | myakumar@deloitte.com | ; Naga; Aman Anand; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | ; nnagasubbareddy@deloitte.com; amananand2@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Integration | 20761 |  |  | * | NA | 2025-09-20 09:00 | 2025-09-20 10:00
20763 | STRIVE.R2.MC1.2384.2536.1.1.75.4 | [5 empty] | IBP_I_001 - BW to OMP : Customer Extract | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20764 | STRIVE.R2.MC1.2384.2536.1.1.75.4.1 | N | N | N | Planned |  | Perform smoke test - IBP_I_001 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Edurado | eduardo.gouveia@us.sasol.com | David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rajat Sahgal | david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rasahgal@deloitte.com | IBP | 20501 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20765 | STRIVE.R2.MC1.2384.2536.1.1.75.6 | [5 empty] | IBP_I_005 - BW to OMP : Sales Forecast Extract | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20766 | STRIVE.R2.MC1.2384.2536.1.1.75.6.1 | N | N | N | Planned |  | Perform smoke test - IBP_I_005 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Edurado | eduardo.gouveia@us.sasol.com | David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rajat Sahgal | david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rasahgal@deloitte.com | IBP | 20505 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20767 | STRIVE.R2.MC1.2384.2536.1.1.75.8 | [5 empty] | IBP_I_010 - BW to OMP : Product Extract | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20768 | STRIVE.R2.MC1.2384.2536.1.1.75.8.1 | N | N | N | Planned |  | Perform smoke test -IBP_I_010 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Edurado | eduardo.gouveia@us.sasol.com | David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rajat Sahgal | david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rasahgal@deloitte.com | IBP | 20509 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20769 | STRIVE.R2.MC1.2384.2536.1.1.75.10 | [5 empty] | IBP_I_011 - BW to OMP : Forecast Item Extract | 73.77 hrs | 2025-09-20 08:00 | 2025-09-23 09:58 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-23 09:58
20770 | STRIVE.R2.MC1.2384.2536.1.1.75.10.1 | N | N | N | Planned |  | Perform smoke test - IBP_I_011 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Edurado | eduardo.gouveia@us.sasol.com | David Conradie; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rajat Sahgal | david.conradie1@sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rasahgal@deloitte.com | IBP | 20513 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20771 | STRIVE.R2.MC1.2384.2536.1.88 | [5 empty] | MDG | 623.95 hrs | 2025-09-20 08:00 | 2025-10-16 09:41 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-16 09:41
20772 | STRIVE.R2.MC1.2384.2536.1.88.1 | N | N | N | Planned |  | Smoke Test for Suppliers in Coupa | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Manoj kovilpillai | mmanickrajkovilpi@deloitte.com | Aparajita Mukherjee; Pournami Nair; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; S2P Team | apamukherjee@deloitte.com; pounair@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; usisasols2p@deloitte.com | S2P_Coupa |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20773 | STRIVE.R2.MC1.2384.2536.91 | [5 empty] | MOR | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20774 | STRIVE.R2.MC1.2384.2536.91.1 | N | N | N | Planned |  | Maintain value of checklists characteristics in IW98 | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Vinod Kumar | vinodkumar692@deloitte.com | suyash Chhawala; Dhruv Kansal; USI STRIVE CUTOVER; Jay Patel; Mousikta chanda; Amit Jha | schhawala@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; jaypatel6@deloitte.com; mouchanda@deloitte.com; ajha2@deloitte.no | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20775 | STRIVE.R2.MC1.2384.2536.91.2 | N | N | N | Planned |  | Maintain number ranges for PPM and PM | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Chaitnya; Abhishek Sharma; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20776 | STRIVE.R2.MC1.2384.2536.91.3 | N | N | N | Planned |  | Perform language translations for Portfolio Project management master data objects | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Chaitnya; Abhishek Sharma; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20777 | STRIVE.R2.MC1.2384.2536.91.4 | N | N | N | Planned |  | Provide access to required users for Maintenance Portfolio and NON- Maintenance structure. | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Elisa Latona | elisa.latona@it.sasol.com | Sergio; Joseph Barber; Jay Patel; Amit Jha; Krishna Teja; Mythili; USI STRIVE CUTOVER; Dhruv Kansal; Nikhil Gupta; suyash Chhawala | sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; krishn@deloitte.com; myboyapati@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mrgupta3@deloitte.com; schhawala@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20778 | STRIVE.R2.MC1.2384.2536.91.5 | N | N | N | Planned |  | Update budget for PS migrated projects | 5 hrs | 2025-09-20 08:00 | 2025-09-20 13:01 | Elisa Latona | elisa.latona@it.sasol.com | Sergio; Joseph Barber; Jay Patel; Amit Jha; Krishna Teja; Mythili; USI STRIVE CUTOVER; Dhruv Kansal; Nikhil Gupta; suyash Chhawala | sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; jaypatel6@deloitte.com; ajha2@deloitte.no; krishn@deloitte.com; myboyapati@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mrgupta3@deloitte.com; schhawala@deloitte.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 13:01
20779 | STRIVE.R2.MC1.2384.2536.91.6 | N | N | N | Planned |  | Create Portfolio items for Maintenance Portfolio | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Chaitnya; Abhishek Sharma; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20780 | STRIVE.R2.MC1.2384.2536.91.7 | N | N | N | Planned |  | Create PS projects for Maintenance Portfolio | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Chaitnya; Abhishek Sharma; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20781 | STRIVE.R2.MC1.2384.2536.91.8 | N | N | N | Planned |  | Update the requesting cost center for MOR Maintenance projects | 2 hrs | 2025-09-20 10:00 | 2025-09-20 12:00 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Chaitnya; Abhishek Sharma; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no | MOR | 20780 |  |  | * | NA | 2025-09-20 10:00 | 2025-09-20 12:00
20782 | STRIVE.R2.MC1.2384.2536.91.9 | N | N | N | Planned |  | Update the profit center for MOR Maintenance Projects | 3.35 hrs | 2025-09-20 12:01 | 2025-09-20 15:22 | Gabriele | gabriele.schwemer@de.sasol.com | Clara Mori; ; Krishna Teja; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda; Roshanlal; Tatiana | clara.mori@it.sasol.com; ; krishn@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D | 20781 |  |  | * | NA | 2025-09-20 12:01 | 2025-09-20 15:22
20783 | STRIVE.R2.MC1.2384.2536.91.10 | N | N | N | Planned |  | Maintain link for Portfolio item with Reactive, Proactive, Improvement | 5.78 hrs | 2025-09-20 13:01 | 2025-09-20 18:48 | Mythili | myboyapati@deloitte.com | Krishna Teja; Nikhil Gupta; Jay Patel; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Chaitnya; Abhishek Sharma; Amit Jha | krishn@deloitte.com; mrgupta3@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; csudhakarraut@deloitte.com; abhisheksharma59@deloitte.com; ajha2@deloitte.no | MOR | 20778 |  |  | * | NA | 2025-09-20 13:01 | 2025-09-20 18:48
20784 | STRIVE.R2.MC1.2384.2536.91.11 | N | N | N | Planned |  | Provide MOR Team with XREF: S/4 Equipment to Asset Number | 3 hrs | 2025-09-20 08:00 | 2025-09-20 11:00 | Michaela Schulz | michaela.schulz@de.sasol.com | Hendrik Kamsteeg; Tatiana; Daniel Lohmann; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Roshanlal | hendrik.kamsteeg@de.sasol.com; tvinogradova@deloitte.de; dlohmann@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; rohemwani@deloitte.com | R2D | 19663,20060 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 11:00
20785 | STRIVE.R2.MC1.2384.2536.91.12 | N | N | N | Planned |  | Execute LSMW to update Asset Master in Equipment Master | 5 hrs | 2025-09-20 11:00 | 2025-09-20 16:01 | Abhishek Sharma | abhisheksharma59@deloitte.com | Chaitnya; Amit Jha; suyash Chhawala; Jay Patel; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | csudhakarraut@deloitte.com; ajha2@deloitte.no; schhawala@deloitte.com; jaypatel6@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | MOR | 20784 |  |  | * | NA | 2025-09-20 11:00 | 2025-09-20 16:01
20786 | STRIVE.R2.MC1.2384.2536.104 | [5 empty] | R2P | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20787 | STRIVE.R2.MC1.2384.2536.104.1 | N | N | N | Planned |  | Update STO config with the Vendor / Customer details | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Hans Jorg | hansjorg.becker@de.sasol.com | Amit das; Abhishek Parab; Pamela Mihali; Sheena Gour; Deepika Agarwal; USI STRIVE CUTOVER; Mousikta chanda; Dhruv Kansal; Torsten Freydt; Jay Saini | amitdas3@deloitte.com; abhparab@deloitte.com; pamihali@deloitte.de; shgour@deloitte.com; deepikaagarwal@deloitte.de; usistrivecutover@deloitte.com; mouchanda@deloitte.com; dhkansal@deloitte.com; Torsten.Freydt-Olek@de.sasol.com; jaysaini4@deloitte.com | R2P | 19548,19518 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20788 | STRIVE.R2.MC1.2384.2536.106 | [5 empty] | R2P - QM | 288.05 hrs | 2025-09-20 08:00 | 2025-10-02 08:51 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-02 08:51
20789 | STRIVE.R2.MC1.2384.2536.106.1 | N | N | N | Planned |  | R2P-QM-Create Condition Record - Shipping - Certificate of Analysis | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Pamela Mihali | pamihali@deloitte.de | Abhishek Parab; Dhruv Kansal; USI STRIVE CUTOVER; Amit das; Mousikta chanda; Nilesh Deshpande | abhparab@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; amitdas3@deloitte.com; mouchanda@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20790 | STRIVE.R2.MC1.2384.2536.106.2 | N | N | N | Planned |  | R2P-QM-Mass update - Custom Business Object - Certificate of Analysis | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Abhishek Parab | abhparab@deloitte.com | Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P | 19634,19548 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20791 | STRIVE.R2.MC1.2384.2536.106.3 | N | N | N | Planned |  | R2P-QM - Verify Job for automatic Usage Decision | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Abhishek Parab | abhparab@deloitte.com | Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20792 | STRIVE.R2.MC1.2384.2536.106.4 | N | N | N | Planned |  | R2P-QM - Verify Job for Automatic Email from SAP inbox to Outlook | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Abhishek Parab | abhparab@deloitte.com | Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20793 | STRIVE.R2.MC1.2384.2536.106.5 | N | N | N | Planned |  | R2P-QM - Maintain CBO for Automatic QN from UD | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Pamela Mihali | pamihali@deloitte.de | Abhishek Parab; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | abhparab@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20794 | STRIVE.R2.MC1.2384.2536.106.6 | N | N | N | Planned |  | R2P-QM - Upload certificate profile and assignment | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Pamela Mihali | pamihali@deloitte.de | Abhishek Parab; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | abhparab@deloitte.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P | 19606,19785 |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20795 | STRIVE.R2.MC1.2384.2536.106.7 | N | N | N | Planned |  | R2P-QM - Create Variant for the QM Email outlook | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Abhishek Parab | abhparab@deloitte.com | Pamela Mihali; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Amit das; Nilesh Deshpande | pamihali@deloitte.de; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; amitdas3@deloitte.com; nideshpande@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20796 | STRIVE.R2.MC1.2384.2536.114 | N | N | N | Planned |  | Blackout period | 71.57 hrs | 2025-09-20 08:00 | 2025-09-23 07:45 | Sarah Geboers | sarah.geboers@de.sasol.com | SVEN GRAF; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | sven.graef@de.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Cutover |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-23 07:45
20797 | STRIVE.R2.MC1.2384.2536.115 | [5 empty] | Ramp up | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20798 | STRIVE.R2.MC1.2384.2536.115.1 | [5 empty] | IBP | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20799 | STRIVE.R2.MC1.2384.2536.115.1.1 | N | N | N | Planned |  | Ensure correct inventory levels flowing through all systems | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Edurado | eduardo.gouveia@us.sasol.com | Marcello Trapani; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | marcello.trapani@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20800 | STRIVE.R2.MC1.2384.2536.115.1.2 | N | N | N | Planned |  | Create plans (PLO, STR, PR) in OMP and interface to SAP | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Marcello Trapani | marcello.trapani@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Rajat Sahgal | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; rasahgal@deloitte.com | IBP |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20801 | STRIVE.R2.MC1.2384.2536.115.4 | [5 empty] | MOR | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20802 | STRIVE.R2.MC1.2384.2536.115.4.1 | Y | Y | Y | Complete |  | Migrate manually created maintenance orders (during blackout) to S/4 (Not relevant for MC1) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Adelfo Roccaforte | Adelfo.Roccaforte@it.sasol.com | Matteo Bartesaghi; Luca Capurro; Dhruv Kansal; Sven Gelking; Mousikta chanda; USI STRIVE CUTOVER; Elisa Latona; Sergio; Joseph Barber | Matteo.Bartesaghi@it.sasol.com; luca.capurro@it.sasol.com; dhkansal@deloitte.com; sven.gelking@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; elisa.latona@it.sasol.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20803 | STRIVE.R2.MC1.2384.2536.115.4.2 | N | N | N | Planned |  | Migrate all goods movement recorded during black out period | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | ; Matteo Bartesaghi; Aureliano Muccio; Dhruv Kansal; Sven Gelking; Mousikta chanda; USI STRIVE CUTOVER; Joseph Barber; Sergio; Elisa Latona | ; Matteo.Bartesaghi@it.sasol.com; Aureliano.Muccio@it.sasol.com; dhkansal@deloitte.com; sven.gelking@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; joseph.barber@us.sasol.com; sergio.guzzo@it.sasol.com; elisa.latona@it.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20804 | STRIVE.R2.MC1.2384.2536.115.4.3 | N | N | N | Planned |  | Manually create P8 Notifications in S/4 HANA + notification raised during the black out | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Daniel Bunge | Daniel.Bunge@de.sasol.com | Guglielmo Arrabito; Antonio Tulumello; Mauro Congiu; Dhruv Kansal; Elisa Latona; Mousikta chanda; USI STRIVE CUTOVER; Sergio; Sven Gelking; Joseph Barber | Guglielmo.Arrabito@it.sasol.com; Antonio.Tulumello@it.sasol.com; Mauro.Congiu@it.sasol.com; dhkansal@deloitte.com; elisa.latona@it.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sergio.guzzo@it.sasol.com; sven.gelking@de.sasol.com; joseph.barber@us.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20805 | STRIVE.R2.MC1.2384.2536.115.4.4 | Y | Y | Y | Complete |  | Complete data load for the migrated Portfolio items in S/4 (Not relevant for MC1) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Angelo | Angelo.Sottosanti@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Sven Gelking; Mousikta chanda; Sergio; Joseph Barber; Elisa Latona | dhkansal@deloitte.com; usistrivecutover@deloitte.com; sven.gelking@de.sasol.com; mouchanda@deloitte.com; sergio.guzzo@it.sasol.com; joseph.barber@us.sasol.com; elisa.latona@it.sasol.com | MOR |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20806 | STRIVE.R2.MC1.2384.2536.115.9 |  |  |  | Complete |  | P2C (Required for Production Cutover) | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20807 | STRIVE.R2.MC1.2384.2536.115.9.1 | Y | Y | Y | Complete |  | Update of ramp up progress for customer fulfilment& logistics | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Hans Ringst | hans.ringst@de.sasol.com | Rob Hall; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | rob.hall@sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20808 | STRIVE.R2.MC1.2384.2536.115.9.2 | Y | Y | Y | Complete |  | Post Go-live transaction processing | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Rob Hall | rob.hall@sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20809 | STRIVE.R2.MC1.2384.2536.115.9.3 | Y | Y | Y | Complete |  | Clean sales orders, product confirmation, deliveries | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria teresa; Dhruv Kansal; USI STRIVE CUTOVER; Rob Hall; Mousikta chanda | mariateresa.denti@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20810 | STRIVE.R2.MC1.2384.2536.115.9.4 | Y | Y | Y | Complete |  | Validate the creation of freight orders, freight units in BN4L, TM | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria teresa; Dhruv Kansal; USI STRIVE CUTOVER; Rob Hall; Mousikta chanda | mariateresa.denti@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20811 | STRIVE.R2.MC1.2384.2536.115.9.5 | Y | Y | Y | Complete |  | Create new sales orders, product confirmation, deliveries, post goods issues and billing documents on S4 | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Hans Ringst | hans.ringst@de.sasol.com | Maria teresa; Dhruv Kansal; USI STRIVE CUTOVER; Rob Hall; Mousikta chanda | mariateresa.denti@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20812 | STRIVE.R2.MC1.2384.2536.115.9.6 | Y | Y | Y | Complete |  | Start Logistics loadings for Sales | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; USI STRIVE CUTOVER; Rob Hall; Mousikta chanda | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20813 | STRIVE.R2.MC1.2384.2536.115.9.7 | Y | Y | Y | Complete |  | Start logistics for FCA | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Joern Ladehoff | joern.ladehoff@de.sasol.com | Michele Imbriani; Dhruv Kansal; USI STRIVE CUTOVER; Rob Hall; Mousikta chanda | michele.imbriani@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; rob.hall@sasol.com; mouchanda@deloitte.com | P2C |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20814 | STRIVE.R2.MC1.2384.2536.115.17 | [5 empty] | R2D | 910.02 hrs | 2025-09-20 08:00 | 2025-10-28 08:33 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-28 08:33
20815 | STRIVE.R2.MC1.2384.2536.115.17.1 | N | N | N | Planned |  | Preparation of plan prices for purchased materials (components) forecast prices for March | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20816 | STRIVE.R2.MC1.2384.2536.115.17.2 | N | N | N | Planned |  | Validate the activity rates | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20817 | STRIVE.R2.MC1.2384.2536.115.17.3 | N | N | N | Planned |  | Upload conditions for profit center valuation | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20818 | STRIVE.R2.MC1.2384.2536.115.17.4 | N | N | N | Planned |  | Upload of planned prices | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Jitender Chhabra | jkchhabra.ext@deloitte.com | Tatiana; Alexandra Ruff; Roshanlal Hemwani; ; Hendrik Kamsteeg; Rohit; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | tvinogradova@deloitte.de; aruff@deloitte.de; rohemwani@deloitte.com; ; hendrik.kamsteeg@de.sasol.com; rokashyap@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20819 | STRIVE.R2.MC1.2384.2536.115.17.5 | N | N | N | Planned |  | Run standard cost estimates with validity 01.04.2025 | 2 hrs | 2025-09-20 10:00 | 2025-09-20 12:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D | 20815,20827,20826 |  |  | * | NA | 2025-09-20 10:00 | 2025-09-20 12:00
20820 | STRIVE.R2.MC1.2384.2536.115.17.6 | N | N | N | Planned |  | Validate the marked prices for all the materials | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Clara Mori | clara.mori@it.sasol.com | ; Francois Conradie; Hendrik Kamsteeg; Michaela; Alexandra Ruff; Roshanlal; Tatiana; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | ; francois.conradie@de.sasol.com; hendrik.kamsteeg@de.sasol.com; michaela.schulz@de.sasol.com; aruff@deloitte.de; rohemwani@deloitte.com; tvinogradova@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20821 | STRIVE.R2.MC1.2384.2536.115.17.7 | N | N | N | Planned |  | Mark new standard cost estimates for release | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20822 | STRIVE.R2.MC1.2384.2536.115.17.8 | N | N | N | Planned |  | Upload of inventory values using manual GL accounts to the target as per 31.03.2025 | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Oluf baren | oluf.braren@de.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20823 | STRIVE.R2.MC1.2384.2536.115.17.9 | N | N | N | Planned |  | Reversal of migrated GL entries as per 01.04.2025 offsetting the revaluation | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Dhruv Kansal | dhkansal@deloitte.com | USI STRIVE CUTOVER; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | usistrivecutover@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20824 | STRIVE.R2.MC1.2384.2536.115.17.10 | Y | Y | Y | Complete |  | Validate Bank statement closure from March, 2025 (Not relevant for MC1) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Patrizia | patrizia.vergani@it.sasol.com | Oluf baren; Francois Conradie; Michaela; Dhaval; Nirali Trivedi; Tatiana; Roshanlal; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | oluf.braren@de.sasol.com; francois.conradie@de.sasol.com; michaela.schulz@de.sasol.com; dhavalshah@deloitte.com; nirtrivedi@deloitte.com; tvinogradova@deloitte.de; rohemwani@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20825 | STRIVE.R2.MC1.2384.2536.115.17.11 | Y | Y | Y | Complete |  | Penny testing in production via MBC (Not relevant for MC1) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Vergani Patrizia | patrizia.vergani@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; Francois Conradie; Roshanlal; Tatiana | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20826 | STRIVE.R2.MC1.2384.2536.115.17.12 | N | N | N | Planned |  | Upload conditions for profit center valuation (internal transfer prices January 25) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20827 | STRIVE.R2.MC1.2384.2536.115.17.13 | N | N | N | Planned |  | Take over of planned activity rates for January 25 | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Clara Mori | clara.mori@it.sasol.com | Christian Canale; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | christian.canale@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20829 | STRIVE.R2.MC1.2384.2536.115.17.15 | Y | Y | Y | Complete |  | Perform penny-test via INBIZ portal for payroll file from INAZ (Not relevant for MC1) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Maria Lusardi | maria.lusardi@it.sasol.com | Patrizia; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Francois Conradie; Roshanlal; Tatiana | patrizia.vergani@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20830 | STRIVE.R2.MC1.2384.2536.115.17.16 | Y | Y | Y | Complete |  | Early Payments Check and Processing (reducing risk of delayed payments in new S/4) (Not relevant for MC1) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Vergani Patrizia | patrizia.vergani@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda; ; Francois Conradie; Roshanlal; Tatiana | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com; ; francois.conradie@de.sasol.com; rohemwani@deloitte.com; tvinogradova@deloitte.de | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20831 | STRIVE.R2.MC1.2384.2536.115.34 | [5 empty] | R2P | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20832 | STRIVE.R2.MC1.2384.2536.115.34.1 | N | N | N | Planned |  | Production schedule | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Salvatore Noto | salvatore.noto@it.sasol.com | Vito Piscopiello; Dhruv Kansal; Dr.Jürgen Heinrichs; Mousikta chanda; USI STRIVE CUTOVER | vito.piscopiello@it.sasol.com; dhkansal@deloitte.com; Juergen.Heinrichs@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20833 | STRIVE.R2.MC1.2384.2536.115.34.2 | N | N | N | Planned |  | Receive Planned orders | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Guglielmo Arrabito | Guglielmo.Arrabito@it.sasol.com | Antonio Tulumello; Dhruv Kansal; Dr.Jürgen Heinrichs; Mousikta chanda; USI STRIVE CUTOVER | Antonio.Tulumello@it.sasol.com; dhkansal@deloitte.com; Juergen.Heinrichs@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20834 | STRIVE.R2.MC1.2384.2536.115.34.3 | N | N | N | Planned |  | Create Process orders | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Guglielmo Arrabito | Guglielmo.Arrabito@it.sasol.com | Antonio Tulumello; Dhruv Kansal; Dr.Jürgen Heinrichs; Mousikta chanda; USI STRIVE CUTOVER | Antonio.Tulumello@it.sasol.com; dhkansal@deloitte.com; Juergen.Heinrichs@de.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20835 | STRIVE.R2.MC1.2384.2536.115.34.4 | N | N | N | Planned |  | Create Inspection plan (QC) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Francesco Geradi | francesco.geradi@it.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Dr.Jürgen Heinrichs | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; Juergen.Heinrichs@de.sasol.com | R2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20836 | STRIVE.R2.MC1.2384.2536.115.39 | [5 empty] | S2P | 410.87 hrs | 2025-09-20 08:00 | 2025-10-07 12:00 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-10-07 12:00
20837 | STRIVE.R2.MC1.2384.2536.115.39.1 | N | N | N | Planned |  | Hold Register Transfer | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20838 | STRIVE.R2.MC1.2384.2536.115.39.2 | N | N | N | Planned |  | Sign off Hold Register Transfer Completion | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Andrea Zucca | Andrea.Zucca@it.sasol.com | Dhruv Kansal; Evan Rademeyer; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; evan.rademeyer@us.sasol.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20839 | STRIVE.R2.MC1.2384.2536.115.39.3 | N | N | N | Planned |  | Balance Sheet Register Handover from R2D to S2P AP reference | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Francois Conradie | francois.conradie@de.sasol.com | Evan Rademeyer; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | evan.rademeyer@us.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20840 | STRIVE.R2.MC1.2384.2536.115.39.4 | N | N | N | Planned |  | Coupa PO Extract with Legacy PO for S2P AP reference | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Evan Rademeyer | evan.rademeyer@us.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20841 | STRIVE.R2.MC1.2384.2536.115.39.5 | N | N | N | Planned |  | Hold Register Goods Receipt/Goods Issue | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Evan Rademeyer | evan.rademeyer@us.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20842 | STRIVE.R2.MC1.2384.2536.160 | N | N | N | Planned |  | AP TEAM to post and process as many invoices as possible into the AP1 before the go live | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Adelin Apotsu | aapostu@deloittece.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20843 | STRIVE.R2.MC1.2384.2536.161 | N | N | N | Planned |  | Set up an automatic email notification for all incoming invoices to the Italian mailbox, informing suppliers that invoices for Italian entities should be sent to Coupa new Email inbox is (invoices@sasolchem.coupahost.com) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Adelin Apotsu | aapostu@deloittece.com | S2P Team; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | usisasols2p@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | S2P |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20844 | STRIVE.R2.MC1.2384.2536.162 | Y | Y | Y | Complete |  | Create entry in V_FAGL_TRVOR (Not relevant for MC1) | 2 hrs | 2025-09-20 08:00 | 2025-09-20 10:00 | Michaela | michaela.schulz@de.sasol.com | Oluf baren; Alexandra Ruff; Roshanlal Hemwani; Tatiana; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | oluf.braren@de.sasol.com; aruff@deloitte.de; rohemwani@deloitte.com; tvinogradova@deloitte.de; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | R2D |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 10:00
20845 | STRIVE.R2.MC1.2384.2536.163 | [5 empty] | Legacy system AP1 | 1221 hrs | 2025-09-20 08:00 | 2025-11-10 08:24 | [8 empty] | * | NA | 2025-09-20 08:00 | 2025-11-10 08:24
20846 | STRIVE.R2.MC1.2384.2536.163.1 | N | N | N | Planned |  | lock userID MOR (detailed list required) | 0.15 hrs | 2025-09-20 08:00 | 2025-09-20 08:09 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:09
20847 | STRIVE.R2.MC1.2384.2536.163.2 | N | N | N | Planned |  | lock userID R2P (detailed list required) | 0.13 hrs | 2025-09-20 08:00 | 2025-09-20 08:08 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:08
20848 | STRIVE.R2.MC1.2384.2536.163.3 | N | N | N | Planned |  | lock userID P2C (detailed list required) | 0.15 hrs | 2025-09-20 08:00 | 2025-09-20 08:09 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:09
20849 | STRIVE.R2.MC1.2384.2536.163.4 | N | N | N | Planned |  | lock userID S2P (detailed list required) | 0.15 hrs | 2025-09-20 08:00 | 2025-09-20 08:09 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:09
20850 | STRIVE.R2.MC1.2384.2536.163.5 | N | N | N | Planned |  | lock userID IBP (detailed list required) | 0.15 hrs | 2025-09-20 08:00 | 2025-09-20 08:09 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:09
20851 | STRIVE.R2.MC1.2384.2536.163.6 | N | N | N | Planned |  | Lock userID R2D (detailed list required) | 0 hrs | 2025-09-20 08:00 | 2025-09-20 08:00 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 08:00
20852 | STRIVE.R2.MC1.2384.2536.163.7 | N | N | N | Planned |  | Reboot the system | 0.17 hrs | 2025-09-20 08:09 | 2025-09-20 08:19 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER; Sarah Geboers | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com; sarah.geboers@de.sasol.com | Sasol GRC | 20846,20847,20848,20849,20850,20851 |  |  | * | NA | 2025-09-20 08:09 | 2025-09-20 08:19
20853 | STRIVE.R2.MC1.2384.2536.163.8 | N | N | N | Planned |  | Display only userID MOR (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20854 | STRIVE.R2.MC1.2384.2536.163.9 | N | N | N | Planned |  | Display only userID R2D (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20855 | STRIVE.R2.MC1.2384.2536.163.10 | N | N | N | Planned |  | Display only userID S2P (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20856 | STRIVE.R2.MC1.2384.2536.163.11 | N | N | N | Planned |  | Display only userID P2C (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20857 | STRIVE.R2.MC1.2384.2536.163.12 | N | N | N | Planned |  | Display only userID IBP (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20858 | STRIVE.R2.MC1.2384.2536.163.13 | N | N | N | Planned |  | Display only userID R2P (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Eurasia SAP Team for Authorization | HBG-SAP-SICHERHEIT-OandS@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20859 | STRIVE.R2.MC1.2384.2536.163.14 | N | N | N | Planned |  | interface job suspension R2D (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Pierangela Donida | piera.donida@it.sasol.com | Italy Monitoring SAP; Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20860 | STRIVE.R2.MC1.2384.2536.163.15 | N | N | N | Planned |  | interface job suspension IBP (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Italy Monitoring SAP | italy.monitoringSAP@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20861 | STRIVE.R2.MC1.2384.2536.163.16 | N | N | N | Planned |  | interface job suspension P2C (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Cristina | cristina.tomascu@it.sasol.com | Italy Monitoring SAP; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20862 | STRIVE.R2.MC1.2384.2536.163.17 | N | N | N | Planned |  | interface job suspension R2P (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Italy Monitoring SAP | italy.monitoringSAP@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20863 | STRIVE.R2.MC1.2384.2536.163.18 | N | N | N | Planned |  | interface job suspension MOR (detailed list required) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Italy Monitoring SAP | italy.monitoringSAP@it.sasol.com | Dhruv Kansal; Mousikta chanda; USI STRIVE CUTOVER | dhkansal@deloitte.com; mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20864 | STRIVE.R2.MC1.2384.2536.163.19 | N | N | N | Planned |  | BW data load - delta load confirmation | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | PC Global BW Support | PCGlobalBWSupport@sasol.com | Italy Monitoring SAP; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20865 | STRIVE.R2.MC1.2384.2536.163.20 | N | N | N | Planned |  | SOST : Suspend job for e-mail outside of Sasol domain | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Christian Hogrefe | Christian.Hogrefe@de.sasol.com | Italy Monitoring SAP; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20866 | STRIVE.R2.MC1.2384.2536.163.21 | N | N | N | Planned |  | Job suspension ALE tranfer of SDS to AP1 | 1 hrs | 2025-09-20 08:00 | 2025-09-20 09:00 | Italy Monitoring SAP | italy.monitoringSAP@it.sasol.com | Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 09:00
20867 | STRIVE.R2.MC1.2384.2536.163.22 | N | N | N | Planned |  | Open FI/CO period Job suspension | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Pierangela Donida | piera.donida@it.sasol.com | Italy Monitoring SAP; Dhruv Kansal; USI STRIVE CUTOVER; Mousikta chanda | italy.monitoringSAP@it.sasol.com; dhkansal@deloitte.com; usistrivecutover@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20868 | STRIVE.R2.MC1.2384.2536.163.23 | N | N | N | Planned |  | check succesfully issue to SDI and notification back (EDOC) | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Dhruv Kansal | dhkansal@deloitte.com | Mousikta chanda; USI STRIVE CUTOVER | mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20869 | STRIVE.R2.MC1.2384.2536.163.24 | N | N | N | Planned |  | All vendor invoice in EDOC not yet posted to be transferred to S/4 Document and compliance Cockpit | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Adelin Apotsu | aapostu@deloittece.com | S2P Team; USI STRIVE CUTOVER; Dhruv Kansal; Mousikta chanda | usisasols2p@deloitte.com; usistrivecutover@deloitte.com; dhkansal@deloitte.com; mouchanda@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00
20870 | STRIVE.R2.MC1.2384.2536.163.25 | N | N | N | Planned |  | validation : All vendor invoice in EDOC not yet posted to be transferred to S/4 Document and compliance Cockpit | 4 hrs | 2025-09-20 08:00 | 2025-09-20 12:00 | Dhruv Kansal | dhkansal@deloitte.com | Mousikta chanda; USI STRIVE CUTOVER | mouchanda@deloitte.com; usistrivecutover@deloitte.com | Sasol GRC |  |  |  | * | NA | 2025-09-20 08:00 | 2025-09-20 12:00